## Project Structure
Folder Structure |  |  | Checklists
Site QA
| Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
| Whiteman Park | To Contain Viaduct Checklist | Ability to Add Viaduct Checklists

## Resources
Type | Name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
Sustainability Action Plan
checkpoint | Inspection & Test Plan - ITP
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Prestress
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Concrete Repair Methodology
checkpoint | Shop Drawings - IFC
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65 Concrete Mix Design Approved by Client
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Prestressing Tendons
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Ensure that all Coil Numbers are recorded
checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint | Stressing Jack Calibration Certificates - Valid
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Lifting Loops
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client - Rigging System + Loops
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items and Ferrules
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Bayswater U Beam Checklist (Stage 1 Casting)
section | Pre-Pour Checklist
text | Cast Number | 1
text | Beam Number & Orientation | 3
text | Beam Number & Orientation | 4
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Oiled
label | Steel Chamfers in Place (East web and West web)
label | Seal tape is in the edge of corbel and drip groove
label | Check angle for shutter
checkpoint | Detailed inspection of mould & cage(HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | Reinforcement in Accordance with Drawings
text | Reinforcement bars with couplers
text | Reinforcement around lifting loops
text | Reinforcement size
text | Lap Length
text | Splicing
text | Bar Chairs
checkpoint | Condek (Top Slab)
checkpoint | Cover maintained and within tolerance
label | 35mm
label | 40mm
label | 50mm
checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | Ferrules KSN16M (Web)
text | Ferrules M20x96 (Bottom Flange)
text | Ferrules M16x70 (Handrails)
text | Ferrules M10x45 (Expansion Joint Cover)
text | Ferrules M16x45 (Ladder)
text | Ferrules M16x70 (Web, Laingorourke Formwork)
text | Ferrules (Other type, specify)
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Other type, specify
checkpoint | All Blockout Conduits are installed in accordance with Drawings
checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | Lifting Loops
checkpoint | All Couplers are installed in accordance with Drawings
text | BT16/A
text | BT28/A
text | BT36/A
text | BT20/A
checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | Earthing Terminals (DB16CS701)
text | 100mm 6mm fillet welds between bars
text | <20 mOhm across cage Length
text | Checklist Completed (North) (attach results)
text | Checklist Completed (South) (attach results)
checkpoint | Prestressing Strands
text | Enter Coil Number Used for this Cast
label | Sag Load all Strand
label | Mutli-Stress as per Pre-stressing Procedures
checkpoint | Prepare Stressing Records and Submit to Client for Review (HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | All Temperature Loggers are installed as per Approved WMS
text | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 2
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket (list all)
checkpoint | Total Concrete Volume
text | Volume (m3) | 6
checkpoint | Mix Design Verified
text | Specify mix used | 5
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance
text | Slump (list all) | 7
checkpoint | Truck Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks is not exceeded
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and checked for stripping strength
text | Stripping Strength | 16
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology
label | Temperature 5 degrees past its peak
label | Differential between Core and Ambient within 30 degrees
label | Differential between Core and Cover within 20 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Ferrules
text | Couplers
text | Stainless Items
text | Lifters
text | Blockouts
text | Earthing and Bonding
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush and Epoxied
text | Couplers are Cleaned and Capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
checkpoint | Survey Hog of Beams (Dumpy)
text | First Reading (Once Stripped)
text | Second Reading (if required)
text | Final Reading (Prior to Delivery)
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report | 17
text | 7 Day Strength (List all) | 18
text | 28 Day Strength (List all) | 19
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)
checklist-sectioned | Bayswater Top Slab (Stage 2 Casting)
section | Pre-Pour Checklist
text | Cast Number | 9
text | Beam Number & Orientation | 11
text | Beam Number & Orientation | 12
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Oiled
label | Steel Chamfers in Place (East web and West web)
checkpoint | Detailed inspection of mould & cage(HOLD POINT FOR CLIENT TO SIGN OFF)
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement bars with couplers
label | Reinforcement around lifting loops
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Condek (Top Slab)
checkpoint | Cover maintained and within tolerance
label | 35mm
label | 40mm
label | 50mm
checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | Ferrules M16x70 (Handrails)
text | Ferrules M10x45 (Expansion Joint Cover)
text | Ferrules M10x45 (Ladder)
text | Ferrules M16x70 (Web, Laingorourke Formwork)
text | Ferrules (Other type, specify)
checkpoint | All Stainless Items are installed in accordance with Drawings
text | Other type, specify
checkpoint | All Blockout Conduits are installed in accordance with Drawings
checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | Lifting Loops
checkpoint | All Couplers are installed in accordance with Drawings
checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | Earthing Terminals (DB16CS701)
text | 100mm 6mm fillet welds between bars
text | <20 mOhm across cage Length
text | Checklist Completed (North) (attach results)
text | Checklist Completed (South) (attach results)
checkpoint | All Temperature Loggers are installed as per Approved WMS
text | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint | QA Engineer Check Completed by
checkpoint | Client Inspector (if present)
section | Supervisor Release
checkpoint | Supervisor Release to Engineering Team
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 10
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Docket (list all)
checkpoint | Total Concrete Volume
text | Volume (m3) | 14
checkpoint | Mix Design Verified
text | Specify mix used | 13
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance
text | Slump (list all) | 15
checkpoint | Truck Tested for strength
text | Test Report Reference Number (list all)
checkpoint | Time Lag Between Trucks is not exceeded
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed
section | Stripping Checklist
checkpoint | Date Stripped
text | Enter Date
checkpoint | Concrete Cylinders Crushed and checked for stripping strength
text | Stripping Strength | 16
label | Strength = Reading / 7.851
checkpoint | Lifting Strength Achieved
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Secondary Curing as per Approved Methodology
label | Temperature 5 degrees past its peak
label | Differential between Core and Ambient within 30 degrees
label | Differential between Core and Cover within 20 degrees
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | Ferrules
text | Couplers
text | Stainless Items
text | Lifters
text | Blockouts
text | Earthing and Bonding
checkpoint | Post-Pour Works Completed (As Required)
text | Strands are Cut Flush and Epoxied
text | Couplers are Cleaned and Capped
text | Roughened Surfaces are Greencut
text | Water Removed out of Cooling Pipes
text | All Miscellaneous Items are Completed
checkpoint | Survey Hog of Beams (Dumpy)
text | First Reading (Once Stripped)
text | Second Reading (if required)
text | Final Reading (Prior to Delivery)
checkpoint | Temperature Logging Completed and Conforming. Attach Results
section | Any Defect Identified
checkpoint | Punchlisting Completed
checkpoint | Repairs Required (if applicable)
checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint | Crack Map Completed
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report | 17
text | 7 Day Strength (List all) | 18
text | 28 Day Strength (List all) | 19
section | Transportation Requirements
checkpoint | Certificate of Conformance
checkpoint | Inspection Release Certificate
checkpoint | Delivery Notes
checkpoint | Delivery Docket
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative (if applicable)