## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Bayswater Top Slab (2nd Stage Casting) |  |  |  |  | Yes | Bayswater Top Slab (2nd Stage Casting) | 1ca2bae7-5cad-475a-a399-702e25126eaa
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-no-status |  |  | checkpoint | Details
text | e3f909b6-f863-5d86-b5a7-810a5e76df01 |  | textbox | Cast Number
text | 11dc543a-4cf8-543c-88e2-7c7309db864c |  | textbox | Beam Number & Orientation
text | e494ec63-89e0-5602-8e5b-6b45472aecf8 |  | textbox | Beam Number & Orientation
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | 32f10718-ab73-53ba-8da1-abef59fad9b0 |  | note | Length
label | 07eb7010-3a74-5d01-841f-7e2d838e2a1e |  | note | Width
label | b85394bb-bdd8-5e41-8c4f-1d2c2cb2d458 |  | note | Height
label | 004ef3ef-54da-5c70-a16f-a0a97dd1e6fd |  | note | Straightness
label | 3534a512-22ec-5cc3-be9e-ec2fa97d2ed6 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | 650fb0e9-2274-51ad-bc7b-8d23cab3ab02 |  | note | Cleaned
label | 71551f66-abb4-5310-9bcb-95cd18137356 |  | note | Sealed
label | c785e137-50cc-5cf7-8845-6713b75c787a |  | note | Oiled
label | 66f9232e-64f3-5a83-bd60-3a724b031d77 |  | note | HDPE Chamfers in place
label | 55784f79-ce34-5d82-a98c-25133f549fea |  | note | Steel Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | c02fa125-f7e1-5fa0-9ae3-13028de0b3ef |  | note | Reinforcement bars with couplers
label | be68035f-6ec3-5a5a-847e-eea23e3c74f0 |  | note | Reinforcement around lifting loops
label | d6b05a44-4fef-5828-aef4-551cb941e856 |  | note | Reinforcement size
label | bd67a68d-33d3-5768-93ac-8dec4151f372 |  | note | Lap Length
label | aa964e8b-10af-5f1c-9197-99e2e21698ef |  | note | Splicing
label | 552e1245-debc-572e-9281-e90c835a9e50 |  | note | Bar Chairs
checkpoint-status |  |  | checkpoint | Condek (Top Slab)
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
label | f9c0acdd-31fd-5c92-85de-c2c20eec256f |  | note | 35mm
label | 61b60ec8-b381-5a89-8dc2-3e1d3682c151 |  | note | 40mm
label | 8955efb4-2bdc-5535-ad68-1cf3b102cc5d |  | note | 50mm
checkpoint-status |  |  | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | d0de34cf-5583-575b-a953-c6896caa883d |  | textbox | Ferrules M16x70 (Handrails)
text | e5a84d7c-b941-5b40-aec2-855b98d02584 |  | textbox | Ferrules M10x45 (Expansion Joint Cover)
text | 6f394183-52eb-5858-aa1b-42802bc7bde6 |  | textbox | Ferrules M20x70 (Ladder)
text | 6dffec09-df65-5962-bec7-a36f6735dc57 |  | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
text | 199a0305-fe16-5212-add2-43e3f99e24f4 |  | textbox | Ferrules (Other type, specify)
checkpoint-status |  |  | checkpoint | All Stainless Items are installed in accordance with Drawings
text | f5d46b12-56f8-508e-b288-0d819be5fe51 |  | textbox | Other type, specify
checkpoint-status |  |  | checkpoint | All Blockout Conduits are installed in accordance with Drawings
checkpoint-status |  |  | checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | 31b9d330-2df7-5f30-9cbf-a89eba0029b9 |  | textbox | Lifting Loops
checkpoint-status |  |  | checkpoint | All Couplers are installed in accordance with Drawings
checkpoint-status |  |  | checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | e909b192-519f-5bca-afee-607b7dfc67c9 |  | textbox | Earthing Terminals (DB16CS701)
text | 304e5270-5f55-51bb-91f1-d0ca52a7d5e2 |  | textbox | 100mm 6mm fillet welds between bars
text | 1c065fff-9197-5851-921f-df81d6b0ef11 |  | textbox | <20 mOhm across cage Length
text | 7a0b4a44-b243-50e8-a4ef-38e8c843ca35 |  | textbox | Checklist Completed (North) (attach results)
text | d679d552-1cfc-5f11-a63d-d083e5dab07b |  | textbox | Checklist Completed (South) (attach results)
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
text | 66c1fa44-e6ab-5faf-a0ce-20e3c0f38838 |  | textbox | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | 96245437-1757-5d24-af4b-e0dedb9187ae |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | 1a7c2e53-a837-55f0-bc31-96f8244d46d2 |  | textbox | Concrete Delivery Docket (list all)
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 11e03592-7d25-5001-bd3b-436a66c13f71 |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified
text | 5dddb2a9-a157-5109-8451-82c92d6dc0cd |  | textbox | Specify mix used
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | ed8fd0fb-4499-5bd0-8252-388b42981a56 |  | note | max 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | 1c0d3c43-fc81-5c09-91c9-b725ea563178 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance
text | edb0cf9d-255b-524d-8938-08c278882cce |  | textbox | Slump (list all)
checkpoint-status |  |  | checkpoint | Truck Tested for strength
text | 014ea2b5-4f89-5c23-937d-cbf34068c117 |  | textbox | Test Report Reference Number (list all)
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks is not exceeded
checkpoint-status |  |  | checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | d317b832-78dd-52e6-ae8b-ba0ebca0b915 |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Submitted to Client
text | 110aaaf4-214a-5d23-bd34-f0f39e2020dc |  | textbox | Stripping Strength
label | e1ec6fab-7673-5a5a-aa7a-b5bc1afcb975 |  | note | Strength = Reading / 7.851
holdpoint |  |  | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint-status |  |  | checkpoint | Secondary Curing as per Approved Methodology
label | 2c5a1e3c-566f-5eb9-a7af-ac52c01680ed |  | note | Temperature 5 degrees past its peak
label | 7279ebf6-8036-581e-88c1-09202b7b1965 |  | note | Differential between Core and Ambient within 30 degrees
label | 97d15fe0-86ea-51bb-bc69-11f78ec4c414 |  | note | Differential between Core and Cover within 20 degrees
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | be862e58-76d4-5626-818a-da05b87e1c70 |  | note | Length
label | 6bd39235-8099-5ca4-9d87-1c5371de148a |  | note | Width
label | 27c5cc69-6e6c-5009-8cae-0b8b42fe5d7d |  | note | Height
label | 88db8e07-5bd5-56b8-9ad9-e1da6bb5acb9 |  | note | Straightness
label | c0430848-e3f2-592d-bbf6-3a7e25324f3f |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | c7fbaa79-d118-5690-9255-87e61f1e9f74 |  | textbox | Ferrules
text | 8190e858-6789-5428-8242-3af51f4d5713 |  | textbox | Couplers
text | b46ddecd-9232-5487-893a-30412f4e77eb |  | textbox | Stainless Items
text | b72b09d7-10af-5f86-9fec-9b2f272da234 |  | textbox | Lifters
text | 9c5c3807-3bef-5907-98a0-ceb52d1e7683 |  | textbox | Blockouts
text | 3d02ccbd-9bf9-555b-873c-2ab030420397 |  | textbox | Earthing and Bonding
checkpoint-status |  |  | checkpoint | Post-Pour Works Completed (As Required)
text | 780c7395-2ad0-5f8d-b3be-56117e41cbc8 |  | textbox | Strands are Cut Flush and Epoxied
text | 6ddf01bc-7f1f-5c6c-b600-de42997df97d |  | textbox | Couplers are Cleaned and Capped
text | 0eff2787-b285-56a6-868b-459e4617ccb1 |  | textbox | Roughened Surfaces are Greencut
text | 3db476f2-3477-5281-a018-dfa3ed04eaad |  | textbox | Water Removed out of Cooling Pipes
text | d6bfb5a4-f9cf-5623-8878-91c14e29cf1f |  | textbox | All Miscellaneous Items are Completed
checkpoint-status |  |  | checkpoint | Survey Hog of Beams (Dumpy)
text | ea23985c-8123-5b6d-910d-90e83cc547bd |  | textbox | First Reading (Once Stripped)
text | 4394b450-6e7d-5312-9281-8a7f0314ee26 |  | textbox | Second Reading (if required)
text | 723349fd-91fa-5cf7-8678-6f4aefb56034 |  | textbox | Final Reading (Prior to Delivery)
checkpoint-status |  |  | checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlisting Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Crack Map Completed
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | 268d04a9-b1b3-5b2d-b7f0-e38e659b48f9 |  | textbox | Concrete Test Report
text | 9dbfd1df-f62f-5aa9-bd4c-9b589f42dd76 |  | textbox | 7 Day Strength (List all)
text | 802267ca-371a-5c38-a458-ffdf05f6db67 |  | textbox | 28 Day Strength (List all)
checkpoint-group |  |  | section | Transportation Requirements
checkpoint-status |  |  | checkpoint | Certificate of Conformance
checkpoint-status |  |  | checkpoint | Inspection Release Certificate
checkpoint-status |  |  | checkpoint | Delivery Notes
checkpoint-status |  |  | checkpoint | Delivery Docket
checkpoint-group |  |  | section | Final Acceptance
checkpoint-status |  |  | checkpoint | Completed by
checkpoint-status |  |  | checkpoint | Reviewed by
checkpoint-status |  |  | checkpoint | Client Representative (if applicable)
checklist-sectioned |  |  | checklist | Bayswater Viaduct Checklist |  |  |  |  | Yes | Bayswater Viaduct Checklist | aee38372-2bb8-4b76-824b-418cc46d9e35
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-no-status |  |  | checkpoint | Details
text | 02ce3ac9-9a57-566a-be97-5ff78e5d2d7e |  | textbox | Cast Number
text | 66c71d04-bf09-5398-a80d-e2b164fe7a08 |  | textbox | Beam Number & Orientation
text | 63008788-a4f3-5d00-bc34-b6b0818449d3 |  | textbox | Beam Number & Orientation
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | dbe8ad35-ea06-507f-b006-da35b6d707ff |  | note | Length
label | c86ada52-7d38-529d-a835-fc2e78e3a77f |  | note | Width
label | 2707dda0-f399-5b0d-95aa-a9142cf140cd |  | note | Height
label | 6f9582b8-ab46-5c99-b686-f3bb59fd02e9 |  | note | Straightness
label | a1b84f65-dc49-5fad-8e52-1abba4b7b64f |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | 648c03ac-07bd-5128-9242-4d991ae0f351 |  | note | Cleaned
label | bbfd914e-0aee-5951-8540-e322e0b85878 |  | note | Sealed
label | 36a3b096-d922-5ef4-bb25-d67c218f5735 |  | note | Oiled
label | 2998188c-dbfc-53c5-99c8-4c4f7d061240 |  | note | HDPE Chamfers in place
label | 828788c7-3e19-5051-b128-ed117c61ed52 |  | note | Steel Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | 89c77959-5e0b-53c1-b939-39008c30151b |  | note | Reinforcement bars with couplers
label | aeae309b-268a-5062-b8a1-2897218c43de |  | note | Reinforcement around lifting loops
label | 3a75ab54-7f21-514a-bf07-0f746c58abd6 |  | note | Reinforcement size
label | 05cbe847-3444-54b5-ab78-bd3f19cf2e33 |  | note | Lap Length
label | 6b549bba-2b59-5baf-98c3-39620e2fb4d6 |  | note | Splicing
label | fb297583-db62-5dac-a39b-8037ae47ac2e |  | note | Bar Chairs
checkpoint-status |  |  | checkpoint | Condek (Top Slab)
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
label | 19eb935d-6120-59cd-bac6-9d26202ce8d8 |  | note | 35mm
label | 6e825e57-04d0-5058-854d-6f4bc206c63e |  | note | 40mm
label | d3bf2b27-d1a9-5acb-a17c-ef45a7651f76 |  | note | 50mm
checkpoint-status |  |  | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | 64875996-a496-526d-ad16-39173a1f910f |  | textbox | Ferrules KSN16M (Web)
text | 8d6f276d-4fe8-59f9-aea2-79f0ceccba3a |  | textbox | Ferrules M20x96 (Bottom Flange)
text | 5dc63d41-e8c2-586f-a35b-1381b27ce910 |  | textbox | Ferrules M16x70 (Handrails)
text | 91f63159-4e9e-5b8c-910b-6f9fd366e4e6 |  | textbox | Ferrules M10x45 (Expansion Joint Cover)
text | 97f9f6f1-8e67-5f5a-9be3-b20cb3f59ace |  | textbox | Ferrules M20x70 (Ladder)
text | 422de958-9e06-5e6d-a766-66540ed2640d |  | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
text | 5b6d6ff2-1a8a-52ac-be0c-10f4a7626e17 |  | textbox | Ferrules (Other type, specify)
checkpoint-status |  |  | checkpoint | All Stainless Items are installed in accordance with Drawings
text | d4725405-4904-525f-9fc6-dd63dfb4712a |  | textbox | Other type, specify
checkpoint-status |  |  | checkpoint | All Blockout Conduits are installed in accordance with Drawings
checkpoint-status |  |  | checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | 0e7152c3-c2ab-5035-a150-9e7989f1bd1d |  | textbox | Lifting Loops
checkpoint-status |  |  | checkpoint | All Couplers are installed in accordance with Drawings
text | 2a634aff-1c43-5603-bf71-430f2ba4e321 |  | textbox | BT16/A
text | 2be0aa3e-465d-5c23-837e-7eedba613035 |  | textbox | BT28/A
text | 0e4bbad3-4d10-5724-b237-03b0a1c44647 |  | textbox | BT36/A
text | 7ec4ddd5-c0a6-5128-bc9b-94d73c868882 |  | textbox | BT20/A
checkpoint-status |  |  | checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | 196533fa-86cd-5e2f-a0d1-3d2517e65018 |  | textbox | Earthing Terminals (DB16CS701)
text | 55791f71-08db-5b6a-80d8-cfd7cf49ac28 |  | textbox | 100mm 6mm fillet welds between bars
text | 5343d879-89ab-5e04-b862-d6ddf571f268 |  | textbox | <20 mOhm across cage Length
text | 3f11b4a8-da4c-5ebc-b097-47d9fda0c150 |  | textbox | Checklist Completed (North) (attach results)
text | 945c0fa2-709c-5d82-a872-f9608757a645 |  | textbox | Checklist Completed (South) (attach results)
checkpoint-status |  |  | checkpoint | Prestressing Strands
text | ba44a442-a0e0-5a0e-b86f-a29e48a1e95d |  | textbox | Enter Coil Number Used for this Cast
label | d79d6a23-e45c-515b-b595-419fd34384e8 |  | note | Sag Load all Strand
label | fbcbdcfb-c7ec-59e3-b146-2db6d1ad3e1d |  | note | Mutli-Stress as per Pre-stressing Procedures
checkpoint-status |  |  | checkpoint | Prepare Stressing Records and Submit to Client for Review
holdpoint |  |  | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
text | 34b8543a-547f-5be7-8a67-b6cbdcc9b35b |  | textbox | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | abfd6964-8867-571d-9579-4c72532a82d5 |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | 8531cfd0-4eba-51ad-b447-55af400a83e5 |  | textbox | Concrete Delivery Docket (list all)
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 93fef86d-2ee4-5fa9-8e2b-0c91e6596831 |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified
text | c77be049-fc7b-5ce5-ba55-29cd3ac7aa05 |  | textbox | Specify mix used
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | da390ca8-dbfc-56f2-a62a-1a6082c12268 |  | note | max 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | a6ec505e-191b-525e-9ee4-12692f0a0949 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance
text | 14bf4cd8-31ea-5a20-8574-7c72aeb942e3 |  | textbox | Slump (list all)
checkpoint-status |  |  | checkpoint | Truck Tested for strength
text | f1c65881-60fa-5335-90d0-dd1c1f611853 |  | textbox | Test Report Reference Number (list all)
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks is not exceeded
checkpoint-status |  |  | checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 21903566-b321-5ac1-8806-c6e435058e23 |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Submitted to Client
text | ce1eb2b8-5eb3-5d0e-81c7-0c7534c69346 |  | textbox | Stripping Strength
label | 4e64d6e6-890a-552c-8725-f0b5d7241169 |  | note | Strength = Reading / 7.851
holdpoint |  |  | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checklist-sectioned |  |  | checklist | Preliminary Activities and Materials Approval |  |  |  |  | Yes | Preliminary Activities and Materials Approval | f6027664-facb-4ec7-8be8-f30911edf4c1
checkpoint-group |  |  | section | Preliminary Activities (Approved by Client)
checkpoint-status |  |  | checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint-status |  |  | checkpoint | Permacast Project Quality Management Plan
checkpoint-status |  |  | checkpoint | Sustainability Action Plan
checkpoint-status |  |  | checkpoint | Inspection & Test Plan - ITP
checkpoint-status |  |  | checkpoint | MDR Index
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Prestress
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Curing
checkpoint-status |  |  | checkpoint | Concrete Repair Methodology
checkpoint-status |  |  | checkpoint | Shop Drawings - IFC
checkpoint-status |  |  | checkpoint | Test Panel Prepared and Inspected by Client
checkpoint-status |  |  | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | S65 Concrete Mix Design Approved by Client
checkpoint-group |  |  | section | Steel Reinforcement
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
checkpoint-group |  |  | section | Prestressing Tendons
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Ensure that all Coil Numbers are recorded
checkpoint-status |  |  | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint-status |  |  | checkpoint | Stressing Jack Calibration Certificates - Valid
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-group |  |  | section | Lifting Loops
checkpoint-status |  |  | checkpoint | Lifting Design Approved by Client
checkpoint-status |  |  | checkpoint | Lifting Devices Approved by Client - Rigging System + Loops
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checkpoint-group |  |  | section | Cast-in Items and Ferrules
checkpoint-status |  |  | checkpoint | All Cast in Materials Approved
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality