## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Hollowcore | itp |  |  |  |  | ITP - Hollowcore
section | 1.0 Pre Construction Tests
checkpoint | 1.1 - Concrete Mix Design Approval
label | Acceptance Criteria - 60 MPa at 28 days (S6014PC)
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once per Mix design / per supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Confirmation of Approval
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 1
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - 1
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.2 - Reinforcement Supply
label | Acceptance Criteria - Micro Alloying Deformed Bars Grade 500E (HD)
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Size, Per Supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Supplier Mill Certificates
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.3 - Strand Supplier Verification
label | Acceptance Criteria - ACRS accredited supplier
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - ACRS Accreditation
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.4 - Strand Supply
label | Controlling Documents - NZS 3109
label | Acceptance Criteria - 15.2mm diam. Prestressing superstrand
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Size, Per Supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Supplier Mill Certificates
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.5 - Strand Certification
label | Controlling Documents - AS/NZS 4672
label | Acceptance Criteria - Conformance to AS/NZS 4672 in relation to:
label | ○ Chemical analysis
label | ○ Geometrical characteristics
label | ○ Breaking force or tensile strength
label | ○ Proof load or proof stress
label | ○ Elongation at maximum load
label | ○ Load extension diapgram
label | ○ Ductility
label | ○ Relaxation
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Size, Per Supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Material Test Certificates
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.6 - Shop Drawing Approval
label | Controlling Documents - IFC drawing
label | Acceptance Criteria - Shop drawings including strand type, arrangement and stressing notes, details of debonding lengths, concrete strengths, surface finishes, location of cast in items and set-out information
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once Prior to Casting
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Approved Shop Drawings, Issued for Construction
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.7 - Stressing Calculations
label | Acceptance Criteria - Force remaining in each 15.2 mm dia. strand at midpoint of beam immediately after release of tensioning jacks
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - 5 Days Prior to Casting
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Approved Stressing Calculations
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.8 - Jack Calibration
label | Acceptance Criteria - Calibrated within tolerance
label | Inspection or Test: Method - Certificate Inspection
label | Inspection or Test: Freq. - Every 6 Months, Per Jack
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Calibration Certificate
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.9 - Form Release Agent
label | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Material Data Sheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
section | 2.0 In Process Testing
checkpoint | 2.1 - Reinforcement Traceability
label | Acceptance Criteria - Mill Certificate, Heat Number and Bend Schedule traceability
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre-Pour Check Sheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
checkpoint | 2.2 - Reinforcement Fixing
label | Controlling Documents - NZS 3109
label | Acceptance Criteria - clear cover as per drawing to all reinforcing including stirrups and ties
label | ○ Steel to be securely tied and fixed with no movement
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre pour checksheet, photos
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - N
checkpoint | 2.3 - Pre Pour Inspection
label | Acceptance Criteria - Completed pre-pour inspection (dimension/inserts/ reo) permission to commence concrete placement
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Beam, Per Pour
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Approved Pre-Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - D
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 2.4 - Concrete Placement
label | Controlling Documents - NZS-3109
label | Acceptance Criteria - Slump within target 120 +/-40, all concrete to be properly vibrated
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Concrete Delivery / Per Placement
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - In-Pour Checksheet / Delivery Docket
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 2.5 - Concrete Sampling/Testing
label | Acceptance Criteria - Compressive test 1 x 7d and 3 x 28d results + 2 stress transfer cylinder (1 for test + 1 spare) stored at curing temperature
label | ○ 60 MPa at 28 days
label | Inspection or Test: Method - Concrete Sampling/Testing
label | Inspection or Test: Freq. - One set per precast beam with an additional set taken from any truck which has water added after leaving the plant
label | Inspection or Test: Responsible Person - Subcontractor
label | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory for 7 & 28days test)
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - 3
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (Designer to be notified immediately if specimen fails)
holdpoint | HOLD POINT
checkpoint | 2.6 - Heat Curing
label | Controlling Documents - Approved Heat Curing Methodology
label | Acceptance Criteria - Concrete core temperature shall not exceed 70 degrees
label | ○ Steady state inlet and outlet water temperatures recorded
label | Inspection or Test: Method - Temperature Monitoring
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - In Pour Checksheet, Hot Water Curing Methodology
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (Designer to be notified if anomalous temperature readings encountered)
holdpoint | HOLD POINT
checkpoint | 2.7 - Concrete Curing
label | Controlling Documents - NZS 3109
label | Acceptance Criteria - 7 days wet curing required following completion of accelerated curing
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Post Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (Designer to be notified immediately if water supply interrupted)
holdpoint | HOLD POINT
checkpoint | 2.8 - Type B Construction Joint
label | Controlling Documents - NZS 3109
label | Acceptance Criteria - 5mm amplitude and free of latinece, cut with water blaster and with use of High Strength Spray on Retarder
label | ○ Top surface of all beams and end blocks of integral beams
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Post Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
checkpoint | 2.9 - Post Pour Inspection / Draw-in Measurement
label | Controlling Documents - IFC Drawings
label | Acceptance Criteria - Surface Finish Requirements- (F5 for seen faces) / Dimension/inserts/cut-outs as per drawing
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Post Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
section | 3.0 Stessing Related Operations
checkpoint | 3.1 - Strand Positioning
label | Acceptance Criteria - +/- 3 mm in any direction
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
checkpoint | 3.2 - Stressing
label | Acceptance Criteria - Collation of stressing records incl unit ID, strand extention, jack pressures and general comments
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Stressing Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (All anomalous readings not in line with Stressing calculations to be submitted)
holdpoint | HOLD POINT
checkpoint | 3.3 - Stress Transfer
label | Acceptance Criteria - Concrete Cylinder Tests to be minimum 40MPa
label | ○ Cylinder to be kept in similar conditions to beam
label | Inspection or Test: Method - Cylinder Compressive Strength Test
label | Inspection or Test: Freq. - Once Per Beam
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Cylinder Compressive Strength Report (In-house)
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - S
label | Inspection / Test Authority: Witness - S
label | Inspection / Test Authority: Produce Record - S
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (No Stress transfer before 30MPa)
holdpoint | HOLD POINT
section | 4.0 Final Documentation
checkpoint | 4.2 - Producer Statement (PS3)
label | Acceptance Criteria - Signed PS3
label | Inspection or Test: Method - Report Production
label | Inspection or Test: Freq. - Once
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Signed PS3
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - N