## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Mangakootukutuku ST Rev 3 | itp |  |  |  |  | ITP - Mangakootukutuku ST Rev 3
section | A. Pre-Construction
checkpoint | 1 - Shop Drawing Approval
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Shop drawings to be submitted for approval.
label | Reference - Structural drawings
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Approved IFC Shop Drawings
label | Records - Client approval
label | Responsibility - Project Manager
holdpoint | HOLD POINT
checkpoint | 2 - Concrete Mix Design Approval
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Concrete mix design to be submitted for approval prior to concrete being supplied to site.
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Minimum compressive strength at 28 days 60MPa. The mix design to comply with aspects of the contract specification.
label | Records - Client approval
label | Responsibility - Project Manager
holdpoint | HOLD POINT
checkpoint | 3 - Lift Design
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Lift design provided for units demoulding, storage and transportation.
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Specific Lift design (Lifting eyes and position) produced and followed
label | Records - Lift design Shop Drawings
label | Responsibility - Project Manager
holdpoint | HOLD POINT
checkpoint | 4 - Steel Reinforcement compliance
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Mill certificates for steel reinforcing to be provided
label | Reference - AS/NZS 4671
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Steel to be manufactured with ACRS certificate details and verification
label | ○ Mill certificates to match ACRS certificates.
label | Records - Mill Certificates Detail sheets Test Certificates
label | Responsibility - Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 5 - Steel pre-stressing material (Strands) compliance
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Mill certificates for prestressing strand coils to be provided
label | Reference - AS/NZS 4672
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Prestressing strands (coils) to be supplied by ACRS accredited Manufacturer.
label | ○ Mill certificates checked against size, type and strand - mill certificate to match ACRS certificate
label | Records - Mill Certificates ACRS Certificate
label | Responsibility - Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 6 - Design Stressing calculation
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Design stressing calculation and calibration certificates to be submitted to the Design Engineer
label | Reference - Structural drawings
label | Frequency - Prior to casting
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Expected extensions and gauge readings to be calculated for each cast.
label | Records - Design Stressing Calculation Calibration Certificates Client Approval
label | Responsibility - Project Manager
holdpoint | HOLD POINT
section | B. During Casting
checkpoint | 7 - Steel Reinforcement cage assembly
label | ACTION (Hold, Monitor, Witness) - Monitor
label | Detail - Steel reinforcing cage to be assembled and inspected.
label | Reference - Approved shop drawings
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Cage assembly to comply with correct size, class, length, shape and location/spacing as specified in shop Dwgs.
label | ○ Free from visual damage.
label | Records - Pre-Pour Inspection sheet REO detail sheets
label | Responsibility - Production / Quality Coordinator
checkpoint | 8 - Mould Preparation
label | ACTION (Hold, Monitor, Witness) - Witness
label | Detail - Before casting ensure mould has been prepared to comply with tolerances.
label | Reference - NZS3109 Table 5.1
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
label | Conformance Criteria - Tolerance on placement of moulds shall be a per NZS 3109
label | Records - Pre-Pour Inspection sheet
label | Responsibility - Production / Quality Coordinator
checkpoint | 9 - Pre-Stressing
label | ACTION (Hold, Monitor, Witness) - Monitor
label | Detail - Review actual strand extension/pressure compliance with approved design calculation. Draw-in measurements to be taken and recorded
label | ○ Check that debonding has been included as required. Debonding shell be by plastic sleeves around the strand.
label | Reference - Approved shop drawings Design Stressing calculation
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection/Measure
label | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
label | Records - Stressing Calculation sheet Pre-Pour Inspection sheet
label | Responsibility - Stressing Controller
checkpoint | 10 - Steel Reinforcement Placement
label | ACTION (Hold, Monitor, Witness) - Witness
label | Detail - Reinforcing steel shall be handled, placed as per NZS 3109.
label | Reference - Approved shop drawings NZS 3109
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Steel reinforcing cage placed as per approved shop drawings.
label | ○ Spacers shall be installed evenly to ensure correct cover as per shop drawings achieved.
label | Records - Pre-Pour Inspection sheet
label | Responsibility - Production / Quality Coordinator
checkpoint | 11 - Cast-in Items
label | ACTION (Hold, Monitor, Witness) - Witness
label | Detail - All cast in items positioned as per shop drawings Lifters positioned as per lift design
label | Reference - NZS3109 Table 5.1 Approved shop drawings Approved Lift Design
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Correct type and number of cast in items used Correct Lifters used, positioned in accordance with approved lift design
label | Records - Pre-Pour Inspection sheet
label | Responsibility - Production / Quality Coordinator
checkpoint | 12 - Pre Pour Inspections
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Pre Pour Inspection shall be carried out before casting.
label | ○ The Engineer's Rep shall be advised at least 48 hours before the proposed pour.
label | Reference - Approved shop drawings
label | Frequency - Prior to each cast
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure, Document review
label | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards for tolerances.
label | Records - Pre Pour inspection sheet Marked up shop drawing, Stressing records
label | Responsibility - Foreman & Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 13 - Concrete Mix Conformance
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - All concrete dockets reviewed at time of delivery.
label | Reference - Approved mix design
label | Frequency - Prior to placement of concrete
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - All concrete delivered to site shall be produced in accordance with the approved mix design
label | Records - Concrete Delivery Dockets
label | Responsibility - Supervisor & Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 14 - Concrete Mix Workability
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Fresh concrete to be visually assessed for its workability compliance.
label | Reference - Approved mix design
label | Frequency - Prior to placement of concrete
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Workability as per mix design.
label | ○ Concrete slump test to be performed by concrete supplier before delivery
label | Records - Concrete Delivery Dockets
label | Responsibility - Supervisor & Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 15 - Concrete Finish
label | ACTION (Hold, Monitor, Witness) - Witness
label | Detail - Concrete to be placed to achieve the specified formed and unformed finishes
label | Reference - Approved shop drawings NZS3114
label | Frequency - During and after placement of concrete
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - ST Beam to be Type F4 finish
label | ○ All construction joints - Type B / UNO
label | ○ Top surface Type B / CJ and U2 where specified
label | Records - Pre-Pour Inspection sheet
label | Responsibility - Foreman & Production / Quality Coordinator
section | C. Post-Construction
checkpoint | 16 - Curing and Release Strength
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Heat accelerrated curing as per approved methodology.
label | ○ 7 Day post mould water curing as per approved methodology
label | Reference - NZS 3109, NZS 3112
label | Frequency - Prior to every unit transfer
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing (Schmidt hammer or Compressive strength test)
label | Conformance Criteria - Minimum compressive strength at transfer of prestressed units to be 40MPa prior to stripping and demoulding.
label | Records - Post-Pour Inspection sheet
label | Responsibility - Production Manager
holdpoint | HOLD POINT
checkpoint | 17 - Transfer
label | ACTION (Hold, Monitor, Witness) - Monitor
label | Detail - Visual inspection to ensure strands are tight and no slippage of strand into concrete. Locallised spalling around full bonded strand at transer as result of excessive slippage will be identified as non conformance and the unit will be rejected and remade.
label | Reference - Approved shop drawings
label | Frequency - Prior to transfer
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
label | Responsibility - Production / Quality Coordinator
checkpoint | 18 - Draw-in
label | ACTION (Hold, Monitor, Witness) - Monitor
label | Detail - Strand draw-in to be measured on each cast. If ave draw-in for group exceeds 2mm, or 4mm for single strand, then results to be submitted to Eng
label | Reference - NZS3109 C8.72.3
label | Frequency - Every unit - at transfer
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
label | Conformance Criteria - Draw-in to be measured on each beam at transfer
label | Records - Post-Pour Inspection sheet
label | Responsibility - Production / Quality Coordinator
checkpoint | 19 - Lifting
label | ACTION (Hold, Monitor, Witness) - Monitor
label | Detail - Units are to be demoulded following lift design
label | Reference - Approved lift design
label | Frequency - Every unit
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Approved lift design to be followed.
label | Responsibility - Production / Quality Coordinator
checkpoint | 20 - Marking
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Units are to be clearly marked each end with unique number, cast date and installation direction (Super T).
label | Reference - Approved shop drawings
label | Frequency - Every unit - after demoulding, prior storing
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Ensure every unit is clearly marked
label | Responsibility - Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 21 - Concrete Supply Testing
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Concrete compressive strength test to be carried out by supplier. 1 Set per beam with additional set for any truck with water added after leaving the batch plant
label | Reference - NZS 3112, Part 2
label | Frequency - 1 test sample for every beam [1 cylinder - at 7 days age, 3 cylinders - at 28 days age, 3 cylinders - transfer strength]
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing
label | Conformance Criteria - Compressive Strength result to be a minimum orf 60MPa at 28 days
label | Records - Concrete suppliers Test Reports
label | Responsibility - Concrete Supplier + Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 22 - Post Pour Inspection
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - All units shall be inspected for its compliance prior to delivery
label | Reference - Approved shop drawings
label | Frequency - Every unit - prior delivery
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards
label | Records - Post-Pour Inspection sheet (red pen mark-up - as-built)
label | Responsibility - Production / Quality Coordinator
holdpoint | HOLD POINT
checkpoint | 23 - QA Package / As-Built
label | ACTION (Hold, Monitor, Witness) - Hold
label | Detail - Compliance documentation is to be collated as per project requirements
label | Frequency - At Delivery and installation
label | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | Conformance Criteria - Compliance documentation is to be submitted to the Engineer.
label | Records - Post Pour inspection sheet Marked up shop drawings - as built
label | Responsibility - Production / Quality Coordinator
holdpoint | HOLD POINT