## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Precast Barrier | itp |  |  |  |  | ITP - Precast Barrier
section | 1.0 Pre Construction Tests
checkpoint | 1.1 - Concrete Mix Desisgn Approval
label | Acceptance Criteria - 50 MPa at 28 days (S5019MS8)
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once per Mix design / per supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Confirmation of Approval
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 1
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - 1
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.2 - Reinforcement Supply – Certificate of Origin
label | Controlling Documents - Approved Drawings
label | Acceptance Criteria - Provide certificate of origin for all steel reinforcing supplied.
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per Size, Per Supplier
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Supplier Mill Certificates
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - 4
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.3 - Shop Drawing Approval
label | Controlling Documents - IFC Drawings
label | Acceptance Criteria - Shop drawings including, concrete strengths, surface finishes, location of cast in items and set-out information
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once Prior to Casting
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Approved Shop Drawings, Issued for Construction
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 1.4 - Form Release Agent
label | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Once
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Material Data Sheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Produce Record - S
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
checkpoint | 1.5 - Cast-in Items
label | Acceptance Criteria - Provide certificate of origin for cast-in-items
label | Inspection or Test: Method - Review
label | Inspection or Test: Freq. - Per batch delivered
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Suppliers Mill Certificate
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - 4
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - 4
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
section | 2.0 In Process Testing
checkpoint | 2.1 - Inspection of The Reinforcing
label | Acceptance Criteria - 40 mm min. clear cover to all reinforcing including stirrups and ties
label | ○ Steel to be securely tied and fixed with no movement
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre pour checksheet, photos
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - N
checkpoint | 2.2 - Checking Formwork
label | Acceptance Criteria - Dimension including edge details and rebates as per drawing
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre pour checksheet, photos
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 2.3 - Pre Pour Inspection Prior to concrete placement
label | Acceptance Criteria - Completed pre-pour inspection, permission to commence concrete placement
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Pre-Pour Check Sheet/ photos
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - D
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
section | 3.0 Concrete Testing and Inspection
checkpoint | 3.1 - Concrete Delivery
label | Acceptance Criteria - Approved Mix Design (S5019MS8)
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Concrete Delivery
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Delivery Dockets
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
checkpoint | 3.2 - Concrete Placement
label | Controlling Documents - NZ 3109
label | Acceptance Criteria - Vibration of concrete to ensure suitable compaction
label | ○ Slump within target 100+/-40
label | Inspection or Test: Method - inspect
label | Inspection or Test: Freq. - Per unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Witness inspection
label | Records required for handover package: Yes/No - N
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Hold Point - N
section | 4.0 Post Concrete Testing and Inspection
checkpoint | 4.1 - Concrete smpling / testing
label | Acceptance Criteria - 1 x 7d and 3 x 28d - 50 MPa at 28 days
label | Inspection or Test: Method - Concrete Sampling
label | Inspection or Test: Freq. - Per 75 m3 (not part thereof)
label | Inspection or Test: Responsible Person - Subcontractor
label | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory)
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - 3
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y (Designer to be notified immediately if specimen fails)
holdpoint | HOLD POINT
checkpoint | 4.2 - Surface Finish Requirements
label | Controlling Documents - IFC Drawings
label | Acceptance Criteria - F5 / Type B construction joint to NZ 3109
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Post Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - Y (Designer to be notified if finish requirement not meant)
holdpoint | HOLD POINT
checkpoint | 4.3 - Concrete Curing
label | Acceptance Criteria - Curing with curing compound (e-cure)
label | Inspection or Test: Method - Inspect
label | Inspection or Test: Freq. - Per Unit
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Post Pour Checksheet
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Witness - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - C
label | Hold Point - Y
holdpoint | HOLD POINT
section | 5.0 Final Documentation
checkpoint | 5.1 - Producer Statement (PS3)
label | Acceptance Criteria - Signed PS3
label | Inspection or Test: Method - Report Production
label | Inspection or Test: Responsible Person - PRECO
label | Verifying Document - Signed PS3
label | Records required for handover package: Yes/No - Y
label | Inspection / Test Authority: Conduct - C
label | Inspection / Test Authority: Produce Record - C
label | Inspection / Test Authority: Approval - D
label | Hold Point - N