## Guardrail & Wire Rope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F- Tangoio Falls Steep Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guardrail Installation |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Teams meassage from Dave Hooker 21/12/23 | Andrew Harrall / behalf Trudy- 08/01/24 | Quality Eng.
Lot No: B1004F- Tangoio Falls Steep Underslip |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 608 RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 |  | H | Earthworks and pavement construction shall be completed prior to barrier installation. | Prior to commencement | Review |  |  | Site Engineer | CPS Engineer
2 |  | H | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | OFI or NTD/NTC | CPS Engineer | CPS Engineer
3 | Survey Setout | H | Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing. | Site Engineer
4 | Material Compliance | H | All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4 | Prior to commencement | Visual inspection/ Document review | TNZ M/23:2009 | Manufacturing certificates and delivery dockets | Site Engineer
5 | Guardrail Installation | W | Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
6 |  | W | Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
7 |  | W | Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010 | CS-4117 | Site Engineer
8 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
9 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
10 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Asbuilts, NCR's and RFI's | Site Engineer
11 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date:
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Drawing 0002 clause 5.4 requires earthworks and pavement to be complete. Make Hold point 1?