## Reinforced Slope
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F - Tangoio Fall Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Reinforced Slope (Rock Bolts, Soil Nails) |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Dave Hooker / Gre Bailey via Teamsmessage | Andrew Harrall/ Belhalf Trudy Guy | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEB-SH2SOUTHHAWKESBAY/ETnWr4WChDhGjRR1PaDE0vgBodebGIpsi1M9S9fvWr5ZOg?e=U8xS4r |  | Compliance with Work Instructions and Specifications
Detailed Location: Tangoio Falls Steep Underslip- SH 02- RS 608 -RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Erosion and Sediment Control Plan | H | Need ESCP before construction begins | Prior to commencement | Visual Inspection | Erosion and Sediment Control Plan must be submitted to the design team |  | Site Engineer | Design Engineer
2 |  | H | Implement ESCP approved by environmental team | Prior to commencement | Visual Inspection |  |  | Site Engineer | CPS Engineer
| Road Safety Barriers | H | Propriitary barrier system type and installation methodology | Prior to commencement | Review | Approval from Design Engineer |  | Site Engineer | Design Engineer
|  | W | Propritary barrier system compliance records | Daily | Review | Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained |  | Soite Engineer
3 | Clearing & Earthworks | H | Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed | Prior to commencement | Visual Inspection | In accordance with TNZ F/1 | Photos | Site Engineer
4 |  | H | Any excavation and filling required is to be carried out. Excavation should be kept to a minimum | Prior to commencement | Visual Inspection | In accordance with TNZ F/1. | Photos | Site Engineer
5 | Survey Setout | H | Arrange for a set out survey to be carried out & check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer | CPS Engineer
6 | Material Compliance and Methodology Approval | H | Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings | Prior to commencement | Document Review | Grade 500E soil nail Class II corrosion protection Lengths and diameters shown on drawings are the minimum required | Delivery Docket | Site Engineer
|  | H | Concrete quality plan | Prior to commencement | Submission | Including: - Name, qualificationand expoerience of concrete works inspector - Form and content of concrete placement card | Email | Site Engineer | CPS Engineer
|  | W | Details of concrete supply plant, copy od certificate of audit for plant | Three weeks prior to pouring concrete | Submission | Including: - Plant test Results - ASR Compliance Records | Email | Site Engineer
|  |  | Concrete work plan | At least 10 days before commencing works oinsite | Submission |  | Email | Site Engineer
|  | W | Reinforcing steel manufactureers test reports and certificates | Prior to undertaking works | Submission | Including despatch records | Email | Site Engineer
8 |  | W | Submit all concrete mix designs, trial mixes and compliance records | Three weeks prior to pouring concrete | Submission | Mix Design to be approved by CPS Engineer before commencing construction | Email | Site Engineer | CPS Engineer
9 |  | H | Test to be carried out on Grout mix before it is ordered for construction | Prior to commencement | Testing | Mix design to be approved by CPS Engineer before commencing construction | Test results to CONQA Procore | Site Engineer | CPS Engineer
10 |  | W | Grout checked if its free from lumps & segregation | Prior to commencement | Visual Inspection |  |  | Site Engineer
11 |  | H | Request for use of alternative Drilling Fluid (Section 7.5.2) | Prior to Commencement | Submission | If required |  | Site Engineer | CPS Engineer
12 |  | H | Soil Nail construction methodology plan must be submitted two weeks prior to works starting | Prior to commencement | Submission | Include sprayed concrete, grouting and tremie concrete in methodology |  | Site Engineer | CPS Engineer
Sacfrifical Testing has been Completed and the Results are in the Design Report
13 | Working Bench | H | The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times. | Prior to commencement | Measure |  | Photos | Site Engineer
21 |  | H | Location of all Test Nails to be agree on site (Section 7.8.1) | Prior to Trial | Inspection |  | Photos, Site Diary | Site Engineer | CPS Engineer
17 |  | H | Insert micropile bar (ReidBar RB32) to full required length | During Construction | Measure | Embedded length of micropile 3.0m into ground | Photos | Site Engineer
|  |  | Drill hole | During construction | Submission | Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any. Submit all installation records for each soil nail and pile. |  | Site Engineer | Design Engineer
29 |  | H | Flush all soil nail holes with water and air after drilling to remove smear and drilling debris | During Construction | Visual Inspection |  |  | Site Engineer
31 |  | H | Insert soil nails as specified | During Construction | Visual Inspection | Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage | Subcontractor QA Records | Site Engineer | CPS Engineer
32 |  | W | A record is to be maintained showing the type and installation date for each soil nail | During Construction | Submission | Installation records shall include: - Length of bar - Depth of drill hole - Inclination/Verticality achieved - Level of grout placed - Batch numbers associated with grout placed in each hole | Subcontractor QA Records | Site Engineer | CPS Engineer
18 |  | H | Install Grout | During Construction | Visual Inspection | Including : - Concrete despatch records - Compression test results Must notify CPS for any failed result and cease works until resolved | Subcontractor QA Records | Site Engineer
33 |  | H | Install Grout on the same day of drilling unless otherwise approved by designer | During Construction | Visual Inspection |  | Photos | Site Engineer
34 |  | H | Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch | During Construction | Testing | Must reach specified minimum 7-day and 28-day compressive strengths | CONQA | Site Engineer | CPS Engineer
35 |  | W | Loss of grout shall be monitored and recorded for each hole during and immediately after grouting | During Construction | Submission |  | Subcontractor QA Records | Site Engineer
36 |  | H | Install Bolts/Nails washers & nuts | During Construction | Measure | All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed. | Delivery Dockets | Site Engineer
37 | Testing of Soil Nails | H | All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified | After Construction | Submission | Certifications of all testing equipment within the last 3 months | Certifications | Site Engineer
38 |  | H | Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved | After Construction | Measure |  |  | Site Engineer
39 |  | H | Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2) | After Construction | Testing | Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails | Test results to CONQA Procore | Site Engineer | CPS Engineer
40 |  | H | Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails | After Construction | Document Review | CPS Engineer to give approval via a NTC | Email | Site Engineer | CPS Engineer
41 | Shotcreting | H | Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened | During Construction | Visual Inspection |  | Photos | Site Engineer
42 |  | W | Apply shotcrete - 200mm Nominal thick (Vertical) | During construction | Visual Inspection |  | Photos | Site Engineer
43 |  | W | Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal) | During Construction | Visual Inspection |  | Photos | Site Engineer
44 |  | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores | After Construction | Visual Inspection |  | Test results to CONQA Procore | Site Engineer
45 |  | H | Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m | After Construction | Visual Inspection | Surface Inspected by CPS Engineer & Approval given to carry on with works | Email | Site Engineer | CPS Engineer
46 | Post Construction Survey | H | Survey final position of bolts for as-built purposes | At completion of Lot | Visual Inspection | Survey report complete and conforms to specification | Survey receipt | Site Engineer
47 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
48 |  | W | All subcontractor documentation to be included in QA file | At completion of Lot | Document Review |  | Subcontractor QA Records | Site Engineer
49 | As-built | H | Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file | During and at completion of work. | Survey / Drawings |  | Survey receipts, As-built plans | Site Engineer
50 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Asbuilts, NCR's and RFI's | Site Engineer
51 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: