## Reinforced Slope
|  |  |  | Inspection Test Plan |  |  | Approved / Signature
|  |  |  | Contract Name: | H1501A Tupiko Stream Bridge - Scour Protection |  | CPS Engineer | Dave Hooker | Quality Manager: | Trudy Guy
|  |  |  | Procedure: | Reinforced Slope (Rock Bolts, Soil Nails) |  | Approval via Teams message to Josin |  | Andrew Harrall Approved on Behalf
Inspection & Test Plan / Checklist | [6 empty] | Message on 21-12-2023 |  | Dated : 08-01-2024
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Others Initials (Grey if not required) | Date(s)
1 | Clearing & Earthworks | H | Before setout of the reinforced slope method all vegetation clearance & any bulk earthworks is to be completed | Prior to commencement | Document Review | QA-6002 - Tree Felling & Vegetation Clearance | QA-6002 Process Control Plan Tree Felling & Vegn Clearance Check Sheet | Site Engineer
2 | Survey Setout | H | Arrange for a set out survey to be carried out & check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
3 | Material Compliance | H | Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings | Prior to commencement | Document Review |  | Delivery Docket | Site Engineer
4 |  | H | Shotcrete Mix Design & Work Method Statement approved by Design Engineer | Prior to commencement | Document Review | Mix design to be approved by Design Engineer before commencing construction | Lab Test Results/ NTC | Site Engineer | Design Engineer
5 |  | H | Test to be carried out on Grout mix before it is ordered for construction | Prior to commencement | Document Review | Mix design to be approved by Design Engineer before commencing construction | Lab Test Results/ NTC | Site Engineer | Design Engineer
6 | Working Bench | H | Bench to be 2m of less - the top of the row not to be above 1.5m above the bench | Prior to commencement | Measure |  | Photos | Site Engineer
7 | Trial installation of Bolts/Nails | H | Drill hole, install Bolt/Nail, install Grout | Test | Visual Inspection |  | Lab Test Results | Site Engineer | Design Engineer
8 |  | H | Test after a 7 day period. Load up to the specified requirements with the Design Engineer overseeing proceedings | Test | Visual Inspection/ Document Review | Design Engineer to observe testing and provide feedback on a NTC | NTC | Site Engineer | Design Engineer
9 | Installation of Bolts/Nails on the created working bench | H | Drill holes as specified | During Construction | Measure | Drill within +/- 2 degrees and +/- 100mm of position | Subcontractor QA Records | Site Engineer
10 |  | H | Install Bolts/Nails as specified | During Construction | Visual Inspection | Ensure lengths are that specified on the drawings | Subcontractor QA Records | Site Engineer
11 |  | H | Install Grout - take sample of each truck load delivered to site | During Construction | Measure | Compression cylinders to be tested at Lab | Lab Test Results | Site Engineer
12 |  | H | Install Bolts/Nails washers & nuts | After Construction | Measure | All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed. | Delivery Dockets | Site Engineer
13 |  | H | Testing of Bolts/Nails - after 7 days when the Grout strength has reached 20Mpa | After Construction | Measure | Load testing - Design Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails | NTC | Site Engineer | Design Engineer
14 |  | H | Final inspection of Design Engineer to give approval to remove bench and start on next rows of Bolts/Nails | After Construction | Document Review | Design Engineer to give approval via a NTC | NTC | Site Engineer | Design Engineer
15 |  | W | Remove working bench and continue with same process as above | During Construction | Document Review |  | Photos | Site Engineer
16 | Shotcreting | H | Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened | During Construction | Visual Inspection |  | Photos | Site Engineer
17 |  | W | Apply shotcrete - minimum 150mm thick and nominal 175mm | During Construction | Visual Inspection |  |  | Site Engineer
18 |  | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores | After Construction | Visual Inspection |  | Lab Results | Site Engineer
19 |  | H | Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m | After Construction | Visual Inspection | Surface Inspected by Design Engineer & Approval given to carry on with works | NTC | Site Engineer | Design Engineer
20 | Post Construction Survey | H | Survey final position of bolts for as-built purposes | At completion of Lot | Visual Inspection | Survey report complete and conforms to specification | Survey receipt | Site Engineer
21 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
22 |  | W | All subcontractor documentation to be included in QA file | At completion of Lot | Document Review |  | Subcontractor QA Records | Site Engineer
23 | As-built | H | Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file | During and at completion of work. | Survey / Drawings |  | Survey receipts, As-built plans | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: