## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CS-4072 - ITS Pit Inspection Record |  |  |  |  | Yes | CS-4072 - ITS Pit Inspection Record | 0172b0c6-fd6e-4711-81a1-3f0f9891c839
checkpoint-no-status |  |  | checkpoint | ITS Pit Inspection Record
text | 2c8070b3-95cd-5021-9333-587624d9f659 |  | textbox | Project No.
text | 2619c507-9ec4-5774-b096-88f252f5affa |  | textbox | Drawing No (& Rev No):
text | cbe6387f-8219-5b8f-88cb-7736cf1358ab |  | textbox | Pit #:
checkpoint-status |  |  | checkpoint | Pull Pit/ Joint chamber set out by surveyor
text | 62109141-7e69-580d-90db-701a38fe0375 |  | textbox | Initials:
date | c624d3fe-81cc-5e87-a28f-9b05004ddb07 |  | date | Date:
label | 5e0bf12c-4568-501e-ba6b-9d395062920b |  | note | Comments: Survey Receipt
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | de02bc6b-c561-5f65-91de-da0c798d68a8 |  | textbox | Initials:
date | 683bf4f5-dab2-5e64-ae08-74e3219640b1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Depth shall be determined prior to excavating
text | bddd8583-8abf-5961-af82-022a00c7758d |  | textbox | Initials:
date | afc8908e-a5b8-57e8-9b49-ed8630d7b39e |  | date | Date:
label | 0f15d416-1551-58a1-94b3-1363418c79c5 |  | note | Comments: Grass/Concrete/Asphalt areas – Lid must be flush to FL
label | 862108ff-f688-5b71-82e5-9d5707b31089 |  | note | ○ Planted areas – Lid must be 100mm above ground level with a sloping concrete apron
checkpoint-status |  |  | checkpoint | Slopes >30 lid shall be 100mm above GL on the upper side. Slopes 10-30 lid shall be flush with the GL on the upper side.
text | da8d7830-6d37-567c-afc6-71d052882651 |  | textbox | Initials:
date | 218c2195-4c8f-54b6-a5b8-ebfff13fbd00 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bedding shall be 150mm of GAP65 compacted
text | 584b57e7-166d-573f-a3d9-ecd0acea8599 |  | textbox | Initials:
date | 4783374c-bed7-5473-b6db-64b1f56b237d |  | date | Date:
checkpoint-status |  |  | checkpoint | Ducts shall be connected perpendicular to the chamber wall.
text | cdd0dc5c-b076-5795-9b0d-f300f36fc979 |  | textbox | Initials:
date | 4373ede8-6b5f-5a24-9edf-9cd1ddc783f4 |  | date | Date:
label | a9ddf59e-8882-5d43-9222-9d3f0c76c933 |  | note | Comments: Ducts must not protrude more than 100mm into the chamber
checkpoint-status |  |  | checkpoint | Seal ducts using suitable epoxy resin (outside) to ensure water tight
text | 0e6f8026-3ac7-52f6-a92d-5beef6b0e36a |  | textbox | Initials:
date | 43a76e1b-d89b-5b7e-b80e-f9103d8f7bf3 |  | date | Date:
label | 5c4e0fc4-da15-583c-9eb9-44c0a5499fd5 |  | note | Comments: All joints must be smoothed off to form a fillet between the duct & chamber wall
checkpoint-status |  |  | checkpoint | Ensure all ducts are capped inside the chambers to keep water tight
text | ee8f6737-42cc-5670-a6c1-e569400bb3ec |  | textbox | Initials:
date | bda02b42-ceaf-5615-8b42-4d3df0c524f2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure backfill material is correct and compacted
text | 269735df-08f8-5887-aa80-a97fcb3a0e5e |  | textbox | Initials:
date | 07342369-6422-5011-beef-0e32142cefb0 |  | date | Date:
label | dcbc114d-e6c4-56e8-b65f-37703b84005d |  | note | Comments: Berm – sand/excavated material 200mm lifts CIV of 8
label | 925c0021-529f-5d7d-9e53-95e09ed0c454 |  | note | ○ Carriageway – GAP65 200mm lifts 95% MDD
checkpoint-status |  |  | checkpoint | Top 300mm of the chamber shall be concreted to a width of 150mm around the lid
text | 9d701df5-ad71-56ad-8f31-7de93111e586 |  | textbox | Initials:
date | 640f93e6-e9dd-5906-b9a2-c735670991dd |  | date | Date:
checkpoint-status |  |  | checkpoint | Roof, collar & lid installed to manufacturer’s requirements
text | 91521ed0-9b3c-5c9c-8e72-95365a745ca7 |  | textbox | Initials:
date | 02ff7b6e-b5fe-5036-b1da-6de52104e108 |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean out jointing chambers at completion.
text | 9a474b3a-a3b5-53bc-bf75-1187abbbc07f |  | textbox | Initials:
date | c6c6ddcf-6d8d-5e98-971b-505f2b9b1e18 |  | date | Date:
label | def5f9a7-52e1-555c-bab3-9b80e9dbd759 |  | note | Comments: Remove any construction materials or contaminates from Pit
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 97a76f6c-abcd-53c0-95d3-0f96695cf78a |  | textbox | Name:
text | b7809d2f-995c-55e0-afc2-475ca6b19725 |  | textbox | Position:
date | e080ec35-5df4-55c3-ba61-559b68c6c1ec |  | date | Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4098 - Bottom Driven Pile Card |  |  |  |  | Yes | CS-4098 - Bottom Driven Pile Card | 0bb50945-c377-46ce-a952-f269dda10da0
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 8adbe2b0-be40-57f5-8929-df35c661bc16 |  | textbox | Project No.
text | 1a297583-c94d-555d-a9d2-d67f3446dce7 |  | textbox | Pile Type:
text | 671c3990-a2eb-508d-a5e6-c44549776e27 |  | textbox | Yield Stress: |  |  | MPa
text | 7119a28f-e327-5d98-8157-f42ec85215c5 |  | textbox | Capacity kN (calculated):
text | b68762be-790d-56b4-becc-35274ff52568 |  | textbox | Capacity kN (required):
text | 69cb9681-40be-55d5-8eda-aadea40cbcaa |  | textbox | Temporary Compression (C): |  |  | Mm measured
text | f1810efb-6e0d-50b4-aaff-b84c13ec68dc |  | textbox | Set mm (measured):
text | 979cf3d1-3b38-5b58-a610-7b7268d8cb96 |  | textbox | Set mm (required):
text | 1d699f13-b686-5ccd-b2b9-d782537f42bf |  | textbox | Hammer (mass): |  |  | tonnes
text | f45a5bfd-320c-5c73-a08d-910806fe73d1 |  | textbox | Hammer (drop): |  |  | metres
text | f69ce5a0-12e7-585a-a8a5-4a99c6410f0d |  | textbox | Hammer (Efficiency): |  |  | %
text | 54f5721f-e282-5f95-ba34-949c35c64792 |  | textbox | RL top of Pile (1): |  |  | m
text | 1d2d1c9f-7f70-5b7f-bcb2-dfd905eb6a93 |  | textbox | RL top of Pile (2): |  |  | m
text | c75b77a9-509f-5ec0-b2c8-36f329a83f81 |  | textbox | Pile Length: |  |  | m
checkpoint-group |  |  | section | Pile Construction
checkpoint-status |  |  | checkpoint | Pre-Drive / Bore / Jet
date | e1551dae-2fc6-59b2-b8c4-c7e4a66ce5b0 |  | date | Date:
text | ce5651f2-be30-5246-8bc6-a137e1f5468b |  | textbox | Start Time:
text | 2eefd7ba-55fb-5a9b-8e98-2195b7f4452d |  | textbox | Finish Time:
text | 1d85cc74-822f-5b23-9e1d-4131f367ecf7 |  | textbox | Hrs:
text | 23cacb85-d1c7-5ffb-becc-acc17b27fdde |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 1
date | 4f561ddc-6d30-5502-a957-5e0b4f3a36ff |  | date | Date:
text | 6519b0d5-860e-5791-9158-cd382a911b02 |  | textbox | Start Time:
text | dab68389-129d-5b98-9963-a0c8d02524df |  | textbox | Finish Time:
text | 6d1e315a-7388-5eca-9d43-582b52eae1f8 |  | textbox | Hrs:
text | 71846ab7-8fd4-5955-ac13-4fdda160e07b |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 2
date | 43cb7179-46d1-589a-aa2e-8c3731507ab4 |  | date | Date:
text | 3fa59600-feca-5a4a-90aa-b7e38c0ae440 |  | textbox | Start Time:
text | 9707bcf2-8960-5859-b3cf-1b2ff2fb405a |  | textbox | Finish Time:
text | 02c6642a-db61-5184-b5a5-c665707f8b3f |  | textbox | Hrs:
text | a9ce3f66-75ad-5dde-bf44-797596a39676 |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 3
date | 1c827f49-c318-5a8d-8a24-134888975be0 |  | date | Date:
text | e774cf63-6cf7-5b29-aa8c-382b158bd89a |  | textbox | Start Time:
text | 5a84a170-59ef-552a-b40f-80771b8e5fbd |  | textbox | Finish Time:
text | a823b8d4-25a0-51bd-b260-205eb8b5f671 |  | textbox | Hrs:
text | ac523ad4-7c9f-54e9-931c-5850d6f71c3b |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Re Drive:
date | 7975760d-4fad-5883-a048-d66b0b7be421 |  | date | Date:
text | fbc7a32b-9915-5ade-bec8-1725aa03286f |  | textbox | Start Time:
text | 3996de73-16ee-5d36-98cc-f39521e50ef4 |  | textbox | Finish Time:
text | 21db50b0-8268-54d0-9545-d7b2001a5410 |  | textbox | Hrs:
text | 7cb461d1-0962-59c4-8367-db38e67e07e4 |  | textbox | Conditions:
checkpoint-group |  |  | section | Obstructions Encountered
checkpoint-status |  |  | checkpoint | Obstructions Encountered:
text | d0951fc7-f15d-5899-a41c-621a1f74555c |  | textbox | Type:
text | 1b911ca7-977d-5a19-a60c-042990678eab |  | textbox | Depth:
text | 3e069d63-7ed1-512e-99d5-3cb2d7338ee9 |  | textbox | Action Taken:
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Penetration (1 m):
date | 30733ddd-3649-5782-bc4d-161d75145241 |  | date | Date:
text | eff45dc0-6b87-50a0-b902-76fb2ed79bf2 |  | textbox | Time:
text | 908d98d0-bf77-5030-99a9-a18572f4afd8 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (2 m):
date | 00c1026e-6951-54bf-a288-f9d15cc32c3e |  | date | Date:
text | a1527a68-602d-5262-a21e-53e1d1d4bf28 |  | textbox | Time:
text | cdde67a3-be89-566e-8194-e8cf837a3b67 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (3 m):
date | 8bb25850-e743-5c24-8714-88d9cc4f8d73 |  | date | Date:
text | 62387102-1fe7-5350-bc2c-411e433cd9a0 |  | textbox | Time:
text | 37528fff-2d2e-584d-9171-3ef8dcef95b5 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (4 m):
date | f87d538c-e40b-5779-9654-4ee450bb8897 |  | date | Date:
text | 2c8064ca-54da-5a6f-89e1-245b19dfa497 |  | textbox | Time:
text | 4a1f2341-0778-5132-b747-92f50281650f |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (5 m):
date | 62ec8174-5349-541c-b6cf-23225a702805 |  | date | Date:
text | dba5437d-b8f1-5e38-8c6f-a61fbe8d3a73 |  | textbox | Time:
text | 5b572ac4-d3b7-58d4-beb7-8b36fa3db367 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (6 m):
date | 0fbcf11a-7d03-5c8a-9998-06b2e468b2e1 |  | date | Date:
text | 9f170fcf-59c6-505b-82e1-e86433023efb |  | textbox | Time:
text | b973d15c-3381-5b76-a8ee-6b1671ac9a67 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (7 m):
date | ec232c16-6a90-58c6-b596-c40ff4d184cc |  | date | Date:
text | c4180661-8752-51bc-8bb2-88dd22bb8b27 |  | textbox | Time:
text | dacff850-fed4-5fee-a22b-30e44d73f289 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (8 m):
date | 605a065d-7df9-5a53-ad87-3d90098b57e2 |  | date | Date:
text | 92fedec1-09c8-5216-b220-0bdc5a771059 |  | textbox | Time:
text | 467a08b4-7ef0-59f8-8333-9bee9f660fa6 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (9 m):
date | f6a9f6bb-bdee-5bed-ac9e-17eb09959029 |  | date | Date:
text | 7d0e3e18-eaf0-576f-9e21-1a0e9b1a62d0 |  | textbox | Time:
text | d4f4d74f-af3b-5374-9fdb-3b000369e2d6 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (10 m):
date | d8528d24-25e2-5792-bcb5-bffc804ce6a6 |  | date | Date:
text | b6e11ee3-10dd-5aad-86a9-b5190f8c277f |  | textbox | Time:
text | 3b838c26-fed0-5515-b525-34b60a491d6c |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (11 m):
date | 52d963aa-eb2c-54ca-b855-be3dcddf500c |  | date | Date:
text | c3a405a0-a1f8-5d7f-9466-6e7172c9532f |  | textbox | Time:
text | 4b381039-d592-5211-a690-68810d0e9c6a |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (12 m):
date | 362e1a47-e09e-512b-8755-c45ae2e6b41e |  | date | Date:
text | 1329f83a-3238-5a14-ae8f-264defe15d94 |  | textbox | Time:
text | beb327ea-26a7-57f4-b146-6bf2d12e5f60 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (13 m):
date | 0590d268-a8b3-504b-824f-fc886b4db180 |  | date | Date:
text | 83ee8bc5-7f21-5e36-9f86-795fd5aa475a |  | textbox | Time:
text | 7c03f3c8-2b46-552d-bb30-97522b94ba6c |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (14 m):
date | e485604f-255e-5c48-9a2d-e99c4ebaefa4 |  | date | Date:
text | 058a94a1-cf97-56c0-9833-0d98184ffacb |  | textbox | Time:
text | 4c6b2f88-cad2-532c-83bc-7df57d3001a4 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (15 m):
date | 6b88eeb5-a2f4-5f11-a3c7-df13460f9a9c |  | date | Date:
text | 8660e853-33c7-53bf-abdd-94cb7d99b32c |  | textbox | Time:
text | 34240e49-5d54-5ed2-b7cc-a3dc1b47d6f1 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (15.5 m):
date | 508f68d6-c4c5-5862-81e9-432dbb96b644 |  | date | Date:
text | 7e78f254-0810-5b79-97fb-c38979eb2e5a |  | textbox | Time:
text | 0b082392-1353-52ca-9b38-d7b43a891608 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (16 m):
date | 3cc064f3-2da7-5056-b7e7-2ca7264a3d43 |  | date | Date:
text | 87731744-981e-577b-8ca4-6b3c678bb951 |  | textbox | Time:
text | 3416a8b4-f317-5e95-8da8-ee750468d5d1 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (16.5 m):
date | d4029bf0-b562-5d15-a250-37f3805e3fb1 |  | date | Date:
text | 0695d9e3-969b-5ad1-a4cf-2d3a1655707d |  | textbox | Time:
text | 5e3fd34d-5f53-5a38-a6eb-a37f4125c2e0 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (17 m):
date | c193c761-8c68-5374-9444-e8deff241f19 |  | date | Date:
text | 118057f5-2e0a-5489-a13c-c897d0b33a04 |  | textbox | Time:
text | 1256f360-337b-59ed-90a5-45bfd388e0f5 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (17.5 m):
date | d021896a-4196-5c18-b593-ba4151786bde |  | date | Date:
text | 979c22ce-97ed-50a6-86ef-1d9fb094e20b |  | textbox | Time:
text | e5bf035d-49bf-5ced-b19b-ee4fecfec97d |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (18 m):
date | de61762c-d15e-5e73-a8b8-88b6a88f964e |  | date | Date:
text | 1223fcee-483b-5d0a-9338-220e5cf4af3d |  | textbox | Time:
text | f031bc1f-06a2-5932-9e00-4aba1caaee9d |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 1cb59a59-af85-5963-9f43-282f480d5b91 |  | textbox | Name: Site Engineer
date | ac03ef07-8354-5c68-8737-3f2a6ba9c940 |  | date | Site Engineer - Date:
text | 621219e3-7ba2-5e42-aacc-b17c86ceb603 |  | textbox | Name: CPS Engineer – Geotechnical
date | fec96a31-286b-589c-8622-f5476c84b845 |  | date | CPS Engineer – Geotechnical - Date:
text | 80dce77c-5688-5f03-b042-1b3c1c54d324 |  | textbox | Name: CPS Engineer - Structural
date | 22f7b3fd-8099-583b-9251-1bb7233a1ba1 |  | date | CPS Engineer - Structural - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4069 - Stringline Dipsheet |  |  |  |  | Yes | CS-4069 - Stringline Dipsheet | 162365f0-c450-4fe1-b1c7-078a6187be74
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | f03cdd11-a244-5869-a734-09b1565ee7cd |  | textbox | Project No.
text | 91c23354-ebb4-5073-aa36-beefcbc0740d |  | textbox | Stage:
text | e03054d6-3794-538a-ad06-b11928f6d298 |  | textbox | Material:
label | c6e8d299-234a-500a-a325-e5d1fcad6d67 |  | note | ○ Subgrade TNZ F/1 Tolerance: -30mm / 0mm
label | c3584e3d-4b8d-5816-bb7d-d7ed3b5e6ed5 |  | note | ○ SIL TNZ F/1 Tolerance: -30mm / 0mm
label | e5488a17-8c69-5890-8b9c-466e4948bb14 |  | note | ○ Subbase TNZ B/2 Tolerance: -25mm / +5mm
label | f79c4ae2-8564-565f-a5bd-8529e645d950 |  | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+15mm without concrete channel
label | 21753f56-d929-5852-9906-691e69d532c6 |  | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+5mm with concrete channel in locations close to or at the lip of the channel
text | 02a2104a-f6ed-577d-b707-f28e7156e6d2 |  | textbox | String Lift: |  |  | mm
checkpoint-group |  |  | section | Chainage
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | 5b887981-a24d-52d3-803f-befbabfe7558 |  | textbox | (m)
text | d1054695-eb95-57da-afab-34410e99e0d8 |  | textbox | Width - Left Shoulder:
text | 912b6276-827a-5a51-b201-d08ffe04176b |  | textbox | Depth Below String line - Left edge:
text | d2f2e5e1-57fa-5cec-96e1-e34664b70301 |  | textbox | Depth Below String line - Left mid-lane:
text | cff7f958-4ac9-51b1-8fad-7f28a2020a19 |  | textbox | Depth Below String line - Centreline:
text | 31e501e6-70bc-5677-8288-4e1626a87435 |  | textbox | Depth Below String line - Right mid-lane:
text | 268b7f86-96b9-584f-8faa-86adc2fb3998 |  | textbox | Depth Below String line - Right edge:
text | ba57e9e2-43c3-5d71-bf59-09636c1911d7 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | bac71a2d-fd7a-5376-b01c-ef0b461803ef |  | textbox | (m)
text | c575cb9f-4ec3-57c5-8d70-4b2450a4f2d0 |  | textbox | Width - Left Shoulder:
text | b26c1ecd-0fd3-5b51-b198-840cb75da9ca |  | textbox | Depth Below String line - Left edge:
text | 4dbd5b71-f4d0-57c5-a1ad-2a08f110972a |  | textbox | Depth Below String line - Left mid-lane:
text | 953797cc-bae7-51bb-a6d9-60772bef3a4e |  | textbox | Depth Below String line - Centreline:
text | 0fb033fd-c371-5b29-a1ce-9a3c1e235dfa |  | textbox | Depth Below String line - Right mid-lane:
text | b7ce021a-5cc6-594f-956b-f8fdd6da17c8 |  | textbox | Depth Below String line - Right edge:
text | 8c3894d7-5517-57c1-bc2b-2de08217cf4d |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | af8d92a3-7ab7-5dae-9391-4d75adffc78b |  | textbox | (m)
text | 0f56d08a-5a65-53ea-814a-23b3735c8039 |  | textbox | Width - Left Shoulder:
text | d45b9516-267e-5703-a402-6aafdecf8fe6 |  | textbox | Depth Below String line - Left edge:
text | 9188639b-ed99-590f-a13e-7b14fbedcc0d |  | textbox | Depth Below String line - Left mid-lane:
text | 7251606c-1972-55b5-96cb-2c1a73ec237c |  | textbox | Depth Below String line - Centreline:
text | 7b34f12d-4de1-56be-ba7e-e2d31bb1e38f |  | textbox | Depth Below String line - Right mid-lane:
text | b5aa37c5-7909-5d54-b690-2b3c7e6d4192 |  | textbox | Depth Below String line - Right edge:
text | 612f2ee6-7149-592e-9e9c-7866a9a91de0 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | 057f57f3-e08d-5e42-a035-452c48ee9c12 |  | textbox | (m)
text | 2c8c28bf-7969-5a44-8281-bad9b9d8b676 |  | textbox | Width - Left Shoulder:
text | ef38fe96-33d3-5c92-b582-89e7fe02b84a |  | textbox | Depth Below String line - Left edge:
text | 86e8667f-deb3-5cdf-b92e-820f8b5f397b |  | textbox | Depth Below String line - Left mid-lane:
text | 103aee6d-a2d4-59ee-bfc5-32fbe7fbd98a |  | textbox | Depth Below String line - Centreline:
text | 3df5444b-57a2-52e4-bc81-0d771bf00069 |  | textbox | Depth Below String line - Right mid-lane:
text | f2e70831-e8e0-553a-9e2a-17fe7f1ff6b8 |  | textbox | Depth Below String line - Right edge:
text | 1624e91d-cb3b-5259-9203-f954ebdebd17 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | 03568f72-fdbf-56ed-8c6a-c4e19e35b2f9 |  | textbox | (m)
text | b72da2a2-c9a4-5dba-8c56-ec6a8caca0be |  | textbox | Width - Left Shoulder:
text | d8a5cadf-fcf5-56f3-ae6d-aa443f525b59 |  | textbox | Depth Below String line - Left edge:
text | 9f63b3c6-6a2f-5aa3-ab57-6becdb7c8e88 |  | textbox | Depth Below String line - Left mid-lane:
text | a42d6360-5843-5e71-9469-473c15c586bc |  | textbox | Depth Below String line - Centreline:
text | a1303e46-bcd4-561f-80b1-adc7070e3041 |  | textbox | Depth Below String line - Right mid-lane:
text | 9c83d70b-cd54-59fd-aba7-0c97349f1859 |  | textbox | Depth Below String line - Right edge:
text | 7be5fb6f-88af-5545-aeb8-6db9d8c81294 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | 9e81bc47-c736-53e9-93f0-7dadab65ed00 |  | textbox | (m)
text | 243efd87-21f0-554d-b7d3-7d723a0a3504 |  | textbox | Width - Left Shoulder:
text | 018fbda3-a63c-593c-8810-239e75f7a37f |  | textbox | Depth Below String line - Left edge:
text | 14625a6c-7136-5c02-b8d2-aee09b4cb6de |  | textbox | Depth Below String line - Left mid-lane:
text | 37aceb65-0942-5f5c-8d5c-ebdd3c7480f5 |  | textbox | Depth Below String line - Centreline:
text | 52ea3e27-eb1d-57fd-a18e-904b2ee60255 |  | textbox | Depth Below String line - Right mid-lane:
text | 3c35f5be-8a4e-57b8-9fff-dbd303cacbf5 |  | textbox | Depth Below String line - Right edge:
text | 6ddd3930-edb4-5d40-a39f-20b5af16d03a |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | 890edba3-0c36-5e38-9d23-6c30d1c072ea |  | textbox | (m)
text | 14dbd725-83c1-53d0-b04a-729b711c9de7 |  | textbox | Width - Left Shoulder:
text | 310b0911-e03d-5194-8552-aae089cfe40d |  | textbox | Depth Below String line - Left edge:
text | 360dfb32-61ea-5055-89d7-a8db751292f1 |  | textbox | Depth Below String line - Left mid-lane:
text | 21b1c1c1-7940-5d4c-af00-9c77b82def79 |  | textbox | Depth Below String line - Centreline:
text | 311b562c-c911-5a09-bacc-95f2b763efc0 |  | textbox | Depth Below String line - Right mid-lane:
text | fa02bbcf-833b-5ef4-8742-60de4bf60faa |  | textbox | Depth Below String line - Right edge:
text | 829d55c6-f6be-58bd-a583-546bdb78881e |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | 88be5677-b441-58b8-ba0a-4e984cb973fa |  | textbox | (m)
text | d1145507-58a2-54c7-b068-7dd390cbbff2 |  | textbox | Width - Left Shoulder:
text | e838e1df-6a1c-5428-b165-6a38d6b1e3a8 |  | textbox | Depth Below String line - Left edge:
text | c54730fd-b623-5820-ae06-fab642df2191 |  | textbox | Depth Below String line - Left mid-lane:
text | 00caf130-f48b-539a-8810-c194c9678d0e |  | textbox | Depth Below String line - Centreline:
text | 0e55d838-089e-5e0d-aacb-20c91eda5631 |  | textbox | Depth Below String line - Right mid-lane:
text | af06f511-40c8-5818-8456-ef53e14ace1a |  | textbox | Depth Below String line - Right edge:
text | b8d9d73e-b426-5651-863d-89360886f280 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | c458f1a5-b46d-59c9-881f-2e4ca16f2904 |  | textbox | (m)
text | 41949429-3442-5400-8bfd-fe8524de644c |  | textbox | Width - Left Shoulder:
text | a9ac9056-1f55-5e67-b6ea-e7f999c4c655 |  | textbox | Depth Below String line - Left edge:
text | 6b54170f-e2d7-5017-87b7-2cb4f3b7c1ee |  | textbox | Depth Below String line - Left mid-lane:
text | 1d93064d-62d7-507f-981a-eea588244a22 |  | textbox | Depth Below String line - Centreline:
text | 42c66217-3d65-5cce-a75f-c88042f78bff |  | textbox | Depth Below String line - Right mid-lane:
text | 12f15c16-c170-5280-afe7-1a75655c85ad |  | textbox | Depth Below String line - Right edge:
text | 820b24ea-8301-569b-97ed-ac5da6a1bc99 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | 222da97f-d75d-5476-84bf-df55a18ac99b |  | textbox | (m)
text | ae082ab9-6d65-5de1-b0db-82b6a2c98293 |  | textbox | Width - Left Shoulder:
text | 99441f79-56b9-5df9-8390-438d48e7b923 |  | textbox | Depth Below String line - Left edge:
text | 052676a6-868f-5a64-93f1-908fb56d58bb |  | textbox | Depth Below String line - Left mid-lane:
text | 878684c1-5785-52e0-a4da-7569f3f86b4d |  | textbox | Depth Below String line - Centreline:
text | a20aef90-bcc5-5821-aa18-c4ae35e27baf |  | textbox | Depth Below String line - Right mid-lane:
text | 6963ba7f-ff36-5e87-a43c-149a0e00cb6f |  | textbox | Depth Below String line - Right edge:
text | 7980c9d8-a3f2-5aa4-8fc6-f6dd3bfaa0a5 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | 5e32d484-946a-53b0-9ee1-d6b8fb0d55cd |  | textbox | (m)
text | e8de5566-886c-5c28-acf9-40b9eba841f4 |  | textbox | Width - Left Shoulder:
text | 76c2f7c0-77b2-5023-9ea4-1cca22e16a63 |  | textbox | Depth Below String line - Left edge:
text | 48e892db-b03f-5d63-982f-61e41081979c |  | textbox | Depth Below String line - Left mid-lane:
text | e56b3f31-631c-50c4-b862-37760ce5e974 |  | textbox | Depth Below String line - Centreline:
text | 5d02816b-6839-519c-9311-dae27992e9e5 |  | textbox | Depth Below String line - Right mid-lane:
text | a96273fc-2b12-5b64-885e-bcec1300cfd1 |  | textbox | Depth Below String line - Right edge:
text | f466df12-ff76-5901-a4c3-f42fd7091f02 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | 68778421-d077-5ff0-b4e8-6a070bb62b0a |  | textbox | (m)
text | 4e10cf00-f100-5a00-b49c-0f804225774d |  | textbox | Width - Left Shoulder:
text | 36b91b03-f173-5647-8c8c-35d3c8d5e831 |  | textbox | Depth Below String line - Left edge:
text | 6a44d0f3-117c-5598-89d0-d588ba1226b0 |  | textbox | Depth Below String line - Left mid-lane:
text | 7e98f28a-d761-5372-b6a2-23c6babd316c |  | textbox | Depth Below String line - Centreline:
text | a531c501-77f0-532b-b9c7-8302e8a5b7eb |  | textbox | Depth Below String line - Right mid-lane:
text | 65179592-b1fc-5c05-9944-37c37e3a8b9b |  | textbox | Depth Below String line - Right edge:
text | 11bc14fa-e4d2-5bfd-9621-9d94bb5cfbbb |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | bd3ac0db-bb8e-512b-9093-5e676670a8f5 |  | textbox | (m)
text | 5a3d4ffb-5670-5f99-bfae-8253c197ddc1 |  | textbox | Width - Left Shoulder:
text | 21719b03-3594-59c3-9274-0a450e89ea00 |  | textbox | Depth Below String line - Left edge:
text | 88129c6d-de7d-5f32-88b1-00ca4c0117aa |  | textbox | Depth Below String line - Left mid-lane:
text | bd6199e1-6d9d-57fa-8400-b827f1ef2c7e |  | textbox | Depth Below String line - Centreline:
text | 664ff525-9741-5d94-b5bd-b97254784ed0 |  | textbox | Depth Below String line - Right mid-lane:
text | 033b2c27-f7da-56cc-9307-4077863798c8 |  | textbox | Depth Below String line - Right edge:
text | d265f2d9-7828-5a77-af4d-f1a3733ea096 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | 230f39ba-f88b-5721-bf4d-6adb6791ff4b |  | textbox | (m)
text | d69898be-1444-59bd-ac4e-805966ca57db |  | textbox | Width - Left Shoulder:
text | 648e3385-60e5-557b-8940-d250e6fe362e |  | textbox | Depth Below String line - Left edge:
text | ec8377d3-8fa1-508a-abd0-116e97d7e97f |  | textbox | Depth Below String line - Left mid-lane:
text | 5840e63a-bdc9-5292-83a5-b75ef606c55b |  | textbox | Depth Below String line - Centreline:
text | 2a7571bf-e8a2-59ff-8a51-804112fbd073 |  | textbox | Depth Below String line - Right mid-lane:
text | 6c456bc7-e9f8-563d-8f26-64b8a36eaf54 |  | textbox | Depth Below String line - Right edge:
text | 192fa368-d1e5-5da7-b906-4abf5c67b532 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | 12d2aaa1-1b3f-58e2-b2db-3254b0fbeee8 |  | textbox | (m)
text | 0f876d93-c92a-5527-988b-3d9ec0accc9d |  | textbox | Width - Left Shoulder:
text | da3c3033-0e36-517e-a888-54fb9489259a |  | textbox | Depth Below String line - Left edge:
text | 9187cd92-5abc-5c9d-a29c-d3ea60ae2dc8 |  | textbox | Depth Below String line - Left mid-lane:
text | 15a2adf7-5711-52bc-a41d-841aff371b0c |  | textbox | Depth Below String line - Centreline:
text | 10393f5f-65d7-582f-9523-2b0b6f0addb1 |  | textbox | Depth Below String line - Right mid-lane:
text | 87cc4cf7-d59e-5726-8267-d9958d5e8c31 |  | textbox | Depth Below String line - Right edge:
text | 13431708-35fe-5f53-8085-e49da6417d87 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 866b5e67-e0eb-5b9b-b03d-828aad6ff263 |  | textbox | (m)
text | c88f2289-675a-5b3c-ac8c-4ca883ace9c9 |  | textbox | Width - Left Shoulder:
text | 791d83fc-d40e-5d81-96f5-e93ae21c7212 |  | textbox | Depth Below String line - Left edge:
text | 3b564a85-aa86-5eee-af63-24c9a39d0493 |  | textbox | Depth Below String line - Left mid-lane:
text | 4f847f7c-2b5f-5b84-98a1-8987154063f2 |  | textbox | Depth Below String line - Centreline:
text | c12051ba-4c75-59e6-96e6-80ed1820851b |  | textbox | Depth Below String line - Right mid-lane:
text | 331eaaa6-2c3f-56c4-adbc-ca89e6ae4152 |  | textbox | Depth Below String line - Right edge:
text | c595c366-311d-5aea-991e-c16aaa0ef7aa |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (17)
text | 693d1996-e9d6-596b-bf76-f3c7eccaf7bc |  | textbox | (m)
text | cafbbbdc-dca9-5af1-a0c1-418245a38b4b |  | textbox | Width - Left Shoulder:
text | 7e82e9f7-a2ad-5ccd-addc-b6b4660464f8 |  | textbox | Depth Below String line - Left edge:
text | a5130b3c-79a8-5a8f-a4d8-63e7b2c600a5 |  | textbox | Depth Below String line - Left mid-lane:
text | 1fd73b2a-0eaf-5f1a-93a3-832a5ff7b263 |  | textbox | Depth Below String line - Centreline:
text | dcbca0b1-12b7-5c98-b7a6-95117a0e5839 |  | textbox | Depth Below String line - Right mid-lane:
text | 627c0a77-51e4-5187-9f7e-4692807a8886 |  | textbox | Depth Below String line - Right edge:
text | 2c458328-9477-5a39-afb9-618935d638eb |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (18)
text | 3f0bb176-2090-581f-a561-9352bb407156 |  | textbox | (m)
text | 999fb65c-0b17-5c7d-87aa-ba6dc6a208d3 |  | textbox | Width - Left Shoulder:
text | d1da1704-a305-5acf-812f-05377d0f9eb2 |  | textbox | Depth Below String line - Left edge:
text | e2395ddc-4a9e-5bf8-9121-d8882a90a373 |  | textbox | Depth Below String line - Left mid-lane:
text | 752b5df8-021b-5220-90dc-a05272a011ed |  | textbox | Depth Below String line - Centreline:
text | 08c09bf7-2942-52bc-860e-70cdb5bc4b98 |  | textbox | Depth Below String line - Right mid-lane:
text | 46f085c6-aabe-58d2-817e-63a86b3294b5 |  | textbox | Depth Below String line - Right edge:
text | 3c0ddbb6-333c-53bc-8103-8f668ea0676a |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (19)
text | 29cbc3e4-6af8-54ba-abf8-083f861a5d78 |  | textbox | (m)
text | 891300e4-59d9-554b-bc71-63e820352367 |  | textbox | Width - Left Shoulder:
text | 57a061e7-b08a-577e-a7bd-53fa7c0c4137 |  | textbox | Depth Below String line - Left edge:
text | a25d8233-abe0-5897-8163-1f9f1d89f02f |  | textbox | Depth Below String line - Left mid-lane:
text | 6931bf3e-8a3d-550e-8443-e23299414d55 |  | textbox | Depth Below String line - Centreline:
text | 4b12b8f2-a4ce-53e5-a860-f0b0d10aee73 |  | textbox | Depth Below String line - Right mid-lane:
text | 53cfae27-966c-5998-bbfa-5a28c421a945 |  | textbox | Depth Below String line - Right edge:
text | 5dee7b72-ad61-5a77-aacb-8d6e93fbaf49 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (20)
text | 8ed07a57-e5a0-5f2d-a402-c2a7e5fe851a |  | textbox | (m)
text | e86a5584-0077-531b-827e-f826e20fe833 |  | textbox | Width - Left Shoulder:
text | 41695aaf-feb9-590c-89a5-d6f57fb4ddba |  | textbox | Depth Below String line - Left edge:
text | 63387926-875e-5e3f-82fd-4ee67578b636 |  | textbox | Depth Below String line - Left mid-lane:
text | d01d7904-1019-52ee-aa32-1256cf17cbe5 |  | textbox | Depth Below String line - Centreline:
text | f2952d48-6dbf-51b6-834b-ecd16cbd3f5a |  | textbox | Depth Below String line - Right mid-lane:
text | 9cc42e13-8d4f-552c-8b2e-2d9c3ed8fa42 |  | textbox | Depth Below String line - Right edge:
text | 74f29bf2-c6ba-5781-b640-3e66947af4ec |  | textbox | Width - Right shoulder:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 6b1f1326-e7d6-5b48-820a-a6aa22290ec4 |  | textbox | Site Engineer - Name:
text | cc0962b8-7969-5ce2-bd6b-2debc96f98e2 |  | textbox | Site Engineer - Date:
text | 7153d825-7488-5ea7-99de-1e5434618c66 |  | textbox | CPS Engineer - Name:
text | 5d250e0c-0dc9-5dd5-ba64-b6573b887719 |  | textbox | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4048 - ITS Duct Installation |  |  |  |  | Yes | CS-4048 - ITS Duct Installation | 1a549985-5f6b-44a3-b235-636801545d8e
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 15db25fc-f486-5a1b-be5f-252ba200a3de |  | textbox | Project No.
text | 90b69b3e-a30d-5410-bf5f-379fce618869 |  | textbox | Drawing No (& Rev No):
text | 32ef01b7-4eb8-5e3d-a2ca-1cdd774d1a69 |  | textbox | CH Start:
text | 09f9f6c8-ab29-51f8-b308-58044e4533c5 |  | textbox | CH Finish:
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Pull Pit/ intermediate line points set out by surveyor
text | 218a05a3-bd5c-5fb1-b51e-ab0f58fb22fc |  | textbox | Initials:
date | 4398a1e4-c066-59ae-8ec0-2b58c77ba286 |  | date | Date:
label | 09cecd25-b153-5e5d-9235-bbde036735f0 |  | note | Comments: Survey Receipt
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | fad993ec-4602-5381-8a6c-d1beb2264903 |  | textbox | Initials:
date | 513a5ca2-8c02-5c2b-ae34-f971606e7fe1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench must be made safe before any person may enter the trench
text | 3b8241ba-4a56-51bd-9d0c-eb293f36c4e9 |  | textbox | Initials:
date | 34090621-1a15-5031-be92-727d9e51a8b8 |  | date | Date:
label | 5ded4b57-dbb3-5948-9d51-a970bd3d6462 |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | Base of trench is clean and inspected by engineer
text | 203abf17-aa66-5da0-9680-4f9d4e40b65c |  | textbox | Initials:
date | de5d27c4-b4b4-5b51-92f9-0cbcc498a7eb |  | date | Date:
label | c057ce96-e6c8-51ba-a069-4ee38bd900b1 |  | note | Comments: Base to be as flat as possible
checkpoint-status |  |  | checkpoint | Bedding material to be placed in layers 100mm thick
text | 276e6d70-8022-57dd-b3da-a338f5e67bbe |  | textbox | Initials:
date | 6958769d-31fc-5bab-8046-0744f339804e |  | date | Date:
label | bc1d36d3-f89c-583e-b457-0fba5a39e1a9 |  | note | Comments: Lab test 85% of MDD (CIV=8) or 95% of MDD under carriageway, Frequency 1/20m
checkpoint-status |  |  | checkpoint | Glue ducts together and lower carefully into trench.
text | a7bf8176-7647-5594-b314-8bbd03e09f14 |  | textbox | Initials:
date | 1cf3568d-d7be-5303-a90c-d68d9e5e4466 |  | date | Date:
label | 1d537949-4943-5ffa-be5b-241583171b8e |  | note | Comments: All open ends shall be taped up to prevent material entering
checkpoint-status |  |  | checkpoint | Guide wire installed in ducts before lowered into the trench
text | fe742993-b284-5c30-8ac5-97ab3ab9bfb0 |  | textbox | Initials:
date | 79faf838-587f-55d8-a0a9-b8577e54e988 |  | date | Date:
checkpoint-status |  |  | checkpoint | As built survey every 20m
text | f9df219b-183f-5825-832f-951c3f2be94d |  | textbox | Initials:
date | d33e2346-e0bc-508d-b375-3a08708ef3a9 |  | date | Date:
label | c5f6b3ec-0706-5f4d-8b33-419a09cca933 |  | note | Comments: Must pick up all changes in direction
checkpoint-status |  |  | checkpoint | Ensure 50mm gap between ducts sitting in the base of trench
text | 55c552d5-f976-5bb2-aeb8-67eeaccf6f23 |  | textbox | Initials:
date | 1e90c513-2af2-5be7-83b0-dd283544c181 |  | date | Date:
label | 3347cd57-3014-54f3-aa04-20cbbbbe9ec1 |  | note | Comments: Check gaps before backfilling
checkpoint-status |  |  | checkpoint | Ensure backfill material is suitable and un-contaminated. Compacted and tested in 200mm lifts
text | fe7a8fd8-708d-500c-a285-bc85973d6697 |  | textbox | Initials:
date | 025252b5-bbe2-5f9a-a03f-c9e5821ba28a |  | date | Date:
label | db9d65e6-b3c0-518b-ba1f-9d7633fcd692 |  | note | Comments: Footpath/Berm - Backfill with excavated material. CIV 8 required.
label | f098bc85-1c72-5323-a959-a4192686d44b |  | note | ○ Carriageway – Hardfill (GAP65) 95% of MDD
checkpoint-status |  |  | checkpoint | Warning Tape to be installed 200mm above the top ducts
text | b660a1ce-ce0c-5aff-b324-f1d5f6aa68d7 |  | textbox | Initials:
date | 36bb7bf3-da50-5b93-8876-3a45066a0d2c |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 8227cd1c-602f-5d40-b5fd-3bff248f1060 |  | textbox | Name:
text | c2f86c36-e59e-5595-9845-6b649febe134 |  | textbox | Position:
date | d367a5de-c8f3-5861-918f-6846efe35d0b |  | date | Date:
holdpoint |  |  | signoff | Sign:
checkpoint-no-status |  |  | checkpoint | Trench Cross Section
text | 006a33ba-3de5-5da9-bb61-51be0d0b26fb |  | textbox | H |  |  | (m)
text | 91b98746-5041-57cb-b55f-7eceab5588ee |  | textbox | L |  |  | (m)
text | c49b045f-fd9a-598b-a088-421d48c84fb0 |  | textbox | Backfill: Warning Tape 200mm above top of duct
text | a96ada8e-eab7-5f00-8e45-77baa3ee2b98 |  | textbox | Backfill Material Type & Source
text | 7b6266d9-0808-5717-9e41-5c2dfff7c7fe |  | textbox | Bedding layer Material Type & Source
checklist-sectioned |  |  | checklist | CS-4040 - Concrete Inspection Record |  |  |  |  | Yes | CS-4040 - Concrete Inspection Record | 1fd0b5fc-6a9f-4fe4-a5f9-1d145bdb021e
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Concrete Inspection Record
text | 027effd2-a858-5c79-b391-70245ee53b6a |  | textbox | Location / Description of Pour:
text | c33ebd8b-3f21-5e02-9e3f-15f3f6a927ed |  | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
text | 83fd61e8-2217-5007-97f4-0b105068cfec |  | textbox | Concrete Grade |  |  | MPa
text | 53c84e75-f898-520a-89bf-3d39c16b40a4 |  | textbox | Concrete Quantity |  |  | M3
text | 116cee17-b98d-5522-ae29-6ec1414d7853 |  | textbox | Pour No.:
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Adequately braced and supported
checkpoint-status |  |  | checkpoint | Grout tight
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Formed surfaces straight
checkpoint-status |  |  | checkpoint | Major penetrations located
checkpoint-status |  |  | checkpoint | Embedded items located
checkpoint-status |  |  | checkpoint | Specified surface finish:
checkpoint-status |  |  | checkpoint | Adequate seating Pre Cast units
checkpoint-status |  |  | checkpoint | Permit to Load Obtained
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content and size
checkpoint-status |  |  | checkpoint | Grade markings:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
checkpoint-status |  |  | checkpoint | Rigidity and cover
checkpoint-status |  |  | checkpoint | Clean steel
checkpoint-status |  |  | checkpoint | Lap location and lengths
checkpoint-status |  |  | checkpoint | Starters/dowels correctly located
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Roughened
checkpoint-status |  |  | checkpoint | Clean
checkpoint-status |  |  | checkpoint | Water bar placed if specified
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Mix ordered:
text | c138aba5-1210-57e6-9531-6f9c4ab1e045 |  | textbox | Mix ordered:
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
checkpoint-status |  |  | checkpoint | CPS Engineer notified (48)
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Mix delivered:
text | 6bbcf374-65ad-5b0e-99cb-f6b026e01162 |  | textbox | Mix delivered:
checkpoint-status |  |  | checkpoint | Slump/flow Target:
text | 8004fab2-3d96-5997-8a45-51993ac164aa |  | textbox | Slump/flow Target:
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
checkpoint-status |  |  | checkpoint | Surface to required finish eg U2, U4
text | b9f0a7e8-8780-5910-8254-9634668aba3a |  | textbox | Surface finish achieved:
checkpoint-status |  |  | checkpoint | Retarder applied at end of the pour
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
text | 40a167be-06a8-5119-a980-73d895e50ffd |  | textbox | Pour Start Time:
text | 423d4eeb-62fe-52cd-84c1-adde3c24f531 |  | textbox | Pour Complete Time:
text | 2e17bc70-26f5-543f-965f-5ed8fef066ef |  | textbox | Volume Placed:
checkpoint-no-status |  |  | checkpoint | POUR ISSUES – Add as comments (e.g. formwork failure)
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Curing correctly carried out
text | 0f526c77-d4f7-594b-9068-31ba2162602e |  | textbox | Concrete Strength for Striking:
text | df14a079-76d3-503d-93ba-1a22deb0cbf1 |  | textbox | Concrete Strength for backfilling:
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
label | 1af75cac-b272-55ed-9880-2c70c6a93956 |  | note | CPS Engineer Inspected.
checkpoint-status |  |  | checkpoint | As-Built complete
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 48be283f-368f-5d16-96f4-5c611bee1fe6 |  | textbox | Site Engineer:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  | Yes | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails) | 2973051b-ac2f-47a6-b7ed-f70f24c0cc9f
checkpoint-status |  |  | checkpoint | Project Site reps.
text | adc2d7bb-c800-512c-83e0-86d86b07ca5a |  | textbox | CPS Eng.
text | f01a95cb-d428-5e76-abb4-f53c19d6f711 |  | textbox | Site Engineer
text | 0567ecde-61e4-553b-93df-9b42e32f838d |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Clearing & Earthworks
label | 23045c02-4b03-5193-99e9-83545db693d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ca7edc54-3203-5656-8c5e-93338edae1e2 |  | note | Detail - Before setout of the reinforced slope method all vegetation clearance & any bulk earthworks is to be completed
label | d4849d8d-0ef8-5e68-b2c5-41c5e7e751f2 |  | note | Frequency - Prior to commencement
label | 72410357-faf3-563e-a9e2-4e2527e6d1c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 55e7b9c8-1d70-5d09-8bfe-1decce88d8fe |  | note | Conformance Criteria - QA-6002 - Tree Felling & Vegetation Clearance
label | 13dbaad5-65d6-5d13-b263-0b1af59b7495 |  | note | Records - QA-6002 Process Control Plan Tree Felling & Vegn Clearance Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 833a91b5-1bdc-5b8c-b3c9-6128386f45f3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bc433580-ef47-5403-bbf7-79b2de7e66c5 |  | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | 0b7f48e3-6b2c-5f3c-b3ad-e01bb83fa111 |  | note | Frequency - Prior to commencement
label | e283ecb4-706c-5936-a250-469ea69af410 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b2d9dee5-c495-574e-9644-17c6257ebd85 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | b27c76d2-43de-5b86-a2cb-562aa76ea3f4 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 6ff4d691-2960-579f-af1a-1973732cf992 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 89134ea2-7f2e-5a76-bedb-839e263b657b |  | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | b559dbab-d00e-5f4b-8e17-761285ba5f1e |  | note | Frequency - Prior to commencement
label | 769abb09-b57f-5af4-aa20-1fe1c25a4007 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0e00a9ee-4c03-5218-83f6-cee3e7fe3778 |  | note | Records - Delivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | ce325a08-8b89-5620-9a05-3e891e198000 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1f1b392b-b987-5b6e-b613-63ad6534f985 |  | note | Detail - Shotcrete Mix Design & Work Method Statement approved by Design Engineer
label | 523e76b4-2a52-5cc0-948f-af830dece90e |  | note | Frequency - Prior to commencement
label | 90344746-c33d-5618-aff3-62f2757b9b9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 24a5b1b6-63d9-5dc0-8b56-a26385009068 |  | note | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | 9ef673f0-56d7-5ad2-b440-fd5522c90a78 |  | note | Records - Lab Test Results/ NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | 32920255-3e0a-5ba9-8550-07ac4411336d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7b68ec88-0ed4-5a2b-8e26-0c489968a427 |  | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | a0ecf37c-420e-5dd6-bb68-2d688d6ae048 |  | note | Frequency - Prior to commencement
label | 01b6073d-5883-5dc3-bf3b-d98d9999d583 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7d8bd241-3d7f-5a3f-b471-303045472526 |  | note | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | fba1362f-2b72-5b8f-a2a6-5485b4b4c86f |  | note | Records - Lab Test Results/ NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Working Bench
label | 77433fc4-ab79-536d-aa01-409812cf4fab |  | note | ACTION (Hold, Monitor, Witness) - H
label | 698e072e-573a-5f3c-9c59-a1f76367e1d0 |  | note | Detail - Bench to be 2m of less - the top of the row not to be above 1.5m above the bench
label | a0c1a829-dc1b-5581-a12b-d089386175e2 |  | note | Frequency - Prior to commencement
label | af8f838b-ab36-5911-975e-1541d7dfd84f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 8ecb8cca-8366-58e4-8939-42088d02044c |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Trial installation of Bolts/Nails
label | 16c70927-b1d1-564e-8839-2ee12497d77a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 97748ca2-3524-5286-bf37-a415d803dc16 |  | note | Detail - Drill hole, install Bolt/Nail, install Grout
label | ea2c60b1-f906-5a75-9027-70f65c41ecb7 |  | note | Frequency - Test
label | 1b70be46-e5f9-5dc7-981a-dbb94fc7c034 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 409cd064-a79f-5f8a-a79e-02768794c682 |  | note | Records - Lab Test Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 -
label | c1589cef-34bf-558e-97d9-2b781d52e88e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4e577a18-1e50-5c12-ab1a-4e5878bef551 |  | note | Detail - Test after a 7 day period. Load up to the specified requirements with the Design Engineer overseeing proceedings
label | 181f3c03-e18b-5ccd-a52f-6cbbb9d5872a |  | note | Frequency - Test
label | b3a84ce2-9feb-59d2-ba15-3e0d380b021e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | 6ca1098d-bb8d-5083-853b-99c89870c667 |  | note | Conformance Criteria - Design Engineer to observe testing and provide feedback on a NTC
label | 15d5b9db-5253-57aa-843d-54a3bdfa2bd9 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Installation of Bolts/Nails on the created working bench
label | 7c9cfb4d-91c6-5175-b513-994e4650b0d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 58ca7115-5c95-585f-abb3-84a6ddd0fdd6 |  | note | Detail - Drill holes as specified
label | 7e9b3031-df6b-5f7e-aa7a-e6439a417a25 |  | note | Frequency - During Construction
label | 220d9e49-56ad-53f5-bfe9-2f7c9377957a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | c63e125d-df6a-5c5e-a99e-c91de9ef89cc |  | note | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | bf741543-e11b-5985-8199-69e00bee9d5e |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 63998613-a1bf-5580-bf97-7a601084a097 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 83838ba6-e6b2-501d-b1e6-21cdb81fb0bf |  | note | Detail - Install Bolts/Nails as specified
label | 1817a6dc-20b8-5d1c-b690-8bad13eb4e80 |  | note | Frequency - During Construction
label | ac896bf7-d09c-5dcf-a7f4-0bb16e708731 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 61401103-b89a-50be-9e9d-ed3b45151ef5 |  | note | Conformance Criteria - Ensure lengths are that specified on the drawings
label | 0646309f-2b57-547c-91fe-406b017ab953 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 -
label | ea2239bb-f78a-5b74-ae61-9f628df3cdb5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1381ae36-5570-50a8-9abd-88a50f908dcc |  | note | Detail - Install Grout - take sample of each truck load delivered to site
label | 00deb1bc-f9ce-5e23-b234-491d921d4c2e |  | note | Frequency - During Construction
label | 7af7abb6-40ee-556f-ba51-f10cb4523fc1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | c5f03aaf-35a8-5ae1-8a74-c9efe38afe6e |  | note | Conformance Criteria - Compression cylinders to be tested at Lab
label | 3db661bf-30bd-5809-9f70-4a8509126b48 |  | note | Records - Lab Test Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 1fdbdfd0-fbb1-5d21-91ca-8d4f40216c8a |  | note | ACTION (Hold, Monitor, Witness) - H
label | a97e7580-5581-5cec-9849-7a6c04beeb9c |  | note | Detail - Install Bolts/Nails washers & nuts
label | 9f72edd1-cd08-5b69-928a-c6e92a7d9a2a |  | note | Frequency - After Construction
label | 8432ab63-a243-5324-a27f-839e19c31840 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 63e1c527-80b0-5989-892d-80fb0b5a9c8b |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | d919dae4-5e00-5dd6-b0e2-1c6da81b43ce |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 -
label | 3b0b39bf-336d-5c12-b7e1-de66ea6166b0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 199cd3b0-a45b-52f0-9dd9-35ac32221d3f |  | note | Detail - Testing of Bolts/Nails - after 7 days when the Grout strength has reached 20Mpa
label | c86e1f71-07f3-5e42-bbee-d6ee59c576b5 |  | note | Frequency - After Construction
label | 514fcc31-b1b0-53f7-84b1-6665d9d7c310 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 88c01932-c6a3-5309-b424-343f18a66323 |  | note | Conformance Criteria - Load testing - Design Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | 577b3552-b9ce-5af0-873b-cde3135c23d4 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 -
label | 00f549e3-719c-5975-a327-11339edc64a8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a660e955-575b-5a2c-93c0-a4eb9952c895 |  | note | Detail - Final inspection of Design Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | 302dc57e-0801-5d9b-a80a-d6c45b2b01bb |  | note | Frequency - After Construction
label | 83236721-6699-5a0d-a99b-b3e9e1f50f6f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 629fd0de-79d8-5ca5-b363-eee3a0c6c079 |  | note | Conformance Criteria - Design Engineer to give approval via a NTC
label | 8bd80881-78d2-552f-98a7-9412da73d95d |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 -
label | b201d15d-8f44-590e-a893-4372480e858f |  | note | ACTION (Hold, Monitor, Witness) - W
label | ea5088e2-cf44-54b5-a4fa-0d248ddcd919 |  | note | Detail - Remove working bench and continue with same process as above
label | 1fb82a41-9793-5eb6-9dca-75b20b6aa722 |  | note | Frequency - During Construction
label | 54a1c6c5-820f-5853-865f-ab820e35127e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ebcd57ab-30cb-5503-bf7a-b5f67031e15e |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Shotcreting
label | b6a6992c-fcd9-5295-92ae-0cab27ff7ff9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7b6944f3-8955-529f-aee6-8704400b5c4f |  | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | 213b73ed-8246-5d6f-b2d6-dac0d05cb4c5 |  | note | Frequency - During Construction
label | 8367c986-b36c-55bc-b7a9-4e101ff76f95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c5f43252-b1e9-5beb-9d26-b8c54dd10ee0 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 -
label | fd2237f0-f1ab-52f1-a4dd-647c026d7737 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3298b6b0-b027-5cf7-99c7-823cb02a0796 |  | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm
label | 18cd06e5-3a31-5149-89a8-0ac506559135 |  | note | Frequency - During Construction
label | 9b6e6c82-9339-566a-986e-daada0fe31a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 18 -
label | c7506c94-300a-5f53-85d6-0f122f1fd15f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 054fb5e8-1f8e-5ff9-a05e-78781096ac67 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | 461b4f2d-f7b2-57a5-b60a-4b43901bdca0 |  | note | Frequency - After Construction
label | b37f88e5-f0d9-576d-ab6b-70f92d2c6e0a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 320b8cdc-4d22-5ee8-afa4-22a70f449a63 |  | note | Records - Lab Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 -
label | ae772ed5-8361-5e87-a3a8-f9475afc98e8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3ff10b89-6216-56d8-ae78-501f5c49b64f |  | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | a6deb2e8-2672-5b89-b616-07ec06c1e663 |  | note | Frequency - After Construction
label | 6caaa008-bee6-50ef-b58a-5470cd985c90 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 460a35b1-c33c-523e-96b9-fdca71345428 |  | note | Conformance Criteria - Surface Inspected by Design Engineer & Approval given to carry on with works
label | f0a6042a-e0d0-5a82-acdf-4de97609fad2 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Post Construction Survey
label | b7f90042-5124-519c-8182-fdb9843ca7e7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 90f00afe-8a84-553a-aa29-076b644e03a0 |  | note | Detail - Survey final position of bolts for as-built purposes
label | 00efc7ae-7dda-5162-b3ff-63b8261f858a |  | note | Frequency - At completion of Lot
label | afc0d8c6-eeca-50ae-9412-aac05991a0f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ea5d8dc8-a59e-5ed4-8208-d6a7a5df5e2f |  | note | Conformance Criteria - Survey report complete and conforms to specification
label | 4be1aa77-06ab-5b6d-ae8d-92d1ee42c4e7 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 - Lot Number QA File
label | 4eb50550-6bd0-59af-a952-2ddfe545fe1c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 35634f66-7664-578f-bad3-ca07da0eee02 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 7e2c3837-f6ce-54ab-becd-b756a5668f41 |  | note | Frequency - At completion of Lot
label | 5db72c7b-cf20-5c22-a992-d43416e091a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 071fe9c3-4e43-5997-9763-a29bc7e21b94 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 40806281-7e00-538b-80da-3951f093cb59 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 22 -
label | ff2aa32b-d408-5c44-a449-501c156feb6f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4cf26b39-6c69-5f05-bc44-02c143242373 |  | note | Detail - All subcontractor documentation to be included in QA file
label | 9258c175-cf32-5767-8b5b-7f051d047bc2 |  | note | Frequency - At completion of Lot
label | 919611a3-779e-56c3-8895-943277e8d532 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 48fe937d-7be7-5d63-9652-f5581c273668 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 23 - As-built
label | d0b8e8dd-e33a-5819-a8aa-9105f1e57a4c |  | note | ACTION (Hold, Monitor, Witness) - H
label | b930315c-cb09-55de-b720-9fdf0033d973 |  | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | e165d0f3-fc85-5a63-bf81-ad08d5102530 |  | note | Frequency - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | 7c8cf3a1-1a10-5605-be73-8ff7f6cf36e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 2cf75d17-b4c0-549e-bbfd-ab412cb3b5c1 |  | note | Records - Survey receipts, As-built plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | CS-4105 - Road Lighting & Cable Installation Record |  |  |  |  | Yes | CS-4105 - Road Lighting & Cable Installation Record | 2aca6d17-ab11-471d-b24e-d75aa9449a80
checkpoint-no-status |  |  | checkpoint | Road Lighting Trench & Cable Installation Record
text | f174cabc-e960-5aad-b42b-56caffad2aa1 |  | textbox | Project No.
text | 578c2c10-63e4-5abc-b095-aa3b4b397ec9 |  | textbox | Drg No:
text | aa6b8374-3aef-5c22-a896-ec6e2146284b |  | textbox | Rev No:
text | a6373b20-b0bd-5a67-8eda-cb7dfd4736f3 |  | textbox | Chainage/Road Light No.:
checkpoint-status |  |  | checkpoint | Road Light Locations set out by Surveyor.
text | e8a61bea-bf20-503e-beb1-9bde5fdbabef |  | textbox | Initials:
date | f138a6f6-fd44-5021-bbd6-291f053a0cfa |  | date | Date:
label | cb47faae-a6a7-5155-a31d-a9fd05db7ec7 |  | note | Comments: Consistency with Construction Drawing, Details and Notes.
checkpoint-status |  |  | checkpoint | Pothole existing services that cross the line of the trench.
text | 583e9f28-a5c8-5a72-8324-9b8934852f34 |  | textbox | Initials:
date | 5822879b-1844-5047-adde-6053ac8a06fc |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to dig obtained and underground services marked out.
text | 889e1bc4-a54b-54bc-b96e-9632f13ed6ce |  | textbox | Initials:
date | 25db49bb-e7ce-5248-9161-14d660eeb401 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench location marked out with offset pegs and checked that it clears other services.
text | adea30a0-d95c-59d4-835a-dc2ebe2fa9cb |  | textbox | Initials:
date | f67ee27e-651a-536b-9d67-cfc40a9c3554 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect trench and ensure it is required depth below Ground level and free from obstruction.
text | 2e9832f4-4bb0-5e3f-b963-e27293597bd0 |  | textbox | Initials:
date | 94a0ed6c-0fc8-55a4-a9db-5bd632942f49 |  | date | Date:
label | dad22563-4f58-594c-85dd-c86a4c0e98fe |  | note | Comments: 600mm below open areas and under footpaths, 900m under roadways and free from obstruction
checkpoint-status |  |  | checkpoint | Ensure the correct cable is being placed in the trench and check if direct buried or duct required.
text | 5c10e600-8f8d-5468-b3ed-dc10e95c64da |  | textbox | Initials:
date | 1a371c59-af1b-5b78-b660-8580326f5c7d |  | date | Date:
label | c303880d-71bc-5b03-9398-9a779cfe561e |  | note | Comments: Ducting is required under roadways, within bridges and when entering concrete foundations
checkpoint-status |  |  | checkpoint | Ensure cable ducts (where required) are clear of obstructions, fitted with Draw Wires and are easily accessible for cable drawing.
text | fa8f4eac-eeb0-560e-925a-90d273526048 |  | textbox | Initials:
date | dc01f48f-6623-5b9c-af18-c452c971a0b0 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure cables are laid without sharp kinks and loops for connection are provided at Pole locations.
text | a36c7395-53e0-5ceb-ab43-4f61acbe173d |  | textbox | Initials:
date | a4ea7962-260a-560a-98a6-f36c6558bb13 |  | date | Date:
label | 1f14eff6-9335-5503-98c2-1d4744909c62 |  | note | Comments: 3m loop on continuous cable, 1.5m loop at cable ends
checkpoint-status |  |  | checkpoint | As built survey Cable in the trench. Ensure the As Built information includes the number and the type of cables and circuit numbers
text | 425297b7-499b-598e-9ba5-594d39bf3307 |  | textbox | Initials:
date | 48c15b3e-acee-59da-9815-b6654dd84c09 |  | date | Date:
checkpoint-status |  |  | checkpoint | Cables buried directly into the ground shall be enclosed.
text | 9f1d8ac8-b883-583e-8501-0e8c96212601 |  | textbox | Initials:
date | 96d8c681-3d02-5847-b90a-74520b3571a8 |  | date | Date:
label | d7c94b85-d0e4-5b2c-ac01-628626e930a2 |  | note | Comments: Min. 50mm of Sand on all sides of the cables or Soil which passed through sieve no greater than 10mm
checkpoint-status |  |  | checkpoint | Ensure trench is backfilled and compacted by hand ramming for the first two layers, followed by power consolidation.
text | 0750cf9a-2780-574a-ac79-f0e4e267fcf0 |  | textbox | Initials:
date | 23213325-c6cf-59ca-b798-0fec99985ffc |  | date | Date:
label | 27a4e058-e77b-5d73-b1e1-6936ac010576 |  | note | Comments: Depth of cover:
label | 2f186851-9c6e-5ff5-8c9f-5045096fad69 |  | note | ○ Open areas or under footpaths = 600mm Under roadways = 900mm
label | 465af57d-4f6a-56c9-babe-b7fd2e1378a6 |  | note | ○ Check compaction with Clegg hammer every 20m
checkpoint-status |  |  | checkpoint | Ensure 100mm Wide Orange Polythene Warning Tape is installed.
text | a5a3eef6-9acb-507b-b272-56186950c1b4 |  | textbox | Initials:
date | a0bc3304-aac3-5836-9344-f91b2d0044de |  | date | Date:
label | 6d559a6e-05c5-5de3-a5e8-64ce3cdcb9e3 |  | note | Comments: 150mm below finished surface of trench.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 00a87e9b-8479-5d09-9413-7b20593af554 |  | note | Position: Site Engineer
text | 93b7d370-a484-5093-aad6-c62bea594a06 |  | textbox | Site Engineer - Name:
date | 5cb0407a-8d49-5b4d-9c72-a25e55fe2744 |  | date | Site Engineer - Date:
label | 0af163aa-3e31-59b8-97fa-c77a35f03667 |  | note | Position: CPS Engineer
text | 7de82334-31cb-502e-8f45-f82eec613548 |  | textbox | CPS Engineer - Name:
date | 263988f8-8d1a-5f2b-8cef-ab402c8b87aa |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | CS-4029 - Concrete Pump - Permit to Pump |  |  |  |  | Yes | CS-4029 - Concrete Pump - Permit to Pump | 2ad94da0-1a88-4ed5-adf0-6bcce63c5894
checkpoint-no-status |  |  | checkpoint | Concrete Pump - Permit to Pump
text | fe638e5f-553d-5ed7-9338-905bf9dd1f8f |  | textbox | Project No.:
text | 88d8c831-dd4d-53a2-ad41-6b524c0e197c |  | textbox | Location:
checkpoint-status |  |  | checkpoint | Pump Operator Pre-start Checks Completed
text | 6cda8204-4064-5c72-a9ad-d9c93a9fb16a |  | textbox | Initial:
date | d5dd19da-37d6-5e57-b943-f111aaea19cf |  | date | Date:
checkpoint-status |  |  | checkpoint | Pump set up level
text | b1064950-fa30-51a6-a9c2-b984f57c9c08 |  | textbox | Initial:
date | 4f395a0d-bf82-588c-adc4-8da186b0a24e |  | date | Date:
checkpoint-status |  |  | checkpoint | Steel delivery line in good condition
text | ce49c8c0-bbfe-528d-829e-00ddd6ecd070 |  | textbox | Initial:
date | 35dd2998-6786-505e-81f6-c08283c9e401 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rubber Delivery hose in good condition
text | 6bd614f1-b369-52eb-98d7-3d2a0a52eec3 |  | textbox | Initial:
date | 50f4ea99-149b-5085-885d-1d99ca2b08ed |  | date | Date:
checkpoint-status |  |  | checkpoint | Delivery Line Adequately Supported
text | c15e40df-5474-5f74-8c8d-2789dd8903e5 |  | textbox | Initial:
date | 19fd51d6-4957-558e-935e-1d551c0a0f61 |  | date | Date:
checkpoint-status |  |  | checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
text | ab21c98a-b41f-5263-bee1-4875274c3ecc |  | textbox | Initial:
date | 71605f7b-9f82-5d62-8acc-4c5721ed9be1 |  | date | Date:
checkpoint-status |  |  | checkpoint | All radios are working satisfactorily and communication checks have been carried out
text | 38c25f13-d70a-5ae1-9292-1085b48c37a3 |  | textbox | Initial:
date | 90c74837-8cc7-59d5-8d2f-dfe1064057a2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concreting Crew briefed on Work Instruction
text | 46cd3090-9681-540b-96a3-f0ce9ff4002a |  | textbox | Initial:
date | b1132919-7f60-50fe-b3a8-abeb7330ab62 |  | date | Date:
checkpoint-status |  |  | checkpoint | All crew have correct PPE, skin fully covered (arms and legs)
text | 0db91b63-9ace-5240-ada2-32f7b382ed04 |  | textbox | Initial:
date | eda65675-542d-588e-9228-f3366828ceef |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Pump
radio | a55c0917-91a8-59e6-b5dc-a263027525c0 |  | radio | Permit to Pump – Issued / Rejected | Issued,Rejected
label | 70fb9f41-17e2-5e52-bd74-10dcf3b392f2 |  | note | Project Engineer / Construction Manager / Superintendent
text | 1b45dcc4-4009-5337-b026-2529fe1097f2 |  | textbox | Name:
date | df638b6a-2eb6-5174-9af9-cf58d1191867 |  | date | Date:
holdpoint |  |  | signoff | Signed:
checkpoint-status |  |  | checkpoint | Prior to Cleaning Lines
label | d85ff6e0-0a60-5fc6-951a-3757d82caab1 |  | note | Reducer and Hose removed
checkpoint-status |  |  | checkpoint | Permit to Clean Lines
radio | e2763b59-5f98-500d-b199-b3da84745ba5 |  | radio | Permit to Clean Lines – Issued/Rejected | Issued,Rejected
label | 89b6ac59-ed4a-544b-af5c-e9d55a258ee4 |  | note | Project Engineer / Construction Manager / Superintendent
text | 8917cbda-caad-575d-908b-d80c95f91036 |  | textbox | Name:
date | 6c91ff8b-d176-5b76-9317-a40845be4332 |  | date | Date:
holdpoint |  |  | signoff | Signed:
checklist-sectioned |  |  | checklist | CS-4044 - Roundabout Kerb Construction Record |  |  |  |  | Yes | CS-4044 - Roundabout Kerb Construction Record | 380ee95a-0b21-48b2-a288-3ba86d6a6a05
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | a3e0e624-9144-5edd-8963-4de2330c066b |  | textbox | Project No:
text | 7cf8753f-b4fc-50cd-a870-aa793a1526d3 |  | textbox | Description of Pour:
text | e0bbbc77-96c2-5cf8-ba3a-dd14fed7ddf8 |  | textbox | Concrete Qty:
text | 9ef81936-ffd3-5770-aa10-41d893aba79b |  | textbox | Kerb Type & Dimensions:
text | f0574407-7fce-5e25-85e3-bb3f0c369cfb |  | textbox | Concrete Grade: |  |  | Mpa
text | 96a13ef4-7872-5fd9-a303-0641b05bc919 |  | textbox | Weather conditions:
text | f563f56b-bfe7-5f5f-b636-fd86a7d83051 |  | textbox | Dwg No/Rev:
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | 1. Cleaned and oiled
text | f75e98ea-910c-5592-ae48-52f070f9d3fe |  | textbox | Initials:
date | a99bfecd-7c4a-596a-bc47-759252a5c37e |  | date | Date:
checkpoint-status |  |  | checkpoint | 2. Correct profile/dimensions for Kerb Type
text | a4a1bc09-638f-52f9-9703-0ffdbad53c73 |  | textbox | Initials:
date | ac758409-b5e6-535d-833a-23314bcda7cd |  | date | Date:
checkpoint-group |  |  | section | Subgrade
checkpoint-status |  |  | checkpoint | 3. Ensure subgrade construction is complete and suitable for kerb
text | bdd91e35-6e8a-5b03-ad9f-731e03b0dea5 |  | textbox | Initials:
date | f73979a6-431d-5d80-b4b6-6886712b9423 |  | date | Date:
checkpoint-status |  |  | checkpoint | 4. Cesspit protection in place
text | 5a5f931f-2a42-5caf-ae7b-a2e42c7bbb7b |  | textbox | Initials:
date | ba7c1924-2a44-533f-b5a5-2f72b73f55bf |  | date | Date:
checkpoint-group |  |  | section | Survey set out
checkpoint-status |  |  | checkpoint | 5. Check survey set out
text | 7770cda7-0c09-5116-90bf-d19c1b738c2a |  | textbox | Initials:
date | 6f47ef0d-c025-55ef-ab7c-74d720dd5662 |  | date | Date:
checkpoint-status |  |  | checkpoint | 6. Check subcontractors string lines for machine
text | dbe5e7b7-6a13-52f7-9710-5f49b8bd4aee |  | textbox | Initials:
date | 87f998ce-a3c2-53aa-b807-2456f56ebdd0 |  | date | Date:
checkpoint-status |  |  | checkpoint | 7. Check crossfall from RAB collar to kerb lip using a tape and level every 5m before kerb is poured
text | 782afe60-ec93-5fe6-9ef5-21366288e3e7 |  | textbox | Initials:
date | a5fc3f9a-fcc7-5e30-8078-723355e373a0 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8. Vertical levels correct to design +/-5mm vertical tolerance
text | c92ec0c6-f80a-5b76-897f-7a7dd2df633b |  | textbox | Initials:
date | 3cf6d111-0861-5f6a-b125-e57702be5b61 |  | date | Date:
checkpoint-status |  |  | checkpoint | 9. Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
text | 3ea8bc5c-5acd-50bf-89c5-bbf3fadcdd38 |  | textbox | Initials:
date | 2feb2fd3-d21b-5e5b-b9f2-f7f42759fd66 |  | date | Date:
checkpoint-status |  |  | checkpoint | 10. Crossings / kerb transitions set out
text | 444b8889-5c9f-5aa9-ab6e-5d3b291b623a |  | textbox | Initials:
date | 8181ae9c-017b-516e-90cc-59bb540c29b9 |  | date | Date:
checkpoint-status |  |  | checkpoint | 11. Engineer to mark kerb types at crossings and kerb transitions
text | 632a49d1-bc59-519c-a802-91bbfa8ec392 |  | textbox | Initials:
date | 2dca1c61-f2ae-5039-a46a-ec19e7b6bf99 |  | date | Date:
checkpoint-status |  |  | checkpoint | 12. Ensure channels fall towards catchpit locations
text | 1fbb1fbf-09fe-528c-b9fc-6c0f46624a08 |  | textbox | Initials:
date | 334d6b3c-0f8b-5d30-9674-bb52ee0ab263 |  | date | Date:
checkpoint-group |  |  | section | Miscellaneous
checkpoint-status |  |  | checkpoint | 13. Construction joint roughened & clean
text | 4f05db3d-27cb-5484-a7ea-0362eacfcdc7 |  | textbox | Initials:
date | 46476752-3db9-579e-b023-9f04da1c670e |  | date | Date:
checkpoint-status |  |  | checkpoint | 14. Correct mix ordered
text | 3e5d828e-b077-58a6-9f3a-3c75a45b5f8b |  | textbox | Initials:
date | 9db8ee67-7c07-56cb-905a-5bc2c3ea8b85 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pre-pour check – HOLD POINT
text | f89201e7-b5d5-5c18-a138-e51d6db09685 |  | textbox | Site Engineer - Name:
date | bc5761fe-4bec-5561-bbb3-f8f02914402a |  | date | Site Engineer - Date:
text | e6d40474-6cc4-51fc-9fe2-8051acec1e48 |  | textbox | Design Engineer - Name:
date | 9e6816af-1102-5f08-9f79-1efc00e96b47 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | 15. Correct mix delivered?
text | 46e567e2-b8d3-5a72-a665-6d7a402e16da |  | textbox | Initials:
date | 0abf0a5c-1a69-527b-afa7-44018a51d749 |  | date | Date:
checkpoint-status |  |  | checkpoint | 16. Correct slump (within tolerances)?
text | 8e424592-6045-5947-ba4e-baa64971d2f0 |  | textbox | Initials:
date | 175ac56a-ce99-54de-b66a-4edc2f8f7570 |  | date | Date:
checkpoint-status |  |  | checkpoint | 17. Concrete Supply Dockets collected?
text | 0ff8a5b8-0560-5573-8212-b41d38ae3570 |  | textbox | Initials:
date | c16d912d-edce-5752-81d6-470ed1e91958 |  | date | Date:
checkpoint-status |  |  | checkpoint | 18. Batching Plant Records received?
text | 47ae9a90-edab-541e-b3b9-345a921423f1 |  | textbox | Initials:
date | c1436b6b-82eb-56d9-b255-b93b35e64cbb |  | date | Date:
checkpoint-status |  |  | checkpoint | 19. Kerb meters completed in m
text | 7b983a7c-1ce5-5c0e-a2b5-d070ba94552e |  | textbox | Completed: |  |  | m
text | 2696f578-25b5-53f3-bf0d-32754eac2ad7 |  | textbox | Initials:
date | e671adf5-eaf1-52fe-b140-da8dfc84b904 |  | date | Date:
checkpoint-group |  |  | section | DURING CONCRETE POUR INSPECTION
checkpoint-status |  |  | checkpoint | 20. Check height between base prep & kerb lip is consistent with #7 during kerb pouring
text | c37d8fad-d9d9-55ba-843d-7c4d143a80ce |  | textbox | Initials:
date | 336cf160-b7cf-5dda-8073-38e018574461 |  | date | Date:
checkpoint-status |  |  | checkpoint | 21. Ensure correct kerb type is being installed in the correct location(s)
text | b5cb407d-759c-57de-a8ac-582f06f0983c |  | textbox | Initials:
date | 6603be0a-d61c-5fc5-9b8c-2abe861eb0f1 |  | date | Date:
checkpoint-status |  |  | checkpoint | 22. Constantly check levels and line to ensure kerb is within design tolerances
text | 052d89d5-3deb-5c22-8361-dae054d7704f |  | textbox | Initials:
date | 971f7abe-1433-53a7-8254-4f015b91ebb9 |  | date | Date:
checkpoint-status |  |  | checkpoint | 23. Ensure protruded kerb has U4 finish
text | c92fdf7b-09f9-5007-8072-efdb1fee99ee |  | textbox | Initials:
date | 8e79136f-4f6e-580a-88e3-4b1c48f14ed4 |  | date | Date:
checkpoint-status |  |  | checkpoint | 24. Ensure Expansion joints are installed
text | 39f78d98-ce4b-5e3b-a914-89e2d2eef5fd |  | textbox | Initials:
date | 0e8b3299-7f67-5d8c-9742-880e44763af7 |  | date | Date:
checkpoint-group |  |  | section | CONCRETE INFILL ISLANDS
checkpoint-status |  |  | checkpoint | 25. ENSURE F3 FINISH AND THE CONCRETE LEVEL IS NO HIGHER THAN THE TOP OF THE KERB THAT FORMS THE MEDIAN/ISLAND
text | cc54a625-2a01-5d23-8b50-125b26bd78ef |  | textbox | Initials:
date | e430579d-66a7-5eb2-8776-fbb4874be10d |  | date | Date:
checkpoint-group |  |  | section | TIE INS TO PRE-CAST ELEMENTS
checkpoint-status |  |  | checkpoint | 26. Aprons to be formed around pre-cast elements
text | b6f8dcc0-ae86-5940-98c7-c5c0be8076b5 |  | textbox | Initials:
date | 7c7fb4fc-1eb2-537c-8d18-1c0779245d2d |  | date | Date:
text | df0e5d17-b73e-578d-b100-dc276f672c13 |  | textbox | Pour Start Time:
text | b3303a93-bc78-545f-8ad4-7e3ec5ccf8de |  | textbox | Pour Complete Time:
text | a0a6673b-afff-55c3-bf16-5e072814f8aa |  | textbox | Volume Placed:
checkpoint-group |  |  | section | PROTECTION
checkpoint-status |  |  | checkpoint | 27. Warning tape to be placed over kerb to prevent any damage
text | 7eb59469-4ed9-5fe5-8c27-f86c86ae03e3 |  | textbox | Initials:
date | 027a6823-6c64-573a-bb1c-ac9b96c49928 |  | date | Date:
checkpoint-status |  |  | checkpoint | 28. Backfilling to commence after 72 hours curing time
text | fdbcc662-b98e-5a28-80f2-c931ff58d479 |  | textbox | Initials:
date | 890e09ba-495a-5d5a-bd51-f36b94cb50b2 |  | date | Date:
checkpoint-group |  |  | section | POST CONCRETE INSPECTION
checkpoint-status |  |  | checkpoint | 29. Complete #7 again after pouring using actual kerb lip
text | ada06e78-fbb7-5e9c-ae0b-25496a126c99 |  | textbox | Initials:
date | 2d6ec250-ed4c-543b-9bc9-e1aeac50291b |  | date | Date:
checkpoint-status |  |  | checkpoint | 30. Surface Finish and levels acceptable
text | 8110263e-553e-56cb-84e4-e89671b517dc |  | textbox | Initials:
date | c9449c20-42de-589a-9bd3-de3e2ff0613f |  | date | Date:
checkpoint-status |  |  | checkpoint | 31. Expansion joints satisfactorily completed
text | 0cf1471d-cba7-586b-8b2e-8caf964d07c4 |  | textbox | Initials:
date | aaa2696c-dde2-570f-bceb-139a07d53916 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | ca151c57-19d0-50d8-829a-0bd558434d98 |  | textbox | Site Engineer - Name:
date | f9a8c429-4c8b-509e-8740-04a2839750ad |  | date | Site Engineer - Date:
text | 786fa4a9-966f-5550-9a41-7da261c92634 |  | textbox | Design Engineer - Name:
date | 02889a0f-7342-5489-b78d-feb035bbb2fb |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | CS-4055 - Pavement Layers Checksheet |  |  |  |  | Yes | CS-4055 - Pavement Layers Checksheet | 3b035369-6d5d-4a1e-b5eb-cfbf6fa43594
checkpoint-no-status |  |  | checkpoint | Details
text | 9500a7f6-33bf-556d-a289-3ec3e71675a5 |  | textbox | Paved Date:
text | 3255e6c2-24ca-5fdd-b83a-f67b716cd620 |  | textbox | Location/ Direction:
text | 5ee027c8-0023-5152-a02c-c7f65b5d77bb |  | textbox | Day:
text | 1504fd52-6a09-5484-8d4f-e8269edefc3f |  | textbox | Shift:
text | ecb3f789-59bb-5362-8663-bf29e9e5d17f |  | textbox | Chainage(s) From:
text | 9de43c51-23a3-5876-8cd9-26ad3fe33394 |  | textbox | Chainage(s) To:
text | 03dd13b6-2e5c-5d68-99c2-8051aabc1700 |  | textbox | Previous Lot(s):
button | 954735cc-f204-5d5a-a84c-f13b0f67eba7 |  | button | Previous Lot(s) Comply? | Yes, No
text | a50ef4bf-01c7-5e7d-bfd6-532d6b2eddeb |  | textbox | Corrective action?
checkpoint-status |  |  | checkpoint | HOLD POINT: Previous Layers Quality Manager signed off
button | 2a3c7dd4-04ea-5966-89eb-d9db7273a5ab |  | button | Pave this layer | Yes, No
checkpoint-status |  |  | checkpoint | Layer Type:
boolean | ac630b80-fc13-50c7-8afa-4813a10c9753 |  | tickbox | AC___ Layer # 1
boolean | 5c7357ea-2d27-5e5c-b72f-5e769030951b |  | tickbox | AC___ Layer # 2
boolean | 7b704ddb-cd92-5fb3-acd4-257955b6faee |  | tickbox | OGPA / SMA
text | 44bd65ff-0744-59f3-bdc0-7e788f75a7e2 |  | textbox | Other:
text | e48d61f5-6db8-5c9e-872f-7c3786495cb6 |  | textbox | Nominal Depth To Pave:
text | a75a62c7-277a-5f55-a029-969a31ef09aa |  | textbox | m² Paved:
text | bc8804b3-b058-5868-9ff4-7f3c8d0a5990 |  | textbox | Linear(m):
text | 442640e1-ec4a-56e8-9b4f-38479bec25f7 |  | textbox | Tack coat/Membrane l/m²:
text | f93fda96-7e91-50b1-a653-3148f463062b |  | textbox | Nº of Cores required:
text | 1cb9b98c-8d7a-5cd0-aaa0-d896e884258f |  | textbox | Mat:
text | 5255b66d-37d1-5358-88f7-41f1887a698e |  | textbox | Joint:
text | fa18662f-0a08-564e-8944-358d1e48330e |  | textbox | Nº of Cores taken:
text | 867735f1-1a85-58ae-b93f-04de555a2c48 |  | textbox | Mat:
text | dbb27469-7928-55ee-a368-7f46ae85a769 |  | textbox | Joint:
button | 056f6656-5c4b-59f2-938e-fd7d06bd8380 |  | button | Cores Taken: | Yes, No
button | 710cad00-5fc9-5c17-8c0f-416412a3b4bd |  | button | Cores Filled: | Yes, No
text | 50a339cb-093f-5431-90a9-766e08b599db |  | textbox | Laid (Ton):
text | 86202897-0f5c-5f1a-af50-aa11de4aa295 |  | textbox | Nº of Binder & Gradings required:
text | df62aa3c-4102-5df1-a640-06343d482a57 |  | textbox | Nº of Binder & Gradings supplied:
text | 425e5fa0-b934-5b4c-892c-25c51a524cf2 |  | textbox | Lab Air Voids (%)
button | 668233fb-73fb-5bb9-85b8-99353551d487 |  | button | Binder & Gradings Comply? | Yes, No
button | 628b5c82-0772-5740-a6f4-1852a5c39de3 |  | button | As built Survey Completed? | Yes, No
checkpoint-status |  |  | checkpoint | Air Voids - Run 1
text | 5d75597b-c1f9-5618-b20a-38f41ba7a354 |  | textbox | Characteristic High:
text | be1754e2-2149-5bc0-8ca5-bcc1454e949a |  | textbox | Characteristic Low:
text | d78eb99f-2032-571a-97e9-b68e704b6643 |  | textbox | Average:
text | 14404926-1711-508f-8a54-9f693c5c8f4d |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 2
text | 2548a894-7a6e-5c35-bb72-530129aef8df |  | textbox | Characteristic High:
text | 78ccc117-d49f-51f0-be61-e320ee7a8623 |  | textbox | Characteristic Low:
text | 83804908-033a-545a-8a37-3354c84f8161 |  | textbox | Average:
text | a1463881-5057-59a8-a66b-343d853570d9 |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 3
text | c3c30cc8-1b25-5644-9700-7502ca2f2189 |  | textbox | Characteristic High:
text | e1ab6fca-42de-5000-9884-86a9972af74c |  | textbox | Characteristic Low:
text | f5777d48-7eb1-54bc-a53b-b7e49921a069 |  | textbox | Average:
text | 733a8cc9-07c5-5e90-b5c4-90795971696b |  | textbox | Joint:
button | ff77e33c-f5a1-5828-854f-fac03495c0ef |  | button | Air Voids Comply? | Yes, No
button | b3d003a1-b6d3-59c5-aa01-ecf9beabda24 |  | button | Core Thickness Comply? | Yes, No
button | 7b8c7525-2bdf-50a5-a945-b0f27e400615 |  | button | OFI attached for non-conformance | Yes, No
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
button | b4b514fd-2f28-59c6-b410-ca75a3317827 |  | button | HOLD POINT: Does everything above comply? | Yes, No
button | a3560b25-2bc3-5de4-be01-3cf1c840a9ca |  | button | Pave next layer | Yes, No
checkpoint-status |  |  | checkpoint | Site Engineer
text | 01771c9e-2a02-5adf-9f30-ddc0673aa5f7 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Quality Engineer
text | 9a911a1a-6138-5f0c-be84-165d1a882cb7 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | EN-4011 - Environmental Field Inspection Record |  |  |  |  | Yes | EN-4011 - Environmental Field Inspection Record | 4b7058d4-04d6-4e9f-be62-d41544bb0150
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 0ec173ca-fb0f-57aa-9087-509de2d93199 |  | textbox | Project No.
date | e86634d1-f668-582e-bec7-d113bf37bfbd |  | date | Date of Inspection:
text | 2159d46e-2f54-5837-9a64-1e2451ddaf7b |  | textbox | Time:
text | 5f06f19c-e9db-5570-b9dc-fd775b7d5bac |  | textbox | Zone / Area:
text | 18cb1130-f408-5042-8371-d62323a80213 |  | textbox | Weather:
text | 3c17b127-ed93-5806-bb61-89cd888fbff6 |  | textbox | Person Contacted During Visit:
checkpoint-status |  |  | checkpoint | Copies of Inspection Sent to
text | 840cad55-da3e-593c-a16b-d962abe30025 |  | textbox | Sent to (1):
text | 3ddf7160-a41f-54b7-b4bb-136a5220465a |  | textbox | Sent to (2):
text | 269773bc-1b78-5530-a7d2-03225417bfe8 |  | textbox | Email (1):
text | 0fbde90f-1be6-5e0a-ab9c-7e1170b88656 |  | textbox | Email (2):
text | 3ca5fb67-2763-560f-9fe9-afeff62a6f8f |  | textbox | Company (1):
text | e1e79b37-538f-5939-9a57-1c7b89606dcc |  | textbox | Company (2):
text | 83a15852-1b12-5775-a7a5-af142959f4cd |  | textbox | Inspected by:
checkpoint-group |  |  | section | Works Required
checkpoint-status |  |  | checkpoint | Item No: 1
text | b93ce969-dd15-5f5c-9f76-5f60f0429919 |  | textbox | Responsibility:
date | 5278a759-d473-55cb-95c0-034bd964d38b |  | date | Date to be Completed by:
text | 4b026f23-8f01-5fcc-8cb2-ad6668053783 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 2
text | e3ed2f81-33d7-55de-8c29-6f6c76f63794 |  | textbox | Responsibility:
date | bdae80c6-5d78-589f-ba91-c947a56552dc |  | date | Date to be Completed by:
text | 15cf22fb-0597-5034-b26d-ed18975436f9 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 3
text | aa9b0388-1866-5482-8976-2d99256a0b33 |  | textbox | Responsibility:
date | 54ab8a94-4437-5a23-8d2e-32f07d2a9d41 |  | date | Date to be Completed by:
text | f26577ac-1e5f-5939-8f89-4d86104d5a32 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 4
text | e7377816-6817-552e-8bca-da0af4c537b5 |  | textbox | Responsibility:
date | 69c254f2-3241-57ad-8249-1ed253594967 |  | date | Date to be Completed by:
text | dd926555-776d-5e0f-a759-8ad416266e66 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 5
text | 60b1444e-fe89-5d4f-8acb-dab961b02d86 |  | textbox | Responsibility:
date | 57da952a-87cf-54c5-87ba-481f338f40f7 |  | date | Date to be Completed by:
text | e7bead48-38ef-51d3-85de-5bd684e4a480 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 6
text | 407b2d82-b0fa-5073-ad28-22335c7ad405 |  | textbox | Responsibility:
date | 7fb6db6d-c8d7-5a51-8439-8fd6186b35c9 |  | date | Date to be Completed by:
text | e9a52859-aa67-560c-84c1-152bc386d1f8 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 7
text | b7f6f71b-a9d6-5152-b240-943891341b32 |  | textbox | Responsibility:
date | 61cf6772-88fd-5871-bd7d-042897979976 |  | date | Date to be Completed by:
text | 6127b345-f3de-5ced-9a93-55e0713b5043 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 8
text | 7dc90b7d-7855-51cd-9f9d-ec3a624e176e |  | textbox | Responsibility:
date | ecff848d-b41f-5bab-9377-43802b57789d |  | date | Date to be Completed by:
text | 45c9415f-063c-5b9e-a139-97f1cf2bb586 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 9
text | eaada2ae-ceb8-5f9c-a973-745cdcee0894 |  | textbox | Responsibility:
date | cfc68836-f5e1-5de2-b2fd-51cd5048bdb7 |  | date | Date to be Completed by:
text | ca71b73a-8d7c-538c-8a7f-84818cc05bc2 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | WORKS REQUIRED HAVE BEEN INSPECTED AND APPROVED
text | b3d24f5f-4ba6-56aa-b6af-31e5f8a0146a |  | textbox | Site Supervisor:
text | 23403777-47ce-5374-a02c-b9fe8a78169f |  | textbox | Construction Manager:
date | 74cc6c73-00de-5283-8af3-42800df13128 |  | date | Date:
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | 4c352ada-8bb8-4301-a3c3-d998d7d962f8
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 23268b9b-9119-556b-8205-fa154e0babb6 |  | textbox | CPS Eng.
text | 2190b7d2-d1c2-5b6e-996e-5888b338140f |  | textbox | Site Engineer
text | eebd02a7-5ea2-50bf-86a3-e0205dcf4236 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Test Anchor Setout
label | bbb0f351-09aa-55f5-b634-687bccbbd8f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 821768a7-bd88-541d-8d0a-4c9e59ba6aa8 |  | note | Detail - Location of the tests (to be agreed with the Engineer, two tests shall be completed), and 1 pull test location.
label | af029eb6-fd67-5c83-99f0-f3809988b74d |  | note | Frequency - At least 1 week prior to Testing
label | 3b1cd78e-4ee2-5970-9013-128c86e48335 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 6a06a246-44e1-5439-b551-acb0ae954fdf |  | note | Conformance Criteria - Consistency with Construction Drawing and agreed with Engineer
label | fc789738-5e33-5654-962c-5f075eedb04e |  | note | Records - Design Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | ffe2582b-c47d-5315-8e7c-03b47ca43a7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | e3825050-d1a8-5750-b9ef-ffc1a2e04e9e |  | note | Detail - Any services in the area are to be clearly marked before any work commence.
label | 28db5995-0e4b-5d4e-9e9d-d44915089874 |  | note | Frequency - At least 1 week prior to Testing
label | f58a6714-0d12-5d2b-8648-35f2b11593cb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Service location
label | b45f83ee-dcb1-5d22-8b23-75cbbec89485 |  | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | 5da6e55d-f3e5-5e8d-a6ed-4a94b9b9d346 |  | note | Records - Asset owner report, site inspection
checkpoint-status |  |  | checkpoint | 3 - Steel Anchor Rod Material Compliance
label | 2881fe03-ff04-588d-9435-ce44066664ac |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d76b4a3-dbc8-5766-b5ff-afcf187b245a |  | note | Detail - Design Life of 30 years
label | acc7b316-5fa7-516d-9fed-fca864a8ef63 |  | note | ○ Design Working Load (DWL) per Anchor: 168kN
label | 23681ecc-fe9d-5dba-b2ba-74508c294e99 |  | note | ○ Anchor rod diameter: minimum 25mm threaded bar, with a minimum yield strength of 500 Mpa
label | 82a9e9d0-82d6-5fe2-9381-30bd5e9b37e6 |  | note | ○ Minimum anchor rod length: 12m
label | 1f372ea4-83aa-522c-9fbd-5e5497865a8b |  | note | Frequency - At least 1 week prior to Testing
label | c39c36f8-e2b7-5f61-b6e1-78543e7bf077 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 58201b60-6e76-56a1-bbdf-c77f2865c385 |  | note | Conformance Criteria - Design Working Load (DWL) per Anchor: 168kN
label | 6b7fd233-0ade-5d47-8cd3-527adcd10fcb |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 8910bcb9-1e97-5a50-ac97-dd4c02057537 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 4 - Steel waler Material Compliance
label | db375b06-22a4-5513-9776-895cd6a20522 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 717dfcaf-951a-5971-b136-41806e787193 |  | note | Detail - The steel structural sections for the Waler assemblies shall be primed with ethyl silicate or alkali silicate zinc rich primer in accordance with AS/NZS 4680, ASNZS 2312 Part 1 Paint Coatings and NZTA S9 respectively.
label | c4de7caa-0566-5d72-a93d-7f2b5d2b31cf |  | note | Frequency - Prior to Install
label | 3c303fff-921f-56e3-9031-cebc944037d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 6a774218-2f10-5bbd-ba92-f71cb65556be |  | note | Conformance Criteria - AS/NZS 3679.1, AS/NZS 4680, ASNZS 2312 Part 1
label | ebbfd09f-2a4d-5d4e-b28c-1da06122b770 |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | e07317d9-7667-50db-9a88-124bae974ead |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 5 -
label | 171c6894-c006-5007-a03a-490b45d55e7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 49d9d488-f686-5f29-9489-988a867e147f |  | note | Detail - The Contractor shall provide the engineer with test certificates giving the tensile and yield strengths of the steel used to manufacture the structural steels and steel plates at least seven days prior to the fabrication of waler.
label | 7f41fa5b-25d8-50fc-8570-e9554bd0bbdc |  | note | Frequency - Prior to Install
label | 6217d645-fc4d-5427-9a0f-fb9d95634bff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5485e335-4634-5c64-ab3c-eded6bdca952 |  | note | Conformance Criteria - Test certificates of tensile and yield strengths, 7 days prior to installation, 150 mm x 75 mm PFC WALER BEAM
label | a6c8bb3f-eebc-5985-bda2-684c1ba67b28 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 6 -
label | 2a9e6d54-ca73-555c-bfaf-41065b82c40e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5a29f75d-d691-5fe4-9a51-418144d00bea |  | note | Detail - Confirmation of waler dimensions
label | 2d354958-401d-5bae-a402-509b8567812a |  | note | Frequency - Prior to Install
label | fb4c8a52-3ddb-575b-84c3-641e911edd2d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | a657737b-338f-5b17-9fbb-43aa1385ddc0 |  | note | Conformance Criteria - 150 mm x 75 mm PFC WALER BEAM
label | ce3ec849-bf72-5797-b1b5-bf12b6e003a2 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 7 - Bearing Plate Material Compliance
label | 29e83b48-0501-5327-9df9-27baa121f9b5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 67b7f40f-8ff6-5219-be20-6107b0964950 |  | note | Detail - Bearing plates shall be steel with a minimum yield strength of 350MPa and the final size and thickness shall be confirmed by the Contractor in conjunction with the anchor supplier.
label | 9b9967c2-58fd-5094-a958-44f762736f3e |  | note | Frequency - Prior to Install
label | f49231ce-cf64-5382-9fc1-adecce0e49a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0b2ac64b-76aa-525b-b41d-870aad53947b |  | note | Conformance Criteria - minimum yield strength of 350MPa
label | 99b29078-56fa-5f1f-a2b0-1e01a28e3ffd |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 95dfd25b-fe7f-530f-b458-19b71c660238 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 8 -
label | db386b6d-5287-5fa1-bb7d-09490c6784e4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9ae4cf23-39d9-571d-8e82-3049258e5374 |  | note | Detail - Confirmation of plate dimensions
label | 1ecf9133-a2bb-5f9d-819d-d8eb69f3c2b1 |  | note | Frequency - Prior to Install
label | 5208c752-e5ed-5e34-ac91-c1fa02225ec4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 2dc2ce37-68dc-583e-b49e-dfa2c9ebbb61 |  | note | Conformance Criteria - 16mm stiffener plates
label | c169f88d-57db-5b3f-9cc0-25c264a5c5fb |  | note | ○ 150x150x20 plates
label | a339a983-f2bf-5075-8250-ff7e45e39b18 |  | note | ○ 200x80x6 plates
label | ed6c4ff4-2910-5b6d-b60a-1117ad5b06e5 |  | note | ○ 250x300x16 plates
label | 13637350-c496-5523-b29a-fe86e6b99b6f |  | note | ○ 250x250x16 plates
label | a73ca856-0b0c-56bc-aba7-85a9e9a22584 |  | note | ○ 100x100x6 washers
label | 088193a0-2316-5164-9a24-d0b6abd9ad55 |  | note | ○ 200x80x6 plates
label | 785d8dfa-4145-540f-bf14-f0f6b4033b06 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 9 - Hex nut/ Washer Plate Material Compliance
label | 15c05c19-ce66-5cfa-b747-8a2e381609d8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0aa129a5-9f8c-55e5-a45a-657b50a42f91 |  | note | Detail - Shall be standard, heavy-duty, high strength, structural quality only, flat base, machined from steel, designed for use with the all-threaded anchor rod.
label | 55d0ff13-7e17-5440-983c-4873223e1f62 |  | note | Frequency - Prior to Install
label | 3b7cc288-1394-5cd0-821c-6f3005300556 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 45c996e5-e927-54b4-b58f-59934ab91b45 |  | note | Conformance Criteria - conforming to Grade AS/NZS 1252
label | ca17e480-cbe7-5e72-ae38-c1e0c1ea8e7b |  | note | ○ Develop more than 125% of the yield strength of the anchor rod & ultimate strength of not less than 100% of the guaranteed ultimate tensile strength
label | c55f67e1-4424-5315-8bb2-236e171ca682 |  | note | ○ Hex nut/washer shall be hot dipped galvanised.
label | ee28f67f-ee15-5771-98db-71532599ed9e |  | note | ○ Certified mill test results
label | 927f074f-53fa-57da-8021-1a0aaabd2bea |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 10 - Mechanical Couplings Material Compliance
label | 0c654219-c5a6-58ef-a97e-250527def15f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 24ae8b56-7f1d-5641-ba84-52e7a63c4cf9 |  | note | Detail - Mechanical couplings, when required, may be used to splice the anchors.
label | c713d6fe-ef6e-5c11-a6f4-b1077647f6e3 |  | note | ○ The couplings shall be stainless steel and wrapped in Denso Tape to satisfy double corrosion protection requirements.
label | 42ef2dca-af78-5b55-a117-a033b82b2976 |  | note | ○ Grub screws or locknuts shall be installed and mechanically tightened either side of the mechanical couple
label | 5994f9a2-9407-5741-973c-541a760633c0 |  | note | Frequency - Prior to Install
label | d974c640-507f-5640-b91b-d976794aa6cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Inspection
label | e31f50ea-4468-5cda-a5b1-63ca2b4d2496 |  | note | Conformance Criteria - 100% of the guaranteed ultimate tensile strength of the anchor rod
label | c9f33b96-bf38-5f46-a81b-54c645b65324 |  | note | ○ Steel conforming to AS/NZS1252.
label | 03486d38-f075-5473-b3ca-c308e07aa5cb |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 6e6b9d39-03da-5f63-818b-0acf04660b4f |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 11 - Anchor Construction Submittals
label | 08caede1-931b-581e-8a9c-73129681492d |  | note | ACTION (Hold, Monitor, Witness) - H
label | c16cace3-8921-569d-880d-24f68a3531c4 |  | note | Detail - The Contractor shall submit a construction plan and detailed construction sequence to the Engineer at least 1 week to commencing pull-out testing
label | 969f9b56-ba14-5bbc-acf9-6b438cf64ed9 |  | note | Frequency - One week prior to install
label | aaa32728-769a-55ba-b134-215d948d3576 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 1261313e-fa4e-5cc8-aee2-7d941f5c19ab |  | note | Conformance Criteria - Document outlining Start date, working drawings, methods, manufacturer certificates, detailed construction sequence
label | 8cf53d19-e777-5e5c-ba57-1af8e4634060 |  | note | Records - Submitted documents
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Anchor Construction Submittals - Working drawings
label | 674ca231-a2b8-51ed-a92c-a34c028be208 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1b8c4d0f-09a6-5d9d-b25f-1f0b4c5f627d |  | note | Detail - The contractor needs to supply working drawings which outline the details and location of the pull out tests
label | e3f95039-07af-55b4-92a2-ad9a142ffc11 |  | note | Frequency - One week prior to install
label | ecf78379-0e0c-5278-9144-f195648aa957 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 6937a615-93d9-5be3-8597-787c9a454857 |  | note | Conformance Criteria - Installation method
label | 5cd4dec9-2d21-5d0d-9d25-0aa25221c8c3 |  | note | ○ Location of the tests (approved by CPS)
label | c2554208-24e0-52d5-90e3-34658909ae3e |  | note | ○ Testing methods and equipment
label | 44d9dec0-4195-57ba-a4c9-20259650d678 |  | note | ○ Ground anchor Schedule
label | 5708a8c2-6666-541e-8361-549073c681d5 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Anchor Construction Submittals - Ground Anchor Schedule
label | 644e173e-fd26-5095-a320-45c2f61047fc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 171d590e-e83f-592b-97da-1c2adedeeb0b |  | note | Detail - The contractor needs to supply a ground anchor schedule which outlines the strength and detailing requirements:
label | eeaa3124-5340-5017-8f0b-5cb93297fb80 |  | note | ○ Ground anchor number
label | e8e52a15-8a9f-5a3b-8801-9d39079938f9 |  | note | ○ Ground anchor DWL
label | 67472420-7116-542b-9fb9-2141a7447a68 |  | note | ○ Ground anchor DUC
label | 5758c266-b610-555c-9504-e3c66c0bae1c |  | note | ○ Ground anchor capacity reduction factors for rod & pull-out
label | 04312f16-2fc8-5693-a95b-c8509791d28e |  | note | ○ Type and size of anchor rod;
label | e5ec270e-f8c2-54fd-83d8-1a23abf5b0bf |  | note | ○ Anchor inclination;
label | c48a2a8b-204a-53ce-8dd4-f8900098e978 |  | note | ○ Minimum total anchor rod length;
label | 398ec44a-7727-5426-965a-689b0ccdc971 |  | note | ○ Corrosion protection system.
label | 9035a750-cf27-5bfe-ad16-b84bafab5b62 |  | note | Frequency - One week prior to install
label | 5371abeb-dc5b-5c86-ab46-ee1b829a54bd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | c6429465-b09a-5462-b9f1-a4088ba003d4 |  | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | eead5b9f-e09f-5d97-a77a-c8546ecb0f73 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Anchor Construction Submittals - Testing Methods
label | 2e0b110b-879a-5de7-a49e-589481fbb9af |  | note | ACTION (Hold, Monitor, Witness) - H
label | b4350c98-cce4-51b6-95a5-fd609cac7e41 |  | note | Detail - Details of the jacking frame and appurtenant bracing.
label | b99d5479-fac2-5291-a921-2730cab0c574 |  | note | ○ Identification number and certified calibration records for each test jack and pressure gauge and
label | e233ec5e-23ec-5559-96f9-6c79c9107b48 |  | note | ○ load cell to be used. Calibration records to include the date tested, device identification number, and the calibration test results and shall be
label | d2f6c338-f338-5b2a-ac17-72849a704570 |  | note | ○ conducted by a qualified independent testing laboratory within forty-five (45) working days prior to submittal
label | 1873e010-7e79-5ec6-af90-3d3dede1deb2 |  | note | Frequency - One week prior to install
label | c3792b9c-72bd-5f41-937d-faacbf992882 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0f7596c6-6772-5a3e-9746-73d5f1e497d7 |  | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | b73b697e-65fc-5893-a548-de525dc5c509 |  | note | ○ Certified for an accuracy of at least 2 percent of the applied certification loads
label | 9ff8786b-72eb-57e1-8a84-7b6f4f47ab18 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Anchor Construction Submittals - Testing equipment
label | c141fa6b-7d39-52be-8f5c-31c0bb60a500 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 90c0f665-fccc-5806-99cb-aebd306be804 |  | note | Detail - Testing equipment shall include dial gauges, dial gauge support, jack and pressure gauge, electronic load cell, and a reaction frame. Contractor shall provide the description to the Engineer prior to testing.
label | 16e1d5cf-adf0-5e1b-a2e7-4a3cf48f52b8 |  | note | Frequency - One week prior to install
label | 77ee96dd-9c54-5b5b-859f-9bde894d5340 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | ccedf6b6-15e8-592f-a78d-983c74944b95 |  | note | Conformance Criteria - description of test setup and jack, pressure gauge and load cell calibration curves
label | 5976ee00-bb9e-5fa2-b213-475b905b1f1f |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 -
label | 34fb898a-59b6-5847-9e73-40f889f019f9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 00bb3889-454c-56fa-9612-fc9bdca93702 |  | note | Detail - The testing reaction frame shall be sufficiently rigid and of adequate dimensions such that excessive deformation of the testing equipment does not occur.
label | f400be07-be73-5757-affc-5f4319371219 |  | note | Frequency - One week prior to install
label | 8c257f5e-1041-5c0d-a993-13ea51bc4d7f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 1123c46f-d8c0-5d16-a4ef-15206b89eb1c |  | note | Conformance Criteria - Reaction frame sufficiently rigid
label | fd021c52-adb9-56cb-90fc-01f4aac3afbc |  | note | ○ Support and centre jackover anchor rod
label | 0f389d6c-0391-5f7f-ba32-fc352ecfb3f2 |  | note | ○ Jack, bearing plates and stressing anchorage aligned with rod to as not require repositioning during test
label | 5e99158c-1995-5771-8439-31275149f66c |  | note | Records - Anchor Test log, photos, submittal doc
checkpoint-status |  |  | checkpoint | 17 -
label | a2f098f1-aa76-5a78-9a04-5e601f61b8a1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1c21ebb8-984f-5dca-b845-16ee522fed01 |  | note | Detail - Test load shall use hydraulic jack and pressure gauge. The pressure gauge shall be graduated in 500 kPa increments or less. The jack and pressure gauge shall have a pressure range not exceeding twice the anticipated maximum test pressure.
label | 1432fb0a-5b29-50bb-938b-ac04c15a6f2c |  | note | ○ Monitor the anchor load during the pull-out test with both the pressure gauge and the load cell. Use the load cell to maintain constant load during the creep test portion of the pull-out test.
label | 885a62a2-3027-5da6-925d-df8dd248954b |  | note | Frequency - Prior/ during testing
label | e5f62759-28c4-50da-84a3-ba57f1bfb5bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspections
label | 13fd0bdb-9e3e-5693-bbb7-1aec83f73f01 |  | note | Conformance Criteria - Jack and pressure gauge shall have a pressure range within requirements
label | 30091e8b-0e19-5a81-877d-214ee8e31aff |  | note | ○ Gauge graduated in specified increments
label | 4c900274-e152-5412-b576-8ba2a1a60b9b |  | note | Records - Anchor testing submittal, Anchor testing log
checkpoint-status |  |  | checkpoint | 18 -
label | f6168c51-f37e-5dd2-ac01-cc7261aec8d1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9048c0cb-4bcc-54cc-bd07-79139b50e552 |  | note | Detail - Measure the anchor head movement with a dial gauge capable of measuring to 0.025 mm. Use two dial gauges when the test setup requires reaction against a soil cut face.
label | 87aecb4a-2152-5052-b502-7da47346ad71 |  | note | Frequency - Prior/ during testing
label | 1b45dade-62e3-5318-96c8-d6704c89519a |  | note | Conformance Criteria - Gauge capable of 0.025mm used
label | 3eb18229-a642-5924-a8f0-414764b09674 |  | note | ○ Sufficient travel to conduct test
label | ee7efd73-96c2-5c76-9a9d-c137a67fbb41 |  | note | ○ Visually aligned gauge parallel with axis of anchor
label | 863a400a-02f7-5dac-bd54-c5c67a93b17e |  | note | ○ Two gauges used during reaction against a soil cut face
label | 993d4cb4-24cb-589f-ba76-0d01d611eb61 |  | note | Records - Visual inspection, photos, Anchor testing log
checkpoint-status |  |  | checkpoint | 19 - Anchor Construction Submittals - Ground anchor report
label | a8f80b50-6fbd-57f7-ae9d-43f761a1df49 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0cc17bf4-f2bb-59aa-8d5f-fd48249d6c23 |  | note | Detail - As-built drawings showing the location and orientation of each ground anchor, anchor capacity, total anchor length as installed. Ground anchor test results, graphs and supporting interpretation
label | 8fcec186-1e61-512e-99fc-f9ba97b01dd7 |  | note | Frequency - within twenty (20) calendar days after completing installation
label | 26bb232e-3c33-525b-9370-a31de5b3f6e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5b596424-9236-5139-afdc-98873f5c478b |  | note | Conformance Criteria - Ground anchor report sent to engineer within twenty (20) calendar days containing:
label | c1dd6ba8-9b1c-5631-9a77-08c5339b4275 |  | note | ○ Ground anchor test results
label | 8edac8f1-1aa3-57fc-9496-715088d50f1f |  | note | ○ As-built drawings
label | 6b36af88-20ea-5011-a99a-0b1c3ed592e1 |  | note | Records - Report, document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Ground Anchors
label | 812e1059-496d-549b-9c23-63af2ffb1070 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 870c146a-3538-564d-9f62-bd5a57766188 |  | note | Detail - store steel and accessories without damage or contamination. All materials shall be stored on timber pallets on hard ground in a secure area, clear of any construction operations.
label | a0197b22-5c12-5c85-9ad3-1a2ca9af644b |  | note | Frequency - Throughout works
label | caf48723-0ae9-5a65-9aa8-40fc93a03fee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 9a1519c9-8717-5773-8261-939ad1691d50 |  | note | Conformance Criteria - Stored on timber pallets
label | 0c0317d0-1690-5436-8486-3f2c9c89913c |  | note | ○ Hard Ground
label | 08fffe2a-3be6-579f-9b5a-9da0c250f8f6 |  | note | ○ Secure Area
label | 8ca9df54-f519-5a32-af66-ce7c8f82593a |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 21 -
label | 17084e57-53f7-5de2-aa89-88db92b5edd4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 08099199-2b0f-5da8-a900-36bd7a3173fe |  | note | Detail - Anchor components incorporated in the wall shall be free of corrosion and physical damage at the time of placement
label | e57c2564-eceb-53e7-8794-be28ae09cb66 |  | note | Frequency - Throughout works
label | 23d929c5-378c-5c86-ab54-5c0a80285646 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 3bca332b-4e7e-5ec1-9a51-11c10c4cb6fc |  | note | Conformance Criteria - Free of corrosion and physical damage, Placed so will not damage ground
label | 9100991a-d393-5b1c-a146-fdae07f25234 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 22 -
label | 67627495-25c7-5dab-8290-c3f0d5383b7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 079a7785-163b-58eb-8b33-8197ec624d59 |  | note | Detail - Works shall be carried out in accordance with NZGS (2023) Ground Anchors: Design and Construction Guideline. Should any discrepancies between the relevant codes and standards contained in the above Guideline and this Specification arise, they shall be brought to the attention of the Engineer
label | 4c93151c-4767-5371-998e-b273a0dcac9a |  | note | Frequency - During Installation
label | 6ed1c0fa-7cff-552b-b7f6-b68f1f078b28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 5ac424d5-c8b4-5b28-9442-aa90bfcdb54b |  | note | Conformance Criteria - NZGS (2023) Ground Anchors: Design and Construction Guideline
label | 5fb2f3f0-938d-5708-85e8-e96e6b4a7b37 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 23 - Ground Anchors - Tolerances
label | 7cd3c381-9cee-5d01-92ce-af4bd92c8de9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2bdf4b5f-5091-5797-b5b8-cf02253ef743 |  | note | Detail - Anchors shall be installed at an angle within ±2 degrees of the angle of the theoretical centreline and shall be located horizontally on the face of the wall accurately
label | ff78d446-9746-5295-8f12-da50b42bafa6 |  | note | Frequency - During Installation
label | da596ff6-dad6-5fa7-8ebe-74230605f81a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ff8fe1eb-1ea1-5d5b-bfc9-400a20f84db1 |  | note | Conformance Criteria - Angle within ±2 degrees of the angle of the theoretical centreline plus or minus 25 mm from the position shown on the drawings.
label | 64ab86d9-4ba2-5152-a4be-17b23d7c55ac |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 24 - Ground Anchors - Anchor Testing
label | cc11aeed-e605-5701-881d-64fff80a4adb |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5b54be5c-6b22-5c35-a459-915d54964f53 |  | note | Detail - No-load greater than 10% of the design load can be applied to the ground anchor prior to testing. The maximum test load shall not exceed 80% of the specified minimum ultimate tensile strength of the anchor rod.
label | 6172d9ea-ff60-5409-81e3-71d1b87cf311 |  | note | Frequency - During Installation
label | f475ab1a-696f-5c51-9694-ad993d3a766e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection,
label | 8df0d540-2d12-5926-9764-513f6d86abdf |  | note | Conformance Criteria - Pull-Out Test Schedule <80% min ULT load
label | 9052ffb9-42c5-5bfe-a01c-ad4b83521739 |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 25 - Ground Anchors - Pull out Testing
label | c0848f19-1c47-53e7-ad59-32e2a7a140fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | fc4b9612-9c78-592a-9177-d7758092dee1 |  | note | Detail - Pull-out testing shall be carried out on one sacrificial ground anchor, The pull-out test shall be done at a location and elevation agreed and approved by the Engineer.
label | 0ccc369a-e70f-502b-90b7-dab263676976 |  | note | Frequency - Prior to installation of anchors
label | 23165f9b-d872-563f-ac15-7c1d39a6f02a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 51df7fbf-9c25-5ee7-8e3d-0c1f0eb4c433 |  | note | Conformance Criteria - Conducted prior to installation, Location approved by CPS Engineer
label | 8f9da01f-59a0-54b0-9285-b3f3f439dc29 |  | note | Records - Pull out test log, Submittal
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 26 -
label | 1b4cd79b-d010-5c72-ac02-fbb12db6e73b |  | note | ACTION (Hold, Monitor, Witness) - M
label | a4b9f5d4-5e26-5dc5-96ae-d9c561ad62fb |  | note | Detail - The pull-out test shall be carried out to 150% of the Design Working Load (DWL) and the contractor shall supply a larger anchor rod (if required) to safely accommodate the maximum test load. Anchor movements during the Creep Test shall be measured and recorded.
label | 542c89c1-b9e4-5dcf-959d-71a265c19e44 |  | note | Frequency - During Pull out testing
label | 2c5fd92d-0527-586a-8b0d-bbebe831b383 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | de4e9419-72a2-580f-aff3-aeebf5858960 |  | note | Conformance Criteria - Refer to the Pull out test schedule
label | 3c0c90d1-80ba-571f-8ab9-6a58625b8386 |  | note | – – – – – – – – – –
label | 7b3e90b5-8f1a-57d4-8dc1-5d422810f2f0 |  | note | Pull-Out Test Schedule
label | f9892107-25ef-5ca5-a7ae-ceea6e51dd8c |  | note | – – – – – – – – – –
label | 7470e92b-8d1f-5640-b9a0-0f6f599116cf |  | note | Load ¦¦ Hold Time
label | d8b17642-48dc-5c4b-903a-900a3ec5154e |  | note | – – – – – – – – – –
label | 2f6e071a-8fc2-5117-9d0d-1bdd134f8dd8 |  | note | 0.05 (DWL) ¦¦ 1 minute
label | 8829115e-7466-5f6b-a2af-ba6c7e439892 |  | note | 0.25 (DWL) ¦¦ 10 minutes
label | 831c2d3f-01f0-5aaf-9076-953572340431 |  | note | 0.5 (DWL) ¦¦ 10 minutes
label | fbf79713-e465-5a23-a91c-14548ebf65ac |  | note | 0.75 (DWL) ¦¦ 10 minutes
label | 5c490679-4bdf-511b-b15e-5f1b92ebb615 |  | note | 1.00 (DWL) ¦¦ 10 minutes
label | 0ac3d99a-3a8a-57d8-a573-df0d7389105d |  | note | 1.25 (DWL) ¦¦ 10 minutes
label | 7a37a96a-f911-5060-acca-926afca8d64b |  | note | 1.50 (DWL) ¦¦ (creep test) 60 minutes
label | 18bd9e0e-07cb-5b71-a553-b8b617cbf99f |  | note | – – – – – – – – – –
label | 1a9e7757-097c-538d-88ed-abb69aa7b7b1 |  | note | ○ Recorded at 1, 2, 3, 5, 6, 10, 20, 30, 40, 50 and 60 minutes
label | f9c3414b-f49b-52ab-9216-77e1aef85beb |  | note | ○ Maintained within 2% of the intended load
label | 1862245d-736c-560d-a421-6d15ddfc86d0 |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 27 -
label | ddb258e7-bcb2-5cbe-9fbd-fbe79e6a2f10 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 121764b5-38a9-5b61-a6b5-86c0bd7b0f15 |  | note | Detail - The alignment load (AL) should not exceed 5% of the DWL. Dial gauges should be set to zero after the alignment load has been applied.
label | 12e384e0-a4ce-5ce3-9f79-d8aa2bd4a43e |  | note | Frequency - During Pull out testing
label | 1d54a500-1ed7-56d1-b9ef-5581f5dacc4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 689b321a-59ae-5654-aa0e-d50470ef67f8 |  | note | Conformance Criteria - AL not exceed 5% of the DWL
label | 16e597a6-f366-51e3-912f-e2577f6a242b |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 29 -
label | 6264c0bc-19ff-5244-b4d8-ef3d180442db |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c1b77bc-8df5-5ced-afb3-80c54f103604 |  | note | Detail - The results of the pull-out test, along with calculations and their interpretation shall be forwarded to the Engineer
label | f20d9c7f-e9ba-5f3a-a95a-24301428d3c7 |  | note | Frequency - During Pull out testing
label | 73d046cf-3f09-5a0d-93e6-08ab74afca09 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 48660374-2d8b-5db0-ba74-fa7f79370313 |  | note | Conformance Criteria - Engineer to send through approval within 48 hours of receiving results
label | f8e1f522-2fea-5dc3-8eed-b03062cdbad3 |  | note | Records - Pull out test log
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 30 - Ground Anchors - Proof Testing of Anchors
label | 16635a30-06b1-54ce-92d7-0d4c117b3d10 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6fbec8f5-31df-5715-9af2-da94df6a6fe7 |  | note | Detail - The proof tests shall incrementally load each ground anchor in accordance with the Proof Test Loading Schedule and in conjunction with the specifications 5.7.3.3
label | 0b4520d1-c3e3-57ea-b3c5-0ea02d570d36 |  | note | Frequency - During Proof testing
label | eabf1fd8-93be-5153-b05d-3e566676e974 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 80d9320b-83ff-5b38-9c1e-82d52ba140e0 |  | note | Conformance Criteria - Proof testing completed on two anchors as selected by the Engineer
label | d1a8ad24-6401-5a1e-9a09-91f4f8f96650 |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 31 -
label | 44418fca-a711-5994-92dc-8fc3e1eecc7c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 464ad6a3-4af4-5aec-ad3d-567b106cee7d |  | note | Detail - The maximum test load in a proof test shall maintain a constant load. The load-hold period shall start as soon as the maximum test load is applied and the ground anchor movement with respect to a fixed reference shall be measured
label | fc9f46c9-605d-548c-bb38-03a1e2b8cd59 |  | note | Frequency - During Proof testing
label | 76ee0662-0767-5519-bafb-42245bd4e6c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | ed3cc313-4ce9-5ce3-bd08-91a89bc93899 |  | note | Conformance Criteria - recorded at 1, 2, 3, 4, 5, 6 and 10 minutes. If creep test up to 10 minutes exceeds 1 mm, the maximum test load shall be held for an additional 50 minutes
label | eee934ef-9c31-5b2a-98b2-700f9f11bcc3 |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 32 -
label | 11a818b3-cb13-53fd-a3f2-ed3ee19e35f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 39266888-6081-5583-b508-7616133a308c |  | note | Detail - The remaining anchors should also be tested to the same methodology up to 1.00 of the DWL unless approved otherwise by the Engineer.
label | c1033b36-6f86-5ce5-8939-463d123f08eb |  | note | Frequency - During Proof out testing
label | 368ce410-e02a-5a3f-a867-426df28cfc2e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 884d8ec3-4d52-5049-afff-2f5c03036420 |  | note | Conformance Criteria - Total movement within the 10 minute hold is less than 1 mm between 1 and 10 minutes.
label | e30f5b3c-bdbc-532b-9c5b-bc7e49b3918a |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 33 - Survey As Built
label | e048e06a-612a-50fd-bd7d-d5f01d1b9a15 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8ead4107-8a60-52db-ac2d-05806a6a219e |  | note | Detail - Survey final position and R.L. of each anchor, produce As-Built drawings
label | ff5c8b89-b6cf-5e6e-a0e8-9ea18f27d811 |  | note | Frequency - Each anchor
label | 17bb6571-bdb1-54ed-9c8a-f8bb81c500eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | 254ec04e-6f45-5e54-88c1-a8d0a09a1df0 |  | note | Conformance Criteria - As-Built Drawing
label | 151042a5-92e3-57c1-8f90-effe2db75a6b |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 34 - Lot Number QA File
label | 6b639507-409f-5a70-8258-46d9dc5ade30 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6caca58d-f01f-5f81-8431-dc1cb59eb796 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 50367b3c-6403-5f06-aff3-bd713d19f811 |  | note | Frequency - At completion of Lot
label | 462cc030-b92b-5de3-8d3f-b618f543ed24 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4cdaca21-67b6-5f12-a594-c76f0ba91de0 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f41a7b0b-add1-52b1-849b-cf063436b679 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 35 -
label | b25338ad-0609-5c85-8e42-1b868b72aa02 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 67656e4e-dcd0-5368-897f-3a65ac79baf8 |  | note | Detail - Check all anchor records are completed and signed by the relevant signatory.
label | 3e56608d-10a8-530d-ad23-c5096ef8d8f8 |  | note | Frequency - At completion of Lot
label | b3d5e95f-60e1-5441-bbd7-9866314ad191 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 67759f6e-b607-5ab8-b293-c55b43d994e8 |  | note | Records - Document Review
checkpoint-status |  |  | checkpoint | 36 - As-builts
label | a41a1fac-b9ee-52c4-958d-fdb2c096e4d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 701d61cd-9257-5d57-be02-51e40e66f052 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 8ecbb795-857e-5fa9-a3f8-3ce3978a18df |  | note | Frequency - At the completion of the Lot of work
label | 9a0b2271-28bb-5de4-95ab-a01b4ef12178 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b6b6abae-4cdb-5872-849a-97f2f780c9de |  | note | Records - As-built Drawing
checklist-flat |  |  | checklist | CS-4074A - Low Pressure Air Test Record for PVC pipes |  |  |  |  | Yes | CS-4074A - Low Pressure Air Test Record for PVC pipes | 4fdcc923-f1b1-4921-8860-14317c73a8f8
checkpoint-no-status |  |  | checkpoint | Details
text | e6c5aff2-ffc6-51e2-ad9d-5523e40cb063 |  | textbox | Work Area(s):
text | fbb0b252-807a-5712-a8a1-406b93258bfb |  | textbox | Sub Work Area(s):
text | 7976f0a3-bfd9-5472-9f37-228e445235f7 |  | textbox | Lot(s):
text | d779cccd-88fa-518f-8762-58925bb01a58 |  | textbox | Sublot(s):
text | 87108388-3341-506e-9cfd-3beadc56784e |  | textbox | Document Date:
text | 7c7c6902-73bc-5633-be86-8c08d80d4ae6 |  | textbox | Updated By:
text | d0ba2fe3-5da6-529d-be74-4bc2f5cb04d9 |  | textbox | Area:
radio | c1e87fb5-e211-5f6f-85d8-b1ca0e6f75e9 |  | radio | Weather: | Fine,Overcast,Showers,Rain
text | a28eb7a4-83b1-59b8-bc69-f243070287d4 |  | textbox | Location:
date | c5ca1b6d-7867-54ff-87b5-589a7b1e4aed |  | date | Date:
label | 26e7850d-5eaf-5ac6-9f24-47296af2fcf5 |  | note | Personnel Conducting:
text | 0430ff42-e839-5e9c-a9ce-a59c4256fe37 |  | textbox | Drain Layer:
label | e48a0564-e00f-52e7-871a-afe23e8564ca |  | note | Witnesses Requiring Notice of Test:
text | 3afe3912-176a-5685-b854-0332b7e9ab2f |  | textbox | QLDC Rep:
text | 0f9913ce-bf48-51a2-96b2-0e4096def94b |  | textbox | CPS Engineer:
text | cfa13bb9-8921-5237-a5b6-aa11a1657b53 |  | textbox | Site Engineer:
checkpoint-no-status |  |  | checkpoint | Pipeline
text | 46c40af9-9971-5367-b854-ffcfa4e686f5 |  | textbox | Pipeline:
text | bf2a26d1-41d7-5cb8-887a-f78ea5639cec |  | textbox | US MH Number:
text | 420f5660-1d4d-58e3-a28b-a7d421aeed84 |  | textbox | DS MH Number:
text | fc44bd16-d7cf-51f9-ada5-0cd48ece73de |  | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
radio | c012fc41-858b-519e-a0d0-affb474da9f3 |  | radio | Plugs Braced? | Yes,No
checkpoint-no-status |  |  | checkpoint | Pipeline Material (non-concrete):
text | 07d8b9bb-40e0-5a32-a657-a7d23b09f452 |  | textbox | Pipeline DN (mm):
text | 91eb1047-12d4-5183-bc41-37913849777c |  | textbox | Pipeline Length (m):
text | e8768aca-e1d6-5de4-b096-8e0f175f1539 |  | textbox | Test Time as per Table C1:
checkpoint-no-status |  |  | checkpoint | Prelim Checks:
radio | e5bae442-52b7-5756-af13-9afa9107cc21 |  | radio | Line at pressure and maintained for 3mins? | Y,N
radio | 6508629a-5efb-5e1c-beff-2eeb4043b4c6 |  | radio | No Leaks Detected? | Y,N
checkpoint-no-status |  |  | checkpoint | Start Pressure
text | 38a97ee3-54f9-5156-9af3-6d4d30752dbc |  | textbox | kPa:
text | 5ae2f1c4-c54f-5516-890b-a85b99df80af |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | End Pressure
text | a5d411dc-d93b-55ff-b843-24111200d87a |  | textbox | kPa:
text | 4a0d7f1c-1a4b-5d5e-99dc-e70aaa88be9d |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | Pressure Drop:
text | 9aaa9e4f-89b3-5885-b244-e9cf39942650 |  | textbox | kPa:
text | 9895d553-ad87-5258-b443-92681f7ccfb2 |  | textbox | Duration of Test: |  |  | Mins
checkpoint-status |  |  | checkpoint | Test Result
label | 7e6d0b7a-4e90-5188-9d59-3a7f30140893 |  | note | Acceptance where the gauged pressure has dropped less than 7 kPa for the time interval shown in table C1 after the shut-off of the air supply.
label | ef638fcb-fbf9-51a0-afdc-cae4155f4ead |  | note | ○ The test length shall be acceptable where the gauged pressure exceeds 18 kPa (or not more than 7 kPa less than the pressure at the start of the test) for the time interval shown in table C1 after the shut-off of the air supply.
label | ec6d25f1-00d8-5c1f-b10e-ea4c80bab25f |  | note | ○ Table C1 is based on an air test pressure of 25 kPa (in excess of any external hydrostatic pressure due to groundwater)
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
text | e0e0fc8b-d334-57e1-944d-c3748baf6026 |  | textbox | Name:
label | c44fff85-a269-5893-8ffe-f1c36833a5dc |  | note | Position: Site Engineer
date | 272174f6-97b4-5d80-be30-47bce6b9065e |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | CS-4009 - Socket Foundation Install Checklist |  |  |  |  | Yes | CS-4009 - Socket Foundation Install Checklist | 53edf9e3-1c3c-4f7c-85a5-bc393d312431
checkpoint-no-status |  |  | checkpoint | Details
text | 82068b19-9e2c-5365-bad9-5be44bee4708 |  | textbox | Date of Pour:
text | 258828c4-28c0-5b92-a5b2-c0dbdfcbe8d4 |  | textbox | Light Pole Number:
text | 71f5e2d7-66e3-595f-91ca-52f7db5eb9ed |  | textbox | Pole Type:
radio | 9fee506e-a8d8-518d-a9d5-9819500cdf1f |  | radio | Retention Socket Type: | RS168 x 750DF,RS168 Shallow,Rse273 x 900
radio | 4d675c91-9ca0-5c07-8cee-d763b1aa6a6c |  | radio | Installation: | Street Installation,Rain Garden Installation
radio | e9e0485a-63a1-5176-8f24-1e10b5a42a74 |  | radio | Services Present: | Yes,No
text | 9beb3117-661c-54e2-8bef-c50f7a80e8bf |  | textbox | Services Maximum Depth:
text | 5c4dc65f-9d33-52b9-aebb-b7b83bf7f65f |  | textbox | Lateral Measurement – Foundation to Services:
text | 6a34fa7a-34f3-5f61-849b-14ab03a5ff71 |  | textbox | Maximum Foundation Depth:
radio | 09403e2a-3bbc-5b19-9222-f9b927f3d7d4 |  | radio | Finished Ground Level Confirmed and Rebar Cage in correct location: | Yes,No
checkpoint-status |  |  | checkpoint | Has minimum cover to rebar of 75mm been achieved?
radio | 730a2b27-c23a-5021-b166-a74c0f1a3fa0 |  | radio | Foundation layout as per approved drawings: | Yes,No
label | 6f4e5884-a6a6-55eb-86cd-eccb783bd149 |  | note | (If NO what approved action is taken?)
text | 9fc46d81-8b01-58b0-a7dd-41ed5a8a1c86 |  | textbox | Action:
radio | dbbd4959-1b1a-54c0-9ebc-09db67adfcca |  | radio | Photos of pre pour foundation taken: | Yes,No
checkpoint-status |  |  | checkpoint | RS168 Foundations Stub Pole in place and checked level. (1)
checkpoint-status |  |  | checkpoint | RSe273 Foundations – Correct pre chamber allowed. (1)
checkpoint-no-status |  |  | checkpoint | Water present in base of foundation to be removed:
text | 997730d2-1ac1-542a-83c0-7150b2eb1d43 |  | textbox | Maximum allowable water in base is:
checkpoint-status |  |  | checkpoint | All fixing locations secure pre concrete pour.
text | aaf931c4-4468-59d5-af0e-40e31689043e |  | textbox | Concrete Batch Number:
radio | 0c86adeb-71ee-550a-a592-dc905d314f70 |  | radio | Pour Correctly Vibrated: | Yes,No
checkpoint-status |  |  | checkpoint | RS168 Foundations Stub Pole in place and checked level. (2)
checkpoint-status |  |  | checkpoint | RSe273 Foundations – Correct pre chamber allowed. (2)
checkpoint-status |  |  | checkpoint | Stub pole should in centre of foundation.
checkpoint-status |  |  | checkpoint | Ensure top of pile is roughed up
checkpoint-status |  |  | checkpoint | All rebar starters are installed
checkpoint-no-status |  |  | checkpoint | Supervisor
text | daa28347-8c9c-5b6a-ac78-f4bec8493edb |  | textbox | Supervisor Name:
checkpoint-no-status |  |  | checkpoint | Levels to be recorded
text | 6a8aeed1-7678-5a0a-a2f0-40adfdf47bca |  | textbox | Ground Level:
text | 13f5594d-ee6c-5d11-9b30-112445e6cf83 |  | textbox | Base of Foundation:
text | b8d31db6-10d1-5f64-9a23-ec85ef96473d |  | textbox | If Plug used base of Plug:
checklist-sectioned |  |  | checklist | CS-4103 - Water Loss Test |  |  |  |  | Yes | CS-4103 - Water Loss Test | 56a03c2a-94a4-4935-b27f-f2d3c161a078
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 288afc6b-9ac6-54d0-a4ee-6299c6e692dd |  | textbox | Contract:
text | 58d75d67-5b8a-5505-9a0a-390eee8f9da3 |  | textbox | Sub Work Area(s):
text | ab8ab6ae-211d-5b24-beaa-82d92de567db |  | textbox | Sublot(s):
text | acb4534d-ba28-5ebb-87b2-dfe98df22772 |  | textbox | Work Area(s):
text | 49886100-6e2b-5d87-a5e9-889709e2e1c6 |  | textbox | Lot(s):
date | 0882c5cf-6246-5b52-96af-45869a1a1977 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Personnel Conducting Test
text | b5b2c2ad-1592-51d8-b70d-08cbaff051e5 |  | textbox | Drain Layer:
text | 4969c795-aca5-50e9-a520-001e4ce56038 |  | textbox | Site Engineer:
text | 821b85da-9c9d-576d-b042-3ff3a10ea11d |  | textbox | CPS Engineer:
text | f6e3b130-0712-521e-b73b-f72b2f79651e |  | textbox | Qualification:
checkpoint-group |  |  | section | Pipe Material and Rating
checkpoint-status |  |  | checkpoint | Pipe Material and Rating
text | 7d403dc1-7490-5a7a-9862-dd51f6463537 |  | textbox | Pipe Internal Diameter (mm) D:
text | 8f5704a5-ac18-572e-8a0f-2868877dc530 |  | textbox | Depth of Pipe Below Water Table:
text | ab15845d-032b-551d-8d68-8bbe4bb21173 |  | textbox | Ambient Air Temperature: |  |  | °C
text | cfe19bb9-d33c-5da4-84fe-96ee61b189a9 |  | textbox | Water Temperature: |  |  | °C
checkpoint-group |  |  | section | Water Loss Method
checkpoint-status |  |  | checkpoint | Water Loss Method
label | beb6a27a-6f47-5dad-8960-176abda3f474 |  | note | Procedure
label | d2e8b394-9644-519a-a04b-79a7893602fc |  | note | 1. Remove air from pipeline
label | 7428bfbf-9253-57b8-b279-9642e5e7110c |  | note | 2. Apply test pressure to pipeline
label | 0d8a91e1-3caf-5904-a3c5-0c261699c5d3 |  | note | 3. Allow pressure to settle for 12 hours
label | c9c1747c-c64a-5cf9-83c0-75a02096463b |  | note | 4. Re-apply and maintain test pressure for 5 hours by successively pumping a sufficient amount of water
label | f06001fb-dbe2-5caf-8a6b-89d18fba0fb5 |  | note | 5. Measure water volume required to maintain pressure between Hour 2 and Hour 3 - V1
label | 7e2ed1d2-f818-592b-8e51-6e45ecfd8e5a |  | note | 6. Measure water volume required to maintain pressure between Hour 4 and Hour 5 - V2
label | cca26ad7-86a5-5021-a951-efeb301376fc |  | note | 7. Calculate:
label | da01a1a6-ed98-5b6c-9aaa-5dcc48811457 |  | note | Where:
label | b174b57c-9e8b-5c6f-a867-6b16908783a9 |  | note | Q = allowable make up water, (L/hr)
label | 8a85b745-907e-5a5c-bc9e-7a4f6a388bc6 |  | note | D1 = nominal diameter of pipe size #1, (m)
label | d07d18c4-4b4c-5236-a6b2-d05f65ec153c |  | note | L1 = length of pipe size #1, (km)
label | 548edc9b-3815-549a-b6a8-77e8c0848c6d |  | note | D2 = nominal diameter of pipe size #2, (m)
label | a8f6f256-fd44-5736-8dc8-63b7e66c4bd2 |  | note | L2 = length of pipe size #2, (km)
label | 30636b82-01ea-56ec-bcae-c96cef930834 |  | note | D3 = nominal diameter of pipe size #3, (m)
label | 45b60ae2-c8da-5577-90ac-15d25ae9ab55 |  | note | L3 = length of pipe size #3, (km)
label | d02027c6-62c5-5319-82d5-11f523680da1 |  | note | H = average test head of pipeline, (m)
text | 7a27e895-436b-599f-81ac-8c6d04e5dfb9 |  | textbox | Standard Test Pressure: |  |  | kPa
label | 8ee20d50-8b6e-573f-86f5-fbeee3572438 |  | note | – – – – – – – – – – – – – – –
label | db8512c1-5da9-5fca-9e2f-0b84bf0f1f9b |  | note | Water Meter Readings
label | 07283fc0-9c27-5fcd-bca0-5dee984cc116 |  | note | – – – – – – – – – – – – – – –
label | c8577294-a2b3-5a31-ad7c-b633d636cddb |  | note | Test Time ¦¦ Time of Day ¦¦ Reading (m3)
text | eb3dbaeb-0b5b-57c4-8a32-992e8ef272f9 |  | textbox | Start ¦¦ 0:00:00 ¦¦
text | 9340be2c-d35f-579e-a84c-edf5f29f321f |  | textbox | 2 hr ¦¦ 2:00:00 ¦¦
text | 975f10e2-949c-5dc6-8d11-52f6f2de845f |  | textbox | 3 hr ¦¦ 3:00:00 ¦¦
text | a6fb76ab-25a1-53aa-a4a3-21e6fab87883 |  | textbox | 4 hr ¦¦ 4:00:00 ¦¦
text | 478f5d3a-ce8e-5365-93e4-aa596d4a8c2a |  | textbox | 5 hr ¦¦ 5:00:00 ¦¦
label | bc883463-253b-5395-bcf6-fcd9771792f8 |  | note | – – – – – – – – – – – – – – –
label | 23fd416e-32db-5945-a047-99f867875ebc |  | note | Water Loss Method Parameters
label | f325dff0-be55-55ef-b927-af97faafc67d |  | note | – – – – – – – – – – – – – – –
text | 9c5c0a0d-bb73-5f97-9853-3286801cf31e |  | textbox | L1 (m)
text | 4e4270c8-837d-540b-b7b5-a93b408429ca |  | textbox | D1 (mm)
text | f1d307fb-ddf5-50d5-9252-9a2be207b2ae |  | textbox | H (m)
text | 363bfdf1-5fe6-5724-8211-35f5af625880 |  | textbox | Q (L/hr)
text | 1a3a20b1-4e2a-5d7b-8a7a-c7f775e7739b |  | textbox | V1 (L)
text | bba63ead-be7b-553c-bf5a-026bbcae452f |  | textbox | V2 (L)
text | fef85cf2-de25-5627-8bb9-4be2950ddf99 |  | textbox | 0.55 V1 + Q
text | 9a28a968-3991-5be0-8847-4bed3fb7b8be |  | textbox | V2 ≤ 0.55 V1 + Q
checkpoint-status |  |  | checkpoint | Acceptance
label | 6996848b-820c-5463-81ce-f69dacb4e12e |  | note | The test length shall be acceptable where:
label | 44c9c0e9-26c5-5f17-99e0-38135e76ad8a |  | note | 1. No failure of any thrust block, pipe, fitting, joint or any pipeline component
label | 8187dea2-4334-57f2-ad5a-a827e338ef87 |  | note | 2. No visible leakage present
label | 7a800a43-63b7-52a6-b0b2-ebcf5100bca6 |  | note | 3. 𝑉_2≤0.55𝑉_1+𝑄
checkpoint-no-status |  |  | checkpoint | Comments:
label | 0b02acc0-60a9-5a79-9eeb-3169464775c6 |  | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
checkpoint-no-status |  |  | checkpoint | General Methodology Details
text | dc8d4b48-0164-55af-b706-23229ad6f082 |  | textbox | Process for removal of air
text | 2f869da7-a377-539a-a9c8-2a35eeb80070 |  | textbox | Details of water meter
text | 78920c02-8dff-5273-8be4-06c99e04c3dc |  | textbox | Details of pressure gauge
text | c4124bd2-1f17-5c67-9f4a-948005797504 |  | textbox | Details of pump
text | 3ba4dab3-6423-5a88-95c7-4ebe5a51b518 |  | textbox | Water source
text | ead9cc03-c21a-5012-8e82-b59bde12827c |  | textbox | Water Disposal
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Checked and Signed by Site Engineer
date | b1138729-581d-5000-a819-7ee52d26b4e1 |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checkpoint-no-status |  |  | checkpoint | Site Photo Records
checklist-sectioned |  |  | checklist | CS-4060 - Pre-Seal Checksheet |  |  |  |  | Yes | CS-4060 - Pre-Seal Checksheet | 665ebeb8-f04b-49b5-9286-97b6619c443e
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | d516fac1-68e1-5253-aacc-13ceac4622ce |  | textbox | Project No.:
checkpoint-group |  |  | section | Surface Shape Check
checkpoint-status |  |  | checkpoint | Surface Shape Check:
label | 288f73d8-9865-5f54-a4d6-e789491729ae |  | note | No point of the surface shall vary more than 10mm when checked with a 3m straight edge (Measurements to be undertaken at a frequency of 1 every 100m)
label | 2a53e0bb-7008-57f7-bf7e-d7c13a9bb386 |  | note | Note: Left and Right when facing increasing chainage.
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | 7e02c059-e3d0-5c83-b96c-c46c12782c1d |  | textbox
label | 29088593-96b6-54a1-af17-37b0205ff67d |  | note | Measurement taken from straight edge to surface level
text | ac7e2a4d-f9f1-5f15-aded-2b98ebc4b8e5 |  | textbox | Bound Left
text | 09b7729b-c4c3-5d6c-9d0a-d252a6915074 |  | textbox | Bound Left - Left:
text | fd63bc5a-f2e5-5465-85d1-42c9fece5d7e |  | textbox | Bound Left - Right:
label | 658801d6-79f0-5893-97c6-8e58471312ec |  | note | ––––––––––
text | 83cf45ed-04ab-57cd-b382-212e1eeaec42 |  | textbox | Bound Right
text | fcb4e10e-bdcf-5c7f-85b8-5f9551b926dd |  | textbox | Bound Right - Left:
text | 708bf958-841c-5be0-80d7-ef4a570955e6 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | bbceb4cd-e61f-5ffa-b270-ee31b7e4df1e |  | textbox
label | b586be0f-bbde-5c94-bf96-afe0a715794e |  | note | Measurement taken from straight edge to surface level
text | 5c466f0f-c069-52d5-a667-5074d93bb996 |  | textbox | Bound Left
text | c7408dca-eb42-5c5a-ba54-fe94cba5fd7a |  | textbox | Bound Left - Left:
text | 4c929668-0d5a-592c-ab21-5aa6a649a00e |  | textbox | Bound Left - Right:
label | ae5b2d99-52eb-552a-93e5-3205c5d4418b |  | note | ––––––––––
text | 44e5313e-be31-53d0-a99c-e913a5f333dd |  | textbox | Bound Right
text | 8f2fac36-6458-543a-b89b-bf2b8ef35cdd |  | textbox | Bound Right - Left:
text | eed4d1a1-3838-5bff-98b3-8830e29c5937 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | 8f24b108-99b6-5757-b25b-8d6f90cb2e4b |  | textbox
label | d7b23651-80cc-5d32-8b1c-3e779743ade2 |  | note | Measurement taken from straight edge to surface level
text | 5420b686-8bb1-511d-a754-683abd726df2 |  | textbox | Bound Left
text | 27a703ce-fbf3-51a9-bd61-8e32894482f2 |  | textbox | Bound Left - Left:
text | beb914b2-a37b-5d3d-8709-3ba8ad5cdbeb |  | textbox | Bound Left - Right:
label | e09cd3b9-7a41-52ca-bbe6-c33978d5a811 |  | note | ––––––––––
text | 3a5f5036-8218-57e2-9912-81e56498f7e5 |  | textbox | Bound Right
text | e01a9694-54ca-5bbd-a539-7b4f05541d56 |  | textbox | Bound Right - Left:
text | 36ff9a74-c658-5f56-a68a-33859ec91cff |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | cfa466e2-cb92-5498-8479-2b2b21fa741d |  | textbox
label | 28f11970-849b-5834-81d5-558aa71f9c25 |  | note | Measurement taken from straight edge to surface level
text | a874b990-eda7-5e93-8069-28c246c78a04 |  | textbox | Bound Left
text | c731a0c0-056f-5cc8-a9fc-cd16d269f00e |  | textbox | Bound Left - Left:
text | c0a413e3-e058-5fa3-9bd6-9f1da72fb56a |  | textbox | Bound Left - Right:
label | 16c166dd-b384-5e85-88c3-490ab666f693 |  | note | ––––––––––
text | 94c20ede-a592-5ba6-bdc8-6dcc2f280c01 |  | textbox | Bound Right
text | 1b2f0934-88fe-5980-8456-b3545ad6e9e2 |  | textbox | Bound Right - Left:
text | 4f340aff-8c19-5b17-9c76-a5a59f9b7d21 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | 7fdbd86d-0f2f-55a4-909d-b7a60f1794cb |  | textbox
label | 3f764d9f-91e7-521f-820b-97c3b33a52bb |  | note | Measurement taken from straight edge to surface level
text | 0c4e1c61-88f2-5952-a6db-c18466e38912 |  | textbox | Bound Left
text | 4d64c4e7-5f2a-5eeb-a42d-48dfe06a0ceb |  | textbox | Bound Left - Left:
text | 5d3e66c5-dce8-5895-8938-a3fa7ac96d25 |  | textbox | Bound Left - Right:
label | f8e7a6d4-2ef5-562a-b59d-07708f51071d |  | note | ––––––––––
text | 65264fd0-8c72-507c-9171-198f01216d90 |  | textbox | Bound Right
text | 46516c58-9b3c-5c27-9fb5-cfa566ba681a |  | textbox | Bound Right - Left:
text | 77b8c5b9-872e-5694-ba98-06ff2c215cbd |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | 995eed9b-e439-5211-ba72-fa3369282a37 |  | textbox
label | a18474b1-5ba0-500c-b97d-1780e4c78f06 |  | note | Measurement taken from straight edge to surface level
text | a25cc02e-8ec3-56c2-a1d3-4c9534aff1a0 |  | textbox | Bound Left
text | 452f6d53-7555-50f1-a9ae-e8c9ad4f682e |  | textbox | Bound Left - Left:
text | 923a08f2-977c-50dd-8b27-c7500eee5977 |  | textbox | Bound Left - Right:
label | b2736d17-d8b2-56b5-9837-eae5c7cd3fdc |  | note | ––––––––––
text | cb15447e-ba2e-59f1-b97a-88b3110d256b |  | textbox | Bound Right
text | 3563c2bc-b4cd-5f9e-aadf-c43a96230f13 |  | textbox | Bound Right - Left:
text | 2261ee7e-6818-585f-9a48-0c5082b2c228 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | aeaadfa1-4035-59dc-9f61-3650425c942c |  | textbox
label | be143674-1e52-561e-b56f-3a699875dbfa |  | note | Measurement taken from straight edge to surface level
text | 7817140f-1a3d-52b3-ae42-b823ed5d6012 |  | textbox | Bound Left
text | 1e529ee5-dd15-52c3-908c-c5ed4d770c10 |  | textbox | Bound Left - Left:
text | 0db22940-c5fc-500b-9476-aee47cbdc54f |  | textbox | Bound Left - Right:
label | 116e5340-f99c-5f87-9fec-453cdbe8631b |  | note | ––––––––––
text | 7ba52c54-6555-5769-9c91-1b5816443d4d |  | textbox | Bound Right
text | 3d6c9f67-e604-5be3-b753-877d2bbcc09c |  | textbox | Bound Right - Left:
text | 401d6970-28bf-5210-8b78-e6b404ac5747 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | 6e2307f6-605b-5608-882e-39b4cbe4fb36 |  | textbox
label | c43a52fd-438d-50dd-8b74-c53e2fa71173 |  | note | Measurement taken from straight edge to surface level
text | 8cff1552-37a1-567c-a463-24f6822b19b7 |  | textbox | Bound Left
text | 48c933f1-48b7-5f2d-9d86-c39ffaaba173 |  | textbox | Bound Left - Left:
text | 92275a68-a0f7-581e-85db-9ea5cb65b06c |  | textbox | Bound Left - Right:
label | cbc4f8ce-0a81-570d-89f4-fd9b15acb2ed |  | note | ––––––––––
text | cfc398d7-44c5-56e0-a0b0-0bb00c4b281e |  | textbox | Bound Right
text | 32161ec4-4e73-5dec-9bb3-cddfd6f4b64f |  | textbox | Bound Right - Left:
text | 8e48253c-ed5a-5bff-a212-d8e45a256e26 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | 9a87c76f-6967-5cfd-b9b8-0d6685de6acb |  | textbox
label | 0c5ea306-2b67-5e4c-96c4-bfe026bf59b1 |  | note | Measurement taken from straight edge to surface level
text | 1a432006-58b4-5f1a-a89d-5c1535d81348 |  | textbox | Bound Left
text | 863bb107-f842-596c-ad49-1b93ddb3e624 |  | textbox | Bound Left - Left:
text | 1bc328be-0f00-5abf-828e-c7d14182491a |  | textbox | Bound Left - Right:
label | 42528aa0-48d7-5840-b9d3-770613ec04c6 |  | note | ––––––––––
text | 2b946db9-a6e9-593d-9261-f06e66d08c2d |  | textbox | Bound Right
text | 3a361744-0cc9-533e-b7fe-5391f3fbc6fd |  | textbox | Bound Right - Left:
text | 3249b266-0857-5994-bb87-cf0c587844bf |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | 935a83d6-e10b-57a8-9758-05dda7a05506 |  | textbox
label | 9c83eaf6-2b0b-50d7-bc7e-f0ea26bcac78 |  | note | Measurement taken from straight edge to surface level
text | 96a28ba8-337c-5a4e-be41-bc75c2681e80 |  | textbox | Bound Left
text | c48e2c6a-ccff-53c1-90a2-8139007c7bd9 |  | textbox | Bound Left - Left:
text | e69896a0-a839-5707-9622-667f65a2e1fd |  | textbox | Bound Left - Right:
label | da4c9665-c6ce-5e05-b6f6-741b26c54aa1 |  | note | ––––––––––
text | 090ab2eb-4f17-53f0-ae88-febef61c5279 |  | textbox | Bound Right
text | d653b8e1-ff9a-5ed2-a0c3-e14eec7552e4 |  | textbox | Bound Right - Left:
text | 55a2f298-60cb-5a15-8de0-c793ace998ba |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | 1fd9c345-7a18-5bc5-aa75-7e1b066164b7 |  | textbox
label | d1d5c134-ec6a-5a0d-9fca-a8d6977b2173 |  | note | Measurement taken from straight edge to surface level
text | 61ce066f-47f0-57aa-aa37-a4dce82db438 |  | textbox | Bound Left
text | cb5d14e8-463b-5785-a4d6-478c77ef14da |  | textbox | Bound Left - Left:
text | 4fac4006-c42a-5522-a5e8-fcef1327eec0 |  | textbox | Bound Left - Right:
label | e5056b60-742d-5843-9c77-3f9bb822e150 |  | note | ––––––––––
text | 783ddb58-b64b-5a4c-be90-2e13b71ebd9d |  | textbox | Bound Right
text | 5f85477a-44bc-5a90-9138-873356a86fe7 |  | textbox | Bound Right - Left:
text | 2d8d3831-0856-51a2-8cb7-900f28fea968 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | 8f98eb3b-9f8f-59ec-9db4-e7d7b73e0306 |  | textbox
label | 6f91e4c4-b9fe-5db2-94b4-843f7af232a2 |  | note | Measurement taken from straight edge to surface level
text | 3bfbc52d-15b7-55c0-ad03-6cdef179c11d |  | textbox | Bound Left
text | 0939510a-9e85-5929-ad1a-bc8a2dca78fe |  | textbox | Bound Left - Left:
text | d5f56541-2979-5e73-84aa-90f7fa476e74 |  | textbox | Bound Left - Right:
label | 89fa01ba-cee7-5bf0-8975-07b0af0bc4ab |  | note | ––––––––––
text | fd014fbe-7837-58df-b142-2c9be00834cf |  | textbox | Bound Right
text | 702342d9-2b8a-5cfa-aeb4-38ea27ca3a42 |  | textbox | Bound Right - Left:
text | c6a2b243-6ea8-5d3a-9f36-a53ed8ea388d |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | 1da80591-5409-50b5-b39b-d1c636467c93 |  | textbox
label | 4ade6d8e-1fa8-5524-b594-4bb65072dee6 |  | note | Measurement taken from straight edge to surface level
text | ab771565-98aa-57e7-8590-12b1d335c416 |  | textbox | Bound Left
text | b35ff412-39af-5239-927c-301bc0e12dc2 |  | textbox | Bound Left - Left:
text | 5a4bff3c-ce8f-54c1-b927-cbc410a0ce97 |  | textbox | Bound Left - Right:
label | 0cdf9925-6b78-59f4-8d31-e852c4329826 |  | note | ––––––––––
text | 68f8d581-fbf6-50a5-99fc-c92636038bd5 |  | textbox | Bound Right
text | 5fcbd1bd-e498-5bec-baf7-9ba6876a86e1 |  | textbox | Bound Right - Left:
text | 2f4fc7d0-adb4-5135-b651-5da5ada9325c |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | 3b562440-55c0-52e1-ad14-fc05ee3e9795 |  | textbox
label | cf9d63d2-570e-52d3-8dcf-83b14183152d |  | note | Measurement taken from straight edge to surface level
text | 76ed6824-666f-527d-84c4-ef4cb239538e |  | textbox | Bound Left
text | d5f7a3c6-b6a2-5188-b308-86570539a104 |  | textbox | Bound Left - Left:
text | 8da42575-0446-5d36-a200-5e8a5d3aa9be |  | textbox | Bound Left - Right:
label | 2d703fe2-a7ab-5369-bbcd-04c2a7232328 |  | note | ––––––––––
text | d6adaf97-31c4-52ba-bfa1-be2bbb49ca25 |  | textbox | Bound Right
text | d64a1b7c-7b75-5766-886a-e1800bde631e |  | textbox | Bound Right - Left:
text | b29f14de-faf8-559c-9d52-d93eef7f69ed |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | 816baa4d-deeb-5bff-a9f8-70b929f29274 |  | textbox
label | 33eadbd1-3dc5-58a5-9246-af2e5d21eb9b |  | note | Measurement taken from straight edge to surface level
text | b6e4582a-c446-5b2e-9182-524f7934c085 |  | textbox | Bound Left
text | 7549c887-4c87-5afb-acd6-9038616bc7d1 |  | textbox | Bound Left - Left:
text | ed3f000a-2d89-5c17-a83f-b91e7fa1dafe |  | textbox | Bound Left - Right:
label | c3d3593a-b4d0-50e3-83dc-300f45736bc6 |  | note | ––––––––––
text | 80c55f3a-a1d9-5847-9431-597a2d89d2be |  | textbox | Bound Right
text | a6abe2e8-859d-58e1-858d-1c80721e69b1 |  | textbox | Bound Right - Left:
text | ffed0534-53fd-5e0e-bb86-7c7106da2437 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 8071be5f-1878-50f2-8aba-8b46c6bdb073 |  | textbox
label | 1963fd54-7a80-5609-8725-1821bfdf7851 |  | note | Measurement taken from straight edge to surface level
text | 60af88e6-e163-5ab7-89ee-c2f56e436a20 |  | textbox | Bound Left
text | fe4b72de-863d-5bfa-870c-01308967119c |  | textbox | Bound Left - Left:
text | 67a5a18a-61ae-5019-aebf-7f47d1648cf8 |  | textbox | Bound Left - Right:
label | 1e804593-b52e-56e5-9cbc-43cfb5fac2da |  | note | ––––––––––
text | 52136c63-a2b4-515b-b7ee-55d38bb562be |  | textbox | Bound Right
text | 0ef14e9a-0441-52aa-940e-7509180af3b4 |  | textbox | Bound Right - Left:
text | 4f498316-ba27-53ee-96a3-c19f9798a897 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (17)
text | 4e021122-c241-5b3a-bfd9-82094cf2f5f1 |  | textbox
label | eb74cf50-ea66-5db9-97f9-ec55955620c2 |  | note | Measurement taken from straight edge to surface level
text | 815a8553-8cf2-5e9d-a049-a244892b9d32 |  | textbox | Bound Left
text | c0fbb48d-395c-5ffd-808c-68df1236ee7d |  | textbox | Bound Left - Left:
text | d55a75c2-751d-5466-adfa-8bf5f8fec81d |  | textbox | Bound Left - Right:
label | 069d20fb-4b91-5695-9e54-584fca60e662 |  | note | ––––––––––
text | 109372d3-eb5d-5ed1-8476-f4b26d33eec9 |  | textbox | Bound Right
text | 427c4e81-922d-5ae4-b127-d3e5a6e55e22 |  | textbox | Bound Right - Left:
text | 13486197-3857-5a0f-8467-debc1f80f763 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (18)
text | 717caec5-6566-509e-86b7-b091dcc9d7b8 |  | textbox
label | 0627bcad-c1eb-5c27-a3d1-511110d3f95d |  | note | Measurement taken from straight edge to surface level
text | 190e9a69-5645-5440-8e5e-1d318d08aee2 |  | textbox | Bound Left
text | 34fda833-28fe-5b9c-9a82-9afb45441709 |  | textbox | Bound Left - Left:
text | 61d7cd59-9810-5e6f-8ed0-68ac18c13ce3 |  | textbox | Bound Left - Right:
label | a303fd7d-6db1-52e8-bc61-6289e56ce2ea |  | note | ––––––––––
text | 69e4ef68-76f9-5a95-b16b-e4ee75c40f0f |  | textbox | Bound Right
text | 0963fbcd-c18f-568c-a576-01bffa0255f7 |  | textbox | Bound Right - Left:
text | f08829b2-09b2-58a4-a9c6-6feec13371f6 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (19)
text | d67cfc4a-f81b-5747-8480-ea6561257f08 |  | textbox
label | d18e7b65-64c7-513e-a7fe-5de03f6dd9b7 |  | note | Measurement taken from straight edge to surface level
text | fa752585-e5d9-5b83-a1c0-07dc0e87d3d9 |  | textbox | Bound Left
text | 9a554a4d-b760-569b-9521-b6fb59db3d52 |  | textbox | Bound Left - Left:
text | 8823df05-b7a0-5464-bfdf-e4ad1544061c |  | textbox | Bound Left - Right:
label | eaa2d3a6-2683-572a-b851-be9177ed4b65 |  | note | ––––––––––
text | 8e8d8866-dfc3-5a90-b9e1-142ee1230ef9 |  | textbox | Bound Right
text | ae2fc34f-3b0b-57a0-b18b-d0c7448b8f6f |  | textbox | Bound Right - Left:
text | 5284f27e-19c6-5750-918e-6901b45ffe9f |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (20)
text | 473ca4ab-a920-5c0f-92b1-899947faabe3 |  | textbox
label | 018742e6-2a93-5e88-bd4f-df17e129f71e |  | note | Measurement taken from straight edge to surface level
text | 65395114-0761-591e-856d-4885ffe71c48 |  | textbox | Bound Left
text | 990f1e6a-416a-5ccb-b736-0c8aa21a51d2 |  | textbox | Bound Left - Left:
text | 320cb02d-e1be-534b-963a-41807dbd6370 |  | textbox | Bound Left - Right:
label | 3558e2be-ffaa-5c7c-a348-5ca9b7899022 |  | note | ––––––––––
text | 4b5dad61-023e-54e3-a1e5-48f71b8efe4e |  | textbox | Bound Right
text | 15e53579-9869-59d7-955a-4baaee58ad76 |  | textbox | Bound Right - Left:
text | 91049d72-cc1d-5b64-9c2e-04370d80db73 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (21)
text | 33ca3fb4-7e7d-5ab2-80db-8e402b5e5c22 |  | textbox
label | 448ab753-0adf-574f-acc8-994f5c8b1f30 |  | note | Measurement taken from straight edge to surface level
text | 0d5baac5-3dcf-574c-9611-4692e87d14e0 |  | textbox | Bound Left
text | 5f79be93-47c3-5729-b9c4-79248e55d225 |  | textbox | Bound Left - Left:
text | d89611f0-59f4-57d1-842c-bc82d3db68a2 |  | textbox | Bound Left - Right:
label | 98c118b1-9d2c-5aeb-b5b2-653c82654b08 |  | note | ––––––––––
text | 66c05965-8d74-5685-b382-90209194b067 |  | textbox | Bound Right
text | 2f2e795a-0852-5cbe-a304-fb47ab3a770f |  | textbox | Bound Right - Left:
text | e2c999b5-9cc0-5ffe-a6c9-bf0c29ac999b |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (22)
text | 0d24fd6a-97ac-53d9-ba3e-36f75ea05689 |  | textbox
label | a81826db-8bd4-583c-974b-a548cb3ea7ec |  | note | Measurement taken from straight edge to surface level
text | 2fa1420b-5ebc-518d-af8b-b485c8232b5e |  | textbox | Bound Left
text | 8e610976-86bb-5324-93e4-3d3b3f7c7679 |  | textbox | Bound Left - Left:
text | ec7f84b7-4e38-5dd7-8351-bc749e244fca |  | textbox | Bound Left - Right:
label | a4ddbae3-c9c9-5687-aa19-926b49135988 |  | note | ––––––––––
text | 0edfad93-c483-52be-aea9-957d0317d146 |  | textbox | Bound Right
text | dfa2f0d5-a5bd-5080-b2d9-9ee39fa16780 |  | textbox | Bound Right - Left:
text | 7342a6c1-1b70-5cc8-ad49-142225ab0e30 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (23)
text | 9b6fe5de-645b-590a-a4ed-075b7f59ae55 |  | textbox
label | f7ff168a-b5f1-578d-84b5-06a62b1155de |  | note | Measurement taken from straight edge to surface level
text | 2f08ac34-fcfa-5ce6-8acf-ef93b349a954 |  | textbox | Bound Left
text | c966849e-3905-5c38-ad62-642cf68ac4d6 |  | textbox | Bound Left - Left:
text | 89a75bda-589b-585b-b29f-640fb3ca1362 |  | textbox | Bound Left - Right:
label | 0a508756-66e1-5e06-9cdc-0dd107683bfe |  | note | ––––––––––
text | a81fbe4f-a07d-5a71-ae22-a357d65221a0 |  | textbox | Bound Right
text | c7695f6b-386e-53d2-9f1d-3a4cf6d6bee6 |  | textbox | Bound Right - Left:
text | e8d28f07-e700-518e-aef2-6d3589d1624f |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (24)
text | 1576365e-2f01-5642-b6c8-0981b16f54f1 |  | textbox
label | 0a403890-f32d-5d9d-b5a0-be01a0843781 |  | note | Measurement taken from straight edge to surface level
text | ec755512-a673-5aae-93c3-fa738b234a4b |  | textbox | Bound Left
text | f64171dd-0ad4-5e30-a467-53d152bbc9da |  | textbox | Bound Left - Left:
text | 12526088-5ff9-5429-9790-b2ae5333222b |  | textbox | Bound Left - Right:
label | 54395948-2f9d-5489-a6ca-840394538857 |  | note | ––––––––––
text | fe6d3bbc-58e5-5c26-81cb-b6d45bff4ef0 |  | textbox | Bound Right
text | 0bfffdff-c857-5677-9519-e0cacbd87d03 |  | textbox | Bound Right - Left:
text | 9107df97-aeb7-5e24-aadb-e4f63107f9e3 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (25)
text | ca1c24d6-fe4f-5926-a676-c333fded1ba5 |  | textbox
label | f7df284f-6bdb-5909-b31e-3f4b5bb5e3ab |  | note | Measurement taken from straight edge to surface level
text | a0e7c933-008d-511e-b0f3-34564a70a99c |  | textbox | Bound Left
text | ba595d32-5656-516c-915e-355b212a6393 |  | textbox | Bound Left - Left:
text | df41cb2e-0d59-5b9a-800e-eec4eeb4ae7f |  | textbox | Bound Left - Right:
label | 322f71d1-cede-5187-ac99-7c104aa9d78a |  | note | ––––––––––
text | 96808f38-c547-51aa-b645-c0d62e2a24f7 |  | textbox | Bound Right
text | c309d634-4972-5ccf-aa62-25c900f803a5 |  | textbox | Bound Right - Left:
text | c6cde08e-0f03-5e44-a093-9a3c24d03bbd |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (26)
text | f2640f07-e4bd-54b7-9c42-8090b5cae7e9 |  | textbox
label | cd61fb5c-cd17-520a-b319-a90e2a829402 |  | note | Measurement taken from straight edge to surface level
text | f4b3bd06-8ed6-560d-8a62-99ad19bc3c24 |  | textbox | Bound Left
text | 3c39646c-0863-5317-b2b6-fb02a63b9bf6 |  | textbox | Bound Left - Left:
text | 44e4f47a-3a13-5b19-ba49-d18b2f99ad67 |  | textbox | Bound Left - Right:
label | fa0307a7-cd91-55a7-8212-acf8d0516b37 |  | note | ––––––––––
text | ec247ce0-bab1-5901-bf7d-5ae2996e827a |  | textbox | Bound Right
text | 2edd1eb6-29fd-5403-a7d7-58079dd1d6df |  | textbox | Bound Right - Left:
text | 2d435444-4429-5746-9747-804dffd1c100 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (27)
text | 387539a5-8259-560d-8022-1eecb955ddb6 |  | textbox
label | b3f66b70-4520-5e71-b4b6-8da7bbcfacd1 |  | note | Measurement taken from straight edge to surface level
text | 53030b42-8564-5bb8-b8f8-5481a873a59f |  | textbox | Bound Left
text | 760bb409-d3fe-58c0-b1af-2fd610e50ab8 |  | textbox | Bound Left - Left:
text | 001864dd-65ab-5001-80ab-bd32f619ddf2 |  | textbox | Bound Left - Right:
label | 7c83bcca-2463-580a-8df5-b273698c3267 |  | note | ––––––––––
text | 3f26105e-a071-5cd2-a831-964616c1ce53 |  | textbox | Bound Right
text | d7ef3942-826e-5566-b7e5-31a1615b6c06 |  | textbox | Bound Right - Left:
text | c158f826-867c-5c1b-85a8-4a615a3ec2bf |  | textbox | Bound Right - Right:
checkpoint-group |  |  | section | Cross Fall Check
checkpoint-status |  |  | checkpoint | Cross Fall Check:
label | c1cd0bc7-7ff8-5bc9-87eb-76c847f46457 |  | note | The cross fall between 2 points more than 2m apart, traverse to the centre line shall not depart from the design cross fall by more than 0.5% (Measurements to be undertaken at a frequency of 1 every 100m)
label | 237d1edf-8393-52f6-81f1-6b38471f421c |  | note | Note: Left and Right when facing increasing chainage.
checkpoint-status |  |  | checkpoint | Chainage
text | 664c4574-172d-5a72-ad66-3d5d423f437b |  | textbox | Bound
radio | 051c4303-6d40-53ca-903d-c78ca64f22be |  | radio | Left Lane / Right Lane (Select one) | Left Lane,Right Lane
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | 2d65e017-fcca-5f00-90c6-434617386ee4 |  | textbox
text | 5025c7a1-7bb3-5072-8d89-ecf8e7326235 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | ed302977-4035-531f-8afb-1d307f244fe1 |  | note | Cross Fall tolerance <= 0.5%
text | f5dc9546-a9e4-5b8c-80bd-e10c97eaa71f |  | textbox | Calculated Cross fall
text | 750dda77-c2e3-5313-8d9d-1fa64af4255d |  | textbox | Design Cross fall
button | b48bf3dc-66ea-5fe7-946f-44c486783064 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | 09b32439-2287-5ee2-bae5-8379089d4a36 |  | textbox
text | 7c51f382-bdf3-59d4-ab0c-c6cb64572c50 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | d5a295ae-305c-5c7c-b71a-b22f0799dd92 |  | note | Cross Fall tolerance <= 0.5%
text | 5cc631a8-7e66-52a0-936c-1151e5a7872c |  | textbox | Calculated Cross fall
text | 4a86a3f2-16b0-5cd0-9978-e2301b06d98b |  | textbox | Design Cross fall
button | b939c0f6-cf0f-5848-810d-59cea23832d8 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | 13b57d50-c79d-529d-87a8-f60c1851531c |  | textbox
text | 24085c88-e101-5afc-b7a9-4700f6e45a57 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | fc9f2cfd-c496-5cf3-be43-c0cbd332ccb5 |  | note | Cross Fall tolerance <= 0.5%
text | f4d5282e-c1d7-5d1b-a154-ec5bd62a4681 |  | textbox | Calculated Cross fall
text | c739eafd-78e7-56a1-b1a5-5ea37484c766 |  | textbox | Design Cross fall
button | 72133ea4-aae9-540e-9f24-a6765a242719 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | 5230fb52-2d7a-5dba-8778-3b56afad03d9 |  | textbox
text | 946d6834-8169-587d-b8f9-72f951697766 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 8cc14ee6-1c32-5c43-9385-9b49c4e6b713 |  | note | Cross Fall tolerance <= 0.5%
text | 1587148d-2036-515b-860f-11b0c1760883 |  | textbox | Calculated Cross fall
text | eec1e0ed-109e-5271-9fcc-704928f9bb19 |  | textbox | Design Cross fall
button | 3a50c8db-b895-5670-b7eb-abe49c0f1f36 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | 9e72f5d4-e44e-51d3-89d4-d2d03499b195 |  | textbox
text | 2570048a-1330-52b9-8e8e-fdbb2b96c19a |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | dfe03200-b2ad-5799-8475-30db1f958978 |  | note | Cross Fall tolerance <= 0.5%
text | 016e88ee-9dba-5508-a5f4-56964b464c9d |  | textbox | Calculated Cross fall
text | b3ada4ed-fb78-59d7-beb4-bf320aa58477 |  | textbox | Design Cross fall
button | e8e1b6b9-0f66-5eed-82ab-b1f4e4f8f839 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | 70088175-6d79-5420-84bd-b5181f1c1ed5 |  | textbox
text | 80b99d4e-2d35-5d10-ada8-0be8fb16a83d |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 46cfb937-2a9c-5bd0-a185-72db3083cb2b |  | note | Cross Fall tolerance <= 0.5%
text | 65db414b-f1ba-5fa7-929e-c4b4a3869b38 |  | textbox | Calculated Cross fall
text | c5621ad0-eb5a-59dd-aa44-1b225678e3bf |  | textbox | Design Cross fall
button | ddabbf77-7b83-56ba-a018-34292c953093 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | 765ccc78-1583-5873-b670-58fae9934807 |  | textbox
text | 6980f47c-df27-5526-b8ef-3362c19a63de |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 99ac9674-4fbb-5bc1-b437-0e9284a8ae99 |  | note | Cross Fall tolerance <= 0.5%
text | 1f83bd32-f161-5dc1-ad1c-0f6bc51ddf69 |  | textbox | Calculated Cross fall
text | d85af46c-b367-5a5e-ae98-1d370f1e7cd5 |  | textbox | Design Cross fall
button | 30833d8f-8735-5511-9bb8-50091fcc46bc |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | 8d51603b-2906-567f-a3c1-a92760b57f21 |  | textbox
text | 6b17a098-1c4c-5e9f-b85f-d71868a525bd |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 31c1db06-3e78-5983-9887-51f2993f7bdf |  | note | Cross Fall tolerance <= 0.5%
text | 1fe67b11-6180-546c-ac40-652c40b1aee8 |  | textbox | Calculated Cross fall
text | 02bdadd4-1d3b-5bf6-80a5-c83b9586de7b |  | textbox | Design Cross fall
button | 193eed54-595a-5f13-bf8c-327e3fb5f4b9 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | 66d0cbfc-a4dd-5afc-812b-2522eca93bb6 |  | textbox
text | 30d89ee5-7d5b-58f1-87a5-743cd93ec6a1 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 7dff83bd-b571-5d63-9274-876b10e82a58 |  | note | Cross Fall tolerance <= 0.5%
text | 15370f15-33c4-5e3a-83d1-20894ac3c089 |  | textbox | Calculated Cross fall
text | fbf467d2-5c56-5782-af57-4088ae14c8bd |  | textbox | Design Cross fall
button | cfea47dd-af7b-533c-be60-e8ab332cab53 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | 92d9818a-cde7-5835-aec3-9aba013efe61 |  | textbox
text | caf7eb5d-fc3e-5f24-9491-ffeaad0f0478 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | b6bc361c-b5cf-5437-8c82-997286da5508 |  | note | Cross Fall tolerance <= 0.5%
text | a345e1b2-c296-57fb-bc43-38b4a335202b |  | textbox | Calculated Cross fall
text | 07c77c2a-30b4-5a5e-8148-cce79f8890ea |  | textbox | Design Cross fall
button | c2bb89b7-df47-591d-9780-d6b071510293 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | 0840ab14-6b88-5e0b-a7d1-a6cecd6509b9 |  | textbox
text | 0b8113ee-f59f-5ca3-ba17-b153df9f928a |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 80ba30c6-98d0-5eaa-b1ac-99edf46f647a |  | note | Cross Fall tolerance <= 0.5%
text | d797e02c-d57f-5558-950a-0393d0a9f49b |  | textbox | Calculated Cross fall
text | afdfc9e8-7b4e-58d3-9040-cf54d4a2d6e7 |  | textbox | Design Cross fall
button | 2b7fcf21-b265-5593-9061-e5a9b1d2d231 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | bbc2eab6-a635-54a2-b5be-c75fb87a909a |  | textbox
text | 07bf40bb-4aa5-5266-8b97-db8b98a7cfc3 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | a2a39f41-3ce8-5857-be9b-8e59762f049e |  | note | Cross Fall tolerance <= 0.5%
text | a50cb5d2-ac70-5c7c-8edb-c40a04e1bd1b |  | textbox | Calculated Cross fall
text | 14df3d94-0bbb-5b11-8ebd-81ceb163fc46 |  | textbox | Design Cross fall
button | 95cbb5e9-974e-57a3-8b67-75826eeab2c9 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | 4210d9a5-35a2-5c77-b3d9-721715062687 |  | textbox
text | 25837365-a827-5c81-9fae-d65ac31f4893 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 5b4e2809-0a96-5e63-b3ad-655cfb1d18a4 |  | note | Cross Fall tolerance <= 0.5%
text | 12786ee9-2576-50e6-88ee-6f8a7804c448 |  | textbox | Calculated Cross fall
text | 7dba8262-016b-5acb-818a-133e1a7c0b5a |  | textbox | Design Cross fall
button | 7b8c7b64-f456-5141-a24a-023b7b1cdd7c |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | 0ad920db-b965-5586-8ce8-871768369945 |  | textbox
text | 6c3486e1-376d-5314-9d10-e7fbd5e9b275 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 99771771-57c5-551d-8330-841972c4fed4 |  | note | Cross Fall tolerance <= 0.5%
text | a04672c5-fb8d-58a3-9b5e-48b62d06801e |  | textbox | Calculated Cross fall
text | 2d408a76-e5b1-5787-abbb-c2a420320ea8 |  | textbox | Design Cross fall
button | 8ab5e08d-5232-58fe-8961-fba862404769 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | e33ccbeb-c493-5017-bdf1-d6e41a39bc16 |  | textbox
text | a9bb79e0-0d51-5db8-852a-e4a5bb8140cf |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 47c037d5-0080-5698-bd80-eebfa6937705 |  | note | Cross Fall tolerance <= 0.5%
text | 042ebb43-4757-5fcb-8922-b6a2282347e2 |  | textbox | Calculated Cross fall
text | 661c7ee7-8f33-5fae-b4e7-1a3140a08d28 |  | textbox | Design Cross fall
button | d4b5a7f8-ff1a-52d0-b9ac-56c4b9a6f7bb |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 824a5acc-1758-5748-b5f0-85b146d4970e |  | textbox
text | 0e01dba9-56f2-5668-b2d2-70f082e1eaab |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 57101c82-49cd-5ab5-88c3-0d048a8038d5 |  | note | Cross Fall tolerance <= 0.5%
text | 1543ba83-4bfd-5136-8bfd-05985c92e719 |  | textbox | Calculated Cross fall
text | c530dfdf-9894-5b3c-9b94-57f5d7005d34 |  | textbox | Design Cross fall
button | 1d6fe066-5d4f-5664-83bc-9a8c10304211 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-status |  |  | checkpoint | Pavement Construction Test Results Spreadsheet – Tests Completed, Checked & Signed
checkpoint-status |  |  | checkpoint | Surface Finish Check
label | ad9922a5-1af6-5c92-8472-89e98ffd6134 |  | note | Site visual Inspection carried out by CPS Engineer & Construction Manager after sweeping and prior to sealing taking place.
label | 4d02dfa9-38ba-5bc3-af45-01c712b07c2d |  | note | Checking that the large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping.
checkpoint-group |  |  | section | HOLD POINT – Final Surface Sign Off & Approval given to Seal Area
checkpoint-status |  |  | checkpoint | Final Surface Sign Off & Approval given to Seal Area
text | 4e2ff48f-6d5c-5d5d-8bf8-987ad9f8e008 |  | textbox | Name: Site Engineer
date | f946d54c-4762-5b18-a49a-eda96c311a4e |  | date | Site Engineer - Date:
text | e9b46678-62a5-5f9f-b1b1-9746a16ea3e0 |  | textbox | Name: Construction Manager
date | 8483c27e-944d-5f89-a625-9309b7deba1c |  | date | Construction Manager - Date:
text | e9f82647-8972-559b-958d-87eb3e94f31c |  | textbox | Name: CPS Engineer
date | a2616465-bb06-50dc-bbe2-319f5b859cdb |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) |  |  |  |  | Yes | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) | 6baec0e3-02ac-46ae-aae8-8cb3e326b51e
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 59aa3793-30f3-50b9-8b89-3edf3cdcf188 |  | textbox | Pile no:
text | 72801494-dcff-58dc-8798-414c3e0bd9e9 |  | textbox | Address:
text | 069f117c-16b6-5bb1-aa5e-045541da7000 |  | textbox | Area:
date | 2f008aaf-4aa3-503f-910a-f0c86622b54f |  | date | Start Date:
text | 8e6e3901-ae77-5906-9190-96cab370ce51 |  | textbox | Start Time:
date | 57f8bb74-6426-57ab-a499-3bbc6e2ae7f9 |  | date | Finish Date:
text | 26924288-55c6-5073-a9d5-4d7e7c505f86 |  | textbox | Completion Time:
checkpoint-group |  |  | section | Piling Bore Log
checkpoint-status |  |  | checkpoint | Pile Diameter (Circle):
text | 62b16fb6-c469-5483-9486-cb415555f9b7 |  | textbox | Casing Length: |  |  | m
text | d329cd64-4044-5ad4-b74c-4a368101a507 |  | textbox | RL Ground Surface: |  |  | m
text | 0fbcf773-c039-5001-8659-76dd3a19e644 |  | textbox | RL Top of Casing: |  |  | m
text | 9763acdc-80ce-5940-a8a5-d48fc23c16eb |  | textbox | RL Bottom of Casing: |  |  | m
text | 4fc7e046-0b15-55f8-8da1-470793de3ffe |  | textbox | RL Underground Water: |  |  | m
checkpoint-status |  |  | checkpoint | RL Founding Levels:
text | b266db71-88ce-5074-b204-914dcf0ba53d |  | textbox | Constructed: |  |  | m
text | e080e398-1a4b-5eea-86fd-480c47998921 |  | textbox | Design: |  |  | m
checkpoint-status |  |  | checkpoint | Shaft Length (top of casing to founding depth):
text | 99cf5c67-a397-5966-9cb8-27aec5cc0746 |  | textbox | Constructed: |  |  | m
text | f1037be3-5126-56e2-80fd-5778b5bd50fb |  | textbox | Design: |  |  | m
checkpoint-status |  |  | checkpoint | Pile Inspection (Site Engineer):
text | 2e2879d0-f783-5aac-80df-35633bb28998 |  | textbox | Name:
date | baa34219-d1f8-53b5-97b9-2ed82e0aeb23 |  | date | Date:
text | adcc02c2-9474-5a69-87aa-d8433a70c707 |  | textbox | Time:
checkpoint-status |  |  | checkpoint | Pile Inspection (Design Engineer):
text | 1b063e6a-da8f-516e-aed0-cdb47b946320 |  | textbox | Name:
date | 770b862b-bff3-522e-b260-0c9c61065e8d |  | date | Date:
text | 95820456-3475-512d-994a-66c295ea252b |  | textbox | Time:
checkpoint-group |  |  | section | Depth from GL
checkpoint-no-status |  |  | checkpoint | 1 - Depth from GL (m)
text | 5fb0f89c-e2bd-55fc-9fa1-2c7718892d89 |  | textbox | Depth from GL (m):
text | ec91d355-ff4f-5253-9683-7d738968e811 |  | textbox | Soil Description:
date | 4586cd94-b89e-5908-b3b6-cc4c80eb91ae |  | date | Date:
text | 2483f64d-b198-5923-962c-b971b87252b0 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 2 - Depth from GL (m)
text | d949d79c-2bc7-5b44-91d7-530f7ea0c04b |  | textbox | Depth from GL (m):
text | e2d15935-b0f5-5d86-8946-57087978e053 |  | textbox | Soil Description:
date | f17240ac-6377-5205-9f55-cf915a33426f |  | date | Date:
text | 0d75b4e9-0e06-5fc6-afbb-cd2ba72b5e8d |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 3 - Depth from GL (m)
text | fccb6616-c903-568f-b207-48c334761fc7 |  | textbox | Depth from GL (m):
text | df5ade37-f67d-50de-a467-9e0cdd33b4ad |  | textbox | Soil Description:
date | b42f9ab5-5026-54fe-8378-60d56b494f6e |  | date | Date:
text | 91981a9a-ec8f-5760-bd0a-f764a663d6ee |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 4 - Depth from GL (m)
text | d1e75735-d7a8-5501-adbe-fb0d8f5cace1 |  | textbox | Depth from GL (m):
text | d7439868-c8f2-529c-9756-a4a13f3aab9b |  | textbox | Soil Description:
date | 180e5f15-110b-5637-971c-51d5312764ac |  | date | Date:
text | 7711b5eb-6628-5419-ba28-4d16d559385c |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 5 - Depth from GL (m)
text | 2c59cd9c-0701-5462-88c0-c308fca736da |  | textbox | Depth from GL (m):
text | be0b3dfa-335d-5841-96f1-167593ecde17 |  | textbox | Soil Description:
date | e341d431-2b33-5c5a-8507-f573941f1dfc |  | date | Date:
text | 84e21671-8fb8-55b6-a085-40098b9aec95 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 6 - Depth from GL (m)
text | 4bfb3f97-724e-5434-bc58-907bbc9bb188 |  | textbox | Depth from GL (m):
text | f1bd6362-54af-5af6-84bc-a388a4dd17ba |  | textbox | Soil Description:
date | d4e2121c-10ac-5e54-891d-dd0c47e5fd02 |  | date | Date:
text | 5357c778-4d80-5ccf-b72f-81d375ff697f |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 7 - Depth from GL (m)
text | b07d9bfd-d63c-55bd-9657-2ffb36f3e44e |  | textbox | Depth from GL (m):
text | be4c3b4b-1414-5f5d-93a6-729167426de9 |  | textbox | Soil Description:
date | 1b694eb9-dbf3-5ac6-8cb1-bf43ef28eb95 |  | date | Date:
text | eebbfdc6-6c25-58dc-9622-de6334b0279f |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 8 - Depth from GL (m)
text | 580868bc-fc4e-53d5-aadd-dc7f6abd8b41 |  | textbox | Depth from GL (m):
text | 68b830e8-ca0d-5c7f-ba25-b90210ee93fe |  | textbox | Soil Description:
date | 2c5ff590-9a01-5dae-8970-801908a5a225 |  | date | Date:
text | c1ab54b8-c273-530d-879d-cf952c99a1a0 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 9 - Depth from GL (m)
text | 962c773e-1095-5020-a1c4-f3000f56f72d |  | textbox | Depth from GL (m):
text | a307f18f-4573-5061-92bb-589391bcf424 |  | textbox | Soil Description:
date | c7e3c690-56e8-5e8b-ad62-124233ee7b4f |  | date | Date:
text | 08e09319-7964-5372-bfd6-7338e4aa4d3a |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 10 - Depth from GL (m)
text | 0e3f6cfe-a90e-5ea6-a6d6-7d435692839f |  | textbox | Depth from GL (m):
text | f1d96b72-469f-51cd-a834-b8d2d884eb0d |  | textbox | Soil Description:
date | fb4fb900-f494-58e2-a90d-fb5aba5b955e |  | date | Date:
text | ca5f8f04-6378-56ec-9290-c76bc5fadc3a |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 11 - Depth from GL (m)
text | 41672869-42c8-51cb-ba9f-d71896871e6d |  | textbox | Depth from GL (m):
text | 4c899851-0a60-53fb-8241-af6b2b6c0e05 |  | textbox | Soil Description:
date | d03c9218-bd38-5c1b-ac50-db2a7441c4aa |  | date | Date:
text | ee901b44-93e0-5cd7-a32f-7e3eb29a626b |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 12 - Depth from GL (m)
text | 29373faf-bbba-5d4f-9689-89d9cf7b4437 |  | textbox | Depth from GL (m):
text | e72d637c-21de-5eae-89e8-71d2bd9599d6 |  | textbox | Soil Description:
date | 44b74bc5-da79-5807-9268-5836cfb1ccfd |  | date | Date:
text | 98b9118f-924f-558d-8c58-4a9a4bdb36e8 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 13 - Depth from GL (m)
text | 2ce31fdd-954c-5025-9c17-aaa10c070eea |  | textbox | Depth from GL (m):
text | 020aaae7-943c-5ac7-9699-c078611e2dff |  | textbox | Soil Description:
date | ca1d64dc-270c-522e-8f07-02216da1030c |  | date | Date:
text | 605da5ff-28e7-5f0c-a60e-5087e9fc2624 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 14 - Depth from GL (m)
text | 28b28828-fd3b-5a2a-8fe4-153cbebf0382 |  | textbox | Depth from GL (m):
text | 39575489-006d-5cce-a31c-8375a5521a46 |  | textbox | Soil Description:
date | 9af32d86-be41-588c-bf43-e8d13e6e31f4 |  | date | Date:
text | 584b570e-d396-5f1a-bec3-836228bbc2e4 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 15 - Depth from GL (m)
text | 53262ccf-ea78-5a75-899a-d549b3cc8295 |  | textbox | Depth from GL (m):
text | 00b40d0a-6ad2-538a-861c-cf91a1108af7 |  | textbox | Soil Description:
date | 773eac9c-5b60-54b6-b8ed-3a4af1f8147e |  | date | Date:
text | cb43a8ed-cd5d-5c59-b3e0-0771e30898b0 |  | textbox | Time:
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | Piling Foreman Sign
text | 5c8c703a-2dee-52e7-a01e-383bad3c71f6 |  | textbox | Name:
date | c01c5e2a-9482-534e-893e-edd1dd71b9c3 |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4046 - Barrier Concrete Inspection Record |  |  |  |  | Yes | CS-4046 - Barrier Concrete Inspection Record | 6bfe4412-9af3-43c5-9617-dbddfe4fccff
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | c9eb58f6-09ed-575b-8b8a-bb32649326c5 |  | textbox | Project No.
text | af19922f-8020-563f-b27c-24dbd33527bf |  | textbox | Location / Description of Pour:
text | 85e4a529-45c7-553b-86cd-7851bcf99b57 |  | textbox | Concrete Grade |  |  | Mpa
text | e216dbcd-ffec-548c-8f45-e11c484be7d3 |  | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
text | 9aef8932-5951-5d27-9d30-a3bc84e183f3 |  | textbox | Pour No.
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | Cleaned and oiled
text | 655f421a-284f-596b-bd8a-73c8de0a187f |  | textbox | Initials:
date | 50bf4bd9-871f-5763-bd1e-9f0ae09416bd |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct profile/ dimensions for Barrier
text | 3ae7e5d4-7360-5ebb-871d-d45c64c384e9 |  | textbox | Initials:
date | 22441ae0-c494-5d1f-8f53-43e4fe91fef4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check set out – 350mm from face of Barrier
text | 5087338d-7ab2-5468-8982-d86a53089cc3 |  | textbox | Initials:
date | d985f0c1-38a9-5302-8150-d3a4228a6c5f |  | date | Date:
checkpoint-status |  |  | checkpoint | Embedded items in correct location
text | a1802f54-9188-584a-b90f-bc67ce7763ea |  | textbox | Initials:
date | 1801eaa7-41a4-558d-9da3-7e87a6c54f30 |  | date | Date:
checkpoint-status |  |  | checkpoint | Horizontal and vertical alignment correct to design
text | 4d32bcfc-1084-5237-93c6-ec9299a7e68d |  | textbox | Initials:
date | 4fb86390-5a87-59cd-a89e-4cfec0067666 |  | date | Date:
checkpoint-status |  |  | checkpoint | Stop-end coated with Rugasol MH Extra, installed and braced
text | be9ae44d-2f38-5134-a3a6-8538e624b61e |  | textbox | Initials:
date | 6785babb-0278-5cdf-9753-2f5c2acb5be1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Grout tight
text | a95d526e-b995-5975-bbd8-90e19871a810 |  | textbox | Initials:
date | 57d3e59a-a6e5-542b-938c-c2f5da350271 |  | date | Date:
checkpoint-status |  |  | checkpoint | Voids set out
text | 7c310d0d-3318-56d9-bd73-c3343a1e15b4 |  | textbox | Initials:
date | fab271de-c284-5187-aa95-1cfa613a49e9 |  | date | Date:
checkpoint-group |  |  | section | Reinforcement/ Strains
checkpoint-status |  |  | checkpoint | Strains/ reinforcement content correct
text | 12481998-8f99-50f0-9cbf-1cb01482765d |  | textbox | Initials:
date | e569a826-cc35-56d2-9a61-53c4fd88090c |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct grade markings
text | 567d19b3-03f9-5046-8d6f-859f22953c00 |  | textbox | Initials:
date | a78780ff-48b9-5a2d-9f3d-4694d2cef910 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct cover
text | 6e7485ce-835d-537a-88c4-09da23aa198a |  | textbox | Initials:
date | 085ac872-f799-57bd-aeb9-5fc68a54daf2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | 8930a171-5165-5efc-a386-758807b6f0ba |  | textbox | Initials:
date | 28b5505c-10a7-5ee5-9d6f-1f095d302c7f |  | date | Date:
checkpoint-status |  |  | checkpoint | Strains placed in correct location
text | 0aa44172-9417-5324-a055-e5755929fab7 |  | textbox | Initials:
date | 39bb39b5-f8d1-5974-a97f-b147940f0f56 |  | date | Date:
checkpoint-group |  |  | section | Subbase/Basecourse
checkpoint-status |  |  | checkpoint | Suitable for Barrier
text | f4fb688e-6aef-516d-a200-50041234cb63 |  | textbox | Initials:
date | 39430cff-1f33-5f2d-8301-aced9c9c292b |  | date | Date:
checkpoint-status |  |  | checkpoint | Cesspit protection in place
text | 8f2c782e-2cdd-5220-b5e5-04178c0ceb91 |  | textbox | Initials:
date | ed86cc0f-ee86-5b50-b37c-4b52ea332e9c |  | date | Date:
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | 4f823ff4-5641-5574-8eca-a0553ade81da |  | textbox | Initials:
date | 08c5327f-fa25-5856-9eba-2a87c1f5cd3c |  | date | Date:
checkpoint-status |  |  | checkpoint | Construction joint roughened & clean
text | 941e2610-92c4-53ca-bbb1-19b53d39da85 |  | textbox | Initials:
date | 4f46056d-3625-5a60-a2c0-2ba9222fcaa7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Road Light/ BG 800 openings secured
text | d843d181-be8e-5f6a-b2f5-de5da81d8b41 |  | textbox | Initials:
date | f7d91d6a-48a6-5d61-a500-2938aa0e672e |  | date | Date:
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
text | 2ebd8bdf-bfb9-5786-a26a-d68616b83428 |  | textbox | Initials:
date | c42d4df2-55c4-59e0-a2fe-88db5e5a9098 |  | date | Date:
checkpoint-status |  |  | checkpoint | CPS Engineer Notified
text | 4970719c-4de7-512a-a9ac-63610d9c599f |  | textbox | Initials:
date | 11bfb706-3a36-5997-a4dd-e998a27ae005 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer & Engineer’s Rep to sign
text | 6c698196-5442-5974-a458-f9dcfdbc4b1f |  | textbox | Site Engineer - Name:
date | 95a7192e-adc1-5d9d-a52b-f0ec7fcd5072 |  | date | Site Engineer - Date:
text | 6405eb40-d6a8-53cf-8bc9-d6cd39c4f097 |  | textbox | CPS Engineer - Name:
date | 98cdc575-324c-5a7e-bdc2-5129c37aa09e |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered
text | d2c17977-44d1-5051-9b4f-b7fc1d5c89ed |  | textbox | Initials:
date | 09b1253e-95f2-5939-aa98-1c34c963483c |  | date | Date:
checkpoint-status |  |  | checkpoint | Slump/flow Target
text | c2ee1396-0452-51f4-98e0-4f499d07944f |  | textbox | Initials:
date | 9db1fcf2-f0f2-5a5b-9c86-399aaa63a451 |  | date | Date:
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
text | 472ef426-6327-52be-83ce-e862928a40c6 |  | textbox | Initials:
date | 9b048229-6c90-58f2-b0ed-891b43340762 |  | date | Date:
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
text | 1afae564-7931-53fb-975f-4c84eb851cf5 |  | textbox | Initials:
date | cdf5dcc8-e598-5108-89a6-594b80a43374 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Vibrated
text | 6b5e57c4-4acf-520d-81df-8a152ce78db4 |  | textbox | Initials:
date | 851c34c3-23f3-5bc5-8fad-4bd2554cceda |  | date | Date:
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
text | 4d0d9656-fd51-5843-96de-426a435482c9 |  | textbox | Initials:
date | f0f8c3b7-4397-5a96-a7e5-883b77e95035 |  | date | Date:
checkpoint-status |  |  | checkpoint | Surface to required finish
text | cd50f76d-7f94-523a-9dce-1a134384d772 |  | textbox | Initials:
date | a483ac03-4695-51ef-8b02-5154bcc1a0d6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
text | c2b79bd8-9b12-5e87-9c6d-0b9d41e34d21 |  | textbox | Initials:
date | 05594515-1ad9-5016-98c2-6bfc730448a9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
text | 9740d0a2-5d0c-54ea-a70e-41738ce516fb |  | textbox | Initials:
date | 23a571f2-5f7f-5840-8d2e-821330d15518 |  | date | Date:
text | e06f3004-0a58-5cf9-8d2b-cdd6c06b6239 |  | textbox | Pour Start Time:
text | 55c5eeca-55e9-5662-bfdc-94cff20d9afa |  | textbox | Pour Complete Time:
text | 45311d0c-92f5-53cc-a29a-6bc7cb04dd62 |  | textbox | Volume Placed:
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Surface Finish F4 or F3
radio | 1b6b49eb-c0d3-50b7-b9b2-fb5639af9087 |  | radio | (select one) | F4,F3
text | afaf5b1a-98da-5f5e-a5aa-2119e1b943de |  | textbox | Initials:
date | 6ce6a6ea-9922-5df7-a61f-c8687a974894 |  | date | Date:
checkpoint-status |  |  | checkpoint | Curing correctly carried out following application of water
text | 6518d774-5430-5fd7-8690-6e303fe69e96 |  | textbox | Initials:
date | 3fe870a7-5518-54a8-bb2b-e78020def9f2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Barrier saw cut within 24h
text | dff6e4ae-4915-5d96-a700-ffc3dc2b0f8c |  | textbox | Initials:
date | bd1686f3-fa83-55a8-ad75-adbc38d7f35d |  | date | Date:
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
text | 054b45a9-6d8f-5cb2-9bd7-6db2badc050e |  | textbox | Initials:
date | 9706a43f-4700-5bfc-9ab2-2a2edc5c193d |  | date | Date:
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
text | 1fa4b99d-3d4c-5314-b163-bcafbc81ef27 |  | textbox | Initials:
date | 7b4e8909-253d-5ed1-b98e-869539dd9a86 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
label | 381ccf74-f1f1-5608-a457-563bed0ed1b3 |  | note | CPS Engineer Inspected.
text | 91634fde-e2ea-58f9-9f73-1e91904c1f1b |  | textbox | Initials:
date | 6a689345-4618-579f-b014-5055ae5a48a7 |  | date | Date:
checkpoint-status |  |  | checkpoint | As-Built complete
text | d1ba7074-10ec-5c92-8f41-0f85d67d31e3 |  | textbox | Initials:
date | 83cce45c-96ad-5fcf-a651-d59d90f2ec99 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 78237217-25e7-592f-b686-04ebefa29dcc |  | textbox | Site Engineer - Name:
date | b0e4ae50-a632-5b64-90e7-652aff2e02bc |  | date | Site Engineer - Date:
text | e6301536-a92d-5a84-8f2b-226856de4d32 |  | textbox | CPS Engineer - Name:
date | 37ce3fc8-fb2a-546b-acac-e6797910a364 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | itp |  |  |  | Yes | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | 770b6e32-6ce5-42cc-a44f-b57055e2d09d
checkpoint-group |  |  | section | Pre-Construction
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 79f83b13-569f-52e5-a9ca-b6fbfd50d7dc |  | textbox | CPS Eng.
text | c3a5e179-0f54-5b1c-ac95-2e9b1c1f0b09 |  | textbox | Site Engineer
text | 04036cc1-181b-5512-acf0-f2381303924d |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Drawings and Specification
label | 0e69d760-b4f5-58ca-b4c9-d97966bba459 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5306936c-ea3f-55ff-9b7b-8334be494e42 |  | note | Detail - Check drawings and spec are the latest version.
label | b1998854-4929-5cfb-b7a1-63b70933b173 |  | note | Frequency - Prior to commencement
label | bba20ce4-39d7-5e62-9920-697756d76b73 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | a00e56da-431e-55cf-8234-baf98115dbab |  | note | ACTION (Hold, Monitor, Witness) - W
label | cdd4758e-87f3-55d8-b324-87c1a57b8fa9 |  | note | Detail - Set out as per design
label | 803829a9-4d40-50b0-9926-2d7c2c827f84 |  | note | Frequency - Prior to commencement
label | 4ef6441d-1475-5a92-93e0-7388dce1a266 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 26f6795e-45bc-5426-ad6a-6042a1bd8879 |  | note | Conformance Criteria - Check against plans for any discrepancies
label | d9ac2ab7-fbcd-5405-9ea6-d684d4a0bd86 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 3 - Material Approval
label | 4b137c95-6607-532e-a71f-22aac00978e4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f9260d02-fc90-5f4c-987f-71e346fedf2f |  | note | Detail - Materials as per design
label | f643a428-6917-5a97-962b-51c3c5224371 |  | note | Frequency - Prior to commencement
label | c2fb43c8-569a-560d-b8ff-2fd690a38a7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 77a16953-d49f-5899-a9d4-add8886b203c |  | note | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint-status |  |  | checkpoint | 4 - Location of underground services
label | 0dda9022-e22c-5de0-bddf-c5f9d67a0559 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 117fa14d-8b9c-58cf-b57a-12d6ed900100 |  | note | Detail - Ensure undderground services are positively identified and asbuilt. If the service conflicts with the design confirm resiolution with CPS
label | c30225b8-2ffa-5b4a-89dc-cdad703539a1 |  | note | Frequency - Prior to commencement
label | b3bee91e-afd4-52e9-b74f-fc209ef157fa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Drainlayer Qualifications
label | 11d0be2a-3d97-5298-899b-08804ebe22d0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ffbfdeae-0dc4-5623-9ec4-19b252b625f7 |  | note | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | 941dd3ec-c119-50d9-b8c5-edfbe808442a |  | note | Frequency - Prior to commencement
label | ccfc206d-debd-5180-bfc2-d394a38057e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 36421d97-414a-58e0-8833-4dac62c66150 |  | note | Conformance Criteria - Drainlayer Certs
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | 6e361085-f9bf-5ea3-ae92-55301d35b78f |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5b3a719-6db2-53fa-bf84-6f02c23cc3d3 |  | note | Detail - Check subgrade with visual inspection and
label | a750e081-3732-5374-81c1-e686a268934d |  | note | Frequency - During Construction
label | 47968c6b-9496-558c-9f99-6a800cba598b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 982d65b1-510a-58c3-a3c2-720cb24629b4 |  | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | ea6acd3e-448e-5213-b1f8-448b72cb486d |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 7 - Surface finish visual inspection
label | 1768b7ec-dda6-5d2b-af77-b1f23fa7bfc2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 97b39c38-5d89-56bb-89e8-891ddb09c2b3 |  | note | Detail - Site walk over
label | a256a169-8fd0-55e1-9d8f-0131d3cdfff9 |  | note | Frequency - Post Construction
label | 5365fcde-752b-5cd7-b5f0-515342428a2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4f21f253-1d9c-5bc1-8105-af295a9ef691 |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | 6924bbae-8745-5b99-95c1-dd8fb562799b |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-builts
label | 5e019847-5c2c-553f-8837-d785d920a7df |  | note | ACTION (Hold, Monitor, Witness) - H
label | 04cb7e7b-5897-598e-84e6-df89d07c2448 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 5a89915e-0277-5fe0-980f-c754772a6df8 |  | note | Frequency - At the completion of the Lot of work
label | ec83cdbb-a0c4-5b29-90f9-ca9aecafba5f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 4e494b31-4ea7-554e-86e0-1f5384c48844 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | 5c20ad53-eab8-5286-b737-2272f0e4e28f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 00cc0a1c-bd4f-56a3-9b66-95247775e505 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | a9c57284-0bc1-5b8a-b37b-72f8a8b4f491 |  | note | Frequency - At completion of Lot
label | a0804abe-4d7d-51ad-9f66-7f032534c814 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 8700cab0-338e-51d8-a4c7-977e5cfcf9cf |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 87b2b2c0-1327-54fb-a1aa-11838e25c84a |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 9762feb8-90cd-5ba6-883e-5b24b024236c |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4090 - Utilities Check Sheet |  |  |  |  | Yes | CS-4090 - Utilities Check Sheet | 78954d02-bc04-402b-af34-f24176af41bf
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | Underground services checked
checkpoint-status |  |  | checkpoint | Survey Set Out
checkpoint-status |  |  | checkpoint | Correct materials and sufficient lengths on site
checkpoint-group |  |  | section | Material Approval
checkpoint-status |  |  | checkpoint | Bedding Material approval
checkpoint-status |  |  | checkpoint | Hard fill approval
checkpoint-status |  |  | checkpoint | Draw wired is 10 gauge galvanised mild steel complying with NZS 3471
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | Trench correct depth and width
checkpoint-status |  |  | checkpoint | Subgrade check (scalas), min. 3 % CBR
checkpoint-status |  |  | checkpoint | Bedding laid in trench to correct depth (100mm)
checkpoint-status |  |  | checkpoint | Correct cable and duct sizes laid as per service drawings
checkpoint-status |  |  | checkpoint | Gas provider trench approval
checkpoint-status |  |  | checkpoint | Chorus provider trench approval
checkpoint-status |  |  | checkpoint | Power provider trench approval
checkpoint-status |  |  | checkpoint | Services laid with correct spacing
checkpoint-status |  |  | checkpoint | Irrigation provided to all Rain Gardens and Garden Beds
checkpoint-status |  |  | checkpoint | Lot connections laid 500mm into lot boundary
checkpoint-status |  |  | checkpoint | Street light cables laid to pole locations
checkpoint-status |  |  | checkpoint | As built service locations
checkpoint-status |  |  | checkpoint | Draw wire in all ducts
checkpoint-status |  |  | checkpoint | All ducts end capped
checkpoint-status |  |  | checkpoint | Mag Slab laid
checkpoint-status |  |  | checkpoint | Bedding covering services to correct depth (100mm over Gas, 50mm over all other services)
checkpoint-status |  |  | checkpoint | Approved backfill material placed in 200mm layers
checkpoint-status |  |  | checkpoint | NDM tests every 30m³ of backfill material, 95% of MDD
checkpoint-status |  |  | checkpoint | Warning Tape 400mm below finished surface
checkpoint-status |  |  | checkpoint | Irrigation Pressure Test complete
checkpoint-status |  |  | checkpoint | Gas Pressure Test complete
checkpoint-no-status |  |  | checkpoint | Weather
button | 4ee64fc8-8e5a-593e-a4cc-bbb10d5e563f |  | button | Weather | Sunny (check plants not left bare root in sun), Raining (ensure soil is not saturated which prevents proper planting), Frost (No planting to be carried out until frost thaws out), Overcast (Good Planting condition)
checkpoint-status |  |  | checkpoint | Sign Off - Site Engineer
label | 00c0331f-5855-5ef0-95df-6a816bdc7954 |  | note | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | CS-4045 - Kerb Construction Record |  |  |  |  | Yes | CS-4045 - Kerb Construction Record | 7deac9fd-64b1-46eb-a5c3-ab7879415e04
checkpoint-group |  |  | section | Kerb Construction Record
checkpoint-no-status |  |  | checkpoint | Kerb Construction Record
text | 48819678-62e1-5931-af1d-2b9f0ee668dc |  | textbox | Description of Pour:
text | 340deec4-0ef5-54f1-abb0-5d7775cc2c4a |  | textbox | Kerb Type & Dimensions:
text | c9ed0682-470c-58f4-bc15-5d8e21c080aa |  | textbox | Weather conditions:
text | 245c0321-1056-5bf6-a8c8-a919dc53f58b |  | textbox | Concrete Qty:
text | 89bca87c-6020-5a4c-b791-f368aba23f1b |  | textbox | Concrete Grade: |  |  | MPa
text | 6509c059-63bf-5798-85b3-2fb4afcd0ba0 |  | textbox | Dwg No/Rev:
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Correct profile/dimensions for Kerb Type
checkpoint-group |  |  | section | Subgrade
checkpoint-status |  |  | checkpoint | Ensure subgrade construction is complete and suitable for kerb
checkpoint-status |  |  | checkpoint | Cesspit protection in place
checkpoint-group |  |  | section | Survey Set Out
checkpoint-status |  |  | checkpoint | Check survey set out
checkpoint-status |  |  | checkpoint | Check subcontractors string lines for machine
checkpoint-status |  |  | checkpoint | Vertical levels correct to design +/-5mm vertical tolerance
checkpoint-status |  |  | checkpoint | Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
checkpoint-status |  |  | checkpoint | Crossings / kerb transitions set out
checkpoint-status |  |  | checkpoint | Engineer to mark kerb types at crossings and kerb transitions
checkpoint-status |  |  | checkpoint | Ensure channels fall towards catchpit locations
checkpoint-group |  |  | section | Miscellaneous
checkpoint-status |  |  | checkpoint | Construction joint roughened & clean
checkpoint-status |  |  | checkpoint | Correct mix ordered
checkpoint-group |  |  | section | Pre-pour check – HOLD POINT
checkpoint-status |  |  | checkpoint | Site Engineer
text | 0cd42c3f-8850-50e5-af17-aa6801802188 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | 0aa45f11-4d6a-593f-9cba-e117f9107a08 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered?
checkpoint-status |  |  | checkpoint | Correct slump (within tolerances)?
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected?
checkpoint-status |  |  | checkpoint | Batching Plant Records received?
checkpoint-status |  |  | checkpoint | Kerb meters completed in m
text | d2e8ca99-50d2-5045-b0a2-0f2475c86208 |  | textbox | Kerb meters: |  |  | m
checkpoint-group |  |  | section | During Concrete Pour Inspection
checkpoint-status |  |  | checkpoint | Ensure correct kerb type is being installed in the correct location(s)
checkpoint-status |  |  | checkpoint | Constantly check levels and line to ensure kerb is within design tolerances
checkpoint-status |  |  | checkpoint | Ensure protruded kerb has U4 finish
checkpoint-status |  |  | checkpoint | Ensure Expansion joints are installed
checkpoint-group |  |  | section | Concrete Infill Islands
checkpoint-status |  |  | checkpoint | Ensure F3 finish and the concrete level is no higher than the top of the kerb that forms the median/island
checkpoint-group |  |  | section | Tie ins to pre-cast elements
checkpoint-status |  |  | checkpoint | Aprons to be formed around pre-cast elements
checkpoint-group |  |  | section | Pour Time
checkpoint-no-status |  |  | checkpoint | Pour Time
text | c9d6abc2-bfe4-5c48-8149-9530e23678e5 |  | textbox | Pour Start Time:
text | e3aedb11-14a1-5092-8621-03020773c53f |  | textbox | Pour Complete Time:
text | 170e2298-a653-5aa4-a1a3-945342b7e846 |  | textbox | Volume Placed:
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Warning tape to be placed over kerb to prevent any damage
checkpoint-status |  |  | checkpoint | Backfilling to commence after 72 hours curing time
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Surface Finish and levels acceptable
checkpoint-status |  |  | checkpoint | Expansion joints satisfactorily completed
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
checkpoint-status |  |  | checkpoint | Site Engineer
text | 135d8bbe-a64e-5ce3-aa0b-c2748d26108e |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | 98b276f4-bf10-59c9-9546-542b8b92db5f |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Ensure surface varies no more than 5mm when checked with a 3m straight edge
checklist-sectioned |  |  | checklist | CS-4114 - Anti-Graffiti Coating Daily Checksheet |  |  |  |  | Yes | CS-4114 - Anti-Graffiti Coating Daily Checksheet | 8b9a7f85-b03a-471d-8208-a7eadeeddffd
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | fe5086b3-3add-5688-88bf-ea2556b90d8d |  | textbox | Project No.
text | 64d1bd82-3c3c-576b-91c0-3dd64249df2e |  | textbox | Applicator:
text | e7270034-f1a0-5fa8-b2e1-778c8f796a7f |  | textbox | Supervisor:
checkpoint-group |  |  | section | Weather Conditions
checkpoint-status |  |  | checkpoint | Humidity
text | a3a4b9cb-8ac5-5277-804a-03b4c81c53c5 |  | textbox | Result:
checkpoint-status |  |  | checkpoint | Temperature
text | bb3fbdcf-e7ed-52b2-bbfb-b5f665934e2b |  | textbox | Result:
checkpoint-status |  |  | checkpoint | General (overcast, windy etc.)
text | 7b7ea78d-10f5-59f2-9bdd-f0fa574319b9 |  | textbox | Result:
checkpoint-group |  |  | section | Material Application
checkpoint-status |  |  | checkpoint | Substrate Material
text | dcf23291-b870-5340-88b1-5af9b83d5978 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 266c91cf-42ed-5c74-8a82-708a6275b2ae |  | textbox | 2nd Coat WFT |  |  | (µm)
text | e123ecb4-4f4f-5911-a055-8c369261b8a9 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Brand Name
text | ad62fb58-1aca-5204-a1cb-46d7422c2847 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 378f7264-4f54-5613-99be-d3ac0632b6dc |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 95095783-7dd5-54e7-9415-aa1de297a5e2 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Batch Number Base
text | 0c4c4bd7-9f5a-5492-9ade-bd53f9b24418 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 2b82ec1f-73c7-50e3-ac01-47b785b18848 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 60c7ee45-c9d1-5bd2-aca2-0c67f12468f6 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Batch Number Hardner
text | 68bcf2cb-6f17-5f6c-bb06-e4b7112584a4 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 14a47df5-1beb-5938-82e9-e66a4cd1ba4d |  | textbox | 2nd Coat WFT |  |  | (µm)
text | a5679282-b5c1-5299-a586-0b1d03da769b |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Colour
text | 46062a61-8e8d-5f49-8f00-8db2b8195178 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 1adff8a2-1562-56e7-a81d-8f5837749e41 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | f6f4af10-edae-5fcc-b7eb-7cd58cec1df5 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Thinner Used (Ref Number)
text | 595261d8-4ba3-5123-b96c-8883ddc55692 |  | textbox | 1st Coat WFT |  |  | (µm)
text | a44103aa-936b-574a-8dc8-be3ce2cb8002 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 692f2ec6-8b01-598f-8a54-5682730c9dd7 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | % Thinner used
text | 6899f9d5-6f3b-5229-a2c1-3da0fe82c6a9 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 66d095ce-e9a8-5672-848c-5af109994d7d |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 147cff98-5f54-5d06-af29-6cc94e81681a |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Brush
text | e3f0be01-5e80-5281-a2e5-0cd1062a5cb4 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 1a0d177b-d34b-5582-890d-ca8c4f9ae4c1 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | b8d7809e-8e4a-5252-a87e-7a825540801b |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Roller
text | 271e49b3-f989-5a29-b1fa-70ca1c09aa7f |  | textbox | 1st Coat WFT |  |  | (µm)
text | 0e647adf-3f51-5372-9f7a-e3fdbe014f7d |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 9dfb1ef1-af3f-5640-863f-4b8424f162c2 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Spray
text | 85268576-31ac-571b-80a0-dc45339dddd8 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 9d572970-c02f-5532-aa27-e4e29a7c5567 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | f6fa1f25-2295-591f-9066-70ede2247627 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-group |  |  | section | To be filled out by Inspector
checkpoint-status |  |  | checkpoint | Dry Film Thickness (µm)
text | 1ab83756-0dea-5b70-82ca-820e185dc0f7 |  | textbox | 1st Coat WFT |  |  | (µm)
text | e026ecbd-8865-57e1-8305-ee758dd5aa73 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 47165cad-a51c-52d7-b5d4-8bd82bbe904e |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Specified (µm)
text | 901f9c75-12d2-572e-a6ed-e881d9a5dfb0 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 82e22dda-99c0-5726-96ee-964a5b055abf |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 968b34cd-5b2a-537a-bac8-071aa7f00ebe |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Average (µm)
text | ee355cd8-e843-5597-8270-bfe6072b300d |  | textbox | 1st Coat WFT |  |  | (µm)
text | a67dd291-0171-523f-8db0-4cc5e14904e9 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 1c7ff3e0-5675-5840-a1a7-bb238be2c2a6 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Maximum (µm)
text | 1cdaa72d-d202-5d5f-8497-2420fe5172aa |  | textbox | 1st Coat WFT |  |  | (µm)
text | cb055519-b7e3-54d4-86b2-7504c1cd03e7 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 17280c02-9a15-5596-af45-0aad3b1c9fe0 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Minimum (µm)
text | 25f0a1b6-b64f-5d23-a5b6-6c6a119dbcaa |  | textbox | 1st Coat WFT |  |  | (µm)
text | a69f0ba0-3911-544b-bd40-8546817b7104 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 693b0695-dcb4-585e-b3c9-7c08bbc8eb75 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Number of Readings taken
text | e07ee1f8-c36e-55ad-bf2b-3180fa8b2737 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 7c84a74b-f3f5-5e20-97c3-16469c5722e8 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 63d140fa-0e62-5fef-a168-15f241b1cc0f |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-group |  |  | section | Outcome
checkpoint-status |  |  | checkpoint | Passed
checkpoint-status |  |  | checkpoint | Rejected
text | b4b3f96f-c82e-501e-8bcb-7fdfd4ebf92e |  | textbox | OFI #
checkpoint-status |  |  | checkpoint | Rework
text | 35fa3766-e80d-5964-b59c-aef0a684d780 |  | textbox | OFI #
checkpoint-status |  |  | checkpoint | Checked and Accepted – HOLD POINT – Applicator, Site Engineer & CPS Engineer to sign
text | 83377e57-9421-5608-bcb1-f349e9b50e5a |  | textbox | Name: Applicator
date | 54842b89-4e8f-5006-ab1f-ef65640d917f |  | date | Applicator - Date:
text | e4c1f586-b868-5f21-a03e-f4ce4909975f |  | textbox | Name: Site Engineer
date | 2642180e-e646-5aab-8577-08124ffa77c5 |  | date | Site Engineer - Date:
text | 4ddc45a4-c68e-5628-ac6c-d80ca70c3e59 |  | textbox | Name: CPS Engineer
date | 97b9b6a7-30d4-5ebd-a4f8-53cc1ec411fb |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4117 - Guardrail Installation Record |  |  |  |  | Yes | CS-4117 - Guardrail Installation Record | 8d8d2869-30b5-44fb-a00b-575c408f0642
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | d2e50bc8-f2f7-548a-ba5f-ad946c7c555d |  | textbox | Work Area:
text | 3bdff61e-33d7-536f-b099-ec7368264397 |  | textbox | Sub Work Area:
text | 491ea800-4925-566e-a773-d6745200eae7 |  | textbox | Lot:
text | 4ea80722-d364-5847-ab97-12083b166e48 |  | textbox | Sublot:
label | 150466c3-6197-514b-934c-f3817abe9777 |  | note | Document Date: 27/11/2019
label | 72d9d7d5-4989-51fd-b2c9-4b1c8402a1f4 |  | note | Created By: Kirsty George
text | 6b38a51b-e4ee-5ef2-94fd-63f883d3123a |  | textbox | Drawing No:
text | 1be8ed19-9deb-538b-83e5-16e4826e3bb0 |  | textbox | Rev No:
text | 2369d3aa-c15b-503c-926b-efb4f271deaf |  | textbox | Chainage:
checkpoint-group |  |  | section | Guardrail Installation
checkpoint-status |  |  | checkpoint | When driving post, use a driving cap with timber or plastic insert to avoid damage to the post
text | 83f2d871-362d-503f-ac1f-c45737aff3fd |  | textbox | Initials:
date | f7b54828-e77c-5a6d-a68a-555657927c5f |  | date | Date:
checkpoint-status |  |  | checkpoint | Height to centre of rail is 635mm
text | bc478843-0534-5ba8-a195-a82de8c050f9 |  | textbox | Initials:
date | 9772aefc-9bfa-5a1f-b955-b0b34a71e593 |  | date | Date:
checkpoint-status |  |  | checkpoint | Top of post should be a minimum of 20mm above top of guardrail
text | 38293f74-ffc2-5e27-90da-c2e3b0561357 |  | textbox | Initials:
date | e5e1fe16-5b5e-5333-970d-a2490d09f9f0 |  | date | Date:
checkpoint-status |  |  | checkpoint | Post is aligned with flanges rail for road side applications and alignment is alternating for median applications
text | 27de49e2-7884-5a36-8198-88bdd5fd414e |  | textbox | Initials:
date | bcac7e85-4d24-55f8-985a-c5827fabcc21 |  | date | Date:
checkpoint-status |  |  | checkpoint | There is a 90mm dia. Washer between rail and post.
text | ef227bee-f7b8-50bf-b309-1a898e0f5b80 |  | textbox | Initials:
date | c02caed4-0931-580b-9348-6594b2b13f89 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rail is lapped in the direction of traffic
text | 23bf0b9d-46df-5aa7-9f8a-40ed4685da20 |  | textbox | Initials:
date | 0d920536-d3f0-5381-aa83-3c43c754ef55 |  | date | Date:
checkpoint-status |  |  | checkpoint | All bolts are fully tightened
text | 7f954b67-a095-51fb-80b9-fb3a0f8cdb7b |  | textbox | Initials:
date | 57613d4a-ec01-506f-94a6-d665e11ee0e2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Nut on backside of post is a splice nut
text | 1d102b5e-573b-5ab9-b57b-81b4990d40d7 |  | textbox | Initials:
date | 7f49bc36-62ff-50fd-a9ca-68709217c734 |  | date | Date:
checkpoint-status |  |  | checkpoint | If a median installation-excessive bolt length is cut off on backside
text | c9b49394-2367-5438-832f-21ce0fe3f77b |  | textbox | Initials:
date | 68a2ad74-6018-5c1b-b7b3-0dc2de2daadd |  | date | Date:
checkpoint-status |  |  | checkpoint | That transition details to existing guardrail or terminations are correct
text | ad298c4d-d2de-5a53-a381-dd10992c4e12 |  | textbox | Initials:
date | d83a0b41-fde9-51a1-8b3f-feb1a685f361 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | ffaee200-b050-53dc-bf8f-71967cc37a73 |  | note | Position: Site Engineer
text | 3a7309f4-c214-5061-8220-2e82a357eac4 |  | textbox | Site Engineer - Name:
date | 2146e471-2bda-58c1-bf05-4eb4ee3c20c3 |  | date | Site Engineer - Date:
label | abc073c6-d047-579a-b199-7240768ffcde |  | note | Position: Design Engineer
text | 3f8127c3-8fb4-555a-8ce7-1fbf1466b6ab |  | textbox | Design Engineer - Name:
date | f3463081-297d-5abe-9aca-23969d9de04f |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checkpoint-group |  |  | section | Thriebeam Installation
checkpoint-status |  |  | checkpoint | Panels are pre-bent to suite curves.
text | c1ed3251-ea01-5e78-b2a9-0338942f27e9 |  | textbox | Initials:
date | cac2ec5e-1747-55cf-a9b0-47d641d8d2f5 |  | date | Date:
checkpoint-status |  |  | checkpoint | The rail height is in accordance with the plans and specification.
text | 74344dbc-6baa-5268-a854-da763c1ecf99 |  | textbox | Initials:
date | b4ed7794-3d36-5a14-ac88-a879f4e94079 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct lapping of rail away from the direction of Traffic.
text | a2423dc6-efb4-5c06-857a-664ad5d75b7b |  | textbox | Initials:
date | 12ea2fa9-59b0-57b7-89d1-75a008c71572 |  | date | Date:
checkpoint-status |  |  | checkpoint | Timber block outs secured to the post.
text | 84fef50e-4df5-55a0-9fe0-d72a32e57955 |  | textbox | Initials:
date | f817110e-0b81-558b-97e5-9a226e185136 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rail is aligned and level.
text | a0525e83-38b7-5a20-a7bc-31db0b2320d8 |  | textbox | Initials:
date | c6a90f8c-beaa-56bd-b586-1e57123f8a21 |  | date | Date:
checkpoint-status |  |  | checkpoint | Posts align, at correct spacing and backfilled compacted.
text | 87bbcf2c-f726-55fd-9390-05d2297d2e64 |  | textbox | Initials:
date | 2a557c68-a589-5255-9bb8-ac390888022f |  | date | Date:
checkpoint-status |  |  | checkpoint | Post bolts are tight and washer is fitted at the back of post.
text | b4594f7c-a248-5c85-93ee-2b6be43f25af |  | textbox | Initials:
date | d38e856a-51d2-54e5-a578-144d3081cf66 |  | date | Date:
checkpoint-status |  |  | checkpoint | Backing pieces are fitted at the intermediate post only.
text | 0a359611-8b9a-5999-bbb7-6f0aad636be5 |  | textbox | Initials:
date | e7a443a3-21db-5527-afd6-251ce4391649 |  | date | Date:
checkpoint-status |  |  | checkpoint | With flange based post the necked bolts are installed with washer.
text | 88d24382-55e0-5835-b51b-8ff39445f117 |  | textbox | Initials:
date | 1ecc7858-b480-53b8-8ed3-2013644ffb08 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | a354c1f3-34f1-5132-9544-934d7668339f |  | note | Position: Site Engineer
text | f8bff98b-dacf-5796-afc6-e890f25f2f64 |  | textbox | Site Engineer - Name:
date | 3daf3e3d-2916-5939-b2c8-bd1f4151e0a2 |  | date | Site Engineer - Date:
label | afe9f5e0-a260-51f8-a366-10a0cff7d3b7 |  | note | Position: Design Engineer
text | 56b12c9e-5c20-5962-acb4-7e44998af662 |  | textbox | Design Engineer - Name:
date | 0b3ce488-af7d-5b54-b4bb-12fb7fa63d5f |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4096 - Bottom Driven Pile Record |  |  |  |  | Yes | CS-4096 - Bottom Driven Pile Record | 90b55a99-5b4b-4c24-8637-d4aaf4c44e5c
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | e1c21a45-e738-5484-b3c7-bce3c112cf38 |  | textbox | Project No.
text | f5491bbf-e532-504a-a3cf-e4f502c382e0 |  | textbox | Drawing No:
text | 502de51d-aa45-56ef-bd38-c4e7bd6bcd97 |  | textbox | Concrete Grade: |  |  | MPa
text | 4d210420-aca4-5a7a-a92a-8d60470d6ae8 |  | textbox | Pile No:
text | c7505824-ad2b-5224-8f16-07b2c71a3e9b |  | textbox | Diameter: |  |  | mm
text | 97befcd5-028b-5d85-a6fa-909a0d022837 |  | textbox | Pile Depth Required: RL:
text | 2d1a9759-1b49-577b-9a25-46f470c6e4d4 |  | textbox | Pile Depth Achieved: RL:
text | 2601e78b-d46b-5807-a502-baa8fc1789bd |  | textbox | Ultimate Bearing capacity required: |  |  | kN
text | 0b1b0025-8b57-5871-8765-f7ccac1b1d3b |  | textbox | Ultimate Bearing capacity achieved: |  |  | kN
label | 0543a629-8383-544c-851b-d740667349bf |  | note | (Note problems experienced during construction on a separate sheet and attach)
checkpoint-group |  |  | section | Set Up
checkpoint-status |  |  | checkpoint | Piling Platform Compacted & Level
text | b7a113ef-ec2f-538f-bdee-aafad574d7fa |  | textbox | Initials:
date | 6b59f187-8318-5422-a377-53e5dd0e0374 |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Dig Obtained
text | 6813012a-edb1-53d0-8ee7-72863a923483 |  | textbox | Initials:
date | 79566dbe-d951-52ba-ae40-7253df17a36f |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Set Out & Checked
text | 90c356cd-deec-556a-a0f2-141feb419496 |  | textbox | Initials:
date | 56e7619f-3657-5272-a5f1-63c765ffacd1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Erosion & Sediment Controls in place
text | c9515638-523d-5319-bbac-5897458c4e8d |  | textbox | Initials:
date | 9d5badb5-680b-5ab8-8575-cf7bcd1a0e53 |  | date | Date:
checkpoint-group |  |  | section | Driving
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | 577eb630-f709-59dc-9b4f-ad95de1396f6 |  | textbox | Initials:
date | d46c859f-442f-564d-b3b0-926812f9dbf3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Hammer drop measured within 500mm of pile set
text | 553742fa-8a52-51d0-aa8a-12356a3ce3c0 |  | textbox | Initials:
date | f68020d9-7d5f-5917-b239-48f67556a17c |  | date | Date:
checkpoint-status |  |  | checkpoint | Damage observed
text | 560a2fed-f20b-5f03-adfc-5109e76d09b1 |  | textbox | Initials:
date | ce7823f3-a67a-55f2-873f-5d6baf2fcd93 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Driving Record attached
text | d2da737b-3444-52a6-b385-722c2cfdc891 |  | textbox | Initials:
date | 6e68adbd-c1ec-5eda-b60c-e7b22a251a58 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rebound card attached
text | 80156ab3-8976-5abc-8045-9a12d3ac6a88 |  | textbox | Initials:
date | 0ab535f6-01b0-5060-8a69-26d0339df8d5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Last blow less then mean set over last ten blows
text | 633b8642-b725-5c46-8505-118cf12928bc |  | textbox | Initials:
date | 013d9a2b-58ce-5985-96b3-5b9ba55e99ce |  | date | Date:
checkpoint-status |  |  | checkpoint | Any Interruptions to driving
text | 7329eaa0-010d-5e9f-b3f1-a658c9ea61be |  | textbox | Initials:
date | f248684f-1d95-53f8-b0ec-c444c9dc186b |  | date | Date:
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content, Grade and size
text | 1d6973a1-6d95-592f-8ed2-fe3ddc7f0f89 |  | textbox | Initials:
date | 1d0a096e-6078-5c5e-bbb7-a2646c1572f9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
text | edca19f2-d556-5f89-9a3e-d7c29a852df0 |  | textbox | Initials:
date | 574dbad3-704b-5582-8c07-37ce9facb432 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rigidity and cover spacers fitted
text | 2176f7a4-2c96-5bb6-b94c-5ec1c0ea21c9 |  | textbox | Initials:
date | d479e0fa-27c6-5921-8037-ffe2dacc24c6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean steel
text | 8c41fd65-4e42-5baa-9c4a-ee4f48001801 |  | textbox | Initials:
date | 26e14af6-d4be-5984-a152-50b5458b4f47 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | ce05bf3a-16ed-5092-9f79-c9332b59d5c7 |  | textbox | Initials:
date | c0cd5b9d-1dc8-5e30-85fe-f9d976c98fdc |  | date | Date:
checkpoint-group |  |  | section | Splice Welding if Applicable
checkpoint-status |  |  | checkpoint | Visual Scan 100%
text | f4b37199-f832-5d7e-b92b-7f9338b56bb4 |  | textbox | Initials:
date | 374bb9ea-1d9e-573b-872c-d874cc5461ca |  | date | Date:
checkpoint-status |  |  | checkpoint | Visual Examination 100%
text | 46d6d156-5c1b-5b78-a23c-8cc8b49f0298 |  | textbox | Initials:
date | 825ec529-86c6-5e12-be79-d5a3ddaff449 |  | date | Date:
checkpoint-status |  |  | checkpoint | Radiography
text | 59cbe31f-a121-5064-b132-cf4558927f5f |  | textbox | Initials:
date | 7c8e0b75-1054-5aa8-8af3-3fc13f6d114a |  | date | Date:
checkpoint-group |  |  | section | Pre Pour Check
checkpoint-status |  |  | checkpoint | As-Built Survey Complete and Within Tolerances (50mm in plan, 2% rake)
text | ff082d0d-ac2a-5112-b377-544b67f649fb |  | textbox | Initials:
date | 833d03cd-1c18-5f93-8873-fd97566d3ff5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | 41297d04-d2a6-5d01-8e51-610aa6229cbc |  | textbox | Initials:
date | deaf5104-994c-5286-a75b-a65c591e0786 |  | date | Date:
checklist-flat |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  | Yes | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | 94259252-c925-4900-855f-1a4e517fa531
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 2e08fbd2-a3b6-5d62-b0f9-a0ada44c7a37 |  | textbox | CPS Eng.
text | 54611865-1909-590a-9a58-5307fac3e2ee |  | textbox | Site Engineer
text | f52a4f33-a0b2-56a6-8161-21ff78fd0212 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Erosion and Sediment Control Plan
label | 9c4923b9-26fb-5282-aa40-54bb2ea3f2db |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f087281-1ae9-5781-b797-6fc0160e9bb4 |  | note | Detail - Need ESCP before construction begins
label | 87d943c6-33f2-5779-984f-eba7f4616c40 |  | note | Frequency - Prior to commencement
label | 8668f1f6-76e5-5e50-bdea-669bdda4c3c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 41c753fe-56e2-5a23-831d-ad7e9f187873 |  | note | Conformance Criteria - Erosion and Sediment Control Plan must be submitted to the design team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | b37b7eab-1daa-5df1-a8b9-5c3586ddf343 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b30b8259-014d-54d2-bd15-5e378228fb82 |  | note | Detail - Implement ESCP approved by environmental team
label | 40c09d8e-65c6-5de3-9778-02ddbe572cdb |  | note | Frequency - Prior to commencement
label | fdc5d510-f84b-553f-9689-b459ef3b2fad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Road Safety Barriers (1)
label | f94407f6-4848-5fd5-87b1-196ecaa64f75 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 37660f0f-ccd0-558f-86cb-ad824d686127 |  | note | Detail - Proprietary barrier system type and installation methodology
label | 78a5d5bd-46c4-5c85-9647-bbaa5209dc18 |  | note | Frequency - Prior to commencement
label | 193f83c4-110f-5354-bddb-a66aade4f46a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | c9091017-556c-5a3a-b5e1-2b57e0e43d00 |  | note | Conformance Criteria - Approval from Design Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Road Safety Barriers (2)
label | 77d2929a-19db-531a-a3ef-2319769c19bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | cc7728de-2884-5ea3-996c-648d6282b8b5 |  | note | Detail - Propritary barrier system compliance records
label | 4764b12e-959d-5f2f-8a57-246dfb9164b9 |  | note | Frequency - Daily
label | cc3a4fa8-ceda-5872-982f-f2396fd713dd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 6606412f-8816-5874-950d-f845e8aec77e |  | note | Conformance Criteria - Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained
checkpoint-status |  |  | checkpoint | 3 - Clearing & Earthworks
label | 4281375b-b432-5196-bcdf-7f9fbae85b1c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 12aaeaec-450c-5e32-8507-7f7a4aa4c70d |  | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | 463321d3-8425-5738-92e6-65c2465fe3b1 |  | note | Frequency - Prior to commencement
label | 758402c3-e96b-577c-99c8-e13f4c48b912 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 11f96e6a-98f7-5190-991f-49809136af49 |  | note | Conformance Criteria - In accordance with TNZ F/1
label | 472762a8-38ff-50b6-be65-9bbb37062f1d |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | cd9254a7-36ea-561b-9860-907a9fefcb42 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2bd05ba1-e814-53f2-bf2f-23b6078ec335 |  | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | 3c8404ec-0f36-5f9c-bb40-912fc9b64f12 |  | note | Frequency - Prior to commencement
label | 5019dac6-4bff-5295-bc90-b1efb136095a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 14bdf43a-5958-59ea-b09e-913e8f4396a1 |  | note | Conformance Criteria - In accordance with TNZ F/1.
label | af911c5e-396b-5e8a-ad8c-ff5fed141144 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | ae1cf51d-518a-597d-9a19-72e9150cee06 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e01d78e4-a035-5fc1-bf6e-974afaedbde6 |  | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | 8dedc862-2ab3-5aa7-8178-c7c4cc4269cd |  | note | Frequency - Prior to commencement
label | 600f1aa2-be0d-5eba-8cc3-2e39cce9a3d5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9fa88142-0560-5af0-a89a-6e02237f0238 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | ef7fd4bb-c2d3-5306-880e-267b88f14730 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (1)
label | 7924f54c-55be-5e73-9d8f-ea3aa0a2128f |  | note | ACTION (Hold, Monitor, Witness) - H
label | c785dfa6-809d-505e-8c2a-e5b3e726765d |  | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | a72c1159-69b0-5ec6-aac0-19bc89bdf12d |  | note | Frequency - Prior to commencement
label | 12bf91e7-781e-5da9-9ee1-1385398660e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | f334f386-37e0-5705-a522-53c520e80491 |  | note | Conformance Criteria - Grade 500E soil nail
label | 9e96c3fc-3a02-59f5-8642-d0b5e436a32d |  | note | ○ Class II corrosion protection
label | a5a5d80f-85f8-5a0d-9cbd-35df09c12f79 |  | note | ○ Lengths and diameters shown on drawings are the minimum required
label | 6180addc-c69e-509f-845e-e78fafa02b63 |  | note | Records - Delivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (2)
label | 0bebe6dd-6a7b-5648-90b1-3e097b3a7e5f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 32b22426-2b02-54d7-86a0-1b30a8f2df9a |  | note | Detail - Concrete quality plan
label | 7e56dce0-4256-5d90-9c08-2d7a804bc232 |  | note | Frequency - Prior to commencement
label | 518ccda1-e334-56ca-a104-9afb67c1f711 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a3b303d2-4aab-51f4-8afc-2b4f3e45bb72 |  | note | Conformance Criteria - Including:
label | ee761071-342a-5d06-bdec-e6a460537b29 |  | note | – Name, qualification and expoerience of concrete works inspector
label | 642e355e-af4a-5e90-b55f-2383b894e9ed |  | note | – Form and content of concrete placement card
label | af257b23-aa95-517e-ae96-5dfc5de47b73 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (3)
label | f7e03c44-5a87-5789-ac43-86d0fa49d817 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ddf62f1-fd3b-51ed-bc56-21d9e725754a |  | note | Detail - Details of concrete supply plant, copy od certificate of audit for plant
label | 779d825b-217d-5348-b473-1376eeb0471a |  | note | Frequency - Three weeks prior to pouring concrete
label | da91a3cc-9dce-5f24-a434-6794cc29d3d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4afbce4f-9d99-5c00-b7c6-3fcde734c63f |  | note | Conformance Criteria - Including:
label | 77a84885-2a90-5cc4-aa82-201a93fbddfb |  | note | – Plant test Results
label | 4b90e87b-da89-5e0d-b3f6-6b0de9cc6cd6 |  | note | – ASR Compliance Records
label | cf6513a1-9eae-5cc3-b6c4-2c8a3bcef0e6 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (4)
label | 28af4e27-67a4-5019-8172-7cfaacce26be |  | note | Detail - Concrete work plan
label | b7d611e9-d81d-509f-89cf-531dc8e42344 |  | note | Frequency - At least 10 days before commencing works oinsite
label | 340cffae-6883-5d87-9979-85ae0b335355 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 5aea05ce-7dee-5d52-8fc0-07b938fd1bd3 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (5)
label | 238bd1ca-ab0f-58b5-86cc-48dd079e82cd |  | note | ACTION (Hold, Monitor, Witness) - W
label | def2d018-bed9-5f35-afc4-97b182e18e09 |  | note | Detail - Reinforcing steel manufactureers test reports and certificates
label | 14cf4d8e-222d-58ca-a22b-d3b24de161c2 |  | note | Frequency - Prior to undertaking works
label | d14ccb4f-73c5-5813-a8ff-8dd98b259e3c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | fc3cedda-658b-5f89-8763-59bd316fe249 |  | note | Conformance Criteria - Including despatch records
label | 8d121cde-6829-5eaf-acf6-b7d269fe0390 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 8 -
label | cc948d8e-fc09-5038-bd7f-1a0b303891de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 86f39136-e6b9-569c-9016-f465278644bd |  | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | 38f82903-3ee1-5b04-afb3-fa2d08158490 |  | note | Frequency - Three weeks prior to pouring concrete
label | fcd32786-381e-5d97-9b0b-bd5b85874215 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | ce6061f1-1982-5cab-b0de-4cd30052f480 |  | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | 015f5c0c-b3bd-5d27-bf6c-40acc0cdafa3 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 9 -
label | 8a8134f1-284b-5dde-b04d-6c3252e9ede5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 65c08e5e-6ceb-5e5a-a8d6-4f89b3f20d63 |  | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | 3b7a6d00-ff27-5879-9ca5-a4c34e6a16f4 |  | note | Frequency - Prior to commencement
label | 09a23709-f1f6-5baf-aed8-3b9ac57b84b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | f1fcc6be-9b0f-5ea9-8e98-3deaac4bb841 |  | note | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | b2af9b3d-f2e3-5745-8700-0d1fb4f63a83 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 5853eb55-dfb2-5145-8ff2-05106696c74d |  | note | ACTION (Hold, Monitor, Witness) - W
label | b65c8cfb-ef28-571d-9079-79bbda5ea456 |  | note | Detail - Grout checked if its free from lumps & segregation
label | a674fe0e-6954-5319-b3fc-8eecd07eb6df |  | note | Frequency - Prior to commencement
label | a3f9beb4-9e72-57a1-98d6-58957d645c67 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 11 -
label | 35b6c3a3-c568-5e9b-b4e3-46f9de823b12 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c0cf27d6-11ce-5691-87c8-4b58c71c1604 |  | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | 4892e9e4-4b78-53fc-ade4-8092c1b42858 |  | note | Frequency - Prior to Commencement
label | 375bd94f-8a51-5ece-8d40-2a067026b31b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4b1be4db-032b-546b-a978-cdd90d2cb3bb |  | note | Conformance Criteria - If required
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 7b40de65-84c3-5055-bcde-1e7bd6e30ebd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 69c5bf4f-bf11-501f-b0e4-aa2f90ccbc18 |  | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | abcad524-d823-58c5-bd19-5d2d3e19f0b2 |  | note | Frequency - Prior to commencement
label | d430108a-28ee-57e2-ba20-5e73efb87277 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c0ec667e-7c91-5101-bf63-c1275ec0e623 |  | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
checkpoint-status |  |  | checkpoint | 13 - Working Bench
label | d05ec5a1-da9b-5eec-850d-0782ab8ed225 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7d8ccc5e-1e91-532f-a264-4f1a8b021570 |  | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less.
label | 3be47c70-9eae-5cfb-b45b-ddd0bb6e3e3d |  | note | ○ The construction team shall protect the face of the excavation from damage at all times.
label | 958e9c02-6712-5d9c-b605-d8c4692cc380 |  | note | Frequency - Prior to commencement
label | 0991d622-6e2d-53cd-8c5b-7ae9e4a17c35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1accea89-427a-5dc8-a526-59782d1ec236 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 -
label | 7a29f3f3-c580-5d36-a879-a74d84f092ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | d69779ea-2fe7-5333-b3b9-f50a10987b74 |  | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | 2147da13-2ac3-5e29-9253-7f2eafd28b62 |  | note | Frequency - Prior to Trial
label | f48bece2-d2f1-5368-a5bd-2324a04f94f7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 3b23ec92-7fb4-5aba-ad50-86c6eac6a81b |  | note | Records - Photos, Site Diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - (1)
label | 9f8d3823-513e-5209-9e9c-137af1450fa8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6ffed7d6-3e21-507a-9b96-a685cc43db85 |  | note | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | e314c402-28f2-5fe0-ad8c-257f3a6bddb8 |  | note | Frequency - During Construction
label | 2d508046-64c2-5eb6-8dff-59250abe8d87 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 04d3d86b-138c-54b3-8c0d-7dfb909737c8 |  | note | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | 494e90db-6153-5756-a72b-20a672c4a7ab |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - (2)
label | 8ed618f7-2498-54b3-ac5a-2dd8b865cd6c |  | note | Detail - Drill hole
label | d570e94e-2bfe-5ab3-904c-c91e35bf70a6 |  | note | Frequency - During construction
label | 25184bba-5b1e-5ed5-9735-662b1ca00e62 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | e2d0f7bd-dfda-5a66-b9e8-b5c5de3bfb4d |  | note | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | 0dfc5cef-17d9-5758-9886-447dd648970d |  | note | ○ Submit all installation records for each soil nail and pile.
checkpoint-status |  |  | checkpoint | 29 -
label | 061b1afb-356a-5705-949f-dfa51a91e4e4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae61c3ab-1250-53cf-aa41-4f0f5c280d5e |  | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | aecc33ec-43ac-5554-ae54-8f73399d7790 |  | note | Frequency - During Construction
label | dc5eae4f-88fc-50d6-b701-fc726b772534 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 31 -
label | 865d3ff4-20d4-5c38-a014-c52ab95580b3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 83da2bf5-586b-52c3-a619-6e89ee0f383b |  | note | Detail - Insert soil nails as specified
label | f76f8fdd-80cb-5fea-a4b4-355937c68967 |  | note | Frequency - During Construction
label | 60335836-dce2-5aaa-befe-087f0b5a49bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | de0fcc36-c47e-5dc6-8bf4-0f03c982377f |  | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | 5c735cdd-f329-5cba-bfbd-e24c31503136 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 32 -
label | e18c8d52-22c2-5d1e-8224-0631d890cc04 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3f306aa4-7a59-50bd-a505-7be978d6e2e7 |  | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | 1d3aae72-3fb2-5c57-b9ed-3de32e2041bd |  | note | Frequency - During Construction
label | e5d82ec9-6570-55c3-bbe0-f9636760354a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 9be4e0b3-23a9-5ca2-a1c4-dde0b4ea335a |  | note | Conformance Criteria - Installation records shall include:
label | b5d45de4-f3a3-5fe5-8eb2-b37ff25b0bc2 |  | note | – Length of bar
label | ed148775-d2fb-52df-b8a1-93f70710edb9 |  | note | – Depth of drill hole
label | cc043f9a-ca59-589f-b764-b9961466e3ff |  | note | – Inclination/Verticality achieved
label | 5c4c2083-9cab-5b7d-9a1e-9c42fca9e4b2 |  | note | – Level of grout placed
label | eb50d99d-3fbd-512d-8129-1638ffca87b3 |  | note | – Batch numbers associated with grout placed in each hole
label | 1ec141b4-6f4e-5f0e-93b0-ef83c3b77347 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 18 -
label | 1337721c-5957-560b-bb27-3b4ad8d85d02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 47d3a89e-acea-59ed-9bd4-3f770e847f44 |  | note | Detail - Install Grout
label | db81b36b-dc4f-53a3-a7e1-b86413ee5f87 |  | note | Frequency - During Construction
label | d476496b-4277-5f13-9c41-c7d38a9b490d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 530473d2-4a5c-51ad-9dd5-7d35de72a55e |  | note | Conformance Criteria - Including :
label | ea775a6a-c04f-5ff2-90bc-46e5a0182f79 |  | note | – Concrete despatch records
label | 6feee161-2388-504e-b824-e8d7adb2ba0f |  | note | – Compression test results
label | 89e6ee14-ed27-5906-971a-5e99504a2e2a |  | note | ○ Must notify CPS for any failed result and cease works until resolved
label | 9360a16c-235b-5769-ae62-e1d697aea97e |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 33 -
label | f5638925-bda7-5a8f-9852-325f74b991d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7d8495b8-05cd-57b9-8085-52611c43edb6 |  | note | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | f1dc0494-8138-5e7a-ba2d-37f124137dc5 |  | note | Frequency - During Construction
label | f30750c9-76ee-52c2-b49d-bec1ba0adbb3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3db3e17d-24b9-5bb1-9502-1d51e0570be0 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 34 -
label | 7d85c194-ea63-58e7-9fa9-92b5fc54b828 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 48eae4eb-52f0-5799-9b9c-0e5b4d3d3ec8 |  | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | 7ad16412-46d1-59eb-afee-ea2640fa4490 |  | note | Frequency - During Construction
label | 79680c5e-cb37-5ca0-be8e-9a7ff2ee34be |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 48d09ecf-3e2c-526a-ae8f-7da459e30060 |  | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | c65839f7-28da-563b-aecc-78c3e2c07baf |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 35 -
label | d4491a30-eb7a-5d20-b58c-924012ec43b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | da03c785-6efd-55d5-9d73-9c42268c55e4 |  | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | a8c10b7a-341f-5942-80bd-3f2953ef617e |  | note | Frequency - During Construction
label | 5f20c536-106a-51b3-bb27-62a51085ddf9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4bf97c30-aeef-5759-97ac-92c59d35da0a |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 36 -
label | 4a32e18c-99d4-5c43-b757-d786aeba77fd |  | note | ACTION (Hold, Monitor, Witness) - H
label | b463f295-f826-5e3a-b7a9-95ce8e67ebc5 |  | note | Detail - Install Bolts/Nails washers & nuts
label | 64bed8dd-c015-533b-be02-65c3b4230307 |  | note | Frequency - During Construction
label | 1b701791-6a15-5882-839f-0eaea1c9c275 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | bcb861f1-6ce6-5bdf-b463-7c7a68915431 |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | 64b7fb8d-9a30-5fb7-8471-6d939c2270ff |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 37 - Testing of Soil Nails
label | f6e444cd-90ca-58ba-90b3-e5dc76a0f3af |  | note | ACTION (Hold, Monitor, Witness) - H
label | a0b94712-f11b-5e61-88be-88a6ce0f2f56 |  | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | c325c938-e2e7-5976-92cb-c7a39a3a24ac |  | note | Frequency - After Construction
label | 72afb0a6-3920-5eb7-bf2c-096e1f09f411 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b26985e6-87e0-54c3-ae3b-5914e39c98df |  | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | 3fb64ab3-2a3b-5518-9fc3-c46c3082fec2 |  | note | Records - Certifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 38 -
label | f1d9f2b7-9029-56ff-98a5-a270527a556d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9171556b-f9e0-563b-a79f-4546327082b4 |  | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | 1618ae3f-cc1d-5a48-a848-8fc68e6e5de7 |  | note | Frequency - After Construction
label | 54fd5915-6c04-5eca-8d55-4c0799f84f36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 39 -
label | 69f7a75b-04f1-5702-b4c4-ef0d1a495a59 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6589b5ab-faf7-5687-a780-8ce513ad7368 |  | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | b395ad4f-9edb-5ffb-828b-cf4d2dd1e578 |  | note | Frequency - After Construction
label | b2637abb-4ae7-57f3-9796-c2d9aa4d45a5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | b45b3c9d-ccf0-5998-a118-0b1b3768b56c |  | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | 2955c343-7592-5443-a32b-764ce5dcd8de |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 40 -
label | 0b537d9f-77cd-552a-8c33-4a93114073d3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6389a486-de36-5b57-99e6-a6e8bc53ac43 |  | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | 5212ceee-d31e-54c7-ba7e-1bf340bc61c5 |  | note | Frequency - After Construction
label | 4f3df9d2-ead0-5600-881d-4efbbdf5ae7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7fa025be-86cd-5f34-a268-3ada64c26c03 |  | note | Conformance Criteria - CPS Engineer to give approval via a NTC
label | 3b34cf71-463b-5343-9e73-b9f989facbda |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 41 - Shotcreting
label | e4154589-58ac-54f7-888a-26170a7f80ed |  | note | ACTION (Hold, Monitor, Witness) - H
label | a40a4dcc-44bf-5774-813e-ee77ecb5a310 |  | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | 1cab9b94-f783-5973-b861-8b05614643f7 |  | note | Frequency - During Construction
label | dda277ac-2127-539f-be53-86c350dc2ded |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3b6a9d14-ff99-561f-9993-039b4831bf10 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 42 -
label | 1f4c1218-eb10-5f98-9e96-dbe776e51cb5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e4315cbd-239c-5b34-823f-a732a5db353e |  | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | 5d16ec90-b722-54d6-9d7e-dd39f69a83dd |  | note | Frequency - During construction
label | 50f9d0e7-86e4-5cc6-b750-20e77a7da38b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3175f56a-8397-5641-b6ac-3b2d8ff5ed62 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 43 -
label | 61454bf7-5f0b-5274-a651-57bf64d75d2f |  | note | ACTION (Hold, Monitor, Witness) - W
label | c22eddac-60f5-52c6-a37f-7f2d6f623d34 |  | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | f420409a-d8e3-5139-a098-a37088b7291c |  | note | Frequency - During Construction
label | 7174d3a5-f81a-50b7-8062-aeed5f6bd220 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3ab633b8-0e62-5fab-9cab-ade69fe271ae |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 44 -
label | 08b30fa7-f611-5af2-bcc3-aaae13d215e9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1190faf1-c170-55b5-9f0c-fd7d7612fb96 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | 252c24fb-5b11-5b4c-acbd-828217ec25b1 |  | note | Frequency - After Construction
label | c256687d-e467-5628-90a3-b92090932c17 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 20cbdd3b-74bc-5926-8dce-e0ee29b08c15 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 45 -
label | 2d127220-0560-58e6-a733-eec5aeb5accc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 724598e5-e2d1-5075-ab3b-ba85522208ef |  | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | 014e80a0-f162-5403-99a6-33237bfed7eb |  | note | Frequency - After Construction
label | cd26d7bd-886d-50ae-a17b-b025db24b4e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4167d080-eec7-5ba3-bca5-bd8329d503a0 |  | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | 26e4607f-34f7-5f21-ba5b-a5452fd44e66 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 46 - Post Construction Survey
label | 6bee2354-423b-53f4-b6e6-923291f08ac2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1154b71e-8116-5446-b9cc-93893ccc4a9e |  | note | Detail - Survey final position of bolts for as-built purposes
label | 8032a508-14e8-5a98-9eb4-da7d1188d7f4 |  | note | Frequency - At completion of Lot
label | b6912d89-32ba-5e24-9fd6-98be3ad02134 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b6d790b6-9c95-5b22-ab79-08bd512ea0c9 |  | note | Conformance Criteria - Survey report complete and conforms to specification
label | d405e6f8-9e45-5f53-bd2f-2d80a93286db |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 47 - Lot Number QA File
label | bf90cd8f-eef5-56b7-87f5-7cc60cceea87 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ba5fca82-2437-5527-8bfc-43bc48b0adab |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | dfb01f9f-07e2-5a94-a005-1e149578c4a6 |  | note | Frequency - At completion of Lot
label | 38c61592-223a-5e17-a4f6-8d5491773085 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0e361d37-2b15-52cc-8ec4-dd9858d845d3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 9561ca11-5d2a-5faf-82bc-12623a7674c1 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 48 -
label | c06cce51-93c8-5346-bde4-ff6d7533d838 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5acdee03-8adf-5209-9099-94e0d8dd466d |  | note | Detail - All subcontractor documentation to be included in QA file
label | 63ff7980-238e-5b46-a7c5-09cce94944fc |  | note | Frequency - At completion of Lot
label | 09b3a1b5-f4ee-5818-89c3-cab8321722af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7ab619be-78c1-5bf0-b3cf-cfaa79208795 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 49 - As-built
label | 1c6f8078-c481-55dc-ac87-07240043c399 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ddde80ac-7209-503c-a476-dd9d0bc77d8f |  | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | 77e1d642-efd3-506d-a962-6f8ecf9796fc |  | note | Frequency - During and at completion of work.
label | 91e43805-8cca-595b-bcdb-826e7fbc0f8f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | c7e62184-7943-596a-aabe-bf399c11b37b |  | note | Records - Survey receipts, As-built plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 50 - Quality Assurance deliverables
label | 44c48998-6a4b-53b8-8b3f-f65af6ee4723 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 127de175-ba10-5b4b-80be-61a993be103f |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | bdf86c6d-5c63-579b-972a-f8a9374f0011 |  | note | Frequency - At completion of Lot
label | f66e3a1e-e9d5-570b-80b7-1a50d7ecf890 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7f5fa922-e07d-5f13-9271-e0fe9c9d47c1 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | bf5a3195-1d2e-5a15-ac51-41d382687398 |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 51 - Completion Sign Off From Fields Below
label | 2ca9959d-2d15-502c-afab-a25fa184aeb7 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4077 - Light Column Installation Record |  |  |  |  | Yes | CS-4077 - Light Column Installation Record | 97786229-a699-4b5b-9ba8-d4fb97dcada9
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 249808da-d237-5009-9929-a0106541552e |  | textbox | Drawing No:
text | 2de6866c-c10d-5b48-8aad-12ee2849b257 |  | textbox | Pole No:
checkpoint-group |  |  | section | Column Foundation
checkpoint-status |  |  | checkpoint | Confirm Light Pole Locations are as per latest Drawing revision and does not clash with other Services.
text | 1cb45f60-e33b-578e-a8ce-ebbb6e4b39f4 |  | textbox | Initials:
date | e4710577-53f9-5ecb-bc77-806f7c71ac6b |  | date | Date:
label | dd18a04c-1e12-5565-8273-0dd2ddf0e954 |  | note | Comments: Design Engineer to approve if the location needs to be moved.
text | c13efc77-55a1-5c0b-a80f-36b40547dba8 |  | textbox | OFI No:
checkpoint-status |  |  | checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
text | b1dae590-a47c-5aa6-bc30-44b6b4e68ec7 |  | textbox | Initials:
date | 481f14d0-7cfd-5e02-9ee0-a719f1aa9687 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm Foundation Type i.e. Ground plant, Barrier mount etc.
text | 64b9a11f-2b4e-5f43-bf3b-090de3bfdfee |  | textbox | Initials:
date | 4065e3b0-e014-5a2d-9e05-61bf88f4c38e |  | date | Date:
checkpoint-group |  |  | section | Excavation
checkpoint-status |  |  | checkpoint | Pothole existing services within close proximity to the foundation.
text | 984eb8f6-2c40-535c-9eaf-1f8547cbe933 |  | textbox | Initials:
date | 5dec71fd-3225-5260-a9c0-1338400b7253 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure permit to dig is in place.
text | 9712f4be-abe9-5c14-a40b-6b81a63a9b7b |  | textbox | Initials:
date | ea7b2890-a39f-5dec-ad74-0ffc5ef34f3e |  | date | Date:
checkpoint-status |  |  | checkpoint | Check depth and diameter at completion.
text | 4a1ada57-3ee7-5e43-bc48-d56c58e7f661 |  | textbox | Initials:
date | 0b0e8585-5e5c-578a-a8bf-82e6eb9e44d3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure base of shaft is clean and dry.
text | e7b03885-5760-5efd-9925-a28afa12ed0d |  | textbox | Initials:
date | c11ec448-e8f6-51ef-b556-c9318eb4394c |  | date | Date:
checkpoint-status |  |  | checkpoint | If fixing onto barrier ensure bolts drilled to correct depth.
text | 90bcc8db-6286-52d9-b55a-bbbcf2207140 |  | textbox | Initials:
date | 5341e6f7-51b8-56ae-9294-26a50c6b80f1 |  | date | Date:
checkpoint-group |  |  | section | Concreting & Backfilling
checkpoint-status |  |  | checkpoint | Check the location, orientation, level and verticality of foundation prior to pouring/backfilling.
text | 8fa206c6-cc66-5dda-bb3a-99104893e4ba |  | textbox | Initials:
date | 0f0cee5d-4946-524e-936a-cc378d88e84e |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure 1 x 65mm dia flexi duct is installed and taped off at each end.
text | 663d90fa-1233-5d28-bc2f-62cae167a237 |  | textbox | Initials:
date | bb7057b5-673c-5d79-bd67-b84908715415 |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspected the foundation prior to pouring
text | d3d276c9-b111-5b05-b4a5-05217e14484b |  | textbox | Initials:
date | dde11fc8-a82f-57e3-a03b-988902c23d21 |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete for shear base, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
text | 4925ffd9-98ac-57da-868d-2e8e4a4b3766 |  | textbox | Initials:
date | 454cae8e-f9ee-5009-afb0-0b911ed1fddb |  | date | Date:
label | 43ec2133-6e69-54cd-9aea-3ae9d9e68fa7 |  | note | Comments:
text | 758852f2-12bd-5b74-ab05-6b9420957828 |  | textbox | Concrete strength |  |  | Mpa
label | 997c7f27-2c2a-5c03-aaa0-8739fe7f5977 |  | note | Attach delivery dockets and write the road light column numbers on the docket
checkpoint-status |  |  | checkpoint | Suitable backfill material to be placed and tampered for compaction
text | 7b795629-114b-515f-8716-7c58f8c0bf81 |  | textbox | Initials:
date | d4a5848c-efd6-5093-87f8-f2e569414915 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete/backfill placed to just below the shear base and concrete splashes onto column washed off.
text | 60dfaea9-7a7b-5b81-832f-00535cbaa39b |  | textbox | Initials:
date | 00191d65-92d7-5071-8b9e-7670c10c6256 |  | date | Date:
checkpoint-status |  |  | checkpoint | At the completion of the concreting/backfilling check the foundation location, level, verticality and height from FRL.
text | f34645d2-c727-5d25-a3e3-6b03338b3afa |  | textbox | Initials:
date | 29badc79-f8c2-5743-9488-31cbfa3fa3ec |  | date | Date:
label | c5aca3dc-d8ee-5f0a-96fd-3ba6288b45e2 |  | note | Comments: Foundation may have moved during concreting/backfilling
checkpoint-group |  |  | section | Installing Column & Outreach
checkpoint-status |  |  | checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting road light column
text | c0f3df34-e8ae-51e7-98cc-1166c9fdfbe7 |  | textbox | Initials:
date | f259e8ba-55f9-5669-a292-861091970711 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check road light column for any damage
text | ac66eb8c-448b-5bef-af6f-54398749319b |  | textbox | Initials:
date | 6e09bfb1-d6b5-50c3-bce3-ae46b227fd89 |  | date | Date:
label | ee1869c0-f23c-53af-a7fe-825861429310 |  | note | Comments: Do not install if damaged
checkpoint-status |  |  | checkpoint | Assemble Light column on the ground (protect column by blocking off the ground)
text | ca05abd1-47aa-583a-a0c3-41afca17bd6d |  | textbox | Initials:
date | 547cf460-757e-5104-aa89-e3650eec091f |  | date | Date:
label | f6f921d1-118f-5c2d-99c2-c9c9f3324d03 |  | note | Comments:
text | 851c32ca-c784-5436-9a61-17388248db2f |  | textbox | Column Type:
text | 5371a149-1d7f-59eb-8056-02c7e0c2b54c |  | textbox | Outreach Type:
text | 647f19d3-e56a-5b28-964f-f205eac7c8d0 |  | textbox | Outreach Length:
text | f119c576-9bf0-5bd8-9f46-9ddb4796790a |  | textbox | Luminaire Type:
checkpoint-status |  |  | checkpoint | Check all bolts on shear bases have been torqued
text | ce2dbbdb-6126-5dcc-9878-de877cb81213 |  | textbox | Initials:
date | 9f810774-0959-5042-8a64-f1d0353af045 |  | date | Date:
label | 36af2da0-538a-51af-ae2f-ef054b53d5cd |  | note | Comments: Adjust column to ensure vertical
checkpoint-status |  |  | checkpoint | Check orientation of road light column and outreach
text | 768faafa-39a1-54fa-b025-7bb2085b6908 |  | textbox | Initials:
date | 281402c3-142c-5e74-97c4-75ad210c75e6 |  | date | Date:
label | cae9a2fb-f5a0-56c9-8677-9bed35e5ce26 |  | note | Comments: Torque to 200kPa, check the bolt and slack back to 100kPa
checkpoint-status |  |  | checkpoint | Check the internal wiring of the road lighting column. Ensure 2.5mm2 cables, 2 core NS
text | 47891be0-d66f-5a7f-a5fd-8e8dd2f1b0ac |  | textbox | Initials:
date | 7d482acd-4924-514a-96f4-50341be3dd4e |  | date | Date:
checkpoint-status |  |  | checkpoint | Check Connectors & Earth Conductors have been installed
text | 9db13d47-24c3-548e-b366-01ad18b930c4 |  | textbox | Initials:
date | 5ffee646-3c82-59e4-8813-2d1f1be8f345 |  | date | Date:
checkpoint-status |  |  | checkpoint | Danger Live Wires sticker on gear door
text | ebc3adaa-d86f-5c14-87f3-803e2eb50dda |  | textbox | Initials:
date | 60a5d71c-8134-5e78-83d4-a8b5f2dc8476 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check that the Road light is installed to the design height above road level
text | 16785c67-e7b8-5aae-9b2a-7be8ada4c475 |  | textbox | Initials:
date | 07dc9735-ff25-5968-a40b-81ab3fcf5a44 |  | date | Date:
label | 22e19d9b-210a-5d77-b28e-e46a9407e5a0 |  | note | Comments:
text | 94925597-d73d-5931-ba45-5dc420332e15 |  | textbox | Laser Measurement:
text | ea3718ff-11fe-54e4-90fd-9701b65c29ab |  | textbox | Design Measurement:
label | 1945acc0-d423-5671-901b-d3c3785c9e66 |  | note | Tolerance = +/-500mm
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 9b8fd8b6-d2a5-5467-baad-f9440f86708e |  | note | Position: Site Engineer
text | 96025105-6a2a-58ec-b470-7eb7f7618270 |  | textbox | Site Engineer - Name:
date | e0b228fd-4cdf-5718-a388-455586849ca6 |  | date | Site Engineer - Date:
label | dddb08f4-a527-578e-8486-0fb7ecd3e931 |  | note | Position: Design Engineer
text | 3ef3f619-dc85-51af-aaa5-47630fb51947 |  | textbox | Design Engineer - Name:
date | 047e5444-de35-57bb-a504-99dff4de7bcf |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4106 - Traffic Sign Foundation Record |  |  |  |  | Yes | CS-4106 - Traffic Sign Foundation Record | 99b2e8ef-ef0f-48b5-99f1-0ce10ddef2d9
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 9af3cdcd-baa2-5181-863b-27b45559a48c |  | textbox | Project No.
text | 71ea44c8-dda8-5fe5-a69f-fd8acefd975a |  | textbox | Drawing No:
text | 121c17da-e1cb-59e1-a331-432066a4680e |  | textbox | Sign No:
checkpoint-group |  |  | section | Sign(s) Location
checkpoint-status |  |  | checkpoint | Check sight distances
text | 843ce4a4-f3f2-59ec-98a9-7ccaab2cc186 |  | textbox | Initials:
date | b9f9834b-b159-509f-bdec-4a99aedf16f8 |  | date | Date:
label | dd831504-50b2-5a93-a861-5ab3b9870426 |  | note | Comments: Ensure the sign will be in a location where drivers can see it clearly without blocking views from driveways, other roads etc.
checkpoint-status |  |  | checkpoint | Check Lateral Distance
text | aa7a65d8-3a47-57b0-a529-0125c134609a |  | textbox | Initials:
date | 60b7c261-c929-5085-8dd2-2a8bed9ce6e8 |  | date | Date:
label | 4917bb7f-3f7d-5b02-ba42-2118ac0217be |  | note | Comments: Ground mounted signs shall be located at least 600mm clear of the outer edge of shoulder, line of edge marker posts or face of road safety barrier; and be between 2-5m clear of the nearest traffic lane edge line
label | 236c32f7-6090-5066-83d0-ebfb39c1dbbe |  | note | ○ Large ground mounted signs shall be located a minimum of 1m clear of the outer edge of a motorway or expressway shoulder, or 4m from the nearest traffic lane edge line, whichever is the greater, or 1m behind the face of a road safety barrier, or 1m behind the face of a kerb, or 1m clear of the outer edge of a ramp shoulder
checkpoint-status |  |  | checkpoint | Check location of existing services, if there is a clash with the new sign location seek approval from CPS Engineer to move the sign to a new location
text | 7ec948bf-57e6-5a56-a171-1cbd0c14814e |  | textbox | Initials:
date | 6ad05527-e402-5bca-9949-56f8356aa09c |  | date | Date:
text | 43c1557b-8a3c-5df2-81e0-f22915249b2c |  | textbox | Comments: OFI # |  |  | (if needed)
checkpoint-group |  |  | section | Sign(s) Foundation
checkpoint-status |  |  | checkpoint | Expose any existing services by potholing
text | 1c2dbe19-5483-5763-9964-c7956c6373b2 |  | textbox | Initials:
date | b7529dbc-ef77-57e9-bdec-807a52c1ccaf |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm Type of Foundation(s) i.e. Ground sockets, Breaksafe etc.
text | c88fefde-9f89-547b-b53d-978d587359f8 |  | textbox | Initials:
date | 9182f2f3-3881-555f-8416-46290cc165ae |  | date | Date:
text | 5d699fa6-3354-5481-bd40-cb34c8072632 |  | textbox | Comments: Type(s) =
checkpoint-status |  |  | checkpoint | Confirm depth and diameter required for augering
text | b4ef6bb9-3568-5cfa-977b-519874e47b89 |  | textbox | Initials:
date | 1b843759-f058-5b3f-9d0c-a92005ae3579 |  | date | Date:
label | a92535db-0412-5203-baa5-9b18f3ce4e8c |  | note | Comments:
text | 1bba9045-a01b-5275-94a1-358b3b7a5340 |  | textbox | ○ Depth(s) =
text | 00941eca-93e9-5ac7-a53d-f9c8cc04ef23 |  | textbox | ○ Diameter(s) =
checkpoint-status |  |  | checkpoint | Mark out post(s) location(s) remembering lateral distance (above) and sign orientation
text | 6d5c67c2-1602-50b9-9fe8-89ef89601e25 |  | textbox | Initials:
date | 7e0c2dec-5603-5a4d-a4a7-7dec6d6a9b0d |  | date | Date:
label | a064c352-53b7-5c9a-92a2-7c1474dfb3e7 |  | note | Comments: Sign orientation should be turned about 5 degrees away from the approaching drivers line of sight, this varies depending on the location on site. This is to help reduce possible specular reflection from reflectorised sign surfaces. If there is still specular reflection on a straight when the sign is turned about 5 degrees away from the drivers’ line of sight, then it shall be increased to a maximum of 10 degrees.
checkpoint-group |  |  | section | Installing Foundation(s)
checkpoint-status |  |  | checkpoint | Install the foundation(s), Check the correct type and sized foundation is being installed
text | 6c9cab0e-3217-53a1-8ce6-08ff3133fa83 |  | textbox | Initials:
date | 1fed0a27-6830-5b83-9411-63ebbe0757b0 |  | date | Date:
label | c90836e5-d77b-5c10-b504-2fbd0e583fb5 |  | note | Comments: E.g. Ground socket diameter and length etc.
checkpoint-status |  |  | checkpoint | Check the location, level and plumbness of foundation(s) prior to pouring concrete
text | 34fd21e4-442b-5bd2-99ba-3b80a5c3f49f |  | textbox | Initials:
date | c8a6acd9-28b7-5dca-9766-da7032f5ea47 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the correct distance between foundations (for 2 post signs)
text | 26aa24df-9a1c-57b0-b01d-21e568e2317c |  | textbox | Initials:
date | 5a5e0cb3-732d-536b-808d-8ef534902a37 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the height from final ground level (FGL) to top of foundation(s)
text | c9882bc8-a394-5b52-abc0-22427468c02b |  | textbox | Initials:
date | bdd9f489-9294-563e-bcfd-cbb23f2a545c |  | date | Date:
checkpoint-status |  |  | checkpoint | Check there is equal cover around the foundation(s) prior to pouring concrete
text | c34da913-0511-51d2-b303-f2727b79ffa2 |  | textbox | Initials:
date | e2c7d519-e524-5738-b2c2-127399aa4ecc |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected and concrete cylinders taken (1 test per group/lot of Signage posts)
text | 1596852b-2d16-5b1c-a78b-ea3db91f0bc1 |  | textbox | Initials:
date | 35959a99-f80f-5de6-95fd-676bf09210fb |  | date | Date:
text | 241f7751-623d-562d-975f-29a272b9fac1 |  | textbox | Comments: Concrete strength ordered = |  |  | MPa
checkpoint-status |  |  | checkpoint | Pour concrete to top of final ground level and wash off any concrete splashed onto the foundation(s)
text | d361c93c-cead-5c94-8ea1-058ca06c31a9 |  | textbox | Initials:
date | a00f3715-adec-53cb-9f86-3bc8ff2ba73b |  | date | Date:
checkpoint-status |  |  | checkpoint | At the completion of the concrete pour check the foundation location, level, plumbness and height from FGL as this may have moved during the concrete pour
text | fa1549eb-a5a5-597d-9bac-2f131a039066 |  | textbox | Initials:
date | 663ef515-f238-5598-8652-7ac30b0f7507 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 17b4a9d7-f736-5e25-900b-d2efad8619a7 |  | note | Position: Site Engineer
text | 120437fa-b1a6-5ed8-890d-60e945974719 |  | textbox | Site Engineer - Name:
date | 353f689c-75a0-5da0-8a02-89a38915525e |  | date | Site Engineer - Date:
label | 25795abc-ce6b-550a-bf0d-9ceb99da3ea0 |  | note | Position: CPS Engineer
text | 202ea3e6-00ee-5c67-9bab-677ac45f64ab |  | textbox | CPS Engineer - Name:
date | 2c6a3c73-ee50-5c01-b5a1-d596a952bfeb |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4047 - Traffic Sign Installation Record |  |  |  |  | Yes | CS-4047 - Traffic Sign Installation Record | a966ce17-2434-48d2-9e00-e681d1c67c75
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | a16ef052-1989-556e-9d76-3b8f865326df |  | textbox | Project No.
text | 7cd59a5e-e555-57d0-815c-a2762db218cb |  | textbox | Drawing No:
text | 8fa6afc8-57cf-59aa-b5f1-ac7677e7a36e |  | textbox | Sign No:
checkpoint-group |  |  | section | Installing Sign(s)
checkpoint-status |  |  | checkpoint | Ensure the posts are the correct length to ensure the sign will be installed at the correct height
text | 327b18c2-20ba-5bbb-814e-897ac56fe88f |  | textbox | Initials:
date | 1e3543ac-c5bb-5d98-97f0-5d78511d3e2a |  | date | Date:
label | 5c8441bf-3fb4-5a57-a730-42688da95442 |  | note | Comments: Minimum mounting height 2m from the underside of the sign(s) and the adjacent road pavement, trafficable shoulder or top of kerb whichever the critical dimension shall be. The exception is for exit signs where the minimum mounting height is 1.2m.
checkpoint-status |  |  | checkpoint | Ensure posts are connected to foundations with correct fixing bolts/brackets and are fixed securely to ensure the posts are firmly installed in the vertical position
text | cb0e20df-3ef2-5f8d-a5de-ff8136be08d2 |  | textbox | Initials:
date | b0b8296b-dbc7-5aa3-9600-4b4f0b951a72 |  | date | Date:
checkpoint-status |  |  | checkpoint | Once posts have been installed check they are plumb and to the correct spacing apart at the location of the sign
text | 55ea0157-0c89-58b6-b88e-88b3bd34db92 |  | textbox | Initials:
date | 117fe1ef-3419-581a-b18a-d7f793094407 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the sign before installation and ensure the sign is exactly as per the shop drawing
text | f2a00f42-5c13-5e57-9d0c-c8fe0280f010 |  | textbox | Initials:
date | 1179106f-c6d7-549a-af01-7d944b22ca88 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect the sign and make a note of any damage
text | 4f7f1c94-b1bc-56a2-bd31-de127476b7c0 |  | textbox | Initials:
date | 621a5f03-cefd-53a3-a36a-742f2d6b733a |  | date | Date:
text | 2460a507-3c63-5c32-9bfd-9113d9288c45 |  | textbox | Comments: Record any damage:
checkpoint-status |  |  | checkpoint | Ensure graffiti guard or dew guard is present on the sign
text | 0ebd5cd2-64d5-5b09-9d1f-6f5c72b54aae |  | textbox | Initials:
date | 9f5ef4d9-d8ae-58fa-8cb8-87f931a68bf4 |  | date | Date:
label | 6a771fef-794c-5206-a05b-04134d6e1d9e |  | note | Comments: Graffiti Guard on Sign, Dew Guard on Sign
checkpoint-status |  |  | checkpoint | Clean the sign (if required) as directed by the manufacturer
text | d825234b-915e-5bce-a432-8b748da39ff8 |  | textbox | Initials:
date | b2b856fd-5d08-5a62-9cc7-f734c7a31624 |  | date | Date:
label | cdf3e9db-2ddd-5b21-be76-ce2f58da615a |  | note | Comments: Signs shall be cleaned in a manner and frequency that maintains visibility of the sign at all times
checkpoint-status |  |  | checkpoint | Ensure signs are connected to posts with correct fixing bolts/brackets and are fixed securely to ensure the sign is firmly installed in the vertical position
text | e509095b-1642-5128-8ba7-17790ee337b7 |  | textbox | Initials:
date | 828dc56d-7985-5598-b925-a103c7280e95 |  | date | Date:
label | d93efb26-8f3a-5f3d-a6fb-f15d3e9c8e4b |  | note | Comments: Do not fix signs to posts by bolting through the sign unless approved otherwise by the CPS Engineer
checkpoint-status |  |  | checkpoint | Overhead mounted signs - Ensure horizontal and vertical axis are checked
text | bd1c5426-d441-558a-adf8-990461515035 |  | textbox | Initials:
date | 0700915f-5aa0-5adc-9506-4ea0f7018b5f |  | date | Date:
label | edc9df7f-b4a6-5e01-bc18-d755fe920c25 |  | note | Comments: Where the road gradient approaching the sign is =2.0% or greater, position the sign so the vertical axis is parallel to a plumb line and the horizontal axis is at right angles to the road.
label | 7036ba5d-0cae-5d4e-91d6-39f06b4da907 |  | note | ○ Where the road gradient approaching the sign is =2.0% or less the sign shall be positioned so its horizontal axis is at right angles to the road, and the vertical axis of the sign is inclined to face upward at a rate of 3mm per 300mm of vertical sign surface for each 1% the road gradient differs from +2%.
checkpoint-status |  |  | checkpoint | For sign installation follow the Work Instruction and ensure Lifting and Working at Height permits are in place
text | 8752b158-bfe9-5c18-a2c5-9c3dbed8eb32 |  | textbox | Initials:
date | 23fed698-0047-573c-92b3-78671543b7bf |  | date | Date:
checkpoint-status |  |  | checkpoint | Measure the mounting height after the sign is installed to ensure it complies with MOTSAM Part 3, Section 1.18.2c) for Ground mounted signs or Section 1.18.3c) for overhead signs
text | 04959ec8-c7e9-54c2-a75a-b3e982be01b2 |  | textbox | Initials:
date | 5dc23c28-3477-5ca8-b184-26efce707da9 |  | date | Date:
text | 0078b90c-b38e-5f47-abf5-d4c0329d80f8 |  | textbox | Comments: Mounting Height =
checkpoint-status |  |  | checkpoint | Ensure the sign is installed above the hinge where hinges are required (Breakaway signs)
text | 34a6c232-1818-5c20-abb5-f8e6c07f4c1c |  | textbox | Initials:
date | 6523fab8-f789-51e7-938f-994fc3957191 |  | date | Date:
checkpoint-status |  |  | checkpoint | Undertake a ‘drive by’ with CPS Engineer and ensure the sign(s) are orientated correctly and sign off below
text | 911be62b-81bb-54ea-94ed-d15b60a56708 |  | textbox | Initials:
date | ba4e2584-774e-5f3a-bf78-b9d47daebbaa |  | date | Date:
label | 16b0d412-33c5-52aa-a9c5-631283f3a20d |  | note | Comments: Ensure signs are directing traffic the right way and are visible.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 0af85ce2-66b6-51da-b3bb-f00deac49b21 |  | note | Position: Site Engineer
text | e2006f49-7c42-57f5-983b-2f7a1f5f0f2d |  | textbox | Site Engineer - Name:
date | 6dcc70d5-8745-5e56-8dc3-28c1c3f248c8 |  | date | Site Engineer - Date:
label | d16708c9-309e-521c-95e9-6f3310f988db |  | note | Position: CPS Engineer
text | 6bf1a409-6dc7-5c18-b931-ddb7a949695f |  | textbox | CPS Engineer - Name:
date | df5e066f-616f-59b4-97d5-1c61f5f023cc |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | CS-4001 - Subsoil Dipsheet |  |  |  |  | Yes | CS-4001 - Subsoil Dipsheet | aa2bc76f-2544-4463-b263-723d82e4bde4
checkpoint-no-status |  |  | checkpoint | Details
text | 72524a50-fc86-58e9-9e01-fbc4d712f09d |  | textbox | Work Area:
text | ad27c923-761f-5a9a-a8b5-4482cbc44418 |  | textbox | Sub Work Area:
text | 186580b2-7f31-531f-998a-43f63a07de20 |  | textbox | Lot:
text | 77f89de0-6014-5792-bca1-2d29ba588944 |  | textbox | Sublot:
date | e3611f28-237f-5438-b8cd-ff31f9a43d87 |  | date | Document Date:
text | 41b89b0f-cb15-548d-ba60-30e1cc28a5cc |  | textbox | Created By:
checkpoint-no-status |  |  | checkpoint | Note that depth is to be checked every 10m as a minimum.
text | 58cc5f60-d74a-524a-adad-1a054e97853b |  | textbox | Drawing No:
text | d4521694-b5bf-5dc3-8e15-4f038e30a34f |  | textbox | Rev No:
checkpoint-status |  |  | checkpoint | Chainage - 1
text | ab52f780-9d0b-5972-8c1d-8b56c797db38 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 2
text | 38e509d9-ca13-514b-842c-891d445cec8c |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 3
text | 37fceb9f-fd6d-5872-ab6a-dd33b0a20358 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 4
text | 423a6377-2038-582c-9230-83ce55436157 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 5
text | 7e1eb064-0c56-505a-b453-5a1e368a5b2b |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 6
text | 97e0e55a-068d-5074-8109-15c0593c4157 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 7
text | f5ed682e-d40e-54c7-853f-dbd0162e2e37 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 8
text | b6e45df0-ddb8-5204-b88d-fc3a0cf00986 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 9
text | b9a3b5e7-9068-5567-a91d-f3d97065cbc3 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 10
text | da3b8425-c11b-53e8-9a35-93b82287d469 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 11
text | f6e6e8c8-10d7-55a3-98a6-72cec2697662 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 12
text | 882ff3ff-26d4-58a7-8f62-daefa8f37dac |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 13
text | 2fe03918-6a07-5783-af2c-3472fc6653eb |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 14
text | bfcd3eaa-a684-5de2-be3a-5c04920ea347 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 15
text | 1e12f2b7-1609-5d2d-9b11-d9f9a995e9fa |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 16
text | bd4f1b3a-b5bb-576c-8fae-ff8867bfddfa |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 17
text | 07ba1f66-04a5-5909-9e00-393d862fcda0 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 18
text | a1526be0-ac87-5bc1-a550-1438b3a36895 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 19
text | 72b2b901-307a-5421-a833-46e7cfdfb1f6 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 20
text | bbe9b221-cc26-5f3d-9508-cb623cb9a158 |  | textbox | Depth:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions.
text | d084c812-9e19-5a27-b945-ff4dedc0a055 |  | textbox | Name:
text | d8121ef4-d10d-528c-b569-4891dd2273bb |  | textbox | Position:
date | aa4cbc16-3d59-5f22-972c-416c38f618b9 |  | date | Date:
holdpoint |  |  | signoff | Signature
checklist-flat |  |  | checklist | CS-4100 - Subgrade Approval Checksheet |  |  |  |  | Yes | CS-4100 - Subgrade Approval Checksheet | b0b52cb6-ff20-48ff-a5dd-13d1e918080a
checkpoint-status |  |  | checkpoint | Area completely stripped of topsoil & organics
text | 22f1b41a-7f2e-5a38-8a68-838796a34476 |  | textbox | Initials - Design Engineer:
date | 0f0242c0-fc11-51b6-97db-314624f95cb1 |  | date | Date:
label | 76c7cd2c-8637-5d2d-af79-51971b4d9356 |  | note | Comments:
text | b2aaffb7-0348-58da-be3b-4e61fed2a372 |  | textbox | Chainage Start:
text | b9eec41c-1065-5598-a9a4-6bfbf1efecd6 |  | textbox | Finish:
label | 131c3094-f9ff-56de-b523-e05b71e6ef9c |  | note | Photos of area are taken & kept with QA records
checkpoint-status |  |  | checkpoint | Topsoil strip topo survey carried out
text | 4f9c6697-f29c-53f1-97c9-526802a93975 |  | textbox | Initials - Site Engineer:
date | e4279bbc-da97-5eea-a53a-e1fd7772a0f3 |  | date | Date:
label | 1ce29c49-1c1e-54ce-a66b-9f9f42522261 |  | note | Comments:
text | 9f82d474-33fe-5b3d-b7ae-b617938032ad |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | Scala Penetrometer Test carried out
text | 0caec590-5fe2-51f3-a91c-42d286da6678 |  | textbox | Initials - Site Engineer:
date | dd65d6f3-ed98-50ca-9509-5b1e14045278 |  | date | Date:
label | d37b8262-1423-5a3d-903b-9575c49b10e6 |  | note | Comments: To the correct frequency & results captured on the earthwork lab testing register
checkpoint-status |  |  | checkpoint | Proof Roll carried out & witnessed
text | 8d097cbf-8086-57fe-a29f-4642702238de |  | textbox | Initials - Design Engineer:
date | c60ea4c5-c71b-5de0-9a9e-34ba9b4b7963 |  | date | Date:
label | e3182ff3-13f9-58b2-bb4f-a0c865283959 |  | note | Comments:
text | 9b1da30c-a097-5d94-ad0c-c43aa4810b11 |  | textbox | Equipment used:
checkpoint-status |  |  | checkpoint | Did Proof Roll pass
text | bd41df85-6089-5820-81f8-ae8360fc4153 |  | textbox | Initials - Design Engineer:
date | 5bcfa9cf-97da-559b-bb4c-6dd9cceb7ced |  | date | Date:
label | 577a6f14-0194-59b8-bb9a-61073a0d89ff |  | note | Comments: If yes moved to #10, If not undercut required continue below
checkpoint-status |  |  | checkpoint | Undercut area is to be marked out onsite by Design Engineer
text | 604057e9-3a25-54ab-a784-4373b9f6d77e |  | textbox | Initials - Design Engineer:
date | 8ec1a189-d594-51be-8d6e-3ef935a82c69 |  | date | Date:
checkpoint-status |  |  | checkpoint | Undercut to be inspected before backfilling commences by Design Engineer
text | 4fd64929-e633-52f0-8197-41e710bb068f |  | textbox | Initials - Design Engineer:
date | 2684c7ea-e1e7-5f34-81ec-cb219d7ef83e |  | date | Date:
label | 2dcc71c2-9f42-5207-9f3c-e8f88a63551a |  | note | Comments: To determine that all undercut areas are prepared to the specifications
checkpoint-status |  |  | checkpoint | Undercut area to be surveyed
text | 07df737b-828e-585b-b0d9-823f4ffa27f6 |  | textbox | Initials - Site Engineer:
date | e14bf673-e09f-5f7f-b5b3-2c584bcde719 |  | date | Date:
label | ba726da4-2b14-5417-9590-09c61b65acf1 |  | note | Comments:
text | d1642d63-a637-5aad-8ca2-11239b9f6f54 |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | Backfill material is approved to be used and is tested in accordance with specifications
text | bf5740e3-ca0a-556b-9298-d3c0f60f8ef4 |  | textbox | Initials - Site Engineer:
date | 7b583b6b-fafc-52f9-be36-ac5e64fab8e4 |  | date | Date:
label | ad3cd54e-193a-57a5-90e5-a650d09ef1f1 |  | note | Comments: Lab Test Result register
checkpoint-status |  |  | checkpoint | Site is prepared for bulk filling to commence
text | 450efe08-b43e-5045-8ebb-2c20048da63f |  | textbox | Initials - Site Engineer:
date | 080be7b5-7194-5a51-ad54-96ae190bcfdc |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 348d0ddb-8a75-5aa8-997a-e77f7ebeb7e6 |  | note | Position: Site Engineer
text | f030357d-770c-54b9-b216-5c49f9637cd9 |  | textbox | Site Engineer - Name:
date | f7f5af3b-9165-5bc6-b9d1-437e9e7730c1 |  | date | Site Engineer - Date:
label | 39838c88-fdd8-5656-86f5-912b8441366b |  | note | Position: Design Engineer
text | 7ad3cefe-fabb-5c23-83d5-26f09e2f9bde |  | textbox | Design Engineer - Name:
date | 46a15695-7424-5da2-a60f-4c68d65075d7 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4020 - Bulk Fill Earthworks Record |  |  |  |  | Yes | CS-4020 - Bulk Fill Earthworks Record | b43a6f20-3c9f-4762-928a-9a2538c2d7c7
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 82d2cb43-dbc7-5ca2-98b3-54c0617e3ca4 |  | textbox | Work Area:
text | 0b27267f-d2c7-52d0-9d35-955848c41c3e |  | textbox | Sub Work Area:
text | 9a7f0ba6-24e3-5484-8c7a-8ae7f7a21e09 |  | textbox | Lot:
text | d939f761-badd-521d-86d2-6fdebe884a5a |  | textbox | Sublot:
date | f5a64cdf-5dc8-5b02-99eb-d6650d332e69 |  | date | Document Date:
text | da8f6bbc-e8c7-5665-b3c3-d134117ceb64 |  | textbox | Created By:
checkpoint-group |  |  | section | Pre-Construction Phase
checkpoint-status |  |  | checkpoint | 1. First 1st lift - Ensure underlying layer has been signed off by Design Engineer – CS-4100
checkpoint-status |  |  | checkpoint | 2. For subsequent layers - Ensure Underlying layer has been signed off by the Site Engineer and/or Design Engineer as well
checkpoint-status |  |  | checkpoint | 3. Ensure previously constructed fill has not deteriorated from required fill standards before placing new fill
checkpoint-status |  |  | checkpoint | 4. All source testing completed in accordance with Specification XXXX – (Example - 1 x PSD completed @ 3000m3)
holdpoint |  |  | signoff | Site Engineer Verification Signature:
checkpoint-group |  |  | section | Construction Phase
checkpoint-status |  |  | checkpoint | 1. Batters to be overfilled by 250mm – Specification XXXX
checkpoint-status |  |  | checkpoint | 2. Visual inspection of fill for contamination, segregation & oversize particles
checkpoint-status |  |  | checkpoint | 3. Minimum dry densities: Example – 95% MDD - MDD = 2200 kg/m3 - Specification XXXX
checkpoint-status |  |  | checkpoint | 4. Scala/Shear Vane/Clegg limits: Example Scala – 2 blows per 100mm (Type 1 material) – 4 blows per 100mm (Type 2 material) – Specification XXXX
checkpoint-status |  |  | checkpoint | 5. Measure Lift thickness and confirm applicable roller and passes are applied in accordance with embankment trial results
checkpoint-status |  |  | checkpoint | 6. Vibratory roller to operate at 3km/hr (or less)
holdpoint |  |  | signoff | Site Engineer Verification Signature:
checkpoint-group |  |  | section | Bulk Fill Earthworks Record
checkpoint-no-status |  |  | checkpoint | Details
text | fdcb37f3-e287-5a2a-abc5-ddd97ad4717e |  | textbox | Weather conditions:
text | 0124251c-186b-5ea9-b4a6-e8340e02e3c9 |  | textbox | Supervisor/Foreman Name:
checkpoint-status |  |  | checkpoint | 1
text | d1b1daee-c676-5844-b179-46c134f34206 |  | textbox | Lift #:
text | 14597f30-99e5-5b98-aaca-1644cfe3fb30 |  | textbox | Chainage From:
text | 2bdcbbda-8b28-583b-ac31-e10edc61efac |  | textbox | Chainage To:
text | 903813b3-eb93-5b08-8667-7bf94bfcbcb0 |  | textbox | Test Spec:
text | 2bfcf86f-e95c-5d35-81cf-9a717ce7d754 |  | textbox | Material Visually Inspected:
text | a8fed40c-c0a7-5ef9-8935-30ffcc7f3f7a |  | textbox | Extent of overfilling checked:
text | ce90f6f7-c502-56fc-b2da-c09d96790891 |  | textbox | Lift thickness (mm):
text | e6504faa-da9b-5f79-8554-947aad08bf3e |  | textbox | Roller type:
text | 3e7347ec-b765-5241-a8ad-d3376f49475b |  | textbox | Minimum Passes:
text | 16b782f1-5639-5aa1-8994-f885f8853940 |  | textbox | URN test numbers:
date | 335bdb9e-f102-5054-97f0-b7eec713c3a0 |  | date | Date Completed:
text | b9da4007-8ef8-5139-ba0c-4b78694df112 |  | textbox | Site Engineer Initial:
text | 7ce9b335-4d32-5c07-9770-3b1e28a0616a |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 2
text | 5fd73407-d77d-5f3d-a1cb-25d76e1c111f |  | textbox | Lift #:
text | d98fb1f9-bb02-5f5c-a807-68dc9a326442 |  | textbox | Chainage From:
text | f9c5df50-7303-563b-89b0-4ef376dd2c67 |  | textbox | Chainage To:
text | de484948-b240-55bd-b5d9-b807e99a56a3 |  | textbox | Test Spec:
text | fa1b1959-06f4-573a-a8ab-0f0325e5f4e5 |  | textbox | Material Visually Inspected:
text | dc8be1c9-3b2b-5ea8-8064-a3fadb81ac4d |  | textbox | Extent of overfilling checked:
text | b1c0f5bd-2dbe-59aa-b009-6d526bc14d3b |  | textbox | Lift thickness (mm):
text | 6f0d2d00-a8de-58da-abd5-7dc203c7668b |  | textbox | Roller type:
text | 5b899932-71fe-52d2-894f-63aee3dea86f |  | textbox | Minimum Passes:
text | 7ebe5d82-66a3-54ab-b05f-7c0a5be3d4b3 |  | textbox | URN test numbers:
date | 2aa75bb5-e3f4-59ff-bbd3-d8536f6572d6 |  | date | Date Completed:
text | d920f610-dec6-55c0-8b91-cb578b52bb85 |  | textbox | Site Engineer Initial:
text | acf76ce0-5086-59be-9242-aafed3dfb224 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 3
text | f77682b1-1c01-53d4-9c9b-c7facb7fab7d |  | textbox | Lift #:
text | db7c28ef-f076-568d-98c5-1d5cdeec9158 |  | textbox | Chainage From:
text | 6cde2a9c-8414-5425-8f2e-82c002d2af9b |  | textbox | Chainage To:
text | 012776d9-e022-5016-96a9-697fe6a8d399 |  | textbox | Test Spec:
text | 1b78d463-4df9-509f-9ef3-357a290bead0 |  | textbox | Material Visually Inspected:
text | b153c96e-b4c5-5ef3-b37f-1602dc436c45 |  | textbox | Extent of overfilling checked:
text | e4fb126e-88f6-5e3f-8663-368fc5dbdb6e |  | textbox | Lift thickness (mm):
text | 9002747e-e292-5e9b-846a-e42a77619950 |  | textbox | Roller type:
text | 0e78ccb6-07a9-5307-ae73-b683fa9ae7d7 |  | textbox | Minimum Passes:
text | 643264a5-a0a2-509c-a898-7ff40cff5d74 |  | textbox | URN test numbers:
date | 7a0aca8c-85cd-5052-9c8c-57d17a8605bf |  | date | Date Completed:
text | 766af33e-4f83-5964-9540-d04d5c1206c1 |  | textbox | Site Engineer Initial:
text | a39daf78-3826-550e-951a-8eb1f3757f05 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 4
text | 338d1d82-b41a-5ea6-a3ec-e06a99b8d9c8 |  | textbox | Lift #:
text | 9b0de1c5-5f2a-58e3-a88d-158dcb2677ef |  | textbox | Chainage From:
text | 8e96b469-4307-5587-98f7-90f21ac70bd3 |  | textbox | Chainage To:
text | 32089386-729a-5922-8069-1fe84880ebb8 |  | textbox | Test Spec:
text | 5936df39-1395-56e7-8aed-a810c4750ca1 |  | textbox | Material Visually Inspected:
text | 71899587-baeb-57ab-a780-3bd7f8955ca6 |  | textbox | Extent of overfilling checked:
text | e783f768-e696-59e1-b894-3e7c7aae2196 |  | textbox | Lift thickness (mm):
text | 297f5f47-6b8f-5639-a7f0-f62528e2009a |  | textbox | Roller type:
text | a36f1655-ba42-5cac-af86-0671ab71c4ab |  | textbox | Minimum Passes:
text | 97deb59e-bdb4-5d69-8b71-499193be5c79 |  | textbox | URN test numbers:
date | 7985efc6-9920-5ae3-b171-d73e77b378f7 |  | date | Date Completed:
text | dd331189-1c5f-5477-8bdf-18e029928c2e |  | textbox | Site Engineer Initial:
text | 3f52ea13-49e1-5843-861d-70fc028c430c |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 5
text | ef168a70-a193-52cd-9408-a20a51e776be |  | textbox | Lift #:
text | 3bb1b30b-884e-5753-89d1-99be4f7eb586 |  | textbox | Chainage From:
text | 39474d63-c03b-551c-994d-aa1dcd6787b1 |  | textbox | Chainage To:
text | 31ec63df-cb7e-549c-b540-d2fbbb50f871 |  | textbox | Test Spec:
text | 6dd00b0f-df2b-533d-a4cf-fdce586bf517 |  | textbox | Material Visually Inspected:
text | ddab98aa-a72c-56a5-9231-1b7e09cf02b1 |  | textbox | Extent of overfilling checked:
text | 28e9267b-b249-5440-93ad-8d1376f03cef |  | textbox | Lift thickness (mm):
text | 6c361fde-529b-531f-9077-9b5dc82b0607 |  | textbox | Roller type:
text | 9797a1f6-bf27-5aee-aa4d-44ca813a8a9f |  | textbox | Minimum Passes:
text | 3ca1ca1f-cc4e-5bd1-8024-68be813bc33f |  | textbox | URN test numbers:
date | 8cf44da2-c593-5e1f-8663-f9d1f77ffd39 |  | date | Date Completed:
text | 26888401-7631-5bf6-bfa1-9bf85331f435 |  | textbox | Site Engineer Initial:
text | b8bbdde7-8cb5-58f0-95a4-28658abda0fe |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 6
text | b83c8108-2150-503a-ab93-9e2409774c94 |  | textbox | Lift #:
text | e79b48b8-6006-5b19-872d-371d23867ce3 |  | textbox | Chainage From:
text | 2a01930c-d7b9-5bc9-a77d-160ac4e79cc5 |  | textbox | Chainage To:
text | cd4ce2cc-6505-51c3-92d5-f5edcd2abf6e |  | textbox | Test Spec:
text | 9d6ace94-36d2-5d49-803f-3a8e045aa97b |  | textbox | Material Visually Inspected:
text | 42b1c110-eeee-5be5-888d-841383a81851 |  | textbox | Extent of overfilling checked:
text | bd260bb6-e4d0-5129-a0da-1e40325009ad |  | textbox | Lift thickness (mm):
text | 91b8d576-7abd-5927-b8ff-f78eff4ef018 |  | textbox | Roller type:
text | 38f802b5-12b7-5583-9b8e-baa8f3d551fd |  | textbox | Minimum Passes:
text | 213d75a9-43bf-5865-8577-726cd5d7f7d4 |  | textbox | URN test numbers:
date | 92b70eb7-f304-5e5e-b3e2-561ab0db6b44 |  | date | Date Completed:
text | cc34b9cb-4852-57e1-b319-61ea96ddc425 |  | textbox | Site Engineer Initial:
text | 7e8dc411-abd3-5194-9819-be7d0ca2045e |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 7
text | c48e70fe-523c-5031-97ea-bc9011399a64 |  | textbox | Lift #:
text | 2a85ca4e-2512-5b5f-965d-26c2d9485a46 |  | textbox | Chainage From:
text | 1a54057d-67c1-5d75-b7de-aaf43cd9bb81 |  | textbox | Chainage To:
text | 0d811e81-622e-51f4-9dd9-8627707af12f |  | textbox | Test Spec:
text | 3dbc6424-9324-5763-94ca-b6db4dfaa137 |  | textbox | Material Visually Inspected:
text | 53ef4596-c688-568b-a572-c7377affc1e6 |  | textbox | Extent of overfilling checked:
text | f3d2f489-d780-5685-b63b-de0222c1e8f7 |  | textbox | Lift thickness (mm):
text | 610166f5-f8c3-52cd-8a16-0589cae54c3d |  | textbox | Roller type:
text | 7bc63d26-7d4d-5d7e-b42b-5a7c0851be6d |  | textbox | Minimum Passes:
text | 52d9fb2f-1c86-5a50-b44d-cfb6344756c9 |  | textbox | URN test numbers:
date | 8d508f80-bfa4-5b85-8653-5e8f0a69018b |  | date | Date Completed:
text | 41a0c67d-26ad-5851-9bf4-ee345cac7216 |  | textbox | Site Engineer Initial:
text | 3081d995-8070-5381-8890-7f1579554b7d |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 8
text | 8cb86a0f-0fbe-5e39-92bf-a86ef815a094 |  | textbox | Lift #:
text | d50b7a95-19dd-5237-b3f3-ebc1708f2c16 |  | textbox | Chainage From:
text | 43c8ac1c-58c2-50f7-a728-dc2a834f21a9 |  | textbox | Chainage To:
text | 495d019d-ba9e-5639-9b46-987043f1c74f |  | textbox | Test Spec:
text | 3e6d2959-d5a0-5f06-bb83-7d5d58d7c2e4 |  | textbox | Material Visually Inspected:
text | 4f620e7a-eb5f-5c2d-8369-8c8044695b92 |  | textbox | Extent of overfilling checked:
text | 809f7a4b-2acc-55cc-894f-b6ae21746f65 |  | textbox | Lift thickness (mm):
text | cb53c632-d40f-549e-b32e-f753356bf1b5 |  | textbox | Roller type:
text | 7d167da4-a4cf-5583-bd28-f2906ee358f1 |  | textbox | Minimum Passes:
text | c3e15a8c-9f0d-531a-bc01-2d8b6d01b11d |  | textbox | URN test numbers:
date | 4e89331e-0acc-5815-8415-aa8927d07825 |  | date | Date Completed:
text | 42f1d8bc-4f41-5302-bd70-4e71ad5179e9 |  | textbox | Site Engineer Initial:
text | 230adc0c-06a0-5ced-9de4-0ced8b15a9aa |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | Signoff
text | 996db487-667d-50b6-8b3f-71f85474bc8e |  | textbox | Site Engineer:
date | cb344002-fd99-5987-9fd0-c24e6d52e9a0 |  | date | Date:
holdpoint |  |  | signoff | Signature
checkpoint-no-status |  |  | checkpoint | Other Information/Comments (photos, survey records, sketches etc.)
label | 0ade57b3-bc6e-5e8d-a472-dadbd51c9489 |  | note | Additional Information please document
text | b3bd2eaf-491f-5b0d-a545-d48bc895faa2 |  | textbox | Quality Manager:
date | 29e13a60-c891-52d3-9bb0-b10612700fbc |  | date | Date:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | CS-4099 - Watermain Disinfection Checksheet |  |  |  |  | Yes | CS-4099 - Watermain Disinfection Checksheet | b55c632b-9603-43f7-b7c6-0e4ebf597ae4
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 83eac77d-a10e-54ba-b1a8-496ae47d6c62 |  | textbox | Work Area(s):
text | a3217c23-40e2-58bb-b1d9-11a39002e082 |  | textbox | Sub Work Area(s):
text | d5e68965-3472-5e39-bf22-efddac8f99db |  | textbox | Lot(s):
text | b15425c7-e65a-5641-9407-8157e551cbb7 |  | textbox | Sublot(s):
date | 09e510cc-cf92-5279-af2b-83064fd1310f |  | date | Document Date:
text | 11843db5-1a15-5e98-9b21-3c14d8f42805 |  | textbox | Updated By:
checkpoint-no-status |  |  | checkpoint | GENERAL INFORMATION
text | 506759f0-5d7f-58af-8887-6f4e5274c287 |  | textbox | Contract No. or Resource Consent No.:
text | 7a6e34b3-038e-552f-8df3-cca13bd90f2f |  | textbox | Contractor:
text | 9ae2f80d-5bef-5716-baa0-8f1c9414ba3c |  | textbox | Site Supervisor:
text | 6f183817-24a7-5930-a19b-2bdc5096e830 |  | textbox | Site Location:
date | f2d0d026-f6f7-5ece-a5f1-0abdd6eade3c |  | date | Date:
text | eaeb41e3-b9e1-517d-95bd-efbe59304d76 |  | textbox | Time:
text | cb23d758-0a3b-5d69-ab89-423fee114754 |  | textbox | Pipe ID:
text | 08d0fdea-38dd-51b5-879c-3c0f91152b63 |  | textbox | Chlorine Type Added:
text | f3589ddf-f5f7-5ecd-a944-2674911bb15e |  | textbox | Pipe Diameter:
text | 53065a2f-e30a-598b-91f6-db7af4fed8f8 |  | textbox | Pipe Length:
checkpoint-group |  |  | section | TEST RESULTS
checkpoint-no-status |  |  | checkpoint | Table 1 Acceptable Laboratory Test Results
label | 72d3bf6c-ec98-5690-8083-d77c6825576f |  | note | Parameter ¦¦ Acceptable Value
label | 28732d85-1131-56f6-9b73-d6e9e1e4d53a |  | note | – – – – – – – – – – – – – – – – – – – –
label | 7d522a3e-10f7-5c3d-951e-26f80fe50804 |  | note | Residual Chlorine ¦¦ Between 0.5 and 1.0 mg/l
label | f16d3226-ce05-5c8f-abdd-9c97359e1031 |  | note | Turbidity ¦¦ <1 NTU
label | 5c56cb1c-bf48-511b-a6b8-ae4134b5ee8b |  | note | E. coli ¦¦ <1/100ml
checkpoint-status |  |  | checkpoint | Test Point (1)
text | 425fff5e-36ee-570a-80dd-b92cc4076012 |  | textbox | Test Point:
text | 30b07283-cedc-5d20-b707-8c1c73913164 |  | textbox | Initial (mg/l)
text | c660cb61-d768-5b6c-80dd-8f8bb99feff0 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (2)
text | 5ef96d2c-0780-5e66-afa9-22d4cbe9582f |  | textbox | Test Point:
text | dc1d81dc-f9c0-5150-a016-79c952a869f1 |  | textbox | Initial (mg/l)
text | 0d9b5c12-d878-5a5c-8a47-59650077d678 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (3)
text | b5a8531c-750e-5e02-a01d-2bd321827dad |  | textbox | Test Point:
text | f8f3ea7a-6078-5032-b97f-6aed0ff85574 |  | textbox | Initial (mg/l)
text | 2b3ae6f0-dac8-5f5d-a63e-b2dfe16c433c |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (4)
text | 067b17c0-c57a-549b-b5dd-1ad65fd6a5e5 |  | textbox | Test Point:
text | 89dc3ab6-662b-54e3-aa25-b0a74b10349c |  | textbox | Initial (mg/l)
text | 2f4d6670-6512-5907-8983-0d8b0a62f9b7 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (5)
text | 06f77f59-02be-55a5-b907-b4ddac7572a5 |  | textbox | Test Point:
text | 999fd985-ec1e-5ce8-b6fc-f62a3885232a |  | textbox | Initial (mg/l)
text | 70545087-8e92-5a6b-9666-54ebcece4fd1 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (6)
text | 57a9d08d-0a6b-59ff-8043-c68f51266971 |  | textbox | Test Point:
text | 69f3836f-c320-50c0-b26d-ab412f790e6d |  | textbox | Initial (mg/l)
text | 0a884dcc-66fa-5861-9e7e-55d321d8c795 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (7)
text | 889fe097-513c-503a-bc38-8ae258aaad05 |  | textbox | Test Point:
text | 6404c17f-4d2d-531d-8f33-7594174082fe |  | textbox | Initial (mg/l)
text | 0673ddec-a4df-5ca5-ab3a-c7dd7b5322d5 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Laboratory Results Acceptable (Attach)
text | c1fa0e9f-5330-56af-b978-742a8d5ccf00 |  | textbox | pH Reading after 12 hours:
checkpoint-status |  |  | checkpoint | Signed:
text | 2aa6d580-84ea-5533-bb09-820a3295a1bf |  | textbox | Print Name:
holdpoint |  |  | signoff | SIGNED
checkpoint-status |  |  | checkpoint | Signed CPS:
text | aafbb568-c63d-5ff2-b5e9-47ce3b6e9e86 |  | textbox | Print Name:
holdpoint |  |  | signoff | SIGNED CPS
checklist-sectioned |  |  | checklist | CS-4010 - Services Relocation Checklist |  |  |  |  | Yes | CS-4010 - Services Relocation Checklist | b93d2aab-9b8a-473f-9ba8-57673015ab76
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | b557098e-83f4-5409-8c82-56fdaa7f08ca |  | textbox | Drawing No:
text | e85d045f-c1f2-510e-8ac1-18d4740c9b8d |  | textbox | Rev No:
text | b29f7551-b36d-50e0-97fc-8f9b56eec8eb |  | textbox | Chainage:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | 1 - Set out by surveyor & handover to Site Engineer completed
text | b29bdd00-b4a3-5ff1-9ec9-219e351b8da5 |  | textbox | Initials:
date | b4ac4b99-83b0-5990-86f6-1e981d90f501 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2 - All existing services exposed and identified before trenching
text | 3cc5f551-03a3-5e9a-ab96-3f022e14205c |  | textbox | Initials:
date | 77bd7d49-43c2-595d-a0c5-72bda6fd3a28 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3 - Trench line and profile as per IFC drawings and as set out by surveyors
text | bf7a1686-03b2-5aae-ad05-61830a661f4c |  | textbox | Initials:
date | 297cad10-a16c-5361-bebb-ce473e868b4d |  | date | Date:
checkpoint-status |  |  | checkpoint | 4 - Trench must be made safe before any person may enter the trench
text | f3e5b131-aff9-5c90-b8e3-294eb3177203 |  | textbox | Initials:
date | f8062ec3-2839-5d51-8cb1-bed10dec146a |  | date | Date:
label | f30bcde1-a985-5791-b395-6f5df94a13f5 |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | 5 - Base of trench inspected and tested if required.
text | 5882ef8a-e3ce-56a0-b5f6-36dcb8b283ea |  | textbox | Initials:
date | da7cd4f0-65c5-5817-81c8-8ac703221f66 |  | date | Date:
radio | 320b0ff3-8fa7-50eb-b393-3a7e54e57849 |  | radio | Under cut required | Yes,No
checkpoint-status |  |  | checkpoint | 6 - Ensure sufficient protection layer is placed around the new services cable
text | 390a041d-a604-5fa6-992d-45ced10d6865 |  | textbox | Initials:
date | 4bd734d9-bfdf-58d6-84de-babdb9e46da3 |  | date | Date:
text | 43cbb162-9fec-5857-864a-c3ce967b5bc3 |  | textbox | At least: |  |  | mm
checkpoint-status |  |  | checkpoint | 7 - Ensure warning tape and/or magslab is laid at the correct cover over the new services cable
text | be7f75b6-8309-55a5-82e4-3f5c5524b679 |  | textbox | Initials:
date | 06d8d084-2a1c-5b37-ac3d-57195f199a0c |  | date | Date:
checkpoint-status |  |  | checkpoint | 8 - Ensure backfill material is suitable and un-contaminated
text | 944cf640-4561-5dc1-a9d1-9e5707fe2256 |  | textbox | Initials:
date | 35287ff6-cc27-5ce5-b12a-7a61457ca1a9 |  | date | Date:
checkpoint-status |  |  | checkpoint | 9 - Backfill compaction tested at every ____mm lift
text | 15a77c68-2097-5b7b-b340-8bc1c6020ff1 |  | textbox | Initials:
date | 42e2716e-ff28-52ae-8470-62e516b39d9c |  | date | Date:
checkpoint-status |  |  | checkpoint | 10 - As-builts updated and surveyed when required
text | 0ffaa3c4-8341-5ce2-9354-52c393c02000 |  | textbox | Initials:
date | 6b26a1aa-3f7a-5a4b-8246-3f37daa1b1f5 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 4e2e1917-dbec-5485-a58a-30844247af38 |  | note | Position: Site Engineer
text | 006d38d3-614b-516f-af7b-408203fb58e1 |  | textbox | Site Engineer - Name:
date | fd36aaaf-df6b-590c-9138-198e99f0b472 |  | date | Site Engineer - Date:
label | ccbb0241-0a91-509c-86c4-e5d82b30d727 |  | note | Position: Design Engineer
text | 86d921dd-a57a-5b1e-b445-f7322618f907 |  | textbox | Design Engineer - Name:
date | 9e72dd92-ac6e-5ff1-abd8-9d6ace156053 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign
checklist-sectioned |  |  | checklist | CS-4076 - Asphalt Laying Checklist |  |  |  |  | Yes | CS-4076 - Asphalt Laying Checklist | beb4df46-b62a-4a90-bcea-e380551fa81a
checkpoint-group |  |  | section | Pre Laying (Tasks 1-7)
checkpoint-status |  |  | checkpoint | Final confirmation job is ready (Site Handover, Job Instruction sheet)
checkpoint-status |  |  | checkpoint | Undertake Emulsion Tack Coat Risk Assessment
label | ab25d602-3f29-59d4-b195-aeb9c63b2209 |  | note | By Who: Foreman
checkpoint-status |  |  | checkpoint | Confirm job matches Laying Plan. If not, confirm and communicate variation with manager/ customer
label | 398515c2-b193-55a3-b0b0-c3b43d7e3fc0 |  | note | By Who: Foreman
checkpoint-status |  |  | checkpoint | Visual Inspection of site and stringlines completed as per Site Handover
checkpoint-status |  |  | checkpoint | Daily Pre-Start Meeting/Hazard ID completed
checkpoint-status |  |  | checkpoint | Approved Traffic Management Plan on site (implemented and effective)
checkpoint-status |  |  | checkpoint | Vehicle Movement Plan
checkpoint-status |  |  | checkpoint | Fences, walls, kerbs protected and environmental controls in place
checkpoint-status |  |  | checkpoint | Pre-seal prep including offset of services/ roadmarking and protection of fixtures
checkpoint-status |  |  | checkpoint | Laying Plan and Rolling pattern confirmed
checkpoint-status |  |  | checkpoint | Paver setup. Screed checked at start of the day (level and feed controls functional)
checkpoint-status |  |  | checkpoint | Stringline Tie in points to calculate required asphalt thickness
checkpoint-status |  |  | checkpoint | Starting blocks in place (including compaction allowance)
checkpoint-group |  |  | section | During Laying (Tasks 8-9)
checkpoint-status |  |  | checkpoint | Tack coat applied and cured
checkpoint-status |  |  | checkpoint | Mix visually inspected and the ‘in hopper’ temperature is within tolerances (contract-specific)
checkpoint-status |  |  | checkpoint | Mat depth control (contract-specific)
checkpoint-status |  |  | checkpoint | Stringline Tie in points for correct depth
checkpoint-status |  |  | checkpoint | Rollers working to agreed pattern
checkpoint-status |  |  | checkpoint | Shape and levels achieved as per specification
checkpoint-status |  |  | checkpoint | QA forms completed as per Job Instruction form
checkpoint-group |  |  | section | Post Laying (Tasks 10-11)
checkpoint-status |  |  | checkpoint | Measure and record area, quantities and spread rate
checkpoint-status |  |  | checkpoint | Post-paving subcontractors notified
checkpoint-status |  |  | checkpoint | Collate QA forms and supporting documentation (refer Job Instruction)
checkpoint-status |  |  | checkpoint | Post paving as-builts, coring, survey
checkpoint-status |  |  | checkpoint | Plant de-established and off-hired as appropriate
checkpoint-status |  |  | checkpoint | Roadmarking checked and completed
checkpoint-status |  |  | checkpoint | Traffic loops / counter loops reinstated
checkpoint-status |  |  | checkpoint | Traffic management de-established
checkpoint-status |  |  | checkpoint | Services exposed, raised and painted
checkpoint-status |  |  | checkpoint | (hydrants, valves, manholes)
checkpoint-status |  |  | checkpoint | Job site safe and tidy
checkpoint-status |  |  | checkpoint | Job site tidy. All AC piles picked up. Kerbs chipped and swept. Drains checked for AC. No footprints left in gardens/berms
checkpoint-status |  |  | checkpoint | Transition joins/tie ins are tight and flush (no high/low ridges, no risk of plucking out).
checkpoint-status |  |  | checkpoint | Longitudinal and fresh joins are all tight and flush (no high/low ridges, no risk of plucking out – water running freely across joins).
checkpoint-status |  |  | checkpoint | Kerbs – height/finish requirements met across 100% of job (refer Job Instruction)
checkpoint-status |  |  | checkpoint | Ride Quality – Drive over site - no bumps can be felt
checkpoint-status |  |  | checkpoint | No visible surface defects (roller / stretch marks)
checkpoint-group |  |  | section | General comments
checkpoint-no-status |  |  | checkpoint | General comments:
label | 7b350b9e-2519-56ce-9f26-45281e8d5a13 |  | note | Score Guideline (record comments/details)
label | bd5e81c4-d3c7-5802-a41d-8b110f53f12a |  | note | 1 - Not Acceptable (remedial/rework required, advise Manager)
label | a37d136d-201f-5697-b9cf-38fc5127c0d6 |  | note | 2 - Acceptable (no obvious problems, can be handed over to client)
label | afe886e0-5a52-5f73-a551-173e2893b80a |  | note | 3 - Excellent (entire job above standard)
checkpoint-no-status |  |  | checkpoint | Job quantities/spread rate
text | d34c01a6-4266-5c4b-82e3-bc665c2578f4 |  | textbox | Hand lay (H), Paver lay (P)
text | 16fb11d2-ff59-5b8e-a729-13f91af14e76 |  | textbox | Mix Type
text | b26223e4-42ac-521c-83cb-5cafe313fb39 |  | textbox | Area (m2)
text | 0ccd3b27-3adf-5a33-bdd6-b3c080bedbed |  | textbox | Depth as per Job Sheet
text | a0fa4032-b559-5c7b-a7a4-163d6714fb53 |  | textbox | Tonnes Purchased
text | 8f928c30-8cf9-5cbb-ba29-3b89b7322a40 |  | textbox | Wastage Tonnes
text | 23fa7a60-72be-5809-9d4d-563b4593836b |  | textbox | Tonnes Laid
text | 43aa292b-9ee8-5156-802e-10c110c5bb26 |  | textbox | Average Depth (mm)
text | 3e722871-fe13-5a96-89e4-820493be7ac9 |  | textbox | Emulsion Primer (l)
label | 4738022d-5131-521e-835b-9bda5def189a |  | note | Depth = Tonnes ÷ Conversion Factor (Density) ÷ area (m2)
checkpoint-status |  |  | checkpoint | Signoff
text | f0ca86d2-a695-5db1-82c7-9ccead4861d3 |  | textbox | Signed by Foreman:
date | 8a3c3654-dd0c-5747-b6ae-75fb22c739f6 |  | date | Signed by Foreman - Date:
text | 3e666f62-220d-5420-aec0-c4ecb9067b89 |  | textbox | Reviewed by Manager:
date | df8cabcb-f5b7-5e57-b0cd-495bd8b8956e |  | date | Reviewed by Manager - Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | CS-4053 - Fencing Checksheet |  |  |  |  | Yes | CS-4053 - Fencing Checksheet | c1355756-b134-491a-93d4-20262bc424cc
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | f6c8bc53-46ae-54ef-a3b7-f8854472a55a |  | textbox | Project No.
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Fence Height - 1200mm
text | c83b3b91-d1cf-5f6e-b60f-62666188c624 |  | textbox | Initials - Site Engineer:
date | 3313057e-7023-5f1d-9ac2-13826d68d4a6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
text | 2696395f-ca44-5722-ab56-57da165d548c |  | textbox | Initials - Site Engineer:
date | d7c9b061-d6e5-5245-87a2-6d0cb6ac21d9 |  | date | Date:
label | 2dbce8cb-9952-5115-9b1a-19ed43b18c21 |  | note | Comments: Max dist between strainers 300m
checkpoint-status |  |  | checkpoint | Posts 1.8m long, 0.6m embedded
text | 94791c3e-1e87-5076-ba46-74966ec0076a |  | textbox | Initials - Site Engineer:
date | 4e60f993-1aa9-52f1-b1b8-2e1706f129f6 |  | date | Date:
label | 4991841b-8a3e-5585-828c-3c9cca40e5fa |  | note | Comments: Max distance between posts 5m, slope spacing as required.
checkpoint-status |  |  | checkpoint | Battens 1.14 x 50 x40
text | b7defd65-18a0-5a4f-bf76-eff4fe071291 |  | textbox | Initials - Site Engineer:
date | 5b4b09a2-7c1a-5168-b446-61229fdbf5b0 |  | date | Date:
label | c3c0b1ed-b35e-527b-9b54-8b95c5958000 |  | note | Comments: Battens placed at not more than 1.0m intervals and stapled at each wire.
checkpoint-status |  |  | checkpoint | 9 wires 2.5mm HT
text | 0c1ca1ba-c76e-528a-9c0c-c4ff4b565635 |  | textbox | Initials - Site Engineer:
date | ab371e88-e989-5c63-b1d5-567b4e582c8b |  | date | Date:
label | 47c8f3c6-b690-54a2-85a9-63458b78c8fa |  | note | Comments: Bottom wire to be max 100mm from ground level
label | d3c96a65-56e2-5c2b-9bb1-2f490dcf5e4b |  | note | ○ Wires spaced at 75, 100, 100, 120, 130, 130, 150, 160, 180mm and all stapled to post/battens.
label | 132efad5-83b0-5877-ada8-65ddcaf68fa3 |  | note | ○ Top wire min 100mm from ground.
checkpoint-status |  |  | checkpoint | Stays
text | ae56248a-6ad8-5c26-9182-f9af040b1dec |  | textbox | Initials - Site Engineer:
date | fda38787-df81-5613-a934-2ab092cff59f |  | date | Date:
label | bd363ddf-be5a-59d5-9afa-109cf2d3ce2c |  | note | Comments: Footed stays must be used on all strainers.
label | e42bcd9a-3959-5c96-8f52-989f628837e2 |  | note | ○ ‘Feet” also to be used on posts in the bottom of gulley’s to prevent pulling out when wire tensioned.
checkpoint-status |  |  | checkpoint | Gate min height 1.2m
text | b1106b55-504d-5bf1-943b-9a0a41a176dc |  | textbox | Initials - Site Engineer:
date | 806527c6-e76c-597b-8448-b6885db7b236 |  | date | Date:
label | 694dda17-d3ae-5e0d-b7bd-4e173529abd8 |  | note | Comments: Alloy/wooden gate new or reused. Hung correctly/does it open?
checkpoint-status |  |  | checkpoint | Is fence vertical & true to line?
text | 370d0d78-fd7f-5b30-935a-3f9d869b18dd |  | textbox | Initials - Site Engineer:
date | 7b9df5a5-ba8c-59ba-baca-a2c1ce8142b5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Fence Height 1200mm
text | 9c7d5ee2-1f59-5267-b089-9a3a577cde01 |  | textbox | Initials - Site Engineer:
date | 7e0474e8-44f5-5b13-b67d-010b0a30c563 |  | date | Date:
checkpoint-status |  |  | checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
text | 8204addd-950a-5b12-9eee-98ed7ee0e1d6 |  | textbox | Initials - Site Engineer:
date | 710ff736-a940-5b77-a412-40e3756f8d71 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | fa91c7b6-2826-5672-a896-9c2c2920d472 |  | note | Position: Site Engineer
text | 5be73000-f500-5089-b88b-93681acc2fed |  | textbox | Site Engineer - Name:
date | cb6b5cd9-b8a4-5127-82c2-c7be894327df |  | date | Site Engineer - Date:
label | f38ca19e-e127-59d0-b047-d96ace4a7a08 |  | note | Position: CPS Engineer
text | 8bba08c8-cbaa-5c77-bc64-42ec0bfeb78e |  | textbox | CPS Engineer - Name:
date | 2ef743a6-a96e-5910-a3fc-9022288cdfd2 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation | itp |  |  |  | Yes | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation | c13fcb74-c6bb-4ccf-af26-adfa7f821e68
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 29030db5-c00a-5b76-8e85-eb4404a9a888 |  | textbox | CPS Eng.
text | b1819594-5ef7-580d-b4ab-2d32a8e7bbeb |  | textbox | Site Engineer
text | 01af451b-070b-54a3-af99-fd72751c6a1f |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 -
label | 6dea88ec-f58b-501d-93d7-ebe9321acfad |  | note | ACTION (Hold, Monitor, Witness) - H
label | e2b7f8d1-f743-5c3d-b96d-ddeec4662f68 |  | note | Detail - Earthworks and pavement construction shall be completed prior to barrier installation.
label | 3d1b7539-b5a4-5fb0-96a4-7a711a9a67d5 |  | note | Frequency - Prior to commencement
label | f7f07292-9d4a-5fe9-bd99-544ff0e59e66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | b4d1b46c-d3cf-5dce-8af9-9b2118e5b1c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd791560-24a0-5cba-89b2-5614beb3ff29 |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | 45bb7fb4-fa52-5425-9cee-20e73b2cdc4e |  | note | Frequency - Prior to commencement
label | da9da46b-3e10-5b2c-a0c4-46c90b193eca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 8cf02767-536a-5b90-93ba-0fb1a6a07af8 |  | note | Conformance Criteria - National Standard for Traffic Signal
label | e1a6c097-4c60-5fd5-992e-458a89670ed9 |  | note | Records - OFI or NTD/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | cc7b4c94-fcc6-5d9b-b31e-c4c3b73a0444 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 74046930-de13-54a9-97bd-75341a09cc5f |  | note | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
label | eecd08ac-cfc5-558e-8fc2-29e426462a0e |  | note | Frequency - Prior to commencement
label | 9179c29a-c84e-5494-b4d1-e5af0211fbf0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ed185c4e-f0e5-5d57-a2de-4d45da1890d4 |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 58cc6129-b50b-54bb-99f3-272f57897a2e |  | note | Records - Approved Construction Drawing.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 233b4d6d-2bb1-5890-a1a7-9d78ae99e9a0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab460161-921d-51a5-88d5-129389fdcdc7 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | 5432a543-85de-50a3-ac6e-93a1495fe1f3 |  | note | Frequency - Prior to commencement
label | 129c1afb-386f-5c1c-bea0-4f202db11fe0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | 3c1bcf6a-5c66-58af-b5cf-d955a2b528ad |  | note | Conformance Criteria - TNZ M/23:2009
label | 5a71919f-4867-5c44-b0d4-c8fb1222b41e |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Guardrail Installation
label | 635c447b-241f-562a-a41a-e64794178222 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 535dd2ef-9199-5ec6-ae4a-eaeba9eee84a |  | note | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | fa3ee647-49fd-5f03-b55a-d00991d50621 |  | note | Frequency - During installation and on completion
label | 48aa63b9-dccb-50c0-af1e-1f9548ba3a66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | ddd40a3e-864f-5ed9-bed5-1b156d454036 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | f20f2faf-8ae1-5e13-b2f3-05d312ee7ed4 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 6 -
label | bd31f059-a6ae-58f5-a3d1-0f696684cea5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fc916c8a-8f72-59ff-b542-a84c12b3b363 |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 3b14b24f-290a-5901-8e36-881d6e834327 |  | note | Frequency - During installation and on completion
label | 2e01dd05-689a-5aae-aa45-8fa7d0d6c2a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | b473369e-cec7-57a9-9841-1fee3b11c242 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 383552a4-6603-5ef4-a69c-09d1a17fe519 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 7 -
label | c4779109-59af-5f99-b511-8b2d4b38941e |  | note | ACTION (Hold, Monitor, Witness) - W
label | b42d7b6c-a6da-5bc4-a39b-0b853b6e25b6 |  | note | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 730916ea-5aaa-5269-8362-6450c76557d9 |  | note | Frequency - During installation and on completion
label | f2793c75-5064-51b2-b568-c5ed5f5c9e44 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 8fc72101-7539-5344-9387-ee862663bddf |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | fdb25ff3-fa19-5687-b44e-9fdd6bfd0b10 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 8 - Lot Number QA File
label | 6a94fcf7-bf73-5fb0-85cd-bc85e8b1aea6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9faec207-dc75-5bc7-beb0-899cf0eb72d0 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | cf38c6b2-2650-5b7e-a488-41a027fdfd23 |  | note | Frequency - At completion of Lot
label | 8404a664-fc35-5666-89c0-37f8b6713dd5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | e114dbe6-7bbd-5767-9f8a-ae0cb7cfacad |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8f12b964-f263-5df6-94fb-6ad076e6ff68 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 9 - As-builts
label | f873b643-3c92-5754-a495-8f8e9fcfc7ba |  | note | ACTION (Hold, Monitor, Witness) - H
label | baaa1cf1-66b9-5b21-97d8-5ea87ed9f116 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 677c987d-f423-5afe-8ae3-e23dee0e244b |  | note | Frequency - At the completion of the Lot of work
label | 46f55ef4-025d-5ae3-98d1-7284c2f83ef8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b4a953d2-9324-5f84-b162-c5d61b856abf |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Quality Assurance deliverables
label | 488bfea8-12ee-5683-a6bb-e585b6e494e5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7bd1409e-5c51-574a-94ea-5d1a577d0ab7 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | afdb8cde-14df-593c-9b6d-cf1b34638285 |  | note | Frequency - At completion of Lot
label | 7d7ce66b-c1e6-5c98-b8ad-041593cf4433 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ff76fa94-d064-5be4-bdbf-4cf71d915da8 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 77b45e4c-4079-5210-b526-133a44e1be5f |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 11 - Completion Sign Off From Fields Below
label | 466662aa-c337-5563-97ac-633f107d1786 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) |  |  |  |  | Yes | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) | c6b9a959-6e4d-420b-9aba-4ebbd9d16be8
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 4f9f7310-e30f-54a4-9c5d-3bc0580ebe41 |  | textbox | Work Area(s):
text | 5cfd1600-ac87-50e3-a677-29c7bcdcb2e2 |  | textbox | Sub Work Area(s):
text | a09c4ba2-35b1-51eb-a710-f0ff10203237 |  | textbox | Lot(s):
text | 1d7b1a4a-44f3-50e5-abeb-6b3c8482d8f8 |  | textbox | Sublot(s):
date | 599572ca-bc98-5713-b9e4-c4029ef0ea07 |  | date | Document Date:
text | 788b187c-f962-5e12-8e5d-0f414fddbee6 |  | textbox | Created By:
text | d4ccf115-650a-5908-a4fb-680b6a960a70 |  | textbox | Drawing No:
text | 7e7f6075-46be-5d58-b276-7e1dbb7e804f |  | textbox | Concrete Grade: |  |  | Mpa
text | 8023604c-825d-524b-9256-4ecd9dc0df42 |  | textbox | Pile No:
text | 2bec978f-3416-5482-9631-79314f3ea69b |  | textbox | Diameter: |  |  | mm
checkpoint-group |  |  | section | Set Up
checkpoint-status |  |  | checkpoint | Piling Platform Compacted & Level
text | 3a2f52ab-f1cb-5746-b1ba-11b3f21ad4b9 |  | textbox | Initials:
date | eab11901-6826-5372-b340-24a60349f71b |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Dig Obtained
text | 3bbde87e-9a0a-5bd0-98d7-ff7ab8c3268c |  | textbox | Initials:
date | 14167d19-50cb-533a-8be0-bcc17078b59a |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Set Out & Checked
text | d6801791-dd6e-576c-a037-ded33373b4ba |  | textbox | Initials:
date | 2ea4b8e9-31e6-5f28-bb36-c3261084247e |  | date | Date:
checkpoint-status |  |  | checkpoint | Erosion & Sediment Controls in place
text | 693b50a1-e7c7-57c1-9329-62c70441d082 |  | textbox | Initials:
date | f2433b24-e974-576a-b2b9-b13a8f680afe |  | date | Date:
checkpoint-group |  |  | section | Drilling
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | a2db02b0-f0f5-5c2f-944f-fa32a9b8cf1d |  | textbox | Initials:
date | 67c305ed-67cc-5d14-9953-3b91f5295a04 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Casing Installed to Rockhead
text | 83573c03-de02-59ef-8639-7568c5bb08e3 |  | textbox | Initials:
date | 59a12f2a-e429-53a3-97bc-d084b17bd1c4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Bore Logged
text | 73ab9b7c-1ae6-5fd4-848e-bfdfd97aa4bd |  | textbox | Initials:
date | 58872e18-37af-5aae-9a13-70410b0d8d4e |  | date | Date:
label | b6b06cac-8166-582f-bceb-9e6515d05ab4 |  | note | Comments: CS-4083
checkpoint-status |  |  | checkpoint | Pile Drilled to Required Toe Level
text | 11d50dc3-0d4e-5c89-91fc-0ff3a05151f4 |  | textbox | Initials:
date | 97f4adcf-2da2-546a-838c-4d09e176351e |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Sides Grooved
text | a6906926-7781-5e16-8e3e-7079d7fa3316 |  | textbox | Initials:
date | 6469e1e5-81b9-55fc-911c-5239c24e703e |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer Inspection of Bore
text | d9030add-35b0-5e18-a0a0-df95d2d5d498 |  | textbox | Initials:
date | 3c0d00c3-a917-5faa-9912-f9b70f532a60 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Toe Cleaned
text | a8fb9589-87cd-5051-a241-7836e3ab88e1 |  | textbox | Initials:
date | 07b10a6e-855b-528e-b4c4-7d3e49cc4f04 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Pumped Dry
text | f691c211-6bb4-54f6-a149-78f0438025b1 |  | textbox | Initials:
date | 2498c165-4365-54e7-9190-300851317261 |  | date | Date:
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content, Grade and size
text | 1506ba79-c769-58d4-baa3-4d0866368827 |  | textbox | Initials:
date | ab2174cb-307e-554b-8dd3-bd8d2f309e09 |  | date | Date:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
text | b03d9188-52b6-5388-85c8-ad8e8c819c95 |  | textbox | Initials:
date | 8e1e781a-fbb2-5944-a66a-74b5f7bad125 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rigidity and cover spacers fitted
text | 1fb4bb5b-5dd8-57a6-a51a-1ab15a56f1f7 |  | textbox | Initials:
date | f322d6d4-904e-5bff-a768-7da95882e6d6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean steel
text | d84572ce-df70-5d72-830f-60d77c2079d1 |  | textbox | Initials:
date | 3161b196-5e5a-53b7-a107-dcd405958b09 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | f529999e-adb1-55f9-be87-9674831f4ccc |  | textbox | Initials:
date | d8fbe4ab-3afb-5ac6-9db7-8257394f95ae |  | date | Date:
checkpoint-status |  |  | checkpoint | Foam liners fixed to Starter bars
text | 4305ad05-78d7-58d2-aa69-f6060c20bfce |  | textbox | Initials:
date | 34724a74-d1ff-50bb-a000-f42ce2d9368f |  | date | Date:
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | c58dffe1-91fb-5dfe-999f-3d32d1bff21b |  | textbox | Initials:
date | 71cc36b0-06db-576a-bbda-ea36123ded30 |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | 87245fb5-d8cc-5a06-8664-00fa3f4cac4a |  | textbox | Initials:
date | f74cd68d-3e33-5ca9-bde4-91df897bc861 |  | date | Date:
checklist-sectioned |  |  | checklist | CS-4012 - MSE Wall Geogrid Checklist |  |  |  |  | Yes | CS-4012 - MSE Wall Geogrid Checklist | cad5c834-006b-49b3-94ee-a48691c20d58
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 1195d586-dc74-50ec-95cc-31d039761edd |  | textbox | Work Area:
text | 5a9e5bb4-e90e-5b32-85f9-c9fa1e94e8cf |  | textbox | Sub Work Area:
text | 5d0c3ecf-a3ed-55a7-a908-91d2da34d0b5 |  | textbox | Lot:
text | f07f7bc9-4fe8-54d2-b761-aec52986a68c |  | textbox | Sublot:
date | 08ef3f1d-52fd-519a-b915-371bbbda5f50 |  | date | Document Date:
text | f6cbef0d-dc5c-52f7-8044-5546067fbcad |  | textbox | Created By:
text | 29731692-3809-55be-879b-7a807d5fd535 |  | textbox | Structure Name:
text | bcd0767f-0a3a-5d96-ae4f-2e00ef9061ba |  | textbox | Drawing No:
text | ac46c1cb-c24f-5ae7-ae07-ed301da219f9 |  | textbox | Grid Layer Number:
text | e7fbd54c-ec64-5171-8265-9d87884ecb42 |  | textbox | Structure Location:
text | 0f2d77a5-05e6-5f2e-8574-885ba035b6e8 |  | textbox | Drawing Rev No:
text | a59a6692-c3ae-5dc7-9c64-fee05b6835d0 |  | textbox | Grid RL:
checkpoint-group |  |  | section | Conformance Criteria
checkpoint-status |  |  | checkpoint | Check installation of each course
label | f1987c8c-3826-508f-a598-4b3b9045abb3 |  | note | No gaps between adjacent units, max. vertical height prior to backfill is 2 units, min. pin connections per block is 2 upper and 2 lower.
text | 27e2439a-997e-52a5-8a12-bb938b54e4da |  | textbox | Initials:
date | ba7ba686-b370-553c-88c0-01c1439fb79c |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm front face alignment in each course is within the allowable tolerance
text | c21cf561-6d41-5c3b-9c99-17b408461463 |  | textbox | Initials:
date | 48753f23-956f-58ce-bda6-4955b71fc735 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect wall batter, wall batter to be within 2 degrees of design batter.
text | 6cb9fda4-fcb7-5a35-9fe0-45e6178c005e |  | textbox | Initials:
date | 8d003abc-cc79-5b3f-b6a8-e1cf9379efe3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm density results before placing Geogrid layer
text | ad7bd405-f2f3-5f2a-b86e-ba5be48b0d6f |  | textbox | Initials:
date | 67e77b02-5e27-5174-83a4-115d10230bd7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the type of Geogrid
text | b4849e20-b2b3-5f36-a25b-8559dc678e5a |  | textbox | Initials:
date | c66059af-e663-52fd-a28f-6e387d08387c |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the correct length of Geogrid
label | 8da9de4a-4a67-5742-ba70-c67288d38d0b |  | note | Inspect bodkin joints (where used) to join shorter pieces of Geogrid, 1 max. per length of Geogrid.
text | 8c0ff96c-cb32-5070-9345-563659e20a43 |  | textbox | Initials:
date | 4febca39-99e0-55a7-9074-bebf53cee8c0 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the correct elevation of Geogrid.
label | 3c3fb2b5-6f78-57e7-b36c-c95c173f650f |  | note | Place within 75mm of design elevation
text | 499662d5-c30a-5b0d-9e9f-6f69c3c71aba |  | textbox | Initials:
date | 71fbae10-f166-5cf7-b467-52ba0c030243 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure Geogrid is placed flat on top of the compacted layer
text | 0d6700c4-9e49-5fb6-98b5-f7d64571aeca |  | textbox | Initials:
date | 6c01f4c2-6868-5ead-af43-2033a1c52538 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure Geogrid is connected correctly to the block pin connectors.
label | a0e5db4e-36cb-550e-befd-3c5fdd237262 |  | note | Max horizontal distance between geogrids at wall face is 10mm
text | b5dc1acb-0553-5b01-908b-d86e8757f30f |  | textbox | Initials:
date | 8c41dde2-8e54-5509-8568-d7e095175e72 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure plant does not track over Geogrid
text | ec1d7c02-a694-574a-9b9f-384bb1790667 |  | textbox | Initials:
date | 7d559460-7844-5eb7-8fd4-c567aa92103c |  | date | Date:
checkpoint-status |  |  | checkpoint | Tension geogrid and peg to hold geogrid tight
text | 3209ddb7-cac5-5d77-90c3-12de4a4d5ead |  | textbox | Initials:
date | bf554995-3141-50d5-bded-8e588fef96c6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Place backfill across the geogrid, plant can track onto geogrid when 150mm min backfill has been placed
text | 1d316e68-0320-53ca-8f74-ac25b1576bf2 |  | textbox | Initials:
date | 71cd74af-04d2-50ff-973a-9b6055ccdb6f |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor plant and equipment keep 1m from front face of wall.
text | 54b7b6fb-df59-51e4-bc97-a5b07ca21c67 |  | textbox | Initials:
date | ce953209-b5d0-553e-ab4a-58fbeb1d5b9c |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspection?
text | 852dfec1-525f-552c-8abb-062990479ff2 |  | textbox | Initials:
date | 173fb9e5-1e19-5aa7-80fc-762187923104 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 59c482a7-0c3d-506c-995e-f9f24611d1c8 |  | note | Position: Site Engineer
text | 5fb43b88-9a52-565c-ad10-f3bd439b5706 |  | textbox | Site Engineer - Name:
date | 40cdb972-13d4-5820-b9b8-bb28d6f17742 |  | date | Site Engineer - Date:
label | dea3eedd-4b7c-5fec-abc0-6c10be82549e |  | note | Position: Design Engineer
text | 7c7fe613-9bb6-51d2-b2c5-851c2306ada7 |  | textbox | Site Engineer - Name:
date | da9037a6-cf4a-54c9-afd3-4c61314c7bd8 |  | date | Site Engineer - Date:
label | 499aa3b8-aeef-59ed-bcdd-7b0ffe6d8636 |  | note | (Note: Attach a sketch showing grid on a separate sheet as necessary)
holdpoint |  |  | signoff | Sign
checklist-flat |  |  | checklist | CS-4095 - Spunlite - Pile Foundation Checksheet |  |  |  |  | Yes | CS-4095 - Spunlite - Pile Foundation Checksheet | cd182cad-3f92-4615-94ff-4d700e580c6d
checkpoint-no-status |  |  | checkpoint | Details
text | 746b7afd-4b94-509d-8aea-66b0812242ce |  | textbox | Project Area:
text | 9e03c454-99eb-57e6-8466-e5f67c8af5e1 |  | textbox | Supervisor:
text | 7fd9f115-fc39-5f97-abfa-7ab1315f69ab |  | textbox | Site Engineer:
text | 0df1a632-eaac-50eb-a5d6-e462345907ca |  | textbox | Pile Number:
text | 69bd5f67-a817-59cc-86fb-c6e1ce2baaf0 |  | textbox | Location Reference:
text | 539065a6-00a4-57b9-b777-78ed6fcad5be |  | textbox | Service Investigation:
checkpoint-status |  |  | checkpoint | PRE-PILING SUMMARY
text | fead7324-bdc9-59c5-9c1a-6606f28e0d79 |  | textbox | Piling Foreman/Supervisor:
date | a6182f42-ed94-5990-a6aa-32aa6815d9c8 |  | date | Hydro-excavation Date:
text | a0c086bf-a196-56a6-a61f-9bfb21742e13 |  | textbox | Casing Length:
text | c67c453c-e03d-5c55-9323-a0c6641b5029 |  | textbox | Cage Length
text | f903b59b-d199-5d75-93dc-99602452578a |  | textbox | Design Pile Depth (min):
text | 3acbe2a7-29bf-5eff-aea8-c9bfa533b23e |  | textbox | Design Pile Diameter (min):
text | 0bb99db9-db7b-5b4c-ae8a-7abba6b8eb53 |  | textbox | Casing Diameter:
text | 553bdc9b-1d3d-5f11-9724-11ca32ab92f3 |  | textbox | Cage Diameter:
radio | 102d80d8-7db2-5f4c-a6e1-d86f4c0530a5 |  | radio | Pole Type / Socket Type: | Standard – RS168 x 750DF,Catenary – RSe273 x 900,Short – RS115
checkpoint-status |  |  | checkpoint | DRILLING AND PRE-POUR CHECKS
text | 7ede1fe7-e688-5946-9c90-d5d5a159bc87 |  | textbox | Services check (depths and offsets):
date | f1ca1187-8f79-5e85-8c6c-c7d22574f4d3 |  | date | Casing Install Date:
text | 1639156f-9b14-5870-97e8-30b6d5af24e1 |  | textbox | Piled depth:
radio | 0296dddb-848e-5ab7-8fba-c70772c6b2f4 |  | radio | Plug Type: | Soil,Concrete,Not required
radio | c20bbe11-fc45-530b-abde-15d763dff80c |  | radio | Top of casing to FL check: | 90mm (Catenary),110mm (Standard)
label | ae3be759-2bbc-544b-9922-ce03575c8159 |  | note | Pre-pour checks
boolean | d22adaa0-7cdf-5cde-ada7-1b4289f5789d |  | tickbox | Speed form
boolean | 0e3d94af-26f5-5187-b2e8-4558eb3b8cc7 |  | tickbox | Cage placed (75mm cover to reo)
boolean | b2486b83-03b7-568d-aaef-6107c42082df |  | tickbox | Socket set in place (check pole centre)
boolean | 096b6eeb-61fc-5a36-b076-3e6e3babde2f |  | tickbox | Socket plumb check (pre-camber check for catenary poles)
boolean | 1e1e015d-1f60-5a81-9e46-a61751c76b09 |  | tickbox | D16 starters installed
text | 262b0444-adb6-5515-bc7e-9f0fc5229ebf |  | textbox | Concrete Mix Type:
text | bd467069-d9a3-5358-8901-bc1f4396cffd |  | textbox | Docket number
date | 45e05e3f-7ccf-5a11-8c03-9c2e80d9eece |  | date | Tremie Pour Date:
checklist-flat |  |  | checklist | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip | itp |  |  |  | Yes | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip TEST | ce42f9af-1533-459c-b379-d391fbc3cacd
checkpoint-status |  |  | checkpoint | 1 - Design
label | 9527ea5d-4ad6-5f6e-a2dd-3b4a7cf2375c |  | note | ACTION (Hold, Monitor, Witness) - H
label | c184153a-d9c2-56e6-a0bf-7376efa6c9eb |  | note | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | a4fc8357-baee-57c1-8e82-7871f4833ccf |  | note | Frequency - Prior to commencement
label | c4ac5ec4-8846-5c24-a802-aa512432c6e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 43bd6591-6e7a-5a7a-8319-7fa884c44fa3 |  | note | Records - Check Drawing Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 53017645-38cb-5d02-87f2-de98e7aa55d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 77950b3b-d513-5355-bc76-fa23313335c8 |  | note | Detail - Setout locations of wicks in accordance with design
label | bdc6b090-27a2-5312-9541-c3c0d6ab2950 |  | note | Frequency - Prior to commencement
label | 2abec7fc-2b22-5b5b-9b2d-de4cba2cace2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 486ad5e6-5617-5f84-b738-8a47d0981753 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | c13ebf17-e464-50f7-bf36-eb0918d0c45d |  | note | ACTION (Hold, Monitor, Witness) - H
label | e433c9ea-6bca-5943-8628-a39c8636b569 |  | note | Detail - Prefabricated wick drains shall consist of a 100mm wide drainage core
label | be039405-b8d5-5885-8464-7d466fc15d56 |  | note | Frequency - Each roll
label | 8770c848-4a06-52ee-881a-3ad68f9384ea |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Certification
label | 16bbcb3d-3792-5c91-9832-de9b8527d27c |  | note | Conformance Criteria - Vertical Wick Drains Specification
label | 06e8bd55-3fca-545d-b6d9-2349e4b18d06 |  | note | Records - Manufacturer Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | ff58c52f-acc7-5df8-83bd-1745fefc5f36 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 861259e7-6291-53c6-9c6b-d5ef2461689a |  | note | Detail - Ensure all wick drains are free from defects, rips, hole and flaws
label | 545e08f3-b785-59d3-904e-dd7fa02dc655 |  | note | Frequency - Each roll
label | 5dc2a9f4-5f94-5ea4-976a-7928aa461325 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Checksheet
label | 5140a341-34a2-576f-a8c1-ccbeca761193 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Wick Drain Installation
label | 6e1d5e57-8a6b-5c91-aef5-6cb4fc3fdc68 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 657b00fd-a624-5f24-a4ce-c9875cda286d |  | note | Detail - Wick drains shall be installed vertically, within a tolerance of not more than 20mm per 1000m.
label | fa7c1ffe-aad3-5ee0-a69d-3b34fef78afe |  | note | Frequency - Daily
label | abf87b5e-9e99-5f2c-abf8-7350a2f38942 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection / measurement
label | dcf186ab-7eaf-5162-872a-4b4fd77c233c |  | note | Conformance Criteria - Contractor to check for plumb as per Vertical Wick Drains Specification
label | ff1952c8-79b2-53e8-9ebc-1875a5b818e8 |  | note | Records - Sub-Contractor Records
checkpoint-status |  |  | checkpoint | 6 -
label | 93cecb21-311c-5d90-8b41-6936813d178e |  | note | Detail - Depth achieved. Min of 500mm wick protruding from the ground
label | 22e2844c-5208-5e03-b99e-3e7d687128c0 |  | note | Frequency - Each Wick
label | 8521b32c-2cc0-541b-ad21-fa1ab302fd7f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f86b2630-5f6b-5fdb-b51f-89d4a0d9cc5d |  | note | Records - Sub-Contractor Records
checkpoint-status |  |  | checkpoint | 7 -
label | 5657c4a7-66dd-5f55-acd1-5b6033dcef71 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6ce37909-80bc-50c6-8552-be2cbf3ec7d4 |  | note | Detail - Splices or connections shall be done in a professional manner that ensures continuity of the drain without diminishing the flow characteristics of the wick material
label | 98218840-4da8-5b39-a8ac-9c84e859485a |  | note | Frequency - Each joint
label | a9c75682-c601-5826-b056-bd5ec25a744c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a2af3e6b-c3ca-5a40-a7db-aab2213efda1 |  | note | Conformance Criteria - Vertical Wick Drains Specification
label | 87a31c7c-8d90-5055-a118-1506cf3abf10 |  | note | Records - Sub-Contractor Records
checkpoint-status |  |  | checkpoint | 8 -
label | e9698526-64a2-547c-aa87-ac98a68d5efa |  | note | ACTION (Hold, Monitor, Witness) - H
label | ac50ad11-fc32-56d0-9c47-108f2fd2247f |  | note | Detail - Design Engineer Inspection prior to backfilling
label | c0b4e08d-9a14-5667-9e1d-356bf3e99966 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Survey Asbuilt
label | d83a3285-8265-51c4-8716-b7f099e5e725 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18df1158-48ae-5f57-aebf-685a7bd69813 |  | note | Detail - Extents of wick drain area to be As Built surveyed
label | b3bc1be0-c5a2-5785-857a-4cdc541c8a35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 46d9e973-3a6d-5d46-b184-0908910a141b |  | note | Records - Survey Receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Lot Number QA File
label | 9b3ace38-9dfc-509b-886e-8c78f68f88f7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4d7882e5-6fe0-583c-83b7-b1967c5451bc |  | note | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | d60ed3e6-e026-5276-87b3-b80d27ca18da |  | note | Frequency - At completion of Lot
label | 5b8d88c7-d87c-58a2-93bb-6195df0b17b0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6b426933-7e77-5ab7-9994-27a71b0175f8 |  | note | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | d432231e-d981-5f2b-b9d1-73228d8c8189 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 11 - As-builts
label | fec78173-e144-5492-93f9-60ea63be52f4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 78a1236c-e08f-56a3-9fd9-a855ed89e830 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 247646c9-dcb0-5aed-8e13-8abdab9d3b1a |  | note | Frequency - At the completion of the Lot of work
label | 35f599ea-31e8-5ca6-81b5-09ca5a767653 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 324b69cd-4147-5497-9a92-9c86eb8ca8c9 |  | note | Records - Asbuilt Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4052 - Landscaping Planting Checksheet |  |  |  |  | Yes | CS-4052 - Landscaping Planting Checksheet | cf9f940b-1d98-4587-91b9-f685ada0ffef
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 5d3b6c64-7aa1-5753-8ba0-066dce3bf1d6 |  | textbox | Work Area:
text | 4585a45a-904e-5b40-9bb0-ddd2ed60b642 |  | textbox | Sub Work Area:
text | 92f02194-704c-515d-b42f-859c7e8c92fb |  | textbox | Lot:
text | 0154f83d-a973-566a-8de2-a340d5d1b6ad |  | textbox | Sub-lot:
date | c76e9b58-5c42-52ca-b6d3-3919db89b83a |  | date | Document Date:
text | 9523e0a0-3e38-538b-b744-9888f3cdda8f |  | textbox | Created By:
text | 96eaf698-b7c0-5e07-84fe-30cd1b7e21f0 |  | textbox | Drawing Number/s & Revision:
label | 8daa6c03-b5ab-56e4-8038-4feebba679dd |  | note | Raingarden (RG), Garden Bed (GB), ), Tree pit (TP), number:
text | c0194094-a377-519d-a164-8008df72ed55 |  | textbox | RG #:
text | bbc8f254-bd06-5da5-b54d-39cdf1b4fa9b |  | textbox | GB #:
text | 077e2356-7658-54d8-bccd-7842885f695b |  | textbox | TP #:
checkpoint-group |  |  | section | Spec./Site Preparation for Seeding or Planting
checkpoint-status |  |  | checkpoint | 8321/8332/Any other site works that will cause rework to landscaping & planting has been completed.
text | a70587e9-4743-5ae9-913c-c3c99036cc41 |  | textbox | Initials:
date | ebc59b18-19d8-5be3-b0bc-7857d8573c45 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8321/Check for service in the area of this work. Avoid interference or damage to them
text | 9d410fd5-b2bd-54ad-b9ab-23ddf56d5671 |  | textbox | Initials:
date | d477f772-e3c9-514a-8551-4be4797bf665 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8321/ HOLD POINT. Garden bed to be approved by Landscape Architect prior to installation of soil media. Strata Vault installation to align with manufacturers recommendations. Photographs to be provided.
text | 1b682279-3f91-5c05-948c-f42470a27fd0 |  | textbox | Initials:
date | 7691ffc1-3864-5405-abf4-ddaf9090b3d7 |  | date | Date:
label | bbda3e7b-00a9-5ed6-a21b-133e3a8c1794 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT. Raingarden drainage layers to be approved by Landscape Architect. Photographs to be provided.
text | 5def7448-6a08-5f50-8caa-1dea7e9cf95f |  | textbox | Initials:
date | 05672ea6-5dbd-513a-8444-e3e6548053cb |  | date | Date:
label | ff6112a7-bfd9-54e1-ab3c-e3b6622742bd |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Raingardens - hydraulic conductivity to be tested to prove this is in line with raingarden material specification.
text | 83ac54b1-7c9f-5418-a31e-1c8ddb1c6663 |  | textbox | Initials:
date | ffefd189-b2e2-589d-9c1f-a16e23f10e5c |  | date | Date:
checkpoint-status |  |  | checkpoint | Soil to be adequately compacted in 200-300mm layers to ensure no pockets of air within garden bed / tree pit.
text | 6ab1ce43-6872-5330-ac16-af78429ba24a |  | textbox | Initials:
date | 03f6e643-91e2-5bf7-bc37-3965600325a1 |  | date | Date:
checkpoint-status |  |  | checkpoint | HOLD POINT. Garden bed profile to be approved by Landscape Architect and Stormwater Engineer post soil media install. Photographs to be provided.
text | 9cee2fac-c22b-5a3b-85f2-d47a52207eba |  | textbox | Initials:
date | 1cef82e0-459f-545e-b1a3-2d38cce240e6 |  | date | Date:
label | 1dedfb95-c8c0-5dc7-8b17-4b5757af0ce8 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Should the soil in the garden bed become compromised (by ongoing site works or any other concern) – pH to be tested to prove this is still in line with the soil product specification.
text | 37552d2a-6c0c-541f-b8a6-e1c434f167b1 |  | textbox | Initials:
date | cea409b3-57a8-5af9-9844-07a75472bf08 |  | date | Date:
checkpoint-group |  |  | section | Spec./Planting
checkpoint-status |  |  | checkpoint | Ensure no standing water at base of tree pits – report to Engineer.
text | 775fbd63-ac78-54dd-87f6-174842bc5bb3 |  | textbox | Initials:
date | da63897d-ff18-5b4d-9a15-29a7af4acac3 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Plant material origin checked on delivery for plant material quality and accepted. All plants to be inspected and approved by Landscaping Architect prior to installation.
text | f93331ab-ff05-5950-a909-bdc0fdfe730e |  | textbox | Initials:
date | 5940adf5-e95d-5c09-958e-563fc6aa98b1 |  | date | Date:
label | c8b4141e-0a85-5eb0-95cf-48d7b5cabb53 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | All trees to be inspected and approved by Landscape Architect prior to delivery on site. 6 monthly photographs to be provided.
text | e8b1ea9c-2081-5eae-94b4-3ec77e171978 |  | textbox | Initials:
date | d1ee6294-171e-5dcf-ac4f-1206f6cbb908 |  | date | Date:
label | 85f6cada-29ef-5cd9-81bf-3a559e5ad32a |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | 8332/Plant material suitability. Roots eased where root bound. Plants not removed from container too far in advance (avoid drying out).Root balls are moist (not dry).
text | 4e7e2cbe-7783-5c98-8947-141719a94ffe |  | textbox | Initials:
date | 4566c9b6-cc8b-5221-b199-84e70b647a20 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Spacing and set out in accordance with Landscaping plans and consistent & correct to specification and schedule. Tree species according to drawings. Approved by Landscaping Architect. Specific placement and orientation of trees to be confirmed with Landscape Architect on site – including any required pruning.
text | 44b8080c-39a1-5841-b85d-a98c3236e8ee |  | textbox | Initials:
date | f3d31eaf-3390-57ab-8013-65915c2a832b |  | date | Date:
label | a3b6a811-4ddd-5f81-9a59-3805e582e804 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8332/Fertiliser/ Crystal Rain Gel incorporated to manufacturers specification
text | c5a45beb-5121-5828-91d0-86217f8bc50f |  | textbox | Initials:
date | 8b165713-9d2e-52aa-9fcc-dd7b93a2f669 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/All plants shall be thoroughly watered a few hours prior to planting and again immediately after planting.
text | e8d6daa6-70fc-56d3-b911-f66d0e3ac695 |  | textbox | Initials:
date | 9d93b73a-51a9-5e2f-9b65-0d5164c12a08 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Mulch clear of plant stem, Soil not left on top or mixed with bark mulch.
text | 514d88d8-8520-5e6a-bf18-2c7ba78d442c |  | textbox | Initials:
date | 9d572bea-2ca1-5834-a998-1e3e4488a39a |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Stakes where required to specification, level and with ties fixed securely.
text | 807e07dd-11ef-51b0-90f5-75e980f3d9c7 |  | textbox | Initials:
date | 8f9b6f58-41ab-5b63-a520-e1d99fd484ee |  | date | Date:
checkpoint-group |  |  | section | Spec./Turf Laying
checkpoint-status |  |  | checkpoint | 8333/Landscape Architect to inspect area prior to turf laying. If not available on site then photos to be provided.
text | 2326a9df-32db-57bf-ba3e-de60266730cd |  | textbox | Initials:
date | 5a75aa2e-531d-5849-9e57-3c23c8a3f24d |  | date | Date:
label | bf474a86-cc5b-5163-a794-328648419e45 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | Lawn areas to be finished 25mm higher than adjacent hard paving to allow for settlement.
text | 8968d042-23f3-577d-9c86-708c1b2742a1 |  | textbox | Initials:
date | 154a0af5-ca76-5c56-90d6-524ce38e0fad |  | date | Date:
checkpoint-status |  |  | checkpoint | 8333/Landscape Architect to inspect area after completion of turf establishment. If not available on site then photos to be provided.
text | a3f5c445-a79f-5356-b382-070ae57cd778 |  | textbox | Initials:
date | b145ea43-a210-58ae-922c-518d84faa3f5 |  | date | Date:
label | 98e20ebe-e88e-5a2f-952d-ace90c8e7883 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | 8333/Remove weeds, root material, stones, rubble and any other debris exposed during cultivation.
text | 8be0a41d-3d8e-5e08-9374-2aa100def40d |  | textbox | Initials:
date | e4a91559-d21d-5933-9f18-cc6f1a5b8600 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8333/ Apply a dressing of fertiliser and work into the top 50mm of soil immediately prior to sowing.
text | fb6c5e6d-bcad-53e5-a9fe-6e96d51e54db |  | textbox | Initials:
date | d0afd24a-1f82-51d3-bfa7-10454226e11b |  | date | Date:
checkpoint-status |  |  | checkpoint | Additional areas to be planted/areas missed (mark-up drawings where additional planting may be required)
text | e2e3372e-b2c6-5289-8daf-5d67f424db27 |  | textbox | Initials:
date | eb527558-7461-5e87-b906-d431f7a82239 |  | date | Date:
checkpoint-group |  |  | section | Spec./Daily Clean Up
checkpoint-status |  |  | checkpoint | 8332/Surplus plants removed to storage area per specification.
text | a191d8f9-cbc9-5749-9d10-186c4cc71e2f |  | textbox | Initials:
date | 21cc83d7-8853-5293-919d-3177b4c11234 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/8333 Site cleared of rubbish and surplus materials (containers) removed
text | e0b8c457-f841-53e4-9c58-a818909f69a5 |  | textbox | Initials:
date | 89234719-cb7d-5768-8d16-d5e8b3bc4127 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Weather
radio | a7d858c3-8724-5db6-be2e-485982f36bd6 |  | radio | (select relevant condition) | Sunny (check plants not left bare root in sun),Raining (ensure soil is not saturated which prevents proper planting),Frost (No planting to be carried out until frost thaws out),Overcast (Good Planting condition)
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 7da54ba4-b0a3-51ce-bf90-39644a2150a5 |  | textbox | Site Engineer - Name:
date | c9e429d9-3f67-581e-bf26-74eea68c236a |  | date | Site Engineer - Date:
text | 3e3515ff-d08c-503d-8975-ed2aaee90cc9 |  | textbox | Landscape Architect - Name:
date | 005046e6-4b65-5a51-851e-ab4a646fde84 |  | date | Landscape Architect - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | CS-4074B - Low Pressure Air Test Record for Concrete Pipes |  |  |  |  | Yes | CS-4074B - Low Pressure Air Test Record for Concrete Pipes | d0b0bbb8-acac-4497-b30d-288379b839f1
checkpoint-no-status |  |  | checkpoint | Details
text | 2bc24c62-3743-51b1-98bc-7301f65f2261 |  | textbox | Work Area(s):
text | 139705d8-9405-5c18-888b-6d27f0cf7999 |  | textbox | Sub Work Area(s):
text | 35fa834d-63ce-5950-9878-7bc628a63cfe |  | textbox | Lot(s):
text | 5c9830cf-fa86-5b77-b6f5-986795d941fe |  | textbox | Sublot(s):
text | 7a1771c3-ff3c-56f5-a183-b8f4c9f48039 |  | textbox | Document Date:
text | 16ae0449-b2ed-51e4-8bee-3411abf0de80 |  | textbox | Updated By:
text | ec396bc1-545b-5ba0-80aa-da97e730e1d9 |  | textbox | Area:
radio | d57c094a-4c3f-5c2e-a3e2-bfbde47b42c4 |  | radio | Weather: | Fine,Overcast,Showers,Rain
text | fdd03647-931a-5cee-bcf1-70d553b48db7 |  | textbox | Location:
date | bb2cb1e4-5fe6-58f6-bfea-84c8aae00859 |  | date | Date:
label | c4124be0-9daf-5285-b81f-c38049aef862 |  | note | Personnel Conducting:
text | 7a9dd5bf-6bd0-5ae1-b95e-b5a93d9e152b |  | textbox | Drain Layer:
label | f53a33f7-a3ce-5a02-8267-1fd1314556d6 |  | note | Witnesses Requiring Notice of Test:
text | 7ea0dc27-83db-5f82-bb98-d5ed9ddd36b5 |  | textbox | QLDC Rep:
text | 48e71688-0207-53d5-9aee-446449232385 |  | textbox | CPS Engineer:
text | cdd549eb-f40e-5544-9ac6-5c49a1d7a9d5 |  | textbox | Site Engineer:
checkpoint-no-status |  |  | checkpoint | Pipeline
text | bbf69f6b-f867-5dce-a4fc-5d90524e3791 |  | textbox | Pipeline:
text | 12d48aca-f412-5ba2-8d4e-4859e6c7ed9e |  | textbox | US MH Number:
text | 0be386ec-6017-532a-88fb-c18a978a6ab5 |  | textbox | DS MH Number:
text | d14b3ef3-48aa-56f9-9ab1-c484f506b21a |  | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
radio | b1fab6a2-6225-5c30-b148-e7458ada7fb5 |  | radio | Plugs Braced? | Yes,No
checkpoint-no-status |  |  | checkpoint | Pipeline Material (concrete):
text | daf9c8ce-db7d-5073-abb7-0940624d9c47 |  | textbox | Pipeline DN (mm):
text | 699cd874-895d-5596-af08-25690e78e6a2 |  | textbox | Pipeline Length (m):
text | 821b496e-54fd-5cab-880b-3fbb7b6731f0 |  | textbox | Test Time as per Table B1:
checkpoint-no-status |  |  | checkpoint | Prelim Checks:
radio | 5e07332f-16d7-5290-9c71-3a4006faf1b6 |  | radio | Stabilisation period (at 10 kPa) for minimum of 15 minutes. Soap solution used to check plugs/fittings. | Y,N
radio | d54d253d-ba7b-5026-a27d-8260d55d43e6 |  | radio | Line water soaked for 24 hours | Y,N
radio | 2e878e58-6147-53c2-9b5d-2271cb280b02 |  | radio | No Leaks Detected? | Y,N
checkpoint-no-status |  |  | checkpoint | Start Pressure
text | 2e215554-c013-5790-9463-a8f216a8cbca |  | textbox | kPa:
text | fa94420c-7db9-508f-8ed7-1762ba8e48d8 |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | End Pressure
text | ed325181-660c-5635-a2f4-f4b63cab2d65 |  | textbox | kPa:
text | 3c56c482-0209-5e01-8d5f-f9dd787cc22b |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | Pressure Drop:
text | 61eb01dd-b980-5ae3-b654-de061423cadb |  | textbox | kPa:
text | 16d6c893-f45b-53e8-98eb-57be62bcbb9a |  | textbox | Duration of Test: |  |  | Mins
checkpoint-status |  |  | checkpoint | Test Result
label | f4d8b110-b79c-598c-9a65-49dd5ae0a133 |  | note | Acceptance where the gauged pressure has dropped less than 2 kPa for the time interval shown in table B1 after the shut-off of the air supply.
label | f698cf87-9b55-5dd9-9382-177afcb96882 |  | note | ○ The test length shall be acceptable where the gauged pressure exceeds 8 kPa (or not more than 2 kPa less than the pressure at the start of the test) for the time interval shown in table B1 after the shut-off of the air supply.
label | 55629989-73fc-52fa-86c3-4b9afb419da4 |  | note | ○ Table B1 is based on an average air test pressure of 9 kPa. Start pressure is 10 kPA.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
text | 231897f2-96cf-5f9f-8bb0-e314b8a9affd |  | textbox | Name:
label | 2733b816-5df0-5bb7-8ab0-cb3925cbdee9 |  | note | Position: Site Engineer
date | b3615c86-3413-57a5-b74a-63bf32940deb |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | CS-4065 - Blast Record |  |  |  |  | Yes | CS-4065 - Blast Record | d73ba3f7-8cfe-4e4f-9315-ee0a21dea5ee
checkpoint-no-status |  |  | checkpoint | Blast Record
text | 2fd94cac-c1e1-55b6-a0c6-9be86f82aff0 |  | textbox | Project No.
date | fcd671de-b5c0-5a80-9ce9-7891e9ace8ae |  | date | Date:
text | caa2129b-6a83-5bbe-92f3-f8af237abd09 |  | textbox | Blast No:
text | 6f9b983f-6aff-5139-b942-e808860067cc |  | textbox | Location:
text | 314b1c96-4699-54bb-8b90-8b4cfd54ff45 |  | textbox | Shot Firer:
checkpoint-status |  |  | checkpoint | Design Powder Factor
text | fadde783-a7ae-56a5-b881-e6d653034ae5 |  | textbox | Initials:
date | 98acb61a-e1d8-5623-8b3d-cbd63339411b |  | date | Date:
checkpoint-status |  |  | checkpoint | Diam. Hole
text | 0c810e43-298e-5be1-8312-63948a4ea78e |  | textbox | Initials:
date | e8aa6cde-b08b-5ea4-8630-9b7cb3fc9b46 |  | date | Date:
text | da15f9c7-c8db-55fa-b0d6-e32f32e97add |  | textbox | Comments: Diam. Hole |  |  | mm
checkpoint-status |  |  | checkpoint | Shot plan attached
text | 1164f838-7bbe-501e-a438-46e21a2c738c |  | textbox | Initials:
date | fb302fae-e191-51ed-8fa1-55029b72fb99 |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor 1 vibration & overpressure report attached
text | 8ef980b4-45b1-51f6-af0c-024b6fffa668 |  | textbox | Initials:
date | dc449734-ea25-5601-9273-eeb485fccdd5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor 2 vibration & overpressure report attached
text | e4c06e19-68a0-5342-bac0-fdfc9cdff03b |  | textbox | Initials:
date | 78efd06f-ba3b-5543-92a7-4e11c64b8f0d |  | date | Date:
checkpoint-status |  |  | checkpoint | Vibration & overpressure beneath consented limits (PPV 10mm/sec (5mm/sec 95% of time) 128 dB) if not OFI
text | 9b7d3873-5ee8-5f8a-bf5c-3d13ceee3a6d |  | textbox | Initials:
date | e3d5367f-bd98-5a41-8b17-6ce6d2d62431 |  | date | Date:
checkpoint-status |  |  | checkpoint | Shot Firer’s Blast Evaluation attached
text | 3bdc7dc8-f8a2-5193-8a65-b1da24c3de94 |  | textbox | Initials:
date | 00c4f750-db3d-520b-85c6-d3256d5842a7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Coordinate (GPS) plan attached on (Contract Name) grid reference
text | ed9c4f31-ded8-5c12-9f41-a9b23a5b9068 |  | textbox | Initials:
date | ea3c668f-b45b-544f-8323-9b0031e53758 |  | date | Date:
checkpoint-status |  |  | checkpoint | Actual powder factor
text | 481a10d1-310c-545b-bfa0-c7264e1f3cac |  | textbox | Initials:
date | 6f46cd5e-6ecd-5cb5-b262-a7bd8c466fb6 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | d7a0d59a-747b-55eb-88ce-5ee0001d94b6 |  | note | Position: Site Engineer/Supervisor
text | 83a9e66d-ec3b-587d-9dbd-fa3ce45ebb7a |  | textbox | Site Engineer/Supervisor - Name:
date | a7537afe-1a36-5709-aea2-1eafe48c8ed3 |  | date | Site Engineer/Supervisor - Date:
label | 89e89ff6-9cd4-5c2b-b311-98ef70a0f5b5 |  | note | Position: Shot Firer
text | d305344b-7aab-581c-b41f-cc296b8c245d |  | textbox | Shot Firer - Name:
date | b73844e7-c7c2-5ca9-b112-99030616147c |  | date | Shot Firer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4015 - Shop Drawings Checksheet |  |  |  |  | Yes | CS-4015 - Shop Drawings Checksheet | d8d03cb5-b8c1-47da-b07a-83671e380bc2
checkpoint-group |  |  | section | Shop Drawing Check Form
checkpoint-no-status |  |  | checkpoint | Shop Drawing Check Form
text | 253a7918-7d82-5249-a007-f45d635f432e |  | textbox | I |  |  | (name)
text | 584ffa1d-bf99-5523-956b-fbfd7fe1cab8 |  | textbox | of |  |  | (firm’s name)
label | ccc475fe-d7f5-5914-9225-47b85ecdf8e8 |  | note | being the Construction Team’s designated person responsible for the preparation of the shop drawings required by specification C0600.7, certify that the drawings listed below have been prepared, reviewed, co- ordinated and checked prior to submission to the Design Team in accordance with the requirements of C0600.7.
checkpoint-status |  |  | checkpoint | 1.0 - Shop Drawings prepared to an acceptable presentation standard
checkpoint-status |  |  | checkpoint | 2.0 - Shop Drawing revisions noted and clouded
checkpoint-status |  |  | checkpoint | 3.0 - Dimensions:
label | acc832cb-ceb9-528e-a10c-b4c977d04d51 |  | note | Relevant dimensions indicated
label | f393e5c1-ca67-5656-b8fa-3445cc7b7a29 |  | note | Site measurement noted and checked
label | 0dcc1b2e-034c-5af7-94ad-8c7233b2820b |  | note | Dimensions co-ordinated and checked with the requirements of the Contract documents and other trades
checkpoint-status |  |  | checkpoint | 4.0 - Drawing numbers and revisions from which Shop Drawings have been prepared noted on the Shop Drawing
checkpoint-status |  |  | checkpoint | 5.0 - All relevant contract information including specification requirements indicated on Shop Drawings
checkpoint-status |  |  | checkpoint | 6.0 - Shop Drawings checked and co-ordinated with the requirements of all Drawings and Specifications (e.g. Architectural, Civil, Structural, Building Services, etc)
checkpoint-status |  |  | checkpoint | 7.0 - Shop Drawing checked and co-ordinated with the requirements of other trades Shop Drawings
checkpoint-status |  |  | checkpoint | 8.0 - Drawings checked for corrections prior to re-submission, where required by Design Team to be re-submitted
checkpoint-status |  |  | checkpoint | 9.0 - Shop Drawings approved by the Construction Team for fabrication, signed and dated
checkpoint-status |  |  | checkpoint | Signoff
text | 3a839867-064a-5245-a452-ed2c1504dd20 |  | textbox | POSITION:
date | 5f4c25e3-d1b2-589b-941f-b0c588259e60 |  | date | DATE:
holdpoint |  |  | signoff | SIGNED
checkpoint-group |  |  | section | Drawing Numbers to which certification applies are listed on the following page
checkpoint-no-status |  |  | checkpoint | 1 - Drawing
text | 8fa05cef-bf33-5b8d-b24e-28b976c621d4 |  | textbox | DRAWING No.
text | f77ee527-1aaf-5fd8-8dfe-660460d90ff2 |  | textbox | REVISION No.
text | d34f9457-63d7-5223-91b1-f5ad0c86d28b |  | textbox | TITLE:
date | aa81a07a-4382-59e5-9cb4-4806cb71e4f5 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 2 - Drawing
text | fc092a87-ac42-5b65-a43f-4586196f33c0 |  | textbox | DRAWING No.
text | 40a3b08a-19ad-57e5-b4e1-0bc96ff87898 |  | textbox | REVISION No.
text | 8f1dd44e-f9e3-57a7-b1f1-fac486641046 |  | textbox | TITLE:
date | 18cda69b-edb3-5298-8239-9c152267134c |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 3 - Drawing
text | 977269eb-f884-587f-9eb5-d4c57ac4cf5d |  | textbox | DRAWING No.
text | 701905b9-444e-54d8-9719-950ede7d0ae3 |  | textbox | REVISION No.
text | cfbce92c-7bf3-511e-aa38-93ddf49a6ff1 |  | textbox | TITLE:
date | ee9cb0d3-aff8-5dd4-8179-81ff6337c1c8 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 4 - Drawing
text | 35819759-9bf2-5c64-bd81-8810f9acd143 |  | textbox | DRAWING No.
text | d914e6a0-ec5a-5fe5-8d32-84022530476c |  | textbox | REVISION No.
text | 5b37bc5f-5b7d-5eb1-90d5-93bbdc122578 |  | textbox | TITLE:
date | 3fe6a7a5-40dd-564c-984f-2c60c386a9a3 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 5 - Drawing
text | 421a90c1-9ebf-53ac-ab09-ea05bbbde447 |  | textbox | DRAWING No.
text | fcdd60ed-34ac-5d6c-a894-60714e3fedd4 |  | textbox | REVISION No.
text | 7a71cbb4-5b75-5dc5-8d3f-4955dcf0d7b4 |  | textbox | TITLE:
date | e54b6c1d-5cb6-5c64-b113-0380a4d621a1 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 6 - Drawing
text | ccc6ec0a-2a42-5005-b2d5-025bb1a16215 |  | textbox | DRAWING No.
text | 683737ec-b441-55ba-8ce9-bee012f4073b |  | textbox | REVISION No.
text | 885f3420-657f-59e7-ab19-3aab40c93ef5 |  | textbox | TITLE:
date | 95b335aa-6b38-5abd-8c85-23be5e3bf748 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 7 - Drawing
text | 60580d4f-44d9-58d2-a5d9-72331a78bbc3 |  | textbox | DRAWING No.
text | af7fc6d1-dc62-5942-9a95-16707df921a3 |  | textbox | REVISION No.
text | 83aab29c-f456-5c56-a33d-9ec3c39be87d |  | textbox | TITLE:
date | 0cc86ad7-919d-57b6-a142-cb5502c495b0 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 8 - Drawing
text | 7ac2ed21-f540-58d1-bc56-30113149e783 |  | textbox | DRAWING No.
text | f7526aa4-7396-5ca7-9906-452deeb1ccd6 |  | textbox | REVISION No.
text | d70106f5-7f99-5990-8265-4fd7ddbce95b |  | textbox | TITLE:
date | 59b10cc4-e2e3-59c5-8a44-537e595fef7e |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 9 - Drawing
text | 6044475a-d9b3-50a9-8200-323b95d8db05 |  | textbox | DRAWING No.
text | 231177c7-487f-564a-821b-f688ef505b2c |  | textbox | REVISION No.
text | cfa139f9-f04c-5761-8512-a8a8a5ba5d63 |  | textbox | TITLE:
date | 9cb26ee1-6af4-5215-a09b-4c20944a704a |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 10 - Drawing
text | 430f3d53-c84b-571d-8b1d-8731ec8598d8 |  | textbox | DRAWING No.
text | 9fe6dc7c-313a-55b2-8302-ffa08560cfd4 |  | textbox | REVISION No.
text | 1581b3a1-4e63-5208-9295-b755e6644c8a |  | textbox | TITLE:
date | bb4d58cd-c636-5214-b97f-dc408f333d8c |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 11 - Drawing
text | 5528a500-45be-52b3-8094-bfa69c8b1c36 |  | textbox | DRAWING No.
text | 5dbcba74-fa5b-5cbf-8dcb-51cb460b6f00 |  | textbox | REVISION No.
text | 34e37db9-0ee1-592d-8bb7-78a1f6019e91 |  | textbox | TITLE:
date | d47250fe-8153-5a51-a721-1d1132460017 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 12 - Drawing
text | f29c2ab0-4327-586b-b390-06e0e88a4ede |  | textbox | DRAWING No.
text | 61ec56b5-89a4-5a2e-9b06-123aabadbe48 |  | textbox | REVISION No.
text | b7722e32-a78e-53f9-ab0b-8fc955d6f2a9 |  | textbox | TITLE:
date | 9da21b2e-39e3-5cce-86a9-a4dd6242b773 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 13 - Drawing
text | a0efa52e-eaec-502a-907a-3a52965189db |  | textbox | DRAWING No.
text | 21d64917-3af0-5a00-9cb8-ea6d18ae3763 |  | textbox | REVISION No.
text | 4fd9236d-4cc5-514c-b6e2-e008ec02e208 |  | textbox | TITLE:
date | 0ad899ff-d115-5ca6-89f1-df877d57f92d |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 14 - Drawing
text | 260a941f-832f-5626-81ac-0bd004a4b874 |  | textbox | DRAWING No.
text | 424edb0b-5d68-5bb2-984c-603cf055c1c5 |  | textbox | REVISION No.
text | d578d9f3-2a5e-56a8-ae86-1f561e20000c |  | textbox | TITLE:
date | e87651e9-663a-5006-92f5-1117d6a8a9e2 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 15 - Drawing
text | 0e33114c-d9c8-5a24-a388-744fd804a678 |  | textbox | DRAWING No.
text | a1f55ec7-3f0a-51a1-88aa-97420f8343a9 |  | textbox | REVISION No.
text | fb18a90d-7453-5a39-8e7d-7847434e9b93 |  | textbox | TITLE:
date | f1f456cb-2fa2-5a78-a9c9-adfa333d53c2 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 16 - Drawing
text | bb27a9e4-c27a-5ea9-9bc4-58a763f07762 |  | textbox | DRAWING No.
text | 74a13cf6-e1db-5cab-9401-b253d127ac1a |  | textbox | REVISION No.
text | fc6d26de-a4cd-56d1-ba1f-fe194e19277d |  | textbox | TITLE:
date | 6afe01a0-b29c-5ede-8fcb-c327ce2ab4d4 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 17 - Drawing
text | 5ecba2f9-cc65-5464-bff2-18b3aed0c05f |  | textbox | DRAWING No.
text | ee32e4ac-d318-5361-be6f-93818061ab77 |  | textbox | REVISION No.
text | d1a46329-9fe7-5717-9626-20506fe454e7 |  | textbox | TITLE:
date | 116ce161-4528-5ce8-b2d3-d23dd861aada |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 18 - Drawing
text | f43599bc-9581-5057-97f4-834439beeb70 |  | textbox | DRAWING No.
text | bef8c980-db34-5c58-b378-9de086563d02 |  | textbox | REVISION No.
text | c669955f-0e13-5559-834d-d8f2931c04d0 |  | textbox | TITLE:
date | 571dedf4-cbb7-5adb-bee8-504385740dc5 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 19 - Drawing
text | 37dac657-a1d4-5e18-ac22-573ed9be601b |  | textbox | DRAWING No.
text | ffa16e67-8dd0-5b45-a547-5d39fcb334df |  | textbox | REVISION No.
text | 9b6cbb22-c468-5abe-acfc-bd118346200b |  | textbox | TITLE:
date | 46fc2dac-d1c7-5d94-8e1c-0d40e99fbffd |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 20 - Drawing
text | 089650aa-d6c1-5619-b967-999ab626a714 |  | textbox | DRAWING No.
text | 26ca9b8a-5b62-5254-8db0-f5f0212b6452 |  | textbox | REVISION No.
text | 001433c0-7051-5556-a1c7-6c2933138f6a |  | textbox | TITLE:
date | df740cc2-be6a-5056-af56-cd71a12a94e3 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 21 - Drawing
text | 4b09548d-dfd2-5d8c-9b51-5a91c4c9ba49 |  | textbox | DRAWING No.
text | 3143d83f-991d-565f-9833-3653a0dbabc4 |  | textbox | REVISION No.
text | a9f04b75-c88f-5659-9696-49bde141b403 |  | textbox | TITLE:
date | 4eb21972-6e17-5287-8275-f57388ded638 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 22 - Drawing
text | d2845909-503a-57c9-9aca-5bf3c04c00c9 |  | textbox | DRAWING No.
text | 98044886-16f5-5fdc-89b1-7bd5989b35eb |  | textbox | REVISION No.
text | 1d96ffb6-e821-5c37-baf5-50c3412f9b70 |  | textbox | TITLE:
date | b8731bb9-8a39-5946-9450-ba408e4da58e |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 23 - Drawing
text | b4c70c0a-c0f5-5608-b3d5-ea365b76431e |  | textbox | DRAWING No.
text | fe6022f6-f98a-548d-a49c-a3b4327a3b12 |  | textbox | REVISION No.
text | 8a345893-41ff-593a-aada-f952f5ad500f |  | textbox | TITLE:
date | e5ef7641-e460-5d16-9799-59073b82ef39 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 24 - Drawing
text | df86cc99-e0ba-5f9f-a589-da4efb578b37 |  | textbox | DRAWING No.
text | 8d90ccec-c9ee-5e3f-ae85-d175fa6166c4 |  | textbox | REVISION No.
text | e63c36ae-7a68-5369-8708-bb284b00bfc6 |  | textbox | TITLE:
date | 111fd689-cdda-5677-bb24-fea7e434b7c6 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 25 - Drawing
text | 0ed3cba2-095b-5f7e-a8f5-7e45a3f8a35d |  | textbox | DRAWING No.
text | 49e8d6be-1ea2-5a60-a297-3619986dafd3 |  | textbox | REVISION No.
text | 62e54f83-b7e3-5891-8a0f-b048638f37e2 |  | textbox | TITLE:
date | 511d0f3a-ca1f-5fc1-ba4c-f783d6a2f574 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 26 - Drawing
text | 4b932adc-aafd-5234-be79-a7b4edd64e9b |  | textbox | DRAWING No.
text | 47fbcf5a-db48-5a43-a51b-cdb2f59b5ccc |  | textbox | REVISION No.
text | 2c5bf03f-e51b-52fa-9de5-0d30cebc1264 |  | textbox | TITLE:
date | 2c0ddfa0-f696-5fbe-b2e6-195c3e5d0f45 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 27 - Drawing
text | 71ce01c1-af7b-5f30-80e8-73ad09ad3565 |  | textbox | DRAWING No.
text | e78ea8d7-8c14-59f6-9386-d89a65b71268 |  | textbox | REVISION No.
text | 4d02dcd6-10ef-53e0-89a9-ba62c7bb15a3 |  | textbox | TITLE:
date | a125fa53-ebfa-506f-bbad-491cb3220f7f |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | Note: A completed copy of this form shall accompany all shop drawing submissions to the Design Team.
checklist-flat |  |  | checklist | CS-4120 - Wire Rope Installation Record |  |  |  |  | Yes | CS-4120 - Wire Rope Installation Record | d9f962f2-250e-4b05-a2d2-308c021ba550
checkpoint-no-status |  |  | checkpoint | Details
text | df05608a-8933-5e61-a8e4-8d4a3b7e9d3e |  | textbox | Work Area:
text | da8409a9-e424-5b5e-b9aa-56dbf3c8ef32 |  | textbox | Sub Work Area:
text | 7dfc399b-b9cc-54ba-ae70-847b7b27ff3e |  | textbox | Lot:
text | 86678851-2bf1-57a0-9d0f-4e5e50c147e2 |  | textbox | Sublot:
label | e2676622-ea2f-53cf-ba5f-01a79ab5ae68 |  | note | Document Date: 27/11/2019
label | 3461a34d-98c5-525f-8818-1928a55ea917 |  | note | Created By: Kirsty George
text | 11a27d8a-9444-548a-969d-1b30b5f2ec7f |  | textbox | Drawing No:
text | 975fb18f-a3e5-529c-89b0-9fd623d2a43b |  | textbox | Rev No:
text | de7783f0-e2a7-5081-a0b6-a150761e0e9a |  | textbox | Chainage:
checkpoint-status |  |  | checkpoint | Drilled holes spacing does not exceed 3M and are 300mm diameter and 750mm deep.
text | d8c01ee7-049b-5480-89c7-7987de652e8a |  | textbox | Initials:
date | 5f3fd89b-5688-540d-a5c9-ad4a82b08381 |  | date | Date:
label | 2e3c05b7-d05f-5c73-89fc-c1fac5cc4b99 |  | note | Comments: Consistency with Construction Drawing, Details and Notes.
checkpoint-status |  |  | checkpoint | Concrete is 25Mpa.
text | abfebc64-dc6f-5892-b630-ba838c28c2b6 |  | textbox | Initials:
date | efcb847f-a476-5e91-a521-0a08a1f8bc1b |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Dockets Collected
text | 2d91cbe3-47b8-5f99-86ce-2c5c5aa8cd08 |  | textbox | Initials:
date | 0a1fd5b3-40a0-5daa-98bf-ed0d1c45f02d |  | date | Date:
checkpoint-status |  |  | checkpoint | The plastic Socket is correctly positioned and a rebar ring is placed 100mm down from top.
text | 8c80a268-11ac-596d-a0ae-d2c016d35bc9 |  | textbox | Initials:
date | 6ac588e5-4bac-5622-88aa-1669bcb6be5e |  | date | Date:
checkpoint-status |  |  | checkpoint | Post are installed with slot orientation consistent for the entire length of the barrier.
text | 0f17e3ec-041e-56a1-af3b-eebfb4c69b0c |  | textbox | Initials:
date | bfbbe908-566c-57fc-a3bf-607de400a036 |  | date | Date:
checkpoint-status |  |  | checkpoint | Top 2 Cables are positioned in the Top slot while the bottom 2 cables sit at the bottom of the slots on either post
text | 2dbeff6b-1591-59ea-85f7-042bec242022 |  | textbox | Initials:
date | 9c2d3229-fbc1-51b3-ba77-e51998a6573f |  | date | Date:
label | 658bd789-9850-515c-af9a-272199dcdc7d |  | note | Comments: Cable Heights 530, 650, 770 and 790mm (+ or – 30mm)
checkpoint-status |  |  | checkpoint | Ensure no corrosion to the internal collars at swage connection
text | 21ee8856-f1db-518d-8d78-45236969494d |  | textbox | Initials:
date | 77c7c3aa-8447-5d9c-a766-cf4968287310 |  | date | Date:
label | 5e7f0b01-2174-507d-a6fa-4bca820c0ae1 |  | note | Comments: Also check swage seat & collar thread connection. Should be tight and should not be able to undo once in place.
checkpoint-status |  |  | checkpoint | All posts have a plastic cap inserted in the Top and pushed hard home.
text | 2a645dec-bf2d-5638-82aa-a3f2beb7f337 |  | textbox | Initials:
date | 52a5039b-b338-528f-a470-bdeff32c3d53 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | df755e8c-17a0-5f4e-b815-415a7cb545ba |  | note | Position: Site Engineer
text | a6aba232-b623-59fe-9727-c406ceed3ff7 |  | textbox | Site Engineer - Name:
date | 6713eabf-fdbf-5c2f-95eb-6340d31f5678 |  | date | Site Engineer - Date:
label | 2f883a07-63a7-5d62-b613-09f6c3214d33 |  | note | Position: Design Engineer
text | e4965e05-4063-57b3-86ba-67cbb03b66dc |  | textbox | Design Engineer - Name:
date | 7c61a6f3-0659-553f-bf1c-692dc9d522c2 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Bored Pile | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Bored Pile | dfd895ab-e858-4f4a-96ce-1a1e1215b4e4
checkpoint-status |  |  | checkpoint | Project Site reps.
text | c0f8c7c2-0f92-5ff4-a561-2fcf05075edb |  | textbox | CPS Eng.
text | cd831d9e-37d6-5ff8-8377-4d3f4c25ff1e |  | textbox | Site Engineer
text | a8b66195-d44a-5c8d-9f5e-8eb6430eb451 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | be193455-e28b-5cd3-96ef-ba0e185c9166 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 20d99eff-930e-5f29-871c-cc2bb7bef108 |  | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | 07f2bd98-80b9-580f-8b33-eb73d54c5891 |  | note | Frequency - Prior to commencement
label | 42b55cf5-da05-5b27-87bd-0c340943e35a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | b2320059-c7f1-5971-8fe3-f95f08299cee |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 24c570fa-d276-542d-b811-bce2547a2984 |  | note | Records - Design Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | 5c46e044-c976-53f2-bca4-5e205278667a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6507584b-e308-585c-a209-82d6436dabc5 |  | note | Detail - Any services in the area are to be clearly marked before any work commence.
label | 5446ad2c-272b-5ec6-9d23-5d3e3a1d58f0 |  | note | Frequency - Prior to commencement
label | 1a1a532b-3cbc-58b0-921d-884f3f16b930 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 283cc7ab-5733-52a6-bf5a-1d88e874f134 |  | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | 8f1d8d1c-c5aa-58a8-a86e-0a236ef016e1 |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 3 -
label | a546c0dd-120f-59bc-9bd8-e825e9f4460c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1f130842-1de6-54b6-91ef-b6208ddf0a17 |  | note | Detail - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer
label | ffe6b519-90d1-5960-804e-8338cb72b514 |  | note | Frequency - Prior to commencement
label | 5ca02a7e-721a-5319-b8c8-13407694ec98 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 5b4579d1-e92c-5f02-b019-97f671a963de |  | note | Conformance Criteria - If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer.
label | 268d0caa-a838-58de-8688-c62c7446bd6d |  | note | Records - Design Engineer Approval (RFI), ConQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | c511fbaa-acf5-5e65-9746-51c3f9ebc28b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 63fa3c53-4122-5bff-b136-00f5a663f594 |  | note | Detail - Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres
label | 61858a11-3a64-5a81-b9c1-ddd6448536af |  | note | Frequency - Prior to commencement
label | 8a189b64-db83-553d-a83b-c4e05b908422 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 5801b3d2-78b5-560c-ba7c-b248e6fb8762 |  | note | Conformance Criteria - MAX 1.10m centres
label | 530d6d38-35bf-5851-8a3e-d17b52fd4f32 |  | note | ○ set at 4 degrees from vertical
label | 25215b6e-be33-51ad-bd3f-18568cc2724f |  | note | ○ 100mm of clearance on all sides of pile
label | 057ba9fd-e0fb-524c-b192-814575d041aa |  | note | ○ 100mm minimum cover of concrete at base.
label | 5c21b524-ffb8-5b31-950a-2e8368d46d51 |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 5 -
label | ea73bac1-8b72-5d57-b59a-0965ff9108f8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 767cdcfe-7508-52ff-8075-dfe55d4a2d83 |  | note | Detail - Minimum Pole embedment to be as outlined in specifications
label | 0e62367e-bd40-5045-87ee-e975a504d5ac |  | note | Frequency - Prior to commencement
label | bca3e34b-f082-596a-89f5-37576a9d9882 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 2109dbbe-bc16-5cfb-b4e3-ade00a168755 |  | note | Conformance Criteria - Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013
label | c4084f5a-9ecb-549b-a83e-e5ad28518864 |  | note | Records - Photos, log, site inspection, ConQA
checkpoint-status |  |  | checkpoint | 6 - Pile Material Compliance - Timber Poles
label | 41cbd10e-15c3-5e33-8ae8-69d1c7274b42 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e1716da8-5749-596f-a36e-9e16f0f1b947 |  | note | Detail - The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified.
label | 86d19c38-b21b-5791-a76d-f2dc676ba3ba |  | note | Frequency - Prior to commencement
label | 87eff655-c3ae-54ba-a5b2-f621f40aad89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 732bce53-d396-532c-a090-d92053947447 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance
label | aaf073f2-3d9a-5960-ab0e-54a766c4afe9 |  | note | Records - Document/ConQA
checkpoint-status |  |  | checkpoint | 7 -
label | 63e0df30-78cc-535c-a64d-8160e52d3abc |  | note | ACTION (Hold, Monitor, Witness) - M
label | e9b6c533-81fb-5ef9-89e8-0c1a6cef8d27 |  | note | Detail - The poles must be H5 treated in accordance with NZS 3640, H5.
label | ebb6f15c-31ec-54c9-b2aa-e54a54afc929 |  | note | Frequency - Prior to commencement
label | 4a2b578f-e0bd-5be4-b713-4dc826cdc85e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | f391808d-f3e7-5d61-8128-c8024e438007 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5.
label | ac54c80f-f01b-5f1f-b879-1f40d327b53d |  | note | Records - Document/ ConQA
checkpoint-status |  |  | checkpoint | 8 -
label | 9df0690b-b75a-5db3-9b73-94fb7a8e5c8c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 77e6bde5-96e1-5b72-bd85-ac76ef5c4c05 |  | note | Detail - Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil.
label | ce999cd9-cac4-57f2-b905-b0281997da75 |  | note | Frequency - Prior to commencement
label | f6f947c8-37a2-5b83-a2a6-3498ba9f30fb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5ad89d19-c448-54d2-9c2f-9b207ad4f105 |  | note | Conformance Criteria - Engineer to inspect as accordance with specifications
label | 6fb43252-2d3b-576a-8005-148bfd9b6e21 |  | note | Records - Photos, log
checkpoint-status |  |  | checkpoint | 9 - Pile Material Compliance - Concrete
label | 7b32a45b-05a4-512b-a9af-998803986d6b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 200da0c0-5684-52cd-8424-54860224acff |  | note | Detail - Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete.
label | 17ea213c-2184-52e8-82c3-576ebceb51ca |  | note | Frequency - Prior to commencement
label | d66fdf8e-3f1a-50e9-9599-b2da5e567896 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | b001da80-a4bc-5982-8155-4e18d0822202 |  | note | Conformance Criteria - Engineer to approve design prior to commencement
label | c69d2744-d2e8-522e-a2e2-430c1b144cd9 |  | note | Records - Design Engineer Approval
checkpoint-status |  |  | checkpoint | 10 -
label | 08860cd6-81d1-5696-b3f3-7af7bd59e6da |  | note | ACTION (Hold, Monitor, Witness) - M
label | f6568834-3ffe-5a16-a2d0-c2c751aeafe1 |  | note | Detail - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | 4a8a2990-c4f6-5754-aa56-d9f86d3a0c20 |  | note | Frequency - Prior to pouring concrete
label | 6bfc8592-42ca-5818-94cb-37998a299329 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | 34bb0b2a-c3b5-5dcb-b8d9-fcda944dceef |  | note | Conformance Criteria - Site engineer to inspect delivery dockets
label | 74dd2563-6e78-50ef-bb8f-50330b98d534 |  | note | Records - Concrete Delivery Dockets
checkpoint-status |  |  | checkpoint | 11 -
label | b88c95d6-e00c-5d2f-84a8-9b51e0d4144f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 31f1af45-5eca-5792-b004-8efcbc7c9136 |  | note | Detail - The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days.
label | 7a9e74b6-043b-5f78-acab-1ee25ba5e5a3 |  | note | Frequency - Each batch
label | 81cfb03b-c060-5dba-a200-8540e0b5d117 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 2dbfe536-5d33-5b17-8439-93f5224ab976 |  | note | Conformance Criteria - 28 day strength of 20MPa
label | 93fa166b-f24e-5dec-a4f2-6c1fe352026d |  | note | Records - Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 12 - Pile Line
label | 23ff5523-b1e2-52b3-b006-1efdca492241 |  | note | ACTION (Hold, Monitor, Witness) - M
label | eeb9fb3d-1961-5256-9c82-d68a7772b7f4 |  | note | Detail - Check if the bench the has been excavated/filled can accommodate the entire pile line
label | 00087894-e7ea-5d19-bb5c-e97b844d2d10 |  | note | Frequency - Prior to Commencement
label | 6117e6d8-518e-50e9-a912-df519b588398 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6b7c1303-1f54-53dd-ab9b-feb105157d82 |  | note | Conformance Criteria - Site engineer to inspect against relevant drawings
label | 7c8e93e9-506e-5717-86a4-66720e8bec18 |  | note | Records - CS-4011
checkpoint-status |  |  | checkpoint | 13 -
label | 82865199-8e1f-502b-b258-4ab485a03643 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7c19f46b-fd2b-5a23-8e24-1037576ed295 |  | note | Detail - Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes
label | 1f81406e-0a71-5d78-b413-c6cce0c616bb |  | note | Frequency - Each Pile
label | c7095c7e-0872-595a-adef-348a88fd793f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d5a7dfe5-47f4-596e-a871-2e3a61f77dd6 |  | note | Conformance Criteria - CPS engineer to inspect
label | 6ed8e71a-0d8d-50ba-a337-032821608a91 |  | note | Records - Photos, log
checkpoint-status |  |  | checkpoint | 14 - Drill Rig Set Up
label | 458cc103-0f33-5a7b-825a-ac2b9b12aa86 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 89880d59-bae6-54c4-a414-569c0c65cd8e |  | note | Detail - Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions.
label | 309d183f-9e9f-5349-befc-9955d0f5fbc3 |  | note | Frequency - Each Pile
label | 808c6b97-9711-5440-9733-28b34b122cbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e05770aa-42b5-509a-aa25-1f1eea175b58 |  | note | Conformance Criteria - Site supervisor to inspect
label | 18f4ad27-33e2-5bca-be44-ab4d22de82a4 |  | note | Records - CS-4011 & CS-4083
checkpoint-status |  |  | checkpoint | 15 -
label | 100bed62-e56b-5a59-86eb-3717fd8f4618 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2b63a9c-75fa-5a89-ab82-46b730c93a66 |  | note | Detail - Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings,
label | d8e6653c-7c2a-5cbe-8853-977e35949f31 |  | note | Frequency - Each Pile
label | bc77a84c-67ed-54c8-85e1-c2a11b1e654e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8d35eddd-d811-5e8e-9ad2-c55febcdd093 |  | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | aa923a38-0c76-5059-a041-9b144295041b |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 16 - Pile Bore Condition & Logs
label | ae67d3b3-ae21-573f-9e63-140528aab307 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8021aa59-91d7-5995-a4bd-aec79a10a213 |  | note | Detail - Inspect pile bore condition, pile depth, rock socket length and toe level
label | adaca05a-17e2-5b17-a0e5-bdfa3b2e6c32 |  | note | Frequency - Each Pile
label | 30f4febe-7691-5ed3-b7ca-7c6250ec0033 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | aeb31c5c-c146-5669-84a8-4ea763b71d51 |  | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | a0f637be-9ee6-5814-a40d-9cf78a1c8460 |  | note | Records - CS-4011 & CS-4083
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 -
label | e2ddfda9-25c7-5f28-a7f2-39735c11ea49 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 362584b8-7dd7-5990-ba35-60b14ea0a031 |  | note | Detail - The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level.
label | a08b49e6-4e0e-53a1-938f-9c0911e6138e |  | note | Frequency - Each Pile
label | b1a2a91e-11d0-5452-bb39-3785ef4a2f1e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspection
label | 0ef29b59-6f56-584e-b9e1-a480bdd47101 |  | note | Conformance Criteria - Information shall be provided to the Engineer at the end of each day's work.
label | ef598990-adcd-5ff9-bff0-83cc0a75a7b0 |  | note | Records - Document
checkpoint-status |  |  | checkpoint | 18 -
label | 580092b6-0633-5235-aead-7cd94f4c637f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 23ca0757-3432-56b2-a25c-441887259475 |  | note | Detail - The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting
label | f97a8dc3-0a74-50f0-b670-13bd5773c57d |  | note | Frequency - Each Pile
label | f0168f8b-cf99-5bee-b1d9-1bd90dc9c82d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | f7e31311-1c55-51e5-9985-36655bfaa698 |  | note | Conformance Criteria - Areas of overbreak are to be reinstated in an approved manner
label | aa66ec7b-0360-5e47-904e-12890e3bfb40 |  | note | Records - Monitor, inspect
checkpoint-status |  |  | checkpoint | 19 -
label | bc145fe6-ca34-5bd8-b080-a9e4b8d310d1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f50ace83-29cb-5634-9419-80491fc41284 |  | note | Detail - The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site.
label | 3d3d91e0-741f-5cd3-ae7a-b5c9f7dbe307 |  | note | Frequency - Each Pile
label | 762f4d8a-0335-5b34-9ac1-fa57a4db7f3b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0973d4fe-90b8-5d56-9a43-44542f3b7e33 |  | note | Conformance Criteria - All drilling must be in line with the EMP and other environmental protection documents
label | 299118da-fc49-5d99-9a83-4a42dd56493b |  | note | Records - Monitor, review document with Environmental team
checkpoint-status |  |  | checkpoint | 20 -
label | d7264ecf-b6ed-527b-aca6-05a3d36e7ed3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 46070096-7058-58d7-8583-79a4742ea727 |  | note | Detail - Check that holes are not to be left open overnight.
label | bf63a037-3488-51fa-8425-808fd4020f4b |  | note | Frequency - Close of works each day
label | 12acfe02-3b37-5910-afd2-e73c73f1043f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | 66903b44-8ad0-5209-afce-0cfc5e87069c |  | note | Conformance Criteria - Site supervisor to check at close of works each day
label | 57edfcd7-90d7-51c8-abde-0c931bf802c6 |  | note | Records - Visual check
checkpoint-status |  |  | checkpoint | 21 - Pile Bore tolerances
label | 6707aec3-f4b7-5c62-8e69-621098d0c89c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8fa464c2-e4be-571c-8a0c-a79b4a4ef78f |  | note | Detail - The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional
label | 94d6083a-cce9-51c6-8828-c170fdb42eac |  | note | Frequency - Completion of stage or bore drilling
label | 60d6fa38-1a9a-5198-b69b-6d026f5284fd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 0cc1f5c4-606d-5e14-a98c-80d1b53d4d96 |  | note | Conformance Criteria - Contractor to notify engineer, Geotechnical Engineer to attend and approve excavation
label | 77de0e13-1253-59a8-accb-e712cd5b51f8 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 22 -
label | 2020aaa2-3f74-5818-b9c9-2ae37391e865 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 61339f11-5d5e-575a-b8b8-130e2cc4d7b7 |  | note | Detail - The hole must be excavated to the tolerances outlined in the specifications
label | 473ec2c1-3429-5f9c-8aa2-893f1072ddd5 |  | note | Frequency - Each Pile
label | 70d0203d-f399-5d8a-9ece-f2304d595197 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 0292e4dc-0e7a-54cf-946f-2dd0e25efaf3 |  | note | Conformance Criteria - Pole hole diameter +50mm / -0mm
label | 8aadc27a-b3af-51a9-9693-204ff88d8018 |  | note | ○ Hole plan position at all depths +/- 20mm
label | 636d6b9b-0f76-5c8f-aa35-92ec44b13c52 |  | note | ○ The pole shall not vary any more than 2 degrees from 20 degrees
label | f9eed877-3790-5aba-b7ff-ac3aefc66fe4 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 23 - Timber Pile tolerances
label | 9409dc89-ef39-5302-a668-6060c7eb1bc9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 24075fe3-f938-5a00-a0b1-b55d3499e874 |  | note | Detail - Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications
label | 9123d3d8-bc3f-591b-b9e3-2285be540e18 |  | note | Frequency - Each Pile
label | ce48f5d4-9580-523b-ab4a-15014e838a80 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 69f4194e-5308-53fb-9dbd-5af30673efd4 |  | note | Conformance Criteria - Deviation of pole centre from line in plan +/- 10mm
label | 4f2093bd-8e35-54d7-a481-a5d375478530 |  | note | ○ Pole top reduced level +/- 10mm
label | 98bbd0d3-5a34-5e64-9ac0-b028dd5a98cd |  | note | ○ Pole base reduced level +/-50mm
label | 1e1cdab8-8851-53fc-a835-ea555f14fe06 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Concrete Pumping Operations
label | 65c0f45f-feb5-5e72-aa09-99a4bbac44db |  | note | ACTION (Hold, Monitor, Witness) - M
label | d3f4776f-4c7e-5082-8494-ecff2456a336 |  | note | Detail - Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences
label | 5519172b-2ab4-5744-8e86-441f24167fe5 |  | note | Frequency - Prior to commencement
label | 4227f32b-55a5-5f04-bfb8-d42958973a46 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | fdb44cc3-f2fe-5650-b067-1f92368e2f68 |  | note | Conformance Criteria - Site Engineer to compete CP and PO checksheets
label | 7789f216-cda0-5e0d-b0ee-9c5015b6c6de |  | note | Records - CS-4029 & CS-4002
checkpoint-status |  |  | checkpoint | 25 - Concreting
label | b2c1139b-48bd-5988-9ac3-763e9b37fa90 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 946451ba-7f1f-53c4-8e9b-8c6b2e336554 |  | note | Detail - Concrete pre pour inspection
label | 8888825a-a5a8-5bbd-95a0-c9681ce22a0f |  | note | Frequency - Prior to concrete pour
label | 9fb2fa5b-9f25-54db-abe0-b2281663adf8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d7c05663-0391-57d0-9aa0-60d406d66257 |  | note | Conformance Criteria - A pre pour inspection checksheet to be completed outlining:
label | 94fc241b-08cb-512c-bf0f-91d5fdb52c2d |  | note | – Pre pour inspection checksheet to be completed
label | 5ec7cb45-fa0c-5740-a694-9fa30874c9c2 |  | note | Records - CS-4011/ TBD
checkpoint-status |  |  | checkpoint | 26 -
label | 41d8b3fa-9ef3-51ce-8b02-fc12bf9f1504 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8abd268c-3f8b-578c-965b-ffacb4e95edd |  | note | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed.
label | 44eeefa4-f4f9-5213-b2aa-eb27c01f08e4 |  | note | Frequency - Prior to concrete pour
label | 6958a507-f390-5d44-b15c-b6078ee76b85 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | 3cef2173-e38d-5dcb-ac48-6a0d3f5e7016 |  | note | Conformance Criteria - NZS 3104 Concrete dockets match design
label | a0528c79-1abf-5d65-b2df-5bf91146f656 |  | note | Records - CS-4090
checkpoint-status |  |  | checkpoint | 27 -
label | 603356dd-f642-5f72-8cf5-92688bfeb308 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7269f070-aa20-50af-a1a7-4b069df3f098 |  | note | Detail - The concrete in each hole shall be completed as one continuous operation
label | b7112cad-2c64-516b-add7-145917a046fe |  | note | Frequency - Each Pile
label | b9fd7a6d-f650-5325-b754-71969cdd2a42 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 79ddcb59-11de-52c3-a263-69e5c00190e1 |  | note | Conformance Criteria - Concrete Inspection Record
label | f647d7c8-6d33-5abe-8e57-5d8fea6916b7 |  | note | Records - Photos, log, site inspection, Document
checkpoint-status |  |  | checkpoint | 28 -
label | 9ea10b46-f5bc-54ee-ae8c-a92e70875f89 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a4a01dcb-c215-53aa-be4b-884a10ca0b66 |  | note | Detail - Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required
label | fe77ace9-752c-547d-af5e-a0c561cb1818 |  | note | Frequency - Each Pile
label | 3b66de67-0ebf-5295-8278-59e944e1b8e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 2fa6e6e5-17b6-544d-a02f-74ace7928cee |  | note | Conformance Criteria - Concrete Inspection Record
label | ca2c3e62-a5e1-58a3-95f2-c1516a9a8024 |  | note | Records - Photos, log, site inspection, Document
checkpoint-status |  |  | checkpoint | 29 -
label | c380e777-1ef7-50c5-b894-eb98cccc5021 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 119c3d92-3d7e-54d4-bdf5-cba839709db6 |  | note | Detail - Check concrete placement method and finish
label | f3e8666b-6ba5-5ba5-bd7f-5e79ae30f902 |  | note | Frequency - At completion of pour
label | bbb5f6b9-0ec8-5c7c-b411-973532253a54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | 99922070-ba2b-5920-934a-795c18b84d29 |  | note | Conformance Criteria - Concrete Inspection Record
label | e8760f80-6b1e-5308-a4d3-f541deb39482 |  | note | Records - CS-4011
checkpoint-status |  |  | checkpoint | 30 - Survey As Built
label | fce2bc97-1068-56e0-bf9d-d6888841d75f |  | note | ACTION (Hold, Monitor, Witness) - M
label | d4947f35-a84d-5361-a62a-de30edc3e5e4 |  | note | Detail - Survey final position and R.L. of each pile, produce As-Built drawings
label | 2081d59c-9e89-58af-ae44-36aca89e2318 |  | note | Frequency - Each Pile
label | 8ccc5d34-eb9e-59cf-8eee-b9ef94268fc6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | 2a51e531-7779-5d1b-a926-28a86c2c578e |  | note | Conformance Criteria - As-Built Drawing
label | 26523812-96bc-5a2f-9bed-e9f2d6c6d697 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 31 - Lot Number QA File
label | 03b92a6e-5576-5638-bc14-fc0ec883132a |  | note | ACTION (Hold, Monitor, Witness) - M
label | a0a9fed7-a577-561a-a4ff-a28d811727ba |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 8a01c41f-06c2-5630-a963-f5a95d2b112a |  | note | Frequency - At completion of Lot
label | c999b3a7-7777-54e9-845b-c9522a33c62b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3f566e6f-5adf-542b-bee3-e3211c677995 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | fc523927-ac25-5585-9593-63e90e89f7f6 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 32 -
label | 59c4c592-b0a7-5223-a9dc-5416044cb72c |  | note | ACTION (Hold, Monitor, Witness) - M
label | bf2c2042-a7dd-5230-b058-0eb12ee0a2d9 |  | note | Detail - Check all piling records are completed and signed by the relevant signatory.
label | 4745cb1e-278d-5469-9ce2-5eb87197c471 |  | note | Frequency - At completion of Lot
label | 7117c316-9c1d-5852-8908-d0876a5ec150 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 11f3d9f0-a03c-51f4-b4a6-eaa75bbe2249 |  | note | Records - All relevant documents
checkpoint-status |  |  | checkpoint | 33 - As-builts
label | d8651c18-89ed-5754-9739-3c4e6474d829 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d0424fc1-eb99-5e28-bc90-a86eb219d30d |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 68219caf-3fb6-5eb8-a4d7-ec0ac338cae8 |  | note | Frequency - At the completion of the Lot of work
label | 9dc031ec-9953-542c-a768-15c2b749967a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 0f0a3b1c-7cd1-5bfc-b665-d84cdd3b4c08 |  | note | Records - Asbuilt Drawing
checklist-flat |  |  | checklist | CS-4000 - 1M Scala Worksheet |  |  |  |  | Yes | CS-4000 - 1M Scala Worksheet | e0ceddf4-dbc2-4a86-b227-bbe1fc7de040
checkpoint-no-status |  |  | checkpoint | 1M Scala Worksheet
text | 8c70d012-7b29-5ceb-8f2b-4966af8255d9 |  | textbox | CH & Offset:
text | f91c5aa5-a40b-56e1-81ad-3aff7730a18d |  | textbox | Date:
text | 4adee10b-90ff-5259-9f78-eace029e5e69 |  | textbox | Start Depth (mm):
checkpoint-status |  |  | checkpoint | Depth [mm] - 0-100
text | 003160ba-4f48-5109-af01-d668eb15cbbd |  | textbox | No. of Blows
text | cf7fafe6-1125-5d4b-b8bc-f72172206367 |  | textbox | mm / blow
text | d0cd8f70-4df2-537c-ac44-26775e67927d |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 100-200
text | 5d1f9fac-a126-5cca-bfa8-59cbb003213d |  | textbox | No. of Blows
text | f97a0b48-4ea9-5424-a466-82700040d4aa |  | textbox | mm / blow
text | 4208a88e-4230-5417-b2a2-b17c9ab66d14 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 200-300
text | 1a014fbe-86f9-55c9-867d-6ab7b0b5e4ca |  | textbox | No. of Blows
text | def71663-8d59-5114-995c-9d514137bd45 |  | textbox | mm / blow
text | affacdd3-29e5-5e29-8cd5-84314019cb78 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 300-400
text | a053d265-45de-5659-82a1-31df64c5f73b |  | textbox | No. of Blows
text | 5f826073-73da-53eb-96a4-6d7a89d59ad7 |  | textbox | mm / blow
text | d125ca15-8309-5d94-b4ba-38dcbe1f954a |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 400-500
text | 56d1f06c-f822-5c90-b3cb-a3a5d65ee6ed |  | textbox | No. of Blows
text | eee7bee8-09d1-546d-9720-c9bc9bedd5e1 |  | textbox | mm / blow
text | 0ea3bf8b-223c-5f80-b3e8-bbee9c63c96c |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 500-600
text | da2965fa-0d41-584a-8035-f5fc66b13489 |  | textbox | No. of Blows
text | 67748d25-edee-521c-a392-2b83647c1d92 |  | textbox | mm / blow
text | b1045f3b-75b6-54a9-9288-fcca1f7136f8 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 600-700
text | b9be3314-ccd3-54a7-955b-4c4e77649f16 |  | textbox | No. of Blows
text | 9bf6301a-fcf9-5f49-b6a8-aa4a465b6153 |  | textbox | mm / blow
text | ad1305e8-4b16-58ec-bb93-46dc4871e958 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 700-800
text | 731bb428-afe1-5a05-b2cb-c983fe9177f8 |  | textbox | No. of Blows
text | 0f5a7739-0107-51c5-8791-af3a4e694a9b |  | textbox | mm / blow
text | dbceaef5-0b38-5c0b-8419-3dfadfb992a5 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 800-900
text | 6c59e348-7cba-55dd-b154-3046f5892905 |  | textbox | No. of Blows
text | 7c4600c9-5d8c-5669-8e69-5f00f422e83c |  | textbox | mm / blow
text | 4e0012e7-26c9-52b6-9434-cb99bccff19d |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 900-1000
text | 1db9f546-0f97-523b-9281-abe6b52fc35a |  | textbox | No. of Blows
text | 73ddad95-ac6d-5f51-a6b6-34830cfe49cf |  | textbox | mm / blow
text | 592c6d4d-e556-5663-997b-1255f23989a4 |  | textbox | CBR
checkpoint-no-status |  |  | checkpoint | Tested by:
text | dd3c9977-abf5-5475-9544-965230612ea3 |  | textbox | Tested by:
checkpoint-no-status |  |  | checkpoint | Checked by:
text | 04e447b7-8ecd-51de-8967-b2d79e7deb1c |  | textbox | Checked by:
checklist-flat |  |  | checklist | CS-4073 - Drainage Structure Water Tightness Test Record |  |  |  |  | Yes | CS-4073 - Drainage Structure Water Tightness Test Record | e26c0ef5-1548-49ed-b05d-1d8e16386deb
checkpoint-no-status |  |  | checkpoint | Drainage Structures Water Tightness Test Record
text | 214d5c27-ff09-5165-9c20-966b6d406c73 |  | textbox | Project No.
text | f270f3c8-7b35-53db-8172-f3ffdb7f1a5b |  | textbox | Weather:
text | 874a3e39-db80-5ec1-9ac9-ffc7c69d9f4d |  | textbox | Location:
date | 6c9d4b55-f848-5bc6-98c7-1a657549c9d4 |  | date | Date:
text | 6bac14d2-0254-5d0e-8f75-a8faecb42990 |  | textbox | Personnel conducting test - Drain Layer:
text | 5de10c2e-476e-53d6-8bc8-1b1b38e42522 |  | textbox | Personnel conducting test - Design Team Rep:
text | 0f8879af-4252-53cf-8e5b-15423d79d58a |  | textbox | Personnel conducting test - Site Engineer:
checkpoint-status |  |  | checkpoint | Structure type & Chainage
text | 0e62d030-d370-5ad9-a409-e3a8e492ed9b |  | textbox | Size of structure (mm dia) |  |  | mm dia
label | 9a261ecd-51d3-5cba-b73a-26b1a32958d1 |  | note | or
text | bc2641c2-2d84-54f8-b59c-5dbb3bed44d4 |  | textbox | Size of structure (mm x mm)
text | 6f7367c7-c693-5e47-8bc0-81435895a906 |  | textbox | Depth |  |  | mm
select | b5571d11-3154-5d9d-a895-e4b5302509db |  | dropdown | Drainage plugs used | Rubber & Aluminium Plugs,Rubber Blow up plugs
button | 6e92e0f2-2c71-575e-ab9c-fc2e87db34d8 |  | button | Plugs Braced? | Yes,No
text | a85db535-0ee3-5896-8db2-b0d7b149fb6c |  | textbox | Structure filled with water |  |  | am/pm
text | 8a464f20-e06d-5d61-9650-0281e448c1e1 |  | textbox | Water absorption duration |  |  | hrs mins
text | 7b58342c-e823-5bf3-bc3c-4d97de288669 |  | textbox | Test start time: |  |  | am/pm
text | 1b48c149-5990-5a95-b8cf-25e55a3c13ac |  | textbox | Test finish time: |  |  | am/pm
text | 50418b01-75b7-540f-ba02-e50e216c7eda |  | textbox | Duration of test |  |  | mins
checkpoint-status |  |  | checkpoint | Acceptance level shall be no more than a 5mm drop of water level in 10 minutes
label | 860d7086-d250-558f-8329-5680c2005daa |  | note | Measure water level from top of structure
text | 2d79bb70-5b4b-53a5-9837-bed9a0eb2af4 |  | textbox | Start |  |  | mm
text | 44283825-3cd5-5d9f-bbfb-01027ed3786b |  | textbox | Finish |  |  | mm
text | e58bea29-9113-5acb-b090-0ab9d0d74b39 |  | textbox | Water level drop |  |  | mm
checkpoint-status |  |  | checkpoint | Test Result
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 9bd79914-a9fc-5e96-add0-fa33cc349e5c |  | textbox | Name:
text | dc5c574f-b33e-5833-a23e-917e1bfdb45e |  | textbox | Position:
text | 1a88a7b6-f675-59ae-b16e-111f0fd8d7f9 |  | textbox | Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4006 - Manhole Catchpit Record |  |  |  |  | Yes | CS-4006 - Manhole Catchpit Record | e2d3c0ed-258d-4d9e-8660-e578326ca17f
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 414be580-0fce-5138-8a30-e5e82e08276e |  | textbox | Drawing No:
text | 529e90c1-bc2d-534f-9c37-6247b87c4e4d |  | textbox | Rev No:
text | e04b148a-b814-559d-b70c-6f3993d8798b |  | textbox | Manhole/Catchpit:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | 1 - Setout
text | 244918f8-02da-5bd3-9824-a947a7dd58db |  | textbox | Initials:
date | a7d1ab42-08fb-547d-8708-933f1daa063d |  | date | Date:
checkpoint-status |  |  | checkpoint | 2 - Excavation
text | 40919602-85c7-505e-a9d9-3e325d47807b |  | textbox | Initials:
date | 142c17f3-1311-57d2-ac6a-130d049d5d46 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3 - Prepare & Level Base Bedding – Testing req?
text | 21ab549b-e0a6-521a-b68e-c645acb229bf |  | textbox | Initials:
date | 95e7fc00-e478-5366-ba56-3ef91ba523e2 |  | date | Date:
checkpoint-status |  |  | checkpoint | 4 - Confined Space Permit required?
text | c0e191ce-d484-59d4-9eec-4bf81d004149 |  | textbox | Initials:
date | 6b5d29fa-92c5-57b8-b74c-0242ca791520 |  | date | Date:
checkpoint-status |  |  | checkpoint | 5 - Installation of Precast Base Unit on Bedding
text | 933ddd24-efaa-5369-a543-e2f03fd1e3fb |  | textbox | Initials:
date | 01008f4d-099a-5124-8075-0b48e5647c91 |  | date | Date:
checkpoint-status |  |  | checkpoint | 6 - Installation of Precast Risers to Lid Level
text | 6c099bf1-b5d1-578d-b5d9-87040583d5fe |  | textbox | Initials:
date | 76dcb82d-3334-5975-a8f8-dbad60b02ed1 |  | date | Date:
checkpoint-status |  |  | checkpoint | 7 - Installation of Manhole/Catchpit Furniture, Steps / clamps
text | feebc52f-af35-53fa-8c8c-6bf50c6b6058 |  | textbox | Initials:
date | 3b56a44a-74ed-5663-9d39-78c16b7afccf |  | date | Date:
checkpoint-status |  |  | checkpoint | 8 - Haunching / Make Good Base. Joints sealed
text | e7c38bf8-e76a-51a6-80cf-c8f990d40071 |  | textbox | Initials:
date | 01785f5a-942f-57f2-b192-cc82fba8dadf |  | date | Date:
checkpoint-status |  |  | checkpoint | 9 - Installation of Precast Lid
text | 7493fbbe-de24-5ef8-a5ac-ce66a187beef |  | textbox | Initials:
date | afe0691b-032d-522a-9863-a7923a05a3de |  | date | Date:
checkpoint-status |  |  | checkpoint | 10 - Backfill Around Manhole/Catchpit – Tested
text | 942303ee-d382-5013-9b34-566a35b9141b |  | textbox | Initials:
date | 993f980c-3b87-59e8-85dc-1ea94e2fa786 |  | date | Date:
checkpoint-status |  |  | checkpoint | 11 - Installation of Cast Iron Frame A Cover Lid Level – set with contour
text | 736a1513-f370-59fb-b51d-dff97d1cb9d6 |  | textbox | Initials:
date | c5713a83-23c1-58cc-a07d-bdeeb7a8d812 |  | date | Date:
checkpoint-status |  |  | checkpoint | 12 - Final Inspection
text | f72aa8d8-f244-5930-a856-e829bc357a00 |  | textbox | Initials:
date | f8bd47f7-508a-58e1-a2c5-ca9681ee1eec |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 9cd44cd3-d8f9-5c06-84f9-ab9bf1ac4541 |  | textbox | Name:
text | 2d16cb33-0110-5f64-b86f-56c1414949cd |  | textbox | Position:
date | ff7999b2-e02d-5324-ab57-cd8bd756dc2c |  | date | Date:
holdpoint |  |  | signoff | Signed by
checkpoint-no-status |  |  | checkpoint | Location/Chainage
text | 7e585026-809c-5cf3-8dc2-02edc6db9a68 |  | textbox | Location/Chainage:
text | fe0db3c3-d986-5f17-8341-52cce4ea33f2 |  | textbox | Size:
text | a57a0258-2e18-5f3c-95ca-33048dad8a31 |  | textbox | Class:
text | 0f84955f-6504-5f46-9eed-b4dd8a416b05 |  | textbox | Concrete manhole lid opening diameter: |  |  | mm
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | e4173bd3-2a17-4f67-a764-abb84968d108
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b05bfea2-e0b7-5f61-8c49-5d042c7c60e3 |  | textbox | CPS Eng.
text | 2a96be31-b54e-5467-ab2a-acc26ff09fb8 |  | textbox | Site Engineer
text | 9523ca51-cedf-51f6-b92b-a3000d53ae21 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 4329d3f1-4b6a-5892-9547-9a0f90d2a381 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c21a4a29-a1b4-5e39-b963-a7b3c84f0af2 |  | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | d58a3b52-34a9-58d7-a9f4-ee2ede24f51c |  | note | Frequency - Prior to commencement
label | 94bdf949-1ed0-56cd-9cfb-75b2850f63f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 96aa777d-2a26-5a0b-806f-642e623a6159 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 347d4a71-ea6a-5ffb-be0a-6c783b67fce9 |  | note | Records - CPS Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Timber Lagging Material Compliance
label | 99f774ff-b79b-537e-a6f6-d519ac5d6b22 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3c299ef5-2e78-57c3-b5d9-2613ceac7dd2 |  | note | Detail - The lagging must be radiata pine planks of normal density, All.
label | 1b3fa55d-b042-5189-b930-719eef1b0f6a |  | note | Frequency - Prior to commencement
label | 2f99d6e6-8e19-5156-851d-d86a7b3e25e2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | f5ce0e92-067c-5d91-b5f9-99e8f30e5bd0 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance:
label | 8b0a0c81-56c8-56de-9b64-abebe3525eb0 |  | note | ○ H4 treated in accordance with NZS 3640, H4
label | 46770623-7dd9-55cb-ba55-0ecb428a2f6d |  | note | ○ Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative
label | 2e35b755-49ca-5060-9a13-eb9326c0c6a1 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 3 -
label | 0ddf14af-6f5a-5b5c-a939-ef4b99798bc7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 74a967be-0a93-54a3-86ed-9fd2fdb6bc1f |  | note | Detail - Each section of lagging shall span a minimum of three poles.
label | f66c9a7c-658b-503f-ac4d-dd64eaf6791c |  | note | Frequency - Prior to commencement
label | b9ccd96f-5734-5aa3-819b-004e58e205f7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 32b940f8-8ad0-53db-b891-43af5148d2e5 |  | note | Conformance Criteria - Inspect and document span of lagging
label | 9c06dd49-6bac-549d-870d-8f66691c8224 |  | note | Records - Photos, site inspection
checkpoint-status |  |  | checkpoint | 4 - Backfill Material Compliance
label | 23053c83-4c80-5e82-9862-a0a3cdbe72b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d6ed38bc-b61c-55e0-8123-0a756136f2c9 |  | note | Detail - The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate
label | e4fd072f-9332-577a-b541-c9746f17b857 |  | note | Frequency - Prior to commencement
label | ad5eb9f2-1ab1-5817-b844-016668c91027 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5aef291a-5655-58aa-ae3e-583ded8fea9f |  | note | Conformance Criteria - Crushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991
label | 24d1d6d6-b0bb-5b50-bc61-d73d28fe48d4 |  | note | ○ Be crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14);
label | 1b01c5b9-3738-5b8e-b3e8-a2f7e7837b9c |  | note | ○ Free of organic and other deleterious material; and
label | 3ec77809-f86a-5308-a70a-d80525bf011d |  | note | ○ Meet the particle size grading envelope outlined in the specifications table in drawing C200
label | a3443625-de32-5127-8b35-ed1a8923fedb |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 5 -
label | 9cf87e2b-8ed0-5292-a5c8-3f13d65c9c26 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 155ece68-d31e-51ca-9a64-c33726bbb039 |  | note | Detail - The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution
label | 386e1c5d-cd6b-5949-a229-cea7f27bf273 |  | note | Frequency - Prior to commencement
label | f63686f6-5b95-5ab3-92f0-7a103a092397 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 945b033a-1387-503b-81ef-c41cfb22d131 |  | note | Conformance Criteria - NZS 4402: 1986 Test 4.1.1, NZS 4402: 1986 Test 2.8 .2
label | 31790dc4-39c0-5b67-bb7e-ac2113c36520 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 6 -
label | 0c1e874b-9c14-5a5e-8fa4-12783569fd50 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d572b8a7-1c8a-503a-b9f9-c3d9f7408fe0 |  | note | Detail - The test results shall be no older than 3 months so that they represent the actual proposed materials.
label | edfe4dcc-4982-5dd6-bb56-bdb5ecfc913c |  | note | Frequency - Prior to commencement
label | 5d9982a6-9322-5856-b40b-2acb1ddebdfe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | fb1d7ff8-9267-548e-8772-c5e1aceeb341 |  | note | Conformance Criteria - Check testing results are less than 3 months old
label | 2427b484-4b7f-5e72-869b-52a2ce9215fa |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 7 -
label | 936002f7-7ec5-56cc-9c99-20d9ced3c6a0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e5407c15-61c0-5592-ab4a-56f30e6b0dda |  | note | Detail - All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel
label | 0b5648c0-8252-57cc-b36f-1d06255b68a7 |  | note | Frequency - Prior to commencement
label | ca460067-51d7-5f21-980b-60b8e36b4169 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 152845bf-694f-5823-9ad5-f7539bcb8193 |  | note | Conformance Criteria - IANZ registered laboratory, laboratory certified to ISO 9001 or 9002
label | 773c0a4d-190b-56b9-ab56-7f4350ced8b7 |  | note | Records - Certification
checkpoint-status |  |  | checkpoint | 8 - Geotextile Material Compliance
label | c1985ada-a9d8-510a-bedd-fbacc49414c4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c3a6cacb-3758-5b4b-9c5e-c09354bf0653 |  | note | Detail - The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent.
label | 27ac0d5d-6938-56d8-a42d-a43252f70acb |  | note | Frequency - Prior to commencement
label | bc3d112c-d1b9-5a26-9f39-5f79d87c9878 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 8debf3f3-59a2-5ad3-971f-0c4e757f0868 |  | note | Conformance Criteria - non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1
label | 53858759-a35b-5dd2-80f3-f107a68827e1 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 9 -
label | 87be8b32-3956-517b-b7dd-2bb94b2512ca |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1ce60f18-6c5f-5b19-b242-69d28a1ff722 |  | note | Detail - The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ
label | ec4bfe89-a947-5b2d-85cf-0f4536dd2ad9 |  | note | Frequency - Prior to commencement
label | d69eec38-ab1a-51a5-a474-55dd678455a4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5ab17b54-faff-570a-b4e0-5edd8aba0999 |  | note | Conformance Criteria - TNZ F/7:2000
label | 89586a6d-81f7-5d79-a461-d170221d1446 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 10 - Subsoil drainage Material Compliance
label | 98f825df-5442-56e6-adc9-6a3881ef930d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6310b2ec-61d2-52d8-9398-7d5977d25be9 |  | note | Detail - The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”.
label | 6e532b45-080c-52f0-b1a6-7284b2082b9e |  | note | Frequency - Prior to commencement
label | a422761f-1118-5020-9c35-ad288e4b383b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 71408f06-e6bb-5e40-8ab5-3a81f518859b |  | note | Conformance Criteria - complying with:
label | 07c6ae30-b833-582c-98a1-fb3bfae112b1 |  | note | ○ NZS 7604:1981
label | 7941c2af-c3f3-532a-b427-fbfc4cc571e1 |  | note | ○ TNZ F/2:2000
label | 04ef69ca-f686-54a1-aa34-5bd7e6e45f24 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 11 -
label | 425308fa-d004-50c0-bdee-289e1de85a8d |  | note | ACTION (Hold, Monitor, Witness) - M
label | d020f1bf-e6e1-5dd7-b0c5-11ee4656a1c5 |  | note | Detail - Outlet and connecting pipes shall be unperforated.
label | 89301b0d-2b01-53d1-9788-7e3d3a143023 |  | note | Frequency - Prior to commencement
label | 782b02b3-647d-5fcb-9891-c103bce845a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | cdd21bdf-985c-5c7d-871c-eb957f6a100b |  | note | Conformance Criteria - complying with:
label | 428e18d5-93dd-5a24-b98d-fce5facd5339 |  | note | ○ NZS 7604:1981
label | 4ee6774d-7c2a-51ab-a54c-8a9615a8c36f |  | note | ○ TNZ F/2:2000
label | 74152d46-a8e8-53dc-ae8f-54075201fc1c |  | note | Records - Material receipt, site inspection
checkpoint-status |  |  | checkpoint | 12 -
label | 9e1999fb-fb8e-56bd-a1f9-a66c8723e89c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0d5f8085-0a2d-5c8c-9167-561aaf565239 |  | note | Detail - The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved.
label | 4e990a0c-a7a7-5055-bffc-b15493b846d6 |  | note | Frequency - Prior to commencement
label | cd165d5c-bb17-572a-be96-dd09181ea6b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | fad49e43-0c8d-56dd-ba5a-80f5359d9100 |  | note | Conformance Criteria - Confirm drainage blanket before install
label | 0f2d605f-e2e9-5586-9168-b1835238ffd5 |  | note | Records - Material receipt, site inspection
checkpoint-status |  |  | checkpoint | 13 - Timber Lagging Installation
label | a635a422-c016-5076-8694-6a6b74affb26 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0a59807b-740e-5e8e-be58-747cf855959f |  | note | Detail - The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation.
label | db68d73b-1622-5dca-afd6-9da1b201491a |  | note | ○ All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint.
label | f76fa834-f0e8-56aa-bdfe-e0bbdee97b0f |  | note | Frequency - Pre/ During install
label | 0b5e4d3d-2e71-579c-ab4c-94f86c9805f9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eeee478b-e909-59b0-87ae-2b1806f95a21 |  | note | Conformance Criteria - Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m
label | ad15b6b9-7d06-522d-a31c-a864b081a615 |  | note | Records - site inspection, Photos, log
checkpoint-status |  |  | checkpoint | 14 -
label | cc9695be-0b06-5c3a-a311-1d712921f8d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | ca6dda3d-1aea-5efe-b704-6ea460ea8a4e |  | note | Detail - The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc.
label | 694dba47-dbfc-5132-8698-a9b9a46ce969 |  | note | Frequency - Pre/ During install
label | 654701fb-66b7-57d7-966e-672cd9aac491 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 53820310-ee37-5364-a092-33b461ef6f2b |  | note | Conformance Criteria - Confirm and document screw installation is correct and lagging timber is appropriate
label | 73ca901b-1876-5f27-bdf0-2f2761b4645f |  | note | Records - site inspection, Photos, log
checkpoint-status |  |  | checkpoint | 15 - Geotextile Filter fabric installation
label | 5075f4ec-0ae6-5f15-bd80-b3882c580a66 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9d061467-9ed1-5a5e-aae1-2a3a3e984933 |  | note | Detail - Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm.
label | 9b9a7aa7-ab0b-5ac3-9a5b-171648cb1a10 |  | note | Frequency - Pre/ During install
label | bc28438b-1578-5726-97b3-2ce0a2d3dffc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 90c45369-f62a-5965-8f50-1ab5cf5065d7 |  | note | Conformance Criteria - At joins overlapped by a minimum of 200mm
label | 690d8337-9de8-5ed3-871a-63093074b164 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 16 -
label | 3c55b368-725c-5aaf-86b2-c360c1f8ec5f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9dcc0ac7-1354-5e84-8341-a3fed103d55d |  | note | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides
label | 0c57c9d2-f624-5807-b96c-1d5217f2b0d1 |  | note | Frequency - Pre/ During install
label | 5c628d35-a8cd-568a-9839-41f69bdf3c48 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fb9229c8-a2f3-576c-b5da-05a7de54588a |  | note | Conformance Criteria - tears shall be repaired by contractor, overlapped by a minimum of 200mm
label | b615a9c4-7287-5011-80dd-96d748a8ea43 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 17 - Subsoil Drainage
label | 2b436e13-f6d4-5b56-b741-e05eb0562cc8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b89d01d8-1eb6-5b4c-8785-7abd4d06570e |  | note | Detail - The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting.
label | a1b40941-d41d-5ee0-b984-a8f56341f93d |  | note | Frequency - Pre/ During install
label | 7c3af5ce-9b67-5bf7-bc5d-2a14cf3d8687 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7f7616a2-f76b-56fa-98de-09d59730aa51 |  | note | Conformance Criteria - Outlets from the subsoil shall be constructed to discharge water clear of the site
label | 16e67474-8c45-55ad-8d25-b9082066aa37 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 18 -
label | a589d508-f4c5-518e-b9b3-b9df08cf53fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f274aa9-746f-55d3-a628-a7e571a2d542 |  | note | Detail - The location of the outlets shall be determined in conjunction with the Engineer on site
label | 1d6369d8-d627-5516-9af5-9fa2a1d8e27c |  | note | Frequency - Pre install
label | eb87262a-f602-56f3-887b-2c06187a55b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document review
label | 9f9a94a1-4ce6-558a-a9e2-e3a42557e624 |  | note | Conformance Criteria - HOLD POINT: CPS engineer to review and approve location of outlets
label | 65b9d6a3-258d-5998-bc26-d48fc7dbe62e |  | note | Records - CPS Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Retaining Wall Backfill
label | 86509298-765d-55c7-b502-036dad0e36d7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3ba880b4-369f-51e7-acba-a89d3f81eac5 |  | note | Detail - The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation.
label | 52675688-027e-56b7-8f50-3752a92af42d |  | note | Frequency - Prior to commencement
label | 97dc0b60-6f2e-5703-9aee-4f3963c71de8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | f2c26d0f-55c3-5691-993e-70c581e5c25b |  | note | Conformance Criteria - Temp works confirmation for excavation area, for placement and compaction
label | 731e0261-8ba3-570b-b337-178aac7176c6 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 20 -
label | cb343e8f-29c7-54a5-bba9-779308cf3652 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 314e56dc-c805-572a-8b75-5f73fd6fd58a |  | note | Detail - Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components.
label | 5647a9f0-6bc9-5307-8eca-29ec342a2831 |  | note | Frequency - Pre/ During install
label | aa9a3dae-1bdc-5c10-976c-e493f8e4fcfc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c1078d49-f3d1-5fee-8589-549b69d85c0f |  | note | Conformance Criteria - Not heavy compaction works within 1m
label | 58b9ae4f-3fa9-5679-9c98-85ce6f06415c |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 21 -
label | e71d75f6-db7e-59f6-a42a-d9957620ca2c |  | note | ACTION (Hold, Monitor, Witness) - M
label | c746a2e7-2b49-5596-96b9-a6b941b42a24 |  | note | Detail - The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction.
label | 8731b274-466a-5971-b504-7e2a7086163c |  | note | ○ Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | 4c7f24db-06ce-5e16-9ea5-959d69d3c414 |  | note | Frequency - Pre/ During install
label | 4d1fd0f3-2dc9-51bb-82a7-a7cf6f87e2e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | afb098b9-f4f7-5016-ba03-9e1388df5b3a |  | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | 50f90d85-cc5d-5656-bbef-c02f4dddcc7c |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 22 -
label | f49bf372-aa4f-5413-a427-bf06584b18ef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 793b562b-0201-5fe3-b38a-7c6d922a3c5b |  | note | Detail - 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | d0d3250b-271e-5f1c-bbc7-ede58b4d3dec |  | note | Frequency - Pre/ During install
label | ee1deeb6-a60b-533f-9943-3f4ee4866c13 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 417a8204-4ad4-51ca-9cea-963ab023e9d3 |  | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | 446d5e87-c759-559e-b25f-8d09d07c8a35 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 23 -
label | fedba573-c4bb-51f6-b10d-53cf12018278 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 73eab55f-f099-504e-93a7-7c7f78cc0536 |  | note | Detail - At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall.
label | 4dc9278f-96d2-54a2-b233-61d458646b1b |  | note | Frequency - During install
label | 2f328b11-170b-54b5-a9cc-b65892b94857 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 51467152-ba2a-5325-ae6f-e36a90a37708 |  | note | Conformance Criteria - l 3 sets of at least 5 NDM tests
label | 658f2408-24cd-5cf2-9c66-1beaf70a83c8 |  | note | ○ Carried out at approx. 1/3, 2/3 and finish level.
label | 37f43e8e-1ccf-56d6-bf42-f979fc9ad229 |  | note | ○ Results shall be forwarded to the Engineer within 24 hours of the tests being carried out
label | dfe1bc85-05f7-5745-99f1-320d69ef597e |  | note | Records - site inspection, Photos, test results
checkpoint-status |  |  | checkpoint | 24 - Subsurface drainage
label | 05e2d470-b159-58e5-b65e-70beb3e3c710 |  | note | ACTION (Hold, Monitor, Witness) - M
label | fb709d71-9b06-5f60-9cfb-4ecda70b4f75 |  | note | Detail - All the surface water should be diverted away from the proposed retaining wall.
label | 7a60a9ba-9256-5359-8b68-61b00eb8661c |  | note | Frequency - Pre/ During install
label | 91b520ee-e5c8-5f1d-be6f-6891b4ca48af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a7127de8-4e21-5dca-a89b-d6bc613d713f |  | note | Conformance Criteria - Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall.
label | da2106af-2c82-54a7-8534-6041685bf2b1 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 25 - Survey As Built
label | 2055fb05-7dd8-50d8-a9b2-9f8e8a83325a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 66f2b5e1-95cd-5f03-a256-72a7558bfe06 |  | note | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | 9007b607-ea8f-514f-98e7-6a1122dffb8a |  | note | Frequency - At completion of sub soil drainage line
label | 59bd4bcd-4a76-5d9b-8677-359550ddbb79 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | a8a86f5d-9ec2-524e-b115-fac809a4154e |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 26 - Lot Number QA File
label | 6a8f9592-6196-5512-800a-bf2b76954b7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 75c03242-6f66-5f36-82b3-88029f4bf65f |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 1873fe6c-886a-5247-a522-3575abd4c444 |  | note | Frequency - At completion of Lot
label | b743ee8e-48e0-58ae-a41b-241c1c5b36a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1266a891-6783-5a8e-80dd-1720b3479860 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 3b403cf2-21a8-5800-ac79-c1fdd684725a |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 27 - As-builts
label | 0efbfb4f-4a08-520a-a507-bb4f060cf59b |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 09730124-cc66-5576-b4cc-600d0ac85f98 |  | note | Frequency - At the completion of the Lot of work
label | 74271c37-7ade-54a3-90b0-e0ac0b2580f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b996e380-26be-5920-a949-63d25944c0b4 |  | note | Records - As-built Drawing
checklist-flat |  |  | checklist | CS-4101 - Water Main Line Record |  |  |  |  | Yes | CS-4101 - Water Main Line Record | ebd39e27-5415-4c0b-85de-da053049d5a4
checkpoint-no-status |  |  | checkpoint | Details
text | ab3de763-9c0f-54d5-a0a6-d364dbf90739 |  | textbox | Drawing No:
text | 97246357-bf8e-58b4-926b-7e4f3b8b438c |  | textbox | Rev No:
text | 3e2c2229-6580-5636-aa83-0785c405b641 |  | textbox | Chainage:
checkpoint-status |  |  | checkpoint | Set out by surveyor & handover to Site Engineer completed
text | 62f0a881-7425-5a8e-b599-7c9c18f8a78d |  | textbox | Initials:
date | cce95abe-4546-55b3-b21a-29d6191faea7 |  | date | Date:
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | fd53d545-0345-521c-a3cd-c080734f44fb |  | textbox | Initials:
date | 99d50591-04a2-59a4-8b88-7adf6ac9eff8 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench line and profile as per IFC drawings and as set out by surveyors
text | 0a2007d1-ee16-585a-96d2-195a740eaf2a |  | textbox | Initials:
date | 91071a7b-bc5c-5553-b776-c68deb2da249 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench must be made safe before any person may enter the trench
text | 8cb09c1d-5d68-54c3-ab22-9ed89443901f |  | textbox | Initials:
date | 2722ff4c-5d3b-5aeb-b1c9-532318bfb06b |  | date | Date:
label | 5bbe1e12-c08e-592b-98bd-9eaf7b306e05 |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | Base of trench inspected and tested if required.
text | 060c0f61-c770-5f1b-ba8b-81cc5c8a5b77 |  | textbox | Initials:
date | 55e8064e-e03a-5982-8bd8-44c885411748 |  | date | Date:
label | 24160c56-44a3-5e15-8c6b-8b88488ed337 |  | note | Comments:
radio | 9e1c0efd-8859-535b-b09a-e88838f806ea |  | radio | Under cut required | Yes,No
checkpoint-status |  |  | checkpoint | Bedding is to be tested
text | bc6c79d7-b698-53cd-9879-3fbac32a0a82 |  | textbox | Initials:
date | 51e31283-33ac-549f-a6bd-23f0c894385d |  | date | Date:
checkpoint-status |  |  | checkpoint | Pipe is laid with appropriate clearance to other services
text | b8d9e5a6-7b39-5ef6-9a40-a62c7ac53886 |  | textbox | Initials:
date | 4ba16fcf-89e0-504e-ab47-868dbc4632e2 |  | date | Date:
label | 1a739d74-899b-5177-80a3-51d92e1d1d76 |  | note | Comments: See “Table 5: Clearances from underground services”
checkpoint-status |  |  | checkpoint | Survey to asbuilt top of pipe before backfilling commences
text | 68abf43d-9943-5732-a83b-fb97cab9dc00 |  | textbox | Initials:
date | d77ef568-1ecf-501d-a3ea-e4fa822c206d |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure warning tape and/or magslab is laid at the correct cover over the new pipes
text | ec1ddf5a-fe10-53f5-b9b4-0a010624607c |  | textbox | Initials:
date | 17b899fe-ae71-59b4-800e-db73597e057f |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure backfill material is suitable and un-contaminated
text | 6e91806b-d206-54d0-9e32-be947e4b1494 |  | textbox | Initials:
date | b701351f-97c2-52e1-92df-f5fb049f7a3a |  | date | Date:
checkpoint-status |  |  | checkpoint | Backfill compaction tested at every __mm lift
text | 794992d5-2d7f-57be-9c2b-16f118a4fa8e |  | textbox |  |  |  | mm
text | 2d25f8ed-aa20-5b60-8f65-f7dad0f032aa |  | textbox | Initials:
date | 1cf681cd-7d03-555b-8efd-ca4b26f13a65 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | f5616414-c342-53b8-96c9-fc5dd105d83f |  | note | Position: Site Engineer
text | 812680f8-603b-51a9-a2a6-f4edfee387cf |  | textbox | Site Engineer - Name:
date | 48f20e80-6d47-5258-91b2-fd0ba00d869a |  | date | Site Engineer - Date:
label | ac10e55b-028f-5faf-8f51-1f03ca188bee |  | note | Position: Design Engineer
text | 19e92298-9895-5c8d-bd7f-d27627aadcfe |  | textbox | Design Engineer - Name:
date | d1b278a2-c198-5ece-be7a-2f6d8449e851 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4078 - Signal Pole Installation Record |  |  |  |  | Yes | CS-4078 - Signal Pole Installation Record | ebf62ff5-210e-4c9a-bae8-ba0565fa8409
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 124f5993-fe2d-5cf4-b5be-d4219cbb0321 |  | textbox | Drawing No:
text | 084a361d-3e77-5711-b3aa-97a63176d93d |  | textbox | Pole No:
checkpoint-group |  |  | section | Pole Footing
checkpoint-status |  |  | checkpoint | Confirm signal pole locations are as per latest Drawing revision and does not clash with other Services.
text | e6a10d41-7b0f-5e14-8fc8-33cbe7f97b04 |  | textbox | Initials:
date | b8248792-c436-544f-be90-585a5855c1fd |  | date | Date:
label | 4832e8a5-84b8-53b9-b610-5b91ab811411 |  | note | Comments: Design Engineer to approve if the location needs to be moved.
checkpoint-status |  |  | checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
text | 69fba348-2fa6-57c1-b60a-08e770bec971 |  | textbox | Initials:
date | 3e3fc71a-7cec-50af-a5b6-c1f49228221f |  | date | Date:
checkpoint-status |  |  | checkpoint | Footing Type
text | aaef06af-73ce-51ff-ab80-bf8fb303e93d |  | textbox | Initials:
date | 68e6f87a-1407-5b47-929d-48820ba413f0 |  | date | Date:
label | 21d3193c-0021-5d23-846d-eb830cdecfec |  | note | Comments:
label | 18d52426-efda-510c-868b-be6e5e611f54 |  | note | ○ RS 115
label | f1cdfb76-545d-5622-9759-fd6a0476d1df |  | note | ○ RS 168
checkpoint-group |  |  | section | Excavation
checkpoint-status |  |  | checkpoint | Pothole existing services within close proximity to the foundation.
text | 416ca2fb-3639-5463-97a8-e54d7f1f8c54 |  | textbox | Initials:
date | 1023ea56-a4e2-5c10-aa38-834ce326fea0 |  | date | Date:
checkpoint-group |  |  | section | Socket / Flange Installation
checkpoint-status |  |  | checkpoint | Ensure duct is connected to socket.
text | 3af5d5e4-b727-59e2-bb26-b36040e02e7b |  | textbox | Initials:
date | 470d9844-8772-5324-bdef-79de258d94db |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspected the foundation prior to pouring
text | 86f1b5fc-4728-5ef3-b2f9-c1fa007b9b8b |  | textbox | Initials:
date | e040e739-50b1-52d3-a240-bff596d89e0f |  | date | Date:
checkpoint-status |  |  | checkpoint | Prepour checksheet completed
text | 916fbe8f-97c1-53f1-8ecc-3ea4ef4564a0 |  | textbox | Initials:
date | a53b2fd3-ef28-5c3c-a09e-a61987a41042 |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete for footing, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
text | ff099841-d870-5eda-8c73-f234b52e9129 |  | textbox | Initials:
date | 45d13fab-319f-58a6-8225-266b48b7ed5f |  | date | Date:
label | d9f89a33-24ff-53c8-91b9-3a0fed55d1a7 |  | note | Comments:
text | d62bb668-9324-5634-a58b-2f4403f2ae80 |  | textbox | Concrete strength |  |  | MPa
label | 1f28c9ab-c1c9-5cf4-b157-00018d1290c8 |  | note | Attach delivery dockets and write the road light column numbers on the docket
checkpoint-status |  |  | checkpoint | Use a stump pole to check verticality and height from FRL.
text | 93c58b41-93f8-57b5-8ba4-20f1599b34cd |  | textbox | Initials:
date | fd7d37d8-bccb-55d0-b34b-b4ba7ad56f83 |  | date | Date:
checkpoint-group |  |  | section | Installing Signal Pole
checkpoint-status |  |  | checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting signal pole
text | 0852b329-bc1a-533b-b5e8-f9ab2de3c274 |  | textbox | Initials:
date | bf392836-448e-513b-aa5e-52f43bad8a20 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check signal pole for any damage
text | 7d5ae10e-4654-5597-8dd3-b0fa6b15a753 |  | textbox | Initials:
date | 1067aa7a-c4a8-507e-937a-845697e4c53b |  | date | Date:
label | 3881024d-0944-58f9-81f6-2c807dcd39b7 |  | note | Comments: Do not install if damaged
checkpoint-status |  |  | checkpoint | Assemble signal pole on the ground (protect column by blocking off the ground)
text | 00d34749-3c69-5bf8-8815-d2d1b9420123 |  | textbox | Initials:
date | 322eb955-21dd-5d68-b9b2-de903303108f |  | date | Date:
label | 5bf50e68-0e65-5d41-b122-10df33b02f36 |  | note | Comments:
text | b6c2469b-e2fb-525d-a809-5f982195c7e2 |  | textbox | Pole Type:
text | 5141473b-8650-5189-8f14-977d668fb3a9 |  | textbox | P43 DWG:
checkpoint-status |  |  | checkpoint | Check orientation of signal lanterns
text | d3a7e0e5-b2bc-5080-a74e-1a78709ef0c1 |  | textbox | Initials:
date | 72ddcc8f-acc4-5c19-857f-e0b598bb8804 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pole identification completed
text | 7629ea88-0c89-5d3b-8af1-ef9b0e211ffe |  | textbox | Initials:
date | e9df72fd-2655-5596-8c0d-77cbc18e2095 |  | date | Date:
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | efa0d589-f232-5a5f-8c83-77346c022f0b |  | note | Position: Site Engineer
text | 6b096d6f-2ad5-5c20-94f4-7bf8627aa262 |  | textbox | Site Engineer - Name:
date | 5fb1959d-2073-50a2-a6af-ed2d3ee6dc68 |  | date | Site Engineer - Date:
label | 38598a0c-6f49-5f2f-8ce6-2f6ec6674a2b |  | note | Position: Design Engineer
text | adcf7903-b78f-532b-a220-bee35e4f6602 |  | textbox | Design Engineer - Name:
date | 35495dec-3957-5498-9469-d8be7cdcf81d |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4025 - Drainage Line Record |  |  |  |  | Yes | CS-4025 - Drainage Line Record | ef3c272a-93d9-4e6f-bade-e06f515a2dd2
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 9bb8d8d9-d3a6-5bef-9f52-a1e4d005273e |  | textbox | Drawing No (& Rev No):
text | 59537013-33c8-552c-9e48-5f765622f513 |  | textbox | Drainage Line:
radio | cbb69cd9-c184-5713-b515-1026a8b1fa37 |  | radio | HS3 / HS2 / H2 | HS3,HS2,H2
date | 29d0de88-cef9-5821-92a8-bf923cedf1b5 |  | date | Date:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | Set out by surveyor & handover to subcontractor completed
text | 5054a653-5d97-5d26-b003-e3a6f419a90f |  | textbox | Initials:
date | 080a7af2-f1a2-58ec-8348-1e07c8b28839 |  | date | Date:
checkpoint-status |  |  | checkpoint | Start point (i.e. manhole/headwall) checked for line & level prior to commencing this drainage line
text | a0baa160-49bb-54a8-a563-823c2a44b48f |  | textbox | Initials:
date | a15ee73b-7323-562d-a78b-f512dbb895f6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Foundation Undercut Compaction base of trench subgrade Scalas taken every __m
text | e581a2da-184a-5bc4-bba3-55812ce4e6bb |  | textbox |  |  |  | m
text | 3b8a5192-5d2a-5020-bc6b-7f9aa35e76c5 |  | textbox | Initials:
date | af81223f-efbb-5d77-9b60-c24dd27e8964 |  | date | Date:
label | 689d72bd-f039-5951-a2e7-1f2885dacbbc |  | note | Comments:
radio | d7d03e34-6683-56b4-9403-7efa25874ad2 |  | radio | Under cut required? | Yes,No
text | d32a7be0-11ff-5381-b580-01e0792fc381 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Bedding Zone Compaction Testing every __m
text | 5d2329b7-0a18-5b31-984e-689d0c972553 |  | textbox |  |  |  | m
text | 62d5b174-4e99-55b2-97f8-e1f6d67d3586 |  | textbox | Initials:
date | 9d823bd7-22b5-50c1-821c-773ee1da0ac9 |  | date | Date:
label | cb0257ed-e131-5bc4-b5f7-bef438dc49b5 |  | note | Comments:
text | 45c64dd7-ef97-58d9-b31a-5c473636ca01 |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Engineer to inspect base of trench
text | cbb8d52c-75fb-5266-afac-651ced800722 |  | textbox | Initials:
date | 81c9c1c9-57f2-52b9-907a-1379700a4d3f |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench width per __m culvert line
text | 1cdd8626-82dd-57aa-97f3-305b749790f7 |  | textbox |  |  |  | m
text | bd56ce60-883b-50de-8787-b2b00d61bf7d |  | textbox | Initials:
date | 30171b06-2783-5813-aef5-b60feeea1427 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pipe Laying Inspected and approved by Site Engineer
text | 80bc31ea-9746-590e-87a8-f58c0a7ec62c |  | textbox | Initials:
date | 202e1165-4d37-56e5-961d-6735eb47894a |  | date | Date:
checkpoint-status |  |  | checkpoint | All Connections completed and inspected as per specifications
text | b2abc755-6df8-5161-8836-0ded1059c87b |  | textbox | Initials:
date | cadda24c-df7c-5a85-95ef-4894356ec9cb |  | date | Date:
label | b3e11363-4cf0-539d-8611-1db2b1be06e7 |  | note | Comments:
text | 99b371af-b2c7-556d-b131-6ac823bec3f8 |  | textbox | Structure (In):
text | ed743099-9857-5109-82d3-ddacd2bfb595 |  | textbox | Structure (Out):
checkpoint-status |  |  | checkpoint | Haunch Zone Compaction Testing every __m
text | ae05ad46-6f86-5f7e-943a-7e5149dbd5d4 |  | textbox |  |  |  | m
text | 056e2a0d-3b1e-5268-b13a-9c1fa6333073 |  | textbox | Initials:
date | 2525d9ee-b7fb-557e-8a1b-78a42a30d0a8 |  | date | Date:
label | cae3493c-07cc-52fe-8fff-b4df6ce7bbe8 |  | note | Comments:
text | a342b88f-b2f7-5a75-a580-f7fac13ba9a5 |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Side Zone Compaction Testing every __m
text | d7042613-6c7b-5463-9d5b-73e871788385 |  | textbox |  |  |  | m
text | dbb79555-e196-5e95-9050-7260a192cc7e |  | textbox | Initials:
date | 4fb8449c-56e4-51de-a70e-12f8550c5a50 |  | date | Date:
label | 62daf727-7fb7-524d-b60d-da8715fd02ec |  | note | Comments:
text | ff884d3f-846f-5d48-8c0b-918215957b5f |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Manhole Conections to Pipe Joints Haunched/Concreted/Epoxied
text | 6a0c7be7-1e9e-5795-8288-6e1f2c405126 |  | textbox | Initials:
date | 3cb27725-297b-5962-9529-f0dbf17d83ba |  | date | Date:
checkpoint-status |  |  | checkpoint | CCTV Completed and passed
text | 8d74fe57-8878-5552-987c-dee45f11cbd3 |  | textbox | Initials:
date | 74d2c8f0-8e0f-5eb6-abc6-3f5209f304c9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Water tightness test passed
text | 4a36c675-b41e-5a42-9d27-c00ccd043802 |  | textbox | Initials:
date | 122cc6da-e07b-5608-89e2-45da5fabc72e |  | date | Date:
checkpoint-status |  |  | checkpoint | Final visual Inspection Completed and approved by Engineer
text | 34112031-0f4e-51e3-8109-f33f7ec8071a |  | textbox | Initials:
date | f1a579a3-683a-5c02-94c3-3d149e029bf7 |  | date | Date:
radio | 013491c2-8f1e-5b04-b4c4-37769c2b140e |  | radio | Invitation to inspect: | Accepted,Declined
label | d4afc681-ae01-52a4-941e-073a5b0f570d |  | note | Design Team
text | 7c0553f5-eda6-5193-a5dd-eaba8b3b42dd |  | textbox | Design Team - Rep:
date | 56162ec4-2a98-5dfa-8474-512537207827 |  | date | Design Team - Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 4139a277-e277-5d32-aa3c-5f83587778e2 |  | textbox | Name:
text | 54357385-50fc-5f5a-b2a9-9c62ee32ba32 |  | textbox | Position:
date | 4d105e5f-841e-5408-b3c2-fa21fc61fcea |  | date | Date:
holdpoint |  |  | signoff | Sign
checkpoint-group |  |  | section | Drainage Line Record
checkpoint-no-status |  |  | checkpoint | Direction of Flow
radio | be22d9c1-8960-5050-ade2-db29cb62f3e0 |  | radio | Indicate Direction of Flow | <,>
checkpoint-no-status |  |  | checkpoint | Invert Level (In)
text | 9b8d0530-9b62-5293-989b-97b13212a4e9 |  | textbox | Design:
text | 838f8837-1dc8-51aa-9489-9d1b4a1a0b38 |  | textbox | As-Built:
checkpoint-no-status |  |  | checkpoint | Invert Level (Out)
text | 22939f4e-ba5c-56c4-963a-b22a2271bb4c |  | textbox | Design:
text | fca65562-bd51-57db-bdc8-ff224882634d |  | textbox | As-Built:
checkpoint-no-status |  |  | checkpoint | Structure (1)
text | 4d210f38-14d8-59aa-9034-382f60cb49c6 |  | textbox | Structure Name:
label | bcc6d046-4a61-5074-9dc4-8fdfab907fb5 |  | note | Status: New
text | 1a645d5b-4abe-5b71-957c-48e0393838d4 |  | textbox | (New) Dia:
label | 0150fe4f-795d-5e9b-bb72-d01db0cba21b |  | note | (New) Type: MH
text | 7aa0084b-b1c8-5ae0-829d-54f2152da1d1 |  | textbox | (New) Distance to Flexi Joint:
text | 688726d1-daab-5593-a997-fe1ce8a8831c |  | textbox | (New) Epoxied:
text | 37fb1e9f-4485-540f-80ff-1351eeb401d9 |  | textbox | (New) Water tight:
text | b6e6d16a-5288-51db-9802-543002ca59f3 |  | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | de58c5fd-83d8-5cdf-8b63-3a6c30da6b0b |  | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | 70d35401-9f02-5868-bd20-7315184a6869 |  | note | Status: Existing
text | 8e40e2aa-d9b6-5425-9b4f-f4343b9d5618 |  | textbox | (Existing) Dia:
label | 02400286-af35-5df8-b6ee-8dc38c642479 |  | note | (Existing) Type: WW
text | d965d09d-e906-512a-a53a-b46a76196c61 |  | textbox | (Existing) Distance to Flexi Joint:
text | 5320dcc1-35d3-5043-ae35-4d9e0e175a93 |  | textbox | (Existing) Epoxied:
text | 754c31bc-17be-58a0-8251-9e8b79759382 |  | textbox | (Existing) Water tight:
text | 7ee30c10-d31c-5356-8627-23996941f89f |  | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | 3afdcd7d-c894-59b9-af35-6d20a2f9dd04 |  | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status |  |  | checkpoint | Pipe Details
text | e27de804-e7b6-50d4-956c-0dd7b7bab038 |  | textbox | (1) Dia:
text | 0501baeb-8565-5e54-9ae5-d52bd9292899 |  | textbox | (1) Length:
text | 666b3fa8-b819-5f27-b19b-cd755f2ba680 |  | textbox | (1) Material:
text | 674f3601-a80b-5fce-b26b-f9c68f3b49d2 |  | textbox | (1) Class:
date | ea9cecd3-a175-5183-85bc-aac69ce01a0b |  | date | (1) Test Date:
label | 8543a9df-a44e-589c-aab2-edcf4ec4bf59 |  | note | (1) Air test: Pass
text | 1f4e6a0e-b68e-52dc-9306-9ff2b81ca170 |  | textbox | (2) Dia:
text | 0418068c-6ef1-5dd3-98d9-6c56bea46611 |  | textbox | (2) Length:
text | 74ed4e74-a033-5966-82a1-7ec51269a38b |  | textbox | (2) Material:
text | 915de46e-6781-5ccc-9506-43e86f1ab87d |  | textbox | (2) Class:
date | c632dbf6-266a-51c4-87a8-7b23e100c221 |  | date | (2) Test Date:
label | 36d71739-f1a6-5694-8d46-1500bb0e9499 |  | note | (2) Air test: Fail
checkpoint-no-status |  |  | checkpoint | Structure (2)
text | 3d672ac6-31d3-5124-a019-ae5878651d9a |  | textbox | Structure Name:
label | f39de27b-670f-5547-bb33-798eab59e6bc |  | note | Status: New
text | a735686e-45ce-55c6-9396-6a37194c7832 |  | textbox | (New) Dia:
label | e62af161-1f4d-50f8-89b6-8fd400fc3954 |  | note | (New) Type: MH
text | 359738b8-d77f-559a-a6b6-991725ea38c0 |  | textbox | (New) Distance to Flexi Joint:
text | 7efed5ea-7099-5ef5-aea8-546ec8b353be |  | textbox | (New) Epoxied:
text | e0cd3cea-a2e3-549e-81ca-0f54e1674b7b |  | textbox | (New) Water tight:
text | 949a78f6-c0f5-5add-b706-f645e5478f00 |  | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | 31411b3f-21a9-579b-867e-cbe2ea19b80e |  | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | 0819d80f-26b8-5fa2-bd56-fe54d12f4902 |  | note | Status: Existing
text | a694d71d-74fc-520a-a549-891f35bb5ca3 |  | textbox | (Existing) Dia:
label | afbd538f-9709-5209-8211-2cc14c6bc990 |  | note | (Existing) Type: WW
text | 3baa25e0-08fb-535a-9494-de434aa2ab2f |  | textbox | (Existing) Distance to Flexi Joint:
text | 91cae105-53ff-5c26-bc3d-f246afc87cc0 |  | textbox | (Existing) Epoxied:
text | 6496eeca-60ab-5b6a-b9b0-c26245dc3bb0 |  | textbox | (Existing) Water tight:
text | c3a9a485-5742-5bff-8bec-6c2eb9a556ca |  | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | f8451c39-ec74-535b-b1c4-fe4a7e031ef2 |  | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status |  |  | checkpoint | MATERIAL TYPES AND SOURCE
text | 9ccca302-94f3-5b1f-add6-96e2c4562f0a |  | textbox | Undercut Depth:
text | ad17e669-e794-5994-8694-00e66926fc4b |  | textbox | Undercut Depth - Type:
text | dbc818a8-6800-5e31-b5ab-c3cb1785ce1d |  | textbox | Undercut Depth - Source:
text | 11b17403-b65a-5b0c-adab-bef50cb20df8 |  | textbox | Bedding, Haunch & Side Zone Depth:
text | 485ea3a8-ed41-5bbb-ae0c-31923a89c0bc |  | textbox | Bedding, Haunch & Side Zone Depth - Type:
text | 874e705a-c4fe-5620-81f5-0e0f3d91bb37 |  | textbox | Bedding, Haunch & Side Zone Depth - Source:
text | 5f8d0c0e-42ce-5dd2-9a4e-4b118106c045 |  | textbox | Backfill Depth:
text | e04df638-c13b-5551-b89b-e4aac47b92a2 |  | textbox | Backfill Depth - Type:
text | 34bbacb1-4ce2-5943-a459-d364c1c928cb |  | textbox | Backfill Depth - Source:
text | d5bd86c8-1a04-5ee0-ba03-58a93fa7038d |  | textbox | Design Grade:
text | 37bf3932-3b36-521a-95fc-27df6ca2bebb |  | textbox | As-Built Grade:
checkpoint-group |  |  | section | Connections
checkpoint-no-status |  |  | checkpoint | 1
text | fef94c28-2c61-5aaa-aaba-97f6abc69c4c |  | textbox | Distance (m)
text | 8e61bbe0-d69f-5134-b3aa-f6ce486a58a2 |  | textbox | Dia (mm)
text | 28456859-9178-5fee-87c7-8b393aaef0ff |  | textbox | Depth @ BDY
text | b7946066-37d2-50f1-bfe7-bd842be6ceac |  | textbox | House / Lot No.
text | 5b5b0e1b-a0dc-5a1f-81a2-119ecbef0040 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 2
text | 407fbdd8-7875-5393-9568-494115ebb3c1 |  | textbox | Distance (m)
text | 54c2b4d3-d0b9-5423-9742-39649bfb29cb |  | textbox | Dia (mm)
text | 1af77ad9-b2f7-5165-8192-6498da28111d |  | textbox | Depth @ BDY
text | aeffc733-5d22-5e92-8721-1299af8cac62 |  | textbox | House / Lot No.
text | c7a24eb9-f675-5cac-9a08-bd250bffa6d6 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 3
text | 5efb43b8-5f76-5a6f-bc5b-4eea49aaa284 |  | textbox | Distance (m)
text | 62ad3c16-c44e-564e-aaff-2ba2cbc1ea18 |  | textbox | Dia (mm)
text | 8f6f9d81-9e5d-5d5f-9efd-1cae40da4ffd |  | textbox | Depth @ BDY
text | 909be3b8-6086-5bd3-8246-caddc604d84d |  | textbox | House / Lot No.
text | 86cc6e10-bfce-5b5d-97c8-cf0404fbdab2 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 4
text | 5e38d997-de84-56a7-8f1b-6f05a0f3b7c6 |  | textbox | Distance (m)
text | 850dfc94-3ec4-5d92-a535-f0c718f14571 |  | textbox | Dia (mm)
text | 3345f7c8-f8e8-5d80-931c-920ca2ed2798 |  | textbox | Depth @ BDY
text | 9762f23a-9ba3-531a-8697-fbae9a2a0886 |  | textbox | House / Lot No.
text | bc231a32-ab7b-51fa-985b-c612aeed8762 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 5
text | bcfbd2ff-6127-5b59-b640-cd8413416cea |  | textbox | Distance (m)
text | 7b423c45-5ecb-5992-9664-99b03a74c7c7 |  | textbox | Dia (mm)
text | c9f7674a-6ae0-5f93-a674-0653ac7e0dca |  | textbox | Depth @ BDY
text | 514b8835-621a-58a7-a093-7d857f4e46ab |  | textbox | House / Lot No.
text | 401eba0d-0ca6-5425-9402-2110759c252c |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 6
text | a607fe27-af8f-567c-b32d-9e9d72ccb0b0 |  | textbox | Distance (m)
text | 00970bc3-a1bb-5920-9fad-6255f2fe73f9 |  | textbox | Dia (mm)
text | 3d13ddb0-3e5f-5115-8f40-1fe71db23bc7 |  | textbox | Depth @ BDY
text | 3464e334-017a-5680-9a9f-b6072d07d803 |  | textbox | House / Lot No.
text | f24e49ef-f726-5d32-8d67-5621c6041736 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 7
text | a43f27fe-5f0b-5b2e-ac65-81d32bd987df |  | textbox | Distance (m)
text | 628ce4d8-e1ed-5724-bdec-3b1484c0c242 |  | textbox | Dia (mm)
text | 35b924e9-fce5-56e7-8ca5-4f5edd0d2c11 |  | textbox | Depth @ BDY
text | 7e78cb2c-e56a-5fc3-a4d9-da6db61581ae |  | textbox | House / Lot No.
text | 718843a3-5c1c-5ef9-a1e3-c8d051eb3973 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 8
text | cbbb8a1c-b844-5eeb-8b50-240eb848fdea |  | textbox | Distance (m)
text | 2a490a21-99f8-5383-8f1f-00ae8b0130c0 |  | textbox | Dia (mm)
text | c1e3e874-3a84-5fc3-a8c3-dd850bbdec45 |  | textbox | Depth @ BDY
text | 6273894b-312f-541d-a2c9-06405a1a8dc4 |  | textbox | House / Lot No.
text | 2d0145fe-8f0d-5b49-b7f1-db12a6fb9d71 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 9
text | b155c03f-d919-56cc-96b4-6537a609d852 |  | textbox | Distance (m)
text | 8813e822-7a87-5c98-bffe-bf556fd72290 |  | textbox | Dia (mm)
text | 260f03a9-c8de-59d2-915e-471d76a7143c |  | textbox | Depth @ BDY
text | 6778e4c9-b5d9-5619-9778-74ac3920fa4c |  | textbox | House / Lot No.
text | 2793ec44-4390-5ee6-b676-31b0844d4d2a |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 10
text | caec4def-1fc2-55e4-b32b-63fd8d12165e |  | textbox | Distance (m)
text | c5c3369b-d741-53f6-9678-11ec31f5f165 |  | textbox | Dia (mm)
text | f599eece-f9c3-5dd4-81e3-c519ffd1712c |  | textbox | Depth @ BDY
text | efbd8b87-ffd5-559e-bc90-eddabff527ad |  | textbox | House / Lot No.
text | b0490c67-819d-5801-822d-1579067693de |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 11
text | 1fcd3798-4640-5256-a453-8293f4b4f318 |  | textbox | Distance (m)
text | b9c027b3-8fa0-5985-8d20-c7805e191b09 |  | textbox | Dia (mm)
text | 8e6baf7d-3d05-5f7a-af18-b7a505ce82b3 |  | textbox | Depth @ BDY
text | f40f481d-a050-5c0e-ac5c-996056fa9b88 |  | textbox | House / Lot No.
text | df0f1178-83cb-5594-91b7-7d45e9fa8e86 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 12
text | c55097ae-a4ce-52b8-baab-13af0aa585bf |  | textbox | Distance (m)
text | 6d6dbed4-836f-53a3-9570-1208cc65762e |  | textbox | Dia (mm)
text | 9a253afd-8ccd-5318-ba97-d48d1c77b025 |  | textbox | Depth @ BDY
text | 6abbaec4-c63a-5c50-8b02-7394d8be9910 |  | textbox | House / Lot No.
text | 4759782d-eed2-5fdc-bd8c-0b50e1e0c32f |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 13
text | 8b3fc0c5-5637-5979-86eb-c6c746b96268 |  | textbox | Distance (m)
text | de0710de-3c35-5a65-ba39-0f15ed2aee54 |  | textbox | Dia (mm)
text | f87248cf-a53d-54a7-acc0-95e6ede83808 |  | textbox | Depth @ BDY
text | 71623cb9-198a-5c20-a17f-0bcd7853ec04 |  | textbox | House / Lot No.
text | d9f155de-4454-50aa-b39a-4cc372c69f9a |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 14
text | 3efa676d-c7f7-54d7-bbc9-8d0c12f389bc |  | textbox | Distance (m)
text | 32e6a20d-bfc5-5e92-8e17-71083c1df8ff |  | textbox | Dia (mm)
text | 77e83605-4a54-56dd-9a48-363a1907b188 |  | textbox | Depth @ BDY
text | 8942c735-6994-51be-b13b-69b989a06780 |  | textbox | House / Lot No.
text | ed3e569d-3095-5687-b6cc-d4542c2d56c3 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 15
text | be1cdb7b-b650-5827-9aeb-c780a33791cd |  | textbox | Distance (m)
text | 7ba01e03-237a-52cf-99c1-953fca398686 |  | textbox | Dia (mm)
text | 549d279b-3e1b-5801-be8a-eb823fbf0196 |  | textbox | Depth @ BDY
text | 5d184b27-0dba-5fda-94f9-dfdf57afbc70 |  | textbox | House / Lot No.
text | 72cff308-49d7-5f68-bbf2-b2a15ddcc99b |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 16
text | e02a4c4d-a1b6-5fec-ab7a-45662f52a13e |  | textbox | Distance (m)
text | 8febeca3-303d-5d82-a9ed-f5e3a24eb6d7 |  | textbox | Dia (mm)
text | a6fb3fba-0e9a-58a6-8ac5-a1adc166b1ee |  | textbox | Depth @ BDY
text | 19a902d8-9aea-5c85-a081-24146a9ca194 |  | textbox | House / Lot No.
text | b2aeb76d-8ef6-5e39-bb50-c2e3e6a91000 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 17
text | 78d4cb35-e1ee-5306-b89e-f84c337dd3d7 |  | textbox | Distance (m)
text | d07344a3-0afd-546a-aa03-53aac474d07f |  | textbox | Dia (mm)
text | dcbe3be4-08dc-5b5a-99fe-e294b8943d66 |  | textbox | Depth @ BDY
text | 8c5e5b21-bfd9-5ce3-9c37-0fb85ff132ec |  | textbox | House / Lot No.
text | 560a0240-c781-5779-8f16-b91d53260ccc |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 18
text | 78939e4d-4e1d-5baf-9212-94d461e62e7a |  | textbox | Distance (m)
text | 8687ae1c-d96e-5566-b52f-bb323a21c05e |  | textbox | Dia (mm)
text | 16987ded-9bcf-5e17-9655-44c551225ce2 |  | textbox | Depth @ BDY
text | 875ec6d1-f216-5200-a2e1-3befd7c00ada |  | textbox | House / Lot No.
text | 22a5f39f-4593-5bc5-96cf-d2eb7aa83031 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 19
text | 321e509a-1f2d-53ce-9306-262713b85e52 |  | textbox | Distance (m)
text | b1f533c6-f95c-56a9-a826-8ac2b2555538 |  | textbox | Dia (mm)
text | 18568d73-869d-558e-99d2-6525cd8ed60e |  | textbox | Depth @ BDY
text | bec10dd4-60fa-5cb2-af04-423ea5169086 |  | textbox | House / Lot No.
text | c7249236-7b97-5070-93df-9c798aa83b20 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 20
text | 84cc089a-abcc-5175-92de-a607a409f807 |  | textbox | Distance (m)
text | 06faa542-2d20-5b97-a091-a1fab94606be |  | textbox | Dia (mm)
text | 8f924f6c-eb4c-513a-afc1-ad94a77f93f6 |  | textbox | Depth @ BDY
text | d0386c88-d488-5ae4-9614-fabf7c2f31ef |  | textbox | House / Lot No.
text | c8707a23-02e9-574c-b4a1-c10055204386 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 21
text | aece24f3-5238-523f-a351-c1cc99f045f9 |  | textbox | Distance (m)
text | e73d1711-fc8a-5eb5-9bbf-8e182e48b3f8 |  | textbox | Dia (mm)
text | f808d8d8-ade0-595f-93a3-7de366720608 |  | textbox | Depth @ BDY
text | e0b2ad3b-71be-5bcf-954f-6fde1a4f1278 |  | textbox | House / Lot No.
text | 71c53539-8652-5107-a9d2-d58cdd8e4df9 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 22
text | 01d3fa1f-d5e8-5307-b44f-0d2424194f0e |  | textbox | Distance (m)
text | b72e8f26-17a9-5c3e-8878-75913fd5b2c1 |  | textbox | Dia (mm)
text | ec8ed97d-2de8-5619-8a37-33c02cf50ed0 |  | textbox | Depth @ BDY
text | 342f866b-dd2e-5fd4-90b3-8d9d0b0ecdf7 |  | textbox | House / Lot No.
text | 47caaaff-de33-58f9-9ead-909b16e2db85 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 23
text | e8cc353c-7e6a-5b66-887d-4d9db75866d8 |  | textbox | Distance (m)
text | b083278b-5c9d-5811-9772-3f63974d1201 |  | textbox | Dia (mm)
text | d9202851-5155-5587-8bd1-2fc7f2418a4b |  | textbox | Depth @ BDY
text | fe48007a-16e0-5569-ae07-2e76d2ea84bc |  | textbox | House / Lot No.
text | c8a0b1e9-d593-52c8-a1aa-a3a1da1c570a |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 24
text | 240c675b-038b-5c9b-85af-9bc55eb08434 |  | textbox | Distance (m)
text | 99c5e649-c3e1-5992-834e-2b4abe642143 |  | textbox | Dia (mm)
text | 1c03aa27-ecd5-5377-aa01-cbcdf995fe55 |  | textbox | Depth @ BDY
text | ce3617f1-5f1c-5fe2-bf20-5bcab23a14ba |  | textbox | House / Lot No.
text | 2b64b0e9-1fee-5681-a481-96125413c65d |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 25
text | db66102c-2932-52d0-8140-6b797048c4de |  | textbox | Distance (m)
text | ac52825c-557d-54d5-adba-43519a251253 |  | textbox | Dia (mm)
text | 20eb0797-5f10-59cb-8f63-cb6335a44b76 |  | textbox | Depth @ BDY
text | fc022a44-c28d-5ead-9fcc-041d7e9301b2 |  | textbox | House / Lot No.
text | 3ff2902d-0a92-5f85-a3eb-b2b119186afa |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 26
text | d2af8b83-375a-567c-b84e-bbe17716c23e |  | textbox | Distance (m)
text | 7f5cf4cc-88c3-5734-9801-37eb311afe46 |  | textbox | Dia (mm)
text | 4f59b1ca-dcf7-5250-91e0-306ee3be92e7 |  | textbox | Depth @ BDY
text | f00bfe7a-cefd-5d5e-9e90-6f0bddb9bf38 |  | textbox | House / Lot No.
text | e5af7f52-57a5-56c2-9256-bccb1e51a965 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 27
text | eef66dbe-3689-5a6b-8915-1eec26f1e422 |  | textbox | Distance (m)
text | f2867c90-9c25-5e2d-bed5-9929298dc5d6 |  | textbox | Dia (mm)
text | 984126a6-f5a8-5e3a-a85e-7ec3db5a687d |  | textbox | Depth @ BDY
text | c349ff68-bc21-5369-a5b3-d162c38fee4f |  | textbox | House / Lot No.
text | f4822f22-cd58-5acf-abb7-2f0f3c0e5410 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 28
text | 4dcaced2-f1cc-573a-9ec4-aeedeb542845 |  | textbox | Distance (m)
text | 2d4bab82-0b68-5321-ae61-7d3411f10057 |  | textbox | Dia (mm)
text | 0be4b85c-f9a0-5c34-b2c6-5bab4f7754b9 |  | textbox | Depth @ BDY
text | 3381cd49-a58a-5a72-b73d-c495625020f8 |  | textbox | House / Lot No.
text | a0de2e6b-f815-54bd-8672-0f8121516fd5 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 29
text | e13ec354-d4d2-5499-b30a-b183b6b81d71 |  | textbox | Distance (m)
text | 424e5f68-4ece-5403-8181-815d075a721b |  | textbox | Dia (mm)
text | 46142e2e-8c69-5283-adc4-7d97626f8de1 |  | textbox | Depth @ BDY
text | 0793fa0b-fb10-51a1-849e-6c3301270797 |  | textbox | House / Lot No.
text | e67ffd69-a0a6-5fa4-b599-4186870a32b5 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 30
text | f9a30ebe-8150-57ff-a9fa-a0daf2ff7374 |  | textbox | Distance (m)
text | 95ceeeac-e30b-5a40-a004-0e29f0f25dd6 |  | textbox | Dia (mm)
text | 44f382da-1cc5-581a-ae57-7f2c2508fb95 |  | textbox | Depth @ BDY
text | 03294e55-e794-5280-9219-14d3b0579cfd |  | textbox | House / Lot No.
text | 9621b184-ce96-564b-a085-d161005370d7 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 31
text | 1510caed-32ff-595c-b45f-524c6d139bd3 |  | textbox | Distance (m)
text | 9f72c562-a6f3-5c6b-9f6a-b4a9528ecf7a |  | textbox | Dia (mm)
text | b1434eed-1a3c-575d-a9b1-e6c8c19396ce |  | textbox | Depth @ BDY
text | c5c9241e-079c-5c7a-aae2-d2a9a046b9ce |  | textbox | House / Lot No.
text | 9bbcb10f-1005-5846-b1f7-56af8e0c4166 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 32
text | 606a1e85-baa0-5cfd-8ba9-e5d5117f5f86 |  | textbox | Distance (m)
text | a0750f25-2c3d-501f-8094-5b38a39cabe8 |  | textbox | Dia (mm)
text | 5aa4c599-5f8c-563b-b0c0-9fc6ae9664f2 |  | textbox | Depth @ BDY
text | fc72abcd-c531-5718-9a93-c663898c55c6 |  | textbox | House / Lot No.
text | 41baebe3-f5d8-5d7f-8085-b69ff6e7a03b |  | textbox | Length (m)
checklist-sectioned |  |  | checklist | CS-4102 - Pressure Rebound Test |  |  |  |  | Yes | CS-4102 - Pressure Rebound Test | f042a2a3-fd4e-4ed9-8ed1-0ae344ce458b
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 8692735f-1f32-5fa1-911d-f761dfef13ef |  | textbox | Contract:
text | d419001b-4ed3-5fe4-8ae3-7ac1118c98c4 |  | textbox | Sub Work Area(s):
text | 2d12ee94-0e18-532f-bf6d-99d40abf24ee |  | textbox | Sublot(s):
text | 2503ad36-e12a-5fbc-893b-5985911400d2 |  | textbox | Work Area(s):
text | 76895275-42b9-5bdf-81a7-bf0b0969c497 |  | textbox | Lot(s):
date | 979c7f24-2a36-5521-9868-b2eb01241b8d |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Personnel Conducting Test
text | 3dd01c39-dae0-5e13-815f-6a9e00c61b20 |  | textbox | Drain Layer:
text | f87cc9a4-e012-591f-bff4-13f73784a94e |  | textbox | Site Engineer:
text | 6a12e515-95c6-560a-94c3-f495bd214c08 |  | textbox | CPS Engineer
checkpoint-group |  |  | section | Pressure Testing Record Sheet For Pressure Pipelines
checkpoint-status |  |  | checkpoint | Pressure Testing Record Sheet For Pressure Pipelines
text | cdae0b1a-857c-557e-8284-95e4fdac7cc1 |  | textbox | Pipe Material and Rating:
text | 57b952a1-4eb7-5b70-a19d-d9bd308184c9 |  | textbox | Test Length (m) L:
text | 8790a58d-8966-50d7-82eb-84bc5314c3c9 |  | textbox | Pipe Internal Diameter (mm) D:
text | 92aed249-d384-5329-ad8c-3f1aeb86dfae |  | textbox | Depth of Pipe Below Water Table:
label | 0dfe5a60-2c76-503b-b1e9-a6ba041f4514 |  | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
text | 1ccb427b-12c6-5050-afd0-ce9cef484b22 |  | textbox | Ambient Air Temperature: |  |  | °C
text | d0554e86-68fe-5df9-8ebf-9c2ae3c91f61 |  | textbox | Water Temperature: |  |  | °C
checkpoint-group |  |  | section | Pressure Rebound Method
checkpoint-status |  |  | checkpoint | Standard Test Pressure
text | 55c650a7-ec4c-5f9b-a58e-727b900f0dbc |  | textbox | Pressure Applied: |  |  | kPa
checkpoint-status |  |  | checkpoint | Preliminary Phase
label | 16c966d8-3afb-5ca3-aea3-05db3abe2483 |  | note | P60 > 70% STP
text | 3622e030-6f42-5dff-89d1-c40277000878 |  | textbox | Acceptance:
checkpoint-status |  |  | checkpoint | Air Volume Assessment
label | fa946e68-0a37-57bd-ad20-7585c7371520 |  | note | 1. Reduce pressure by 10%-15% STP (ΔP)
label | a7664b3c-bdb8-5dc6-a256-c708cc0db2ca |  | note | 2. Measure water volume bled out (ΔV)
label | 34ac6d46-72fd-533a-9ee8-ad238581f824 |  | note | 3. Calculate ΔV max allowable
label | 07199629-ded5-52b2-ba93-36cbd681597c |  | note | Where: 〖∆𝑉〗_max⁡𝑎𝑙𝑙𝑜𝑤𝑎𝑏𝑙𝑒 =1.2𝑉∆𝑃(1/𝐸_(𝑤 ) +𝐷/(𝑒𝐸_𝑅 ))
label | 4c0c30e4-dd47-5c7a-9d0a-755cd04aa0e5 |  | note | Acceptance: ΔV < ΔVmax allowable
label | cd68ce22-4873-5035-9c95-953d0c789c0e |  | note | – – – – – – – – – – – – – – – – – –
label | d60f9554-ae49-537f-9cf6-e4804f1b86b1 |  | note | Air Volume Assessment Parameters
label | e4c5aaf2-545b-586a-a4b1-4478cebd0f4f |  | note | – – – – – – – – – – – – – – – – – –
text | a2a485d0-0884-50cb-9ef1-7da001aa831e |  | textbox | Nominal Size (mm):
text | 4730ce39-5387-530a-81ee-2f79eee06fbc |  | textbox | Mean Bore (mm):
text | 5c9961bc-e279-5b81-903a-e6a6e8f0d41f |  | textbox | Tested Length (m):
text | e554faba-c503-536a-9037-ec346402bc8c |  | textbox | V (m3):
text | 6d6c77b9-286c-53d2-a446-63c22abdd5aa |  | textbox | e (mm):
text | 41ce9492-9509-5ef5-8987-032ae65f63fc |  | textbox | Ew (kPax103):
text | d070c8d3-4a03-5bd8-a120-1b1ded10f42f |  | textbox | Er (kPax103):
text | 67cf9f5f-2d1e-58ed-854d-4a238b9154c2 |  | textbox | ΔP (kPa):
text | 2ad3d82d-3312-5985-b890-603590ecea75 |  | textbox | ΔVmax allowable (L):
text | 7362c0b1-5e1e-5be3-bb20-84c2739896c2 |  | textbox | ΔV (L):
text | db31472a-f386-5685-80ee-22ea8b9385a7 |  | textbox | Acceptance:
checkpoint-status |  |  | checkpoint | Main Test Phase
label | 674d4131-4f38-5717-b65a-a15ce41c859b |  | note | Observe and record pressure for 0.5 - 1.5hrs
label | 3ac59707-d1e2-555b-9330-b6e7fc79b43e |  | note | Acceptance:
label | 2e2fd257-968e-5acf-a875-956bbd63babb |  | note | 1. No failure of any thrust block, pipe, fitting, joint or other pipeline component present
label | db84421c-f92a-5e49-b693-234fb6873a16 |  | note | 2. No visible leakage present
label | 646b7991-d0d4-57d4-bfd6-efec607c362a |  | note | 3. Pressure rises or remains static for 30min period
label | af5ec85d-30fc-5959-9fe3-cef5b6f0be1e |  | note | 4. If doubt exists extend pressure recovery to 90min where pressure drop is to be < 20kPa
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-no-status |  |  | checkpoint | General Methodology Details
text | a02808df-0fb5-5549-ae38-40841b5494dc |  | textbox | Process for removal of air
text | 85a1b965-3653-55a2-8553-859576dd68f5 |  | textbox | Details of water meter
text | 3002a4da-08aa-57a5-9fcd-d329b7eecfb5 |  | textbox | Details of pressure gauge
text | 07ff6dd7-43c2-5b6b-b39b-b6c7277e8899 |  | textbox | Details of pump
text | 3ec96cc5-8e86-51cb-8338-c53f7c7518b3 |  | textbox | Water source
text | 972bce81-2cf5-5316-880d-e59f3b345d13 |  | textbox | Water Disposal
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Checked and Signed by Site Engineer
date | 129aacaa-0e84-549c-b624-9d29130521b5 |  | date | Date:
holdpoint |  |  | signoff | Signature
checkpoint-no-status |  |  | checkpoint | Site Photo Records
checklist-sectioned |  |  | checklist | CS-4002 - Concrete Pump Operator |  |  |  |  | Yes | CS-4002 - Concrete Pump Operator | fe4f3028-0ae0-4b68-9d8c-b900c4e3fb6b
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details:
text | 3ad4de38-4aee-5c6f-bd6b-f47614352567 |  | textbox | Project No.:
date | f1773bcd-0b3a-55a3-b3df-6643c21db8b1 |  | date | Date:
text | 859a16dd-90a2-5cec-b5be-7a10618e1ce1 |  | textbox | Name:
text | 4f97e874-3453-5088-95a7-394695049dc9 |  | textbox | Area:
text | 47705d35-11a3-582f-a34d-e9cda12e6056 |  | textbox | Location:
text | 5887b714-303d-55c4-aa2d-b11bb68cabf7 |  | textbox | Fleet No.:
text | 4d5c0c41-5f8c-543b-9ca2-acae9e0222b2 |  | textbox | Make/Model:
text | ad8b487b-a09d-558b-8198-61fb4379716a |  | textbox | Hour Meter: Start:
text | 4051c9e4-5bee-50df-9fcf-339ef5af5528 |  | textbox | Hour Meter: Finish:
checkpoint-group |  |  | section | CHECK BEFORE STARTING
checkpoint-status |  |  | checkpoint | Grease Points
label | 8e846919-bc69-5258-ac9b-66654363aedb |  | note | PASS = OK
label | e139042c-a2aa-55fd-afe9-8b0705bce703 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Oil / Water Leaks
label | 44ffe946-877d-51f4-9f13-a18174d9cb5a |  | note | PASS = OK
label | 8cdb942b-cc3d-56b1-ac48-5cc56eb5fd63 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Radiator & Fuel Tank Level
label | ee3acc40-4f2f-578e-87e8-17fe82d4b531 |  | note | PASS = OK
label | 5567e4d7-5ff1-58ab-bef8-213bcfc34994 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Engine Oil Level
label | 3dbb125e-d874-54ba-acd2-a422fc310ed8 |  | note | PASS = OK
label | e285fa47-f43e-537f-8c80-315a19de9621 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Oil Level
label | cd03af49-4d8a-57c0-b163-4e6500c6a118 |  | note | PASS = OK
label | a311bc22-eef3-5ad0-b3f9-2c89ff82aeb7 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Fire Extinguisher & First Aid Kit
label | 22cb9ad7-63f6-5420-b810-387b6c94bb3d |  | note | PASS = OK
label | e3bb0335-8ec3-5da5-9219-3df058e96a9b |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Pump set up level & secure
label | cc2d0845-36d0-591e-8bf7-5592a94ca5a0 |  | note | PASS = OK
label | e1649c67-1799-5372-95c2-f7fcc46252c4 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Water Box Full
label | 22b5525b-0bab-589e-a778-70cb16e6ff14 |  | note | PASS = OK
label | 23e9c290-b1f0-5647-9030-d8288ca2da7f |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Guards and Covers in Place
label | 9f900d27-d60c-5819-a4b3-04d52b3be807 |  | note | PASS = OK
label | 2316d994-6dad-5dfb-8075-8367c2122895 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Pipes condition & cleanliness
label | c32e76d8-2314-5562-94df-794730874294 |  | note | PASS = OK
label | 739eae1c-453c-5c9f-8912-b44073bb8820 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
label | a4a8f7c9-5519-53a3-bbb6-c6339ab46efa |  | note | PASS = OK
label | 8d0bc61b-75cb-5cac-8b4a-4d714d5b5929 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Line Adequately Supported
label | 6f7f7b3b-8f88-5fa1-b61b-37a344872f02 |  | note | PASS = OK
label | cb9b128d-43f3-5c90-a3cf-dfbdd4efa1d5 |  | note | FAIL = Defect
checkpoint-group |  |  | section | CHECK AFTER START-UP
checkpoint-status |  |  | checkpoint | Oil Pressure
label | 6e90af60-c7b5-5866-a0f6-2d92ed6b7751 |  | note | PASS = OK
label | 0bab14d1-d1bc-5043-be02-88837cf25b14 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Water Temperature
label | c5960124-aea5-5c88-9d86-d465dd59e4e5 |  | note | PASS = OK
label | 6498b812-7bb9-5566-b219-a0f9b5acba40 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Emergency Stop Button
label | cde7eb6e-cc71-50c2-9a60-8eb899ef0b36 |  | note | PASS = OK
label | 31c83374-d116-5a6a-892f-ba53cfe229dc |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Remote Control Functioning
label | 63ace290-d8c0-53c5-a232-1e62ba3e35bd |  | note | PASS = OK
label | 907d079c-9925-516b-83a7-08a7d56b2ce2 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Oil Pressure
label | 070d0983-0389-5a1a-968e-3b2e883e03b7 |  | note | PASS = OK
label | 0f0c6cd4-cd67-5308-8502-6bc7c6826070 |  | note | FAIL = Defect
checkpoint-group |  |  | section | DEFECTS
checkpoint-status |  |  | checkpoint | DEFECTS:
radio | 8a386d5b-64e5-5530-8244-bcbc9397b5da |  | radio | (Select One) | No Defects Found, Unsatisfactory Condition Found
label | 30d4ff46-c64e-539e-8421-86ab49c805dc |  | note | Defects Corrected By:
text | 5da0dfb0-5792-58be-97ad-171fe0ff57c7 |  | textbox | Name: |  |  | (print)
date | 70ff7f9e-107e-58c8-9fec-52b23d513a88 |  | date | Date:
checkpoint-group |  |  | section | CHECK DURING OPERATION
checkpoint-status |  |  | checkpoint | Deliver Lines Grouted
label | a86b8a75-21f8-5c3e-bf87-4be18db88339 |  | note | PASS = OK
label | ffa81002-a4ba-5b47-b71a-294262d6b70c |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Concrete Slump
label | 81ad622b-c164-5a2b-b896-9ad1079467d1 |  | note | PASS = OK
label | 2ba309d9-b213-5d9d-8ac3-e56c1807dd37 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Pressure during Pumping Max 160 Bar
label | 6c000d27-0f3f-5541-b7d7-5ae1ccbf9e0f |  | note | PASS = OK
label | 5916a961-0d2c-5609-8cc3-ea521bb07c89 |  | note | FAIL = Defect
checkpoint-group |  |  | section | CHECK DURING CLEANING
checkpoint-status |  |  | checkpoint | Direction of Cleaning
label | 592ccb3e-c747-5d26-ae72-442e97e963d2 |  | note | PASS = OK
label | 62a54905-4366-5eac-b288-4a3df2000191 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Reducer & Rubber Hose removed
label | b43b2f2f-6a9c-5e83-adde-8da5d73bbe7d |  | note | PASS = OK
label | 1405723c-435d-5570-b115-12f9a0e9bf0e |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Air manifold and Catch Basket Fitted
label | 629cae30-be07-58b6-b589-29c33efe6ae9 |  | note | PASS = OK
label | 3edb1131-74c9-515f-a39a-8a9fbfc23b59 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Personnel Clear of Discharge End
label | 6d95e179-aa53-5fff-827e-1829c56a1e5a |  | note | PASS = OK
label | ac4f91f6-a1bf-5d40-b4dc-b379a937ce07 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Air Pressure Max 40 Bar
label | 882df109-5f2c-534e-ac0d-b2962b670ea0 |  | note | PASS = OK
label | 44b61534-435c-5307-b2ef-93a4966d34e5 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Equipment Clean
label | 3e8c4d08-0618-593a-b6f9-259bf819f5c0 |  | note | PASS = OK
label | 5e0f592c-3d72-5c0b-b0b3-df186f32c48b |  | note | FAIL = Defect
checkpoint-group |  |  | section | COMMENTS
checkpoint-no-status |  |  | checkpoint | COMMENTS:
label | 9834caad-2fa2-535c-845f-ab2cf474b00d |  | note | This report MUST be handed into your supervisor at the end of each pumping operation
checklist-sectioned |  |  | checklist | CS-4041 - Bearing Installation Record |  |  |  |  | Yes | CS-4041 - Bearing Installation Record | fecbed2a-b02a-4425-8f6b-557078546bac
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 3522ebe1-56d1-53fd-a5b5-68332f4ca392 |  | textbox | Project No.:
checkpoint-group |  |  | section | Pre – Installation
checkpoint-status |  |  | checkpoint | Abutment/Column surface level survey within tolerance
text | 82eb8edc-e60f-572c-bf55-cc742b50aec9 |  | textbox | Initial:
date | cc27ca5e-ed64-5ad8-b682-4fc35e61afbb |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing pockets cleaned and free from debris
text | 92d33d76-47bd-55ff-b22f-b896ca807862 |  | textbox | Initial:
date | 7e6fbeb9-3b9e-52d9-ba21-965bfa6896ae |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing pockets in correct position
text | db622f87-3e4f-5843-86d9-e6bc8e25c627 |  | textbox | Initial:
date | 8f7cf7a4-b7e1-5b9e-8a14-faf79d03a477 |  | date | Date:
checkpoint-status |  |  | checkpoint | Abutment/Column under bearing surface roughened, cleaned and free from debris
text | 99007476-9e61-577a-a6f4-5489791f7ade |  | textbox | Initial:
date | 81bfaab9-cce4-559b-a667-b2d426208f5c |  | date | Date:
checkpoint-status |  |  | checkpoint | Centre lines clearly marked on pier head
text | f8976f6b-7d23-5f27-b912-e5e3c7812303 |  | textbox | Initial:
date | 7bab3034-39e4-5874-b1a4-d8beddf77600 |  | date | Date:
checkpoint-status |  |  | checkpoint | Plastic shims positioned and levelled correctly
text | 7747ffe0-d0cc-58df-aa8a-b214fccf29cd |  | textbox | Initial:
date | 53895c3f-45d6-57a8-bfd7-aba360a1040d |  | date | Date:
checkpoint-status |  |  | checkpoint | All GEWI bars firmly attached to bottom and top, plate and anchor plates fitted using RIC500A epoxy mortar
text | 3a99b195-7962-57e9-8fc8-544e986da90e |  | textbox | Initial:
date | 9f812ea6-4fab-5d3e-be64-6aed7209d63c |  | date | Date:
checkpoint-status |  |  | checkpoint | Approval to lift and position Bearing Unit
text | c92bcc69-00a8-51ee-b9ae-0b6aaa55ec50 |  | textbox | Site Engineer - Name:
date | 8e26bd09-4c23-539b-887d-f1c84719a921 |  | date | Site Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Post – Installation
checkpoint-status |  |  | checkpoint | Top of bearing level checked on all corners
text | 1e47ff08-1e92-5a27-b31c-dd9b16922ca4 |  | textbox | Initial:
date | 9cc22960-6ba5-5404-a4c8-f2f1254e989e |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing orientated correctly (B o/s North G,H o/s South)
text | 000e73a0-b112-5a27-aeec-4260dfa5e4d9 |  | textbox | Initial:
date | 450fbe38-b31d-536e-821d-6433f6a4cfc7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Surveyed centre line of bearing within tolerance
text | e63b8cdc-1452-5d83-a88d-4910012d1c14 |  | textbox | Initial:
date | 8f474f02-088c-558a-8968-d212727457c4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Sufficient space for grouting under bottom plate
text | c576cadd-8c9a-5c26-9ac9-441bd42c04f3 |  | textbox | Initial:
date | 00884d95-a49a-5152-9c0f-6d8affdf62c5 |  | date | Date:
checkpoint-status |  |  | checkpoint | As built survey carried out
text | 0bfd4a60-3faf-50b6-938c-83f73a5cc8b3 |  | textbox | Initial:
date | 085cd624-033c-535d-8bd3-4fd6b67dd6a9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing covered and pockets sealed to prevent filling with debris and water
text | e49e1a13-f3c4-5677-aaed-7696cb48b5a9 |  | textbox | Initial:
date | efce578c-9321-5ff2-90d4-2ffffc9c9154 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing completed & approval to commence given by Design Engineer
text | d70170f9-6ce1-593d-a574-dbd59ee7d03e |  | textbox | Site Engineer - Name:
date | 9933c4f2-de9c-5229-be10-fef53ea90eb4 |  | date | Site Engineer - Date:
text | 10641cee-bd70-5896-9efa-d989c26d809b |  | textbox | CPS Engineer - Name:
date | a57e4ece-23a3-58e8-99d1-6b2d7060a990 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign: