## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | itp |  |  |  |  | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage
section | Pre-Construction
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Drawings and Specification
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check drawings and spec are the latest version.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Check against plans for any discrepancies
label | Records - Survey receipt
checkpoint | 3 - Material Approval
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Materials as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint | 4 - Location of underground services
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure undderground services are positively identified and asbuilt. If the service conflicts with the design confirm resiolution with CPS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Drainlayer Qualifications
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Drainlayer Certs
section | Construction
checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check subgrade with visual inspection and
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | Records - Subcontractor QA Records
checkpoint | 7 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures