## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  |  | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails)
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Erosion and Sediment Control Plan
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Need ESCP before construction begins
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Erosion and Sediment Control Plan must be submitted to the design team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Implement ESCP approved by environmental team
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Road Safety Barriers (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proprietary barrier system type and installation methodology
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Approval from Design Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Road Safety Barriers (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Propritary barrier system compliance records
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained
checkpoint | 3 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E soil nail
label | ○ Class II corrosion protection
label | ○ Lengths and diameters shown on drawings are the minimum required
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete quality plan
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Name, qualification and expoerience of concrete works inspector
label | – Form and content of concrete placement card
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (3)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of concrete supply plant, copy od certificate of audit for plant
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Plant test Results
label | – ASR Compliance Records
label | Records - Email
checkpoint | 6 - Material Compliance and Methodology Approval (4)
label | Detail - Concrete work plan
label | Frequency - At least 10 days before commencing works oinsite
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Email
checkpoint | 6 - Material Compliance and Methodology Approval (5)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Reinforcing steel manufactureers test reports and certificates
label | Frequency - Prior to undertaking works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including despatch records
label | Records - Email
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | Records - Email
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grout checked if its free from lumps & segregation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - If required
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
checkpoint | 13 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less.
label | ○ The construction team shall protect the face of the excavation from damage at all times.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | Frequency - Prior to Trial
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Records - Photos, Site Diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - (2)
label | Detail - Drill hole
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | ○ Submit all installation records for each soil nail and pile.
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 31 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert soil nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Installation records shall include:
label | – Length of bar
label | – Depth of drill hole
label | – Inclination/Verticality achieved
label | – Level of grout placed
label | – Batch numbers associated with grout placed in each hole
label | Records - Subcontractor QA Records
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Including :
label | – Concrete despatch records
label | – Compression test results
label | ○ Must notify CPS for any failed result and cease works until resolved
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 33 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 34 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Subcontractor QA Records
checkpoint | 36 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 37 - Testing of Soil Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | Records - Certifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 38 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 39 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 40 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 41 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 42 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 43 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 44 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 45 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 46 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 47 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 48 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 49 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - During and at completion of work.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 50 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 51 - Completion Sign Off From Fields Below
label | Records - Signatures