## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  |  | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails)
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation clearance & any bulk earthworks is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - QA-6002 - Tree Felling & Vegetation Clearance
label | Records - QA-6002 Process Control Plan Tree Felling & Vegn Clearance Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Shotcrete Mix Design & Work Method Statement approved by Design Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | Records - Lab Test Results/ NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | Records - Lab Test Results/ NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Bench to be 2m of less - the top of the row not to be above 1.5m above the bench
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trial installation of Bolts/Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill hole, install Bolt/Nail, install Grout
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test after a 7 day period. Load up to the specified requirements with the Design Engineer overseeing proceedings
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Design Engineer to observe testing and provide feedback on a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Installation of Bolts/Nails on the created working bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill holes as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure lengths are that specified on the drawings
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout - take sample of each truck load delivered to site
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Compression cylinders to be tested at Lab
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Testing of Bolts/Nails - after 7 days when the Grout strength has reached 20Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - Design Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of Design Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Design Engineer to give approval via a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Remove working bench and continue with same process as above
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Photos
checkpoint | 16 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Lab Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by Design Engineer & Approval given to carry on with works
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 23 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT