## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | itp |  |  |  |  | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | 770b6e32-6ce5-42cc-a44f-b57055e2d09d
section | Pre-Construction
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Drawings and Specification
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Check drawings and spec are the latest version.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Check against plans for any discrepancies
label | Records - Survey receipt
checkpoint | 3 - Material Approval
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Materials as per design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint | 4 - Location of underground services
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure undderground services are positively identified and asbuilt. If the service conflicts with the design confirm resiolution with CPS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Drainlayer Qualifications
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Drainlayer Certs
section | Construction
checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Check subgrade with visual inspection and
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | Records - Subcontractor QA Records
checkpoint | 7 - Surface finish visual inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site walk over
label | Frequency - Post Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation | itp |  |  |  |  | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation | c13fcb74-c6bb-4ccf-af26-adfa7f821e68
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Earthworks and pavement construction shall be completed prior to barrier installation.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - OFI or NTD/NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - TNZ M/23:2009
label | Records - Manufacturing certificates and delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | Records - CS-4117
checkpoint | 8 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 9 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 11 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  |  | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | 94259252-c925-4900-855f-1a4e517fa531
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Erosion and Sediment Control Plan
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Need ESCP before construction begins
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Erosion and Sediment Control Plan must be submitted to the design team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Implement ESCP approved by environmental team
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Road Safety Barriers (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proprietary barrier system type and installation methodology
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Approval from Design Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Road Safety Barriers (2)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Propritary barrier system compliance records
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained
checkpoint | 3 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - In accordance with TNZ F/1.
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Grade 500E soil nail
label | ○ Class II corrosion protection
label | ○ Lengths and diameters shown on drawings are the minimum required
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Concrete quality plan
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Name, qualification and expoerience of concrete works inspector
label | – Form and content of concrete placement card
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Material Compliance and Methodology Approval (3)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Details of concrete supply plant, copy od certificate of audit for plant
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including:
label | – Plant test Results
label | – ASR Compliance Records
label | Records - Email
checkpoint | 6 - Material Compliance and Methodology Approval (4)
label | Detail - Concrete work plan
label | Frequency - At least 10 days before commencing works oinsite
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Email
checkpoint | 6 - Material Compliance and Methodology Approval (5)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Reinforcing steel manufactureers test reports and certificates
label | Frequency - Prior to undertaking works
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Including despatch records
label | Records - Email
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | Frequency - Three weeks prior to pouring concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | Records - Email
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Grout checked if its free from lumps & segregation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | Frequency - Prior to Commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - If required
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
checkpoint | 13 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less.
label | ○ The construction team shall protect the face of the excavation from damage at all times.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | Frequency - Prior to Trial
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Records - Photos, Site Diary
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - (1)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - (2)
label | Detail - Drill hole
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | ○ Submit all installation records for each soil nail and pile.
checkpoint | 29 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 31 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Insert soil nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 32 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Installation records shall include:
label | – Length of bar
label | – Depth of drill hole
label | – Inclination/Verticality achieved
label | – Level of grout placed
label | – Batch numbers associated with grout placed in each hole
label | Records - Subcontractor QA Records
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Including :
label | – Concrete despatch records
label | – Compression test results
label | ○ Must notify CPS for any failed result and cease works until resolved
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 33 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 34 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | Records - CONQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 35 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Subcontractor QA Records
checkpoint | 36 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 37 - Testing of Soil Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | Records - Certifications
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 38 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 39 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 40 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - CPS Engineer to give approval via a NTC
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 41 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 42 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 43 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 44 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Test results to CONQA Procore
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 45 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 46 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 47 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 48 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 49 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - During and at completion of work.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 50 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Asbuilts, NCR's and RFI's
checkpoint | 51 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  |  | ITP - Tupiko Stream Bridge - Scour Protection - H1501A - Reinforced Slope (Rock Bolts, Soil Nails) | 2973051b-ac2f-47a6-b7ed-f70f24c0cc9f
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Clearing & Earthworks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Before setout of the reinforced slope method all vegetation clearance & any bulk earthworks is to be completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - QA-6002 - Tree Felling & Vegetation Clearance
label | Records - QA-6002 Process Control Plan Tree Felling & Vegn Clearance Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Shotcrete Mix Design & Work Method Statement approved by Design Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | Records - Lab Test Results/ NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Mix design to be approved by Design Engineer before commencing construction
label | Records - Lab Test Results/ NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Working Bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Bench to be 2m of less - the top of the row not to be above 1.5m above the bench
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trial installation of Bolts/Nails
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill hole, install Bolt/Nail, install Grout
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test after a 7 day period. Load up to the specified requirements with the Design Engineer overseeing proceedings
label | Frequency - Test
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | Conformance Criteria - Design Engineer to observe testing and provide feedback on a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Installation of Bolts/Nails on the created working bench
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Drill holes as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails as specified
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure lengths are that specified on the drawings
label | Records - Subcontractor QA Records
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Grout - take sample of each truck load delivered to site
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Compression cylinders to be tested at Lab
label | Records - Lab Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Install Bolts/Nails washers & nuts
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Testing of Bolts/Nails - after 7 days when the Grout strength has reached 20Mpa
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - Load testing - Design Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final inspection of Design Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Design Engineer to give approval via a NTC
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Remove working bench and continue with same process as above
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Photos
checkpoint | 16 - Shotcreting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Lab Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Surface Inspected by Design Engineer & Approval given to carry on with works
label | Records - NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Post Construction Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey final position of bolts for as-built purposes
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Survey report complete and conforms to specification
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 22 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All subcontractor documentation to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Subcontractor QA Records
checkpoint | 23 - As-built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Frequency - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Records - Survey receipts, As-built plans
holdpoint | AUTHORITY HOLDPOINT