## Sheet1
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | F2601A - Turitaka Slip Repair |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: |  |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No:F2601 |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:SH35 RP180/5
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1: RECEIVING INSPECTIONS
1.1 | 4t Ecogreen/Kyowa bags | W | Consistency with Construction Specifications 2-U3435.SM(6) SH11 | Prior to commencement | Manufacturers certificate | Purchased from Bluemont or similar approved Traceability of all materials delivered to site | Material cert, delivery dockets | Site Engineer | CPS Engineer
1.2 | Screen river run | H | Consistency with Construction Specifications 2-U3435.SM(6) SH11/SH12 | Prior to commencement | Supplier material test certificate | River run to fill bags 50mm to 175mm screened rock < 2%fines Provide written evidence of supply source to CPS Engineer prior to delivery | Material source test results | Site Engineer | CPS Engineer
1.3 | Class D A39 Geotextile | W | Consistency with Construction Specifications 2-U3435.SM(6) SH11 TNZ F/7 | Prior to commencement | Manufacturers certificate | TNZ F/7 filtration class 1 strength Class D Traceability of all materials delivered to site | Material cert, delivery dockets | Site Engineer
1.4 | Granular fill AP65 | W | Consistency with Construction Specifications 2-U3435.SM(6) SH11 | Prior to commencement | Suppliers grading certificate | Hard durable well graded free draining material 65mm not more than 5% passing 75 micron screen free from organic fines and vegetive matter. Traceability of all materials delivered to site | Material cert, delivery dockets | Site Engineer
Section 2: IN PROGRESS INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawings & specifications 2-U3435.SM(6) | Prior to commencement | Survey | Set out extents of works and check against design drawings. Check and agree on set-out and number of Ecogreen Rock bags required with CPS Engineer | Survey receipt | Site Engineer | CPS Engineer
2.2 | Excavation | H | Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1 | During Construction | Visual inspection | Comply with TNZ F/1. Remove and clear deleterious material when excavating to formation level. Excavated material to be disposed of off-site. CPS engineer to inspect and approve the foundation level material | Photo's, CPS COR report | Site Engineer | CPS Engineer
2.3 | Granular Backfill AP65 | H | Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1 | At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer | Clegg hammer or NDM testing | Comply with TNZ F/1. Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer | Test Reports | Site Engineer | CPS Engineer
2.4 | Rock Bag installation | H | Consistency with Construction Drawings & specifications 2-U3435.SM(6) | During Construction | Visual Inspection | Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V. The final layer will be determined by the CPS Engineer on site | Photo's, CPS COR report | Site Engineer | CPS Engineer
2.5 | Class D (A39) Geotextile | W | Consistency with Construction Drawings & specifications 2-U3435.SM(6) | During Construction | Visual Inspection | Installation between the AP65 fill and rock filled bags. The fabric shall be laid and overlapped as per manufacturers recommendations | Photo's | Site Engineer
2.6 | Bulk Fill Placement access roads | M | Consistency with Construction Drawing 2-U3435.SM(6) SH13, NZS4431:2022, TNZ F/1 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade | Bulk Fill Earthworks checksheet (CS-4020), Photo's | Site Engineer
2.7 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 3 : Final Inspection and Handover
3.1 | Completion | H | Consistency with Construction Drawings & specifications 2-U3435.SM(6) | At completion of Lot | Visual inspection | Upon completion of the works the CPS engineer will be given the opportunity to inspect the works having been done to the required standard and sign it off for completion | CPS COR Report | Site Engineer | CPS Engineer
3.2 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
3.3 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: