## Earthworks - Bulk Cut
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | F3002G Mangahuini Sheet Pile Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Earthworks - Bulk Cut |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | 18.12.2023 |  | Quality Eng.
Lot No:F3002G |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: SH35 R.5 RP.225/9.44
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Set out extents of fill and check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer | CPS Engineer
2 | Excavation | W | Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions | During construction | Visual Inspection | Consistency with Construction Drawing | Photo's | Site Engineer
|  | H | Existing ground/bank & foundation for rock toe to be excavated/trimmed to remove any deleterious and loose material | During construction | Visual Inspection | CPS Engineer to inspect and approve trimmed surface & founding level material before proceeding further. | CPS COR Report, Photo's | Site Engineer | CPS Engineer
4 | Geotechnical Inspection | H | Any areas of concern with the face at any time, ensure the Geotechnical Engineer is involved and any changes that are required are documented | During construction | Visual Inspection | NTC/NFD | CPS COR Report, Photo's | Site Engineer | CPS Engineer
5 |  | H | Any changes to the design (soil nails, rock bolts, shotcrete etc.) are to documented individually | During construction | Document Review | NTC/NFD | CPS COR Report, Photo's | Site Engineer | CPS Engineer
6 | Formation | H | Once cut is down to Formation level complete Scala check sheet | At completion of section | Document Review | As per design/drawings | CS-4000 1M Scala check sheet | Site Engineer | CPS Engineer
8 | As-built Survey | H | Ensure cut/fill slopes comply with design prior to next process taking place | Prior to placing topsoil/pavement/ finished surfaces | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
9 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
10 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: