## Precast Installation
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Precast Dolosse Installation |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | 08.12.2023 |  | Quality Eng.
Lot No: F3002G |  |  |  | Corresponding Work Instruction: |  | (insert Sharepoint link to Construction Work Plan folder here) |  | Compliance with Work Instructions and Specifications
Detailed Location: SH35 R.5 RP.225/9.44
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Precast Installation | W | Delivery Dockets are collected and signed before precast materials are removed from the truck | Prior to commencement | Document Review |  | Delivery Dockets | Site Engineer
3 |  | W | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Prior to unloading | Visual inspection |  | Photo's | Site Engineer
4 |  | H | All Steel brackets, bolts/nuts & steel wire ropes must be inspected on delivery. Any damaged items shall be isolated, repaired or replaced | Prior to commencement | Visual inspection, Document review | Comply with AS/NZS 5131. Brackets will be manufactured from 16mm thick 300 grade steel plate. Steel wire ropes shall be 20mm in diametre. Any welding required to be approved in writing by CPS Engineer | Photo's, CPS COR Report, Manufacturer Test Certificates, Welding tickets | Site Engineer | CPS Engineer
5 |  | W | Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the pre-start/OFI | Prior to commencement | Document Review, Visual inspection |  | OFI, Photo's | Site Engineer
6 |  | H | Precast Components are to be installed in accordance with the design/drawing. Each unit is to be butted tightly against the adjacent unit to present a coherent mass | Prior to commencement | Visual inspection | The position of the dolos groynes will be set out and agreed to with the CPS Engineer | Photo's, CPS COR Report | Site Engineer | CPS Engineer
7 |  | H | Dolosse’s will be secured in position using 20mm diameter steel wire ropes passed through the lifting eyes of the Dolosse’s and secured to brackets welded onto the existing sheet pile wall. | Prior to commencement | Visual inspection | As per design/drawings. Welding to be inspected and be approved in writing by CPS Engineer | Photo's, CPS COR Report, Welding tickets | Site Engineer | CPS Engineer
8 | As-built Survey | H | Ensure cut/fill slopes comply with design prior to next process taking place | Prior to placing topsoil/pavement/ finished surfaces | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
9 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
10 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: