## Sheet1
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | F3002H Mangahauini Bridge Scour |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | 8.12.2023 |  | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage: SH35 RS225 RP6.100
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Rock Armour | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | Prior to commencement | Submission | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall comply with Grading as per design (Rock Rip Rap Grading table) with a minimum specific Gravity SG of 2350kg/m3. | Material source test results, Delivery Dockets | Site Engineer | CPS Engineer
1.2 | Class E A49 Geotextile | W | F3002H Mang Bridge No3 Repair Strategy IFC by SMC, NZTA F/7 | Prior to commencement | Manufacturers certificate | NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
Section 2 : IN PROGRESS INSPECTIONS (Buttress)
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | Prior to commencement | Visual inspection | Remove and clear the vegetation | Photo's | Site Engineer
2.3 | Subgrade Excavation | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | During Construction | Visual inspection | Engineer to assess foundation material suitability | CPS COR report | Site Engineer | CPS Engineer
2.4 | Subgrade Inspection | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | Per area as required | Inspection by the Geotechnical Design Manager | Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences | CPS COR report | Site Engineer | CPS Engineer
2.5 | Form and cut fill batter as per design | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. | Survey as builts | Site Engineer | CPS Engineer
2.6 | Class E (A49) Geotextile placement along the face of fill batter | W | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | During Construction | Visual Inspection | Class E geotextile to be placed between the rock armour and bulk fill | Photo's | Site Engineer
2.7 | Rock Armour placement along the face of fill embankment | W | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | During Construction | Visual Inspection, survey | Install Rock riprap as per design; material to comply with requirements set out in Rock Rip Rap Grading Table located in design documentation | Photos, Survey as builts | Site Engineer
2.8 | Rock Armour key into ground | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | During Construction | Visual Inspection, survey | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. | CPS COR report and survey as built | Site Engineer | CPS Engineer
2.9 | As-built Survey | H | F3002H Mang Bridge No3 Repair Strategy IFC by SMC | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Section 3 : FINAL INSPECTION & HANDOVER
3.1 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
3.2 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: