## Construction ITP
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: |  |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | F3202A - Culvert ID 614 |  | Name / Signature | Name / Signature | Site Engineer
|  |  |  | Inspection & Test Plan / Checklist |  |  | 08.12.2023 |  | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-??-???? |  | Compliance with Work Instructions and Specifications
Detailed Location: Fault IDs (614)
Chainage : SH35 / RS250 / RP6.9
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Specification/Drawings Reference | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
Section 1 : RECEIVING INSPECTIONS
1.1 | Rock Armour (D50=450) | H | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Supplier material test certificate | Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3. Rock size to be confirmed by CPS Engineer | Material source test results | Site Engineer | CPS Engineer
1.2 | Bulk Fill (GAP65/GAP100) or similar | H | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Supplier material test certificate | Should comprise clean granular aggregate and have broken faces. Material source testing | Material source test results | Site Engineer | CPS Engineer
1.3 | Class D A39 Geotextile | W | Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 | Prior to commencement | Manufacturers certificate | Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.4 | Class E A49 Geotextile | W | Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 | Prior to commencement | Manufacturers certificate | Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill | Material certificate(s) | Site Engineer
1.5 | Megaflow strip drain or drainage blanket for seepage if encountered | W | Buttress typical details and F3202B-DS-GT-RP-0001 | Prior to commencement | Manufacturers certificate | Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved. | Material certificate(s) | Site Engineer
1.6 | AP40 (Basecourse) | W | TNZ M/4 | Prior to commencement | Submission, Testing | Comply with TNZ M/4 specification Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery Dockets | Site Engineer
1.7 | AP65 (Sub-base) | H |  | Prior to commencement | Submission, Testing | Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak) All fill material to approved by CPS Engineer | Lab test reports, Delivery Dockets | Site Engineer | CPS Engineer
1.8 | Grade 3/5 Chip | W | NZTA M/6 | Prior to commencement | Submission, Testing | Comply with NZTA M/6 specification Source property testing Traceability of all materials delivered to site | Lab test reports, Delivery Dockets | Site Engineer
1.9 | Cement Material cert | W |  | Prior to commencement | Submission |  | Material certificate(s) | Site Engineer
1.1 | Bitumen | W | TNZ M/1 | Prior to commencement | Submission | Binder to meet TNZ M/1 standard. E2 Certificate | E2 Certificate | Site Engineer
1.11 | Galvanised Traversable grate | W | F3202A-Culvert ID 614 | Prior to commencement | Submission | Galvanised Traversable grate mounted on headwall | Manufacturer cert, Delivery dockets | Site Engineer
1.12 | Precast Headwall | W | F3202A-Culvert ID 614 | Prior to commencement | Submission | Delivery Dockets are collected and signed before precast headwall materials are removed from the truck. | Manufacturer cert, Delivery dockets | Site Engineer
1.13 | Precast RCRRJ 1050 pipe | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614, AS/NZS 4058 | Prior to commencement | Submission | Delivery Dockets are collected and signed before precast pipe materials are removed from the truck. Class 4 RCRRJ 1050 pipe to comply with AS/NZS 4058 | Manufacturer cert, Delivery dockets | Site Engineer
1.14 | Precast materials | H | F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001 | Prior to unloading | Visual inspection | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed | Photo's | Site Engineer | CPS Engineer
1.15 | Rock Rip-Rap | H | F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001 | Prior to commencement | Visual inspection | D50=150mm Rock Rock size to be confirmed by CPS Engineer | Photo's | Site Engineer | CPS Engineer
1.16 | Hydroseed | W | F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001 | Prior to hydroseeding commencing | Document review |  | Delivery dockets
1.17 | 35 Mpa Concrete | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | Prior to commencement | Submission | Mix design 35 Mpa concrete @ 28 days for haunching | Mix design cert, dockets | Site Engineer
1.18 | AP20 (Bedding material) | W |  | Prior to commencement | Submission | Source property testing | Lab test reports, Delivery dockets | Site Engineer
1.19 | D16 Rebar | W | AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001 | Prior to commencement | Submission | Comply with AS/NZS 4671 & NZS3109 Shall be D16 rebar for concrete pipe haunching as per design | Mill Cert, Delivery dockets | Site Engineer
1.2 |  | H | AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001 | Prior to cutting or bending on site | Visual inspection | Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer | Photo's, CPS COR report | Site Engineer | CPS Engineer
Section 2 : IN PROGRESS INSPECTIONS
2.1 | Survey Setout | H | Consistency with Construction Drawing | Prior to commencement | Survey | Set out extents of fill and check against design drawings | Survey receipt | Site Engineer | CPS Engineer
2.2 | Vegetation Clearance and removal of loose debris | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | Prior to commencement | Visual inspection | Remove and clear the vegetation | Photo's | Site Engineer
Section 3 : CULVERT OUTLET EXTENSION
3.1 | Foundation compliance | W | F3202A-Culvert ID 614 | During Construction | Scala testing | Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required | 1M Scala check sheet (CS-4000), Scala test results | Site Engineer
3.2 | Foundation compliance | H | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | CPS to inspect and approve formation level at outlet | CPS COR report | Site Engineer | CPS Engineer
3.3 | Trenching and Excavation | W |  | During Construction | Visual inspection | Ensure trench width is sufficient to provide enough space on either side of the pipe | Photo's | Site Engineer
3.4 | Trenching and Excavation | W | F3202A-DS-GT-RP-0001 | During Construction | Survey | Inspect trench profile and ensure it is correct to lines and levels as per design | Survey As-Builts | Site Engineer
3.5 | Pipe and headwall Bedding (AP20) | W | AS/NZS 3725:2007 | During Construction | Visual inspection | Comply with AS/NZS 3725:2007 Ensure correct thickness of bedding is placed and compacted. 100mm thick bedding for <1500mm dia pipe | Photo's | Site Engineer
3.6 | Pipe and headwall Bedding | H | NZTA F3 | During Construction | Clegg Hammer testing | Ensure bedding material is compacted by Clegg (TBC by CPS on-site) | Test report | Site Engineer | CPS Engineer
3.7 | Pipe and headwall laying | W |  | During Construction | Visual inspection | Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm | Survey As-Builts, Photo's | Site Engineer, Project Engineer
3.8 | Pre-Backfill inspection | H | NZTA F3 | During Construction | Visual inspection | Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface. Check for gaps and/or defects and check pipe alignment for straightness | Photo's, CPS COR report | Site Engineer | CPS Engineer
3.9 | Backfilling (Haunching AP65) | W | NZS 4402:1986, Test 4.1.3 | During Construction | NDM Testing | Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material. 95% of MDD shall be achieved | NDM test reports | Site Engineer
3.1 | Existing road side Swale | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | Reshape and form both ends of road side swale to match the rock chute invert. | Photo's | Site Engineer
3.11 | Swale geotextile installation | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | Class D geotextile to be placed in the swale prior to rock placement and be laid/overlapped as per manufacturers recommendations | Photo's | Site Engineer
3.12 | Swale rock line | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | >1:50 slope rock line D50=150mm, 300mm minimum thickness over Class D geotextile to be placed | Photo's | Site Engineer
3.13 | Swale rock line alignment | H | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | At completion | Survey | Slope rock line should be >1:50 slope | Survey As-Builts | Project Engineer | CPS Engineer
3.14 | Outlet rock chute | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Rocks should be placed to a length of 1800mm in front of the headwall. | Photo's | Site Engineer
3.15 | Geotextile installation | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations | Photo's | Site Engineer
3.16 | Rock Riffle | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Survey, Visual Inspection | Largest rocks 900mm to be installed closely to form an arc shape facing upstream. Reduce grading of rocks towards the toe of the slope. Wash gravel/grit over to fill all voids. Rock riffle to be installed to approx. 1V:5H slope and tie into existing streambed minimum 200mm | Photo's, Survey As-Builts | Site Engineer
3.17 | Slope above the rock chute | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Survey, Visual Inspection | Daylight at maximum 1:2 existing ground and hydroseed / cover with pinned biodegradable erosion control mattting | Photo's, Survey As-Builts | Site Engineer
3.18 | Galvanised Traversable grate installation | W | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | Grate mounted on headwall in accordance with manufacturer's recommendation | Photo's | Site Engineer
Section 4 : BUTTRESS TYPE A
4.1 | Class D (A39) Geotextile installation on the excavated face | W | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill. | Photo's | Site Engineer
4.2 | Megaflow strip or drainage blanket installation for seepage if Encountered | H | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Visual Inspection | Engineer to assess drainage location suitability. Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | Photo's, Drainage Line record check sheet (CS-4025) | Site Engineer | CPS Engineer
4.3 | Bulk Fill placement | M | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Photo's | Site Engineer
4.4 | Bulk Fill Compaction | M | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 | Compaction test reports | Site Engineer
4.5 | Form and cut fill batter as per design 2H:1V | H | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 2H:1V | Photo's, Survey As-Builts | Project Engineer | CPS Engineer
4.6 | Rock Armour Placement | W | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Survey, Visual Inspection | 2 x Layers of Rock riprap (D50=450mm diameter) | Photo's, Survey As-Builts | Site Engineer
4.7 | Rock Armour key into ground | H | Buttress typical details A and F3202-Culvert ID 614 | During Construction | Survey, Visual Inspection | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide. | Photo's, Survey As-Builts | Site Engineer | CPS Engineer
Section 5 :CULVERT INLET EXTENSION
5.1 | Foundation compliance | W | F3202A-Culvert ID 614 | During Construction | Scala testing | Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required | 1M Scala check sheet (CS-4000), Scala test results | Site Engineer
5.2 | Foundation compliance | H | F3202A-DS-GT-RP-0001, F3202-Culvert ID 614 | During Construction | Visual inspection | CPS to inspect formation level at outlet | CPS COR report | Site Engineer | CPS Engineer
5.3 | Trenching and Excavation | W |  | During Construction | Visual inspection | Ensure trench width is sufficient to provide enough space on either side of the pipe | Photo's | Site Engineer
5.4 | Trenching and Excavation | W |  | During Construction | Survey | Inspect trench profile and ensure it is correct to lines and levels as per design | Survey As-Builts | Site Engineer
5.5 | Pipe and Bedding (AP20) | W | AS/NZS 3725:2007 | During Construction | Visual inspection | "Comply with AS/NZS 3725:2007 Ensure correct thickness of bedding is placed and compacted. 100mm thick bedding for <1500mm dia pipe" | Photo's | Site Engineer
5.6 | Pipe and Bedding (AP20) | H | NZTA F3 | During Construction | NDM testing | Ensure bedding material is compacted by Clegg (TBC by CPS on-site) | Test report | Site Engineer | CPS Engineer
5.7 | Pipe laying | W | NZTA F3 | During Construction | Visual inspection | Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm | Photo's, Survey As-Builts | Site Engineer, Project Engineer
5.8 | Pre-Backfill inspection | H | NZTA F3 | During Construction | Visual Inspection | Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface. Check for gaps and/or defects and check pipe alignment for straightness | CPS COR report, Photo's | Site Engineer | CPS Engineer
5.9 | Backfilling (Haunching AP65) | W | NZS 4402:1986, Test 4.1.3 | During Construction | NDM Testing | Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material. 95% of MDD shall be achieved | NDM test reports | Site Engineer
5.1 | Concrete haunch around inlet | H | F3202 Stormwater inlet details, NZS 3109 | During Construction | Testing and visaul inpsection | 300mm concrete apron to be poured around the inlet. 35MPa concrete @ 28Days. | Concrete compression test results and Photo's | Site Engineer | CPS Engineer
5.11 | Concrete haunch around inlet | H | F3202 Stormwater inlet details, NZS 3109 | During Construction | Visual inspection | 300mm concrete apron around the inlet with D16 reinforcing bar centrally, 50mm NOM. Cover. | CPS COR report, Photo's | Site Engineer | CPS Engineer
5.12 | Inlet pipe cut | H | F3202 Stormwater inlet details | During Construction | Visual inspection | Mitre pipe at 1V:2H. Grind back exposed steel 20mm and place bead of epoxy mortar on cut surface | CPS COR report, Photo's | Site Engineer | CPS Engineer
5.13 | Rock chute and rocks around inlet | W | F3202 Stormwater inlet details | During Construction | Visual inspection | Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Extend rocks to top of the embankment. | Photo's | Site Engineer
5.14 | Geotextile installation | W | F3202 Stormwater inlet details | During Construction | Visual inspection | Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations | Photo's | Site Engineer
Section 6 : BUTTRESS TYPE C
6.1 | Class D (A39) Geotextile installation on the excavated face | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill. | Photo's | Site Engineer
6.2 | Megaflow strip or drainage blanket installation for seepage if Encountered | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Engineer to assess suitable drainage location suitability. Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required. | Photo's, Drainage Line record check sheet (CS-4025) | Site Engineer | CPS Engineer
6.3 | Bulk Fill placement | M | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade. | Photo's | Site Engineer
6.4 | Bulk Fill Compaction | M | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Testing | A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 | Compaction test reports | Site Engineer
6.5 | Form and cut fill batter as per design 2H:1V | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Survey | Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 2H:1V | Survey As-Builts | Site Engineer | CPS Engineer
6.6 | ClassE (A49) Geotextile placement along the face of fill batter | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection | Class E geotextile to be placed between the rock armour and bulk fill and be laid/overlapped as per manufacturers recommendations | Photo's | Site Engineer
6.7 | Rock Armour placement along the face of fill embankment | W | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection, Survey | 2 x Layers of Rock riprap (D50=450mm diameter) | Photo's, Survey As-Builts | Site Engineer
6.8 | Rock Armour key into ground | H | Buttress typical details C and F3202B-DS-GT-RP-0001 | During Construction | Visual Inspection, Survey | Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide. | CPS COR report, Survey As-Builts | Site Engineer | CPS Engineer
Section 7 : IN PROGRESS INSPECTIONS (Pavement)
7.1 | Saw cut existing pavement | W |  | Prior to pavement construction | Visual inspection | Smooth and straight saw cut | Photo's | Site Engineer
7.2 | Subgrade construction | W | TNZ B2 | Every 20m | NDM testing | 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92% | Test reports | Site Engineer
7.3 | Subgrade Cement Application rate | W |  |  | Bag test | 2% cement stabilisation at 250mm deep subgrade | Bag test records | Site Engineer
7.4 | Sub-base construction | W | TNZ B2 | Every 20m | NDM testing | 200mm thick AP65 sub-base compacted to a minimum dry density of 95% Average 95% of MDD with nothing less than 92% | Test reports | Site Engineer
7.5 | Sub-base construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports | Site Engineer
7.6 | Sub-base construction | H | TNZ B2 |  | Survey | Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey As-Builts | Project Engineer
7.7 | Basecourse construction | W | TNZ B2 | Every 20m | NDM testing | 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98% Average 98% of MDD with nothing less than 95% | Test reports, Photo's | Site Engineer
7.8 | Basecourse Cement application rate | W |  |  | Bag test | 2% cement stabilisation at 150mm deep basecourse | Bag test records | Site Engineer
7.9 | Basecourse construction | W | TNZ B2 | Every 20m | Survey | Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction | Survey As-Builts | Project Engineer
7.1 | Basecourse construction | W | TNZ B2 | Every 20m | Clegg Hammer testing | CIV>=25 | Test reports, Photo's | Site Engineer
7.11 | Basecourse construction | H | TNZ B2 | Before sealing | Pre-seal checksheet | Mosaic surface | Photo's, Pre-seal checksheet (CS-4060) | Site Engineer | CPS Engineer
7.12 | Applying Bitumen | W | NZTA M/6 |  | Visual inspection | Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours | Spray report, Pre-seal checksheet (CS-4060), Photo's | Site Engineer
7.13 | Degree of saturation | W | NZTA M/6 | Before sealing | Pre-seal checksheet | Degree of saturation should not exceed 80% | Pre-seal checksheet (CS-4060) | Site Engineer
7.14 | Chip seal laying | W | NZTA M/6 | During Construction | Submission | Grade 3 and 5 chip seal | Material certificate(s), Photo's | Site Engineer
Section 8 : FINAL INSPECTION & HANDOVER
8.1 | As-built Survey | H | 2-U3436.BM(14) S01-S03 | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
8.2 | CCTV inspections of culverts | H |  | At completion | CCTV inspection | CCTV to inspect the alignment, no defects, joints are sealed properly | CCTV footage | Site Engineer | CPS Engineer
8.3 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
8.4 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on H51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gurdeep Singh I suggest putting your biodegradeable matting in the materials section at the top of this ITP and request material certs for records