## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Turitaka Slip Repair - F2601A - Works | itp |  |  |  |  | ITP - Turitaka Slip Repair - F2601A - Works
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - 4t Ecogreen/Kyowa bags
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Purchased from Bluemont or similar approved
label | ○ Traceability of all materials delivered to site
label | Records - Material cert, delivery dockets
checkpoint | 1.2 - Screen river run
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11/SH12
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - River run to fill bags 50mm to 175mm screened rock < 2%fines
label | ○ Provide written evidence of supply source to CPS Engineer prior to delivery
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11 TNZ F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D Traceability of all materials delivered to site
label | Records -
checkpoint | 1.4 - Granular fill AP65
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Suppliers grading certificate
label | Conformance Criteria - Hard durable well graded free draining material 65mm not more than 5% passing 75 micron screen free from organic fines and vegetive matter.
label | ○ Traceability of all materials delivered to site
label | Records - Material cert, delivery dockets
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of works and check against design drawings. Check and agree on set-out and number of Ecogreen Rock bags required with CPS Engineer
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Remove and clear deleterious material when excavating to formation level. Excavated material to be disposed of off-site. CPS engineer to inspect and approve the foundation level material
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | Records - Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Rock Bag installation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | ○ The final layer will be determined by the CPS Engineer on site
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Class D (A39) Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.6 - Bulk Fill Placement access roads
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3435.SM(6) SH13, NZS4431:2022, TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | Records - Bulk Fill Earthworks checksheet (CS-4020), Photo's
checkpoint | 2.7 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Completion
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Upon completion of the works the CPS engineer will be given the opportunity to inspect the works having been done to the required standard and sign it off for completion
label | Records - CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.3 - Completion Sign Off From Fields Below
label | Records - Signatures