## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Photo's
checkpoint | 2 - Excavation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Existing ground/bank & foundation for rock toe to be excavated/trimmed to remove any deleterious and loose material
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to inspect and approve trimmed surface & founding level material before proceeding further.
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Geotechnical Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any areas of concern with the face at any time, ensure the Geotechnical Engineer is involved and any changes that are required are documented
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - NTC/NFD
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any changes to the design (soil nails, rock bolts, shotcrete etc.) are to documented individually
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - NTC/NFD
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Formation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Once cut is down to Formation level complete Scala check sheet
label | Frequency - At completion of section
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - As per design/drawings
label | Records - CS-4000 1M Scala check sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures