## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ground Improvements / Dig Outs for soft areas
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Granular Fill (AP65)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Granular fill material to fill any voids in the batter slope shall be crushed AP65 material
label | Frequency - Prior to receiving rock rip rap
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - AP65 shall be a hard, durable, well graded, free draining material with a maximum particle size of 100mm and 65mm respectively and not more than 5% by mass passing a 75- micron sieve. The fill material shall be free of organic fines and vegetative matter.
label | Records - Delivery Dockets, Material certificate(s)
checkpoint | 4 - Subgrade Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Subgrade Cut and Fill Construction
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure clearing and topsoil stripping does not extend past survey & clear the site with organic material / unsuitable soils
label | Records - CS-4100 Subgrade Approval Check Sheet
checkpoint | 5 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any voids larger than 300mm to be filled with 100 to 300mm diameter chinker rock
label | Records - Photo's
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Granular Fill (AP65) used in voids for batter slopes shall be placed in layers not exceeding 200mm loose thickness and be compacted
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - The material shall be compacted by using hand-held mechanical tampers achieving 95% of the maximum dry density as determined by NZS 4402 1986 Test 4.1.1.
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures