## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Precast Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Delivery Dockets are collected and signed before precast materials are removed from the truck
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Dockets
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All Steel brackets, bolts/nuts & steel wire ropes must be inspected on delivery. Any damaged items shall be isolated, repaired or replaced
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Document review
label | Conformance Criteria - Comply with AS/NZS 5131. Brackets will be manufactured from 16mm thick 300 grade steel plate. Steel wire ropes shall be 20mm in diametre. Any welding required to be approved in writing by CPS Engineer
label | Records - Photo's, CPS COR Report, Manufacturer Test Certificates, Welding tickets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the pre-start/OFI
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual inspection
label | Records - OFI, Photo's
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Precast Components are to be installed in accordance with the design/drawing. Each unit is to be butted tightly against the adjacent unit to present a coherent mass
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - The position of the dolos groynes will be set out and agreed to with the CPS Engineer
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Dolosse’s will be secured in position using 20mm diameter steel wire ropes passed through the lifting eyes of the Dolosse’s and secured to brackets welded onto the existing sheet pile wall.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per design/drawings. Welding to be inspected and be approved in writing by CPS Engineer
label | Records - Photo's, CPS COR Report, Welding tickets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures