## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Geotextile material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile filter fabric to be compliant with Bidim A49 or similar approved
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The material shall be non-woven geotextile and comply with TNZ F/7: 2003 meeting filtration class 1, strength class E requirements.
label | Records - Material certificate(s), Photo's
checkpoint | 3 - Rip Rap Grading
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Armouring Construction Material compliant with Rock Rip Rap Grading tableas per Typical Sections Views sheet S03 Rev 1
label | Frequency - 1 test per 75m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing, Visual inspection
label | Conformance Criteria - 100% smaller than 2400Kg, 20% greater than 1000Kgs,50% greater than 600kgs 80% greater than 175Kgs. Stone shape shall be as close as possible to cubical. Long, thin, slabby shapes are unacceptable.
label | Records - Lab Test Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Geotextile Filter fabric installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filter fabric shall be placed under rock and against the end faces of the excavation as per design/drawings
label | Frequency - Prior to placing rock fill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Placement of fabric shall be as per design shown on Typical Sections Views sheet S03 Rev 1 and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 4 - Geotextile Filter fabric installation (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - tears shall be repaired by contractor
label | Records - Photos
checkpoint | 5 - Armour/Riprap Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that rock material is placed in such a manner to minimise segregation. Rock is not to be end dumped or allowed to fall from an appreciable height. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per design/drawings. Rock toe construction to be sighted and approved by CPS Engineer
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures