## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Mangahauini Bridge Scour - F3002H ID501 | itp |  |  |  |  | ITP - Mangahauini Bridge Scour - F3002H ID501
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall comply with Grading as per design (Rock Rip Rap Grading table) with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Class E A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer to assess foundation material suitability
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Form and cut fill batter as per design
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class E (A49) Geotextile placement along the face of fill batter
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
label | Records - Photo's
checkpoint | 2.7 - Rock Armour placement along the face of fill embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Install Rock riprap as per design; material to comply with requirements set out in Rock Rip Rap Grading Table located in design documentation
label | Records - Photos, Survey as builts
checkpoint | 2.8 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer.
label | Records - CPS COR report and survey as built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: FINAL INSPECTION & HANDOVER
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures