## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - F3202A - Culvert ID 614 | itp |  |  |  |  | ITP - F3202A - Culvert ID 614 | 198da203-19c9-4d91-875e-d1d8e191d2d4
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=450)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material.
label | ○ Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | ○ Rock size to be confirmed by CPS Engineer
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.4 - Class E A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material certificate(s)
checkpoint | 1.6 - AP40 (Basecourse)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | Conformance Criteria - Comply with TNZ M/4 specification
label | ○ Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery Dockets
checkpoint | 1.7 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | ○ All fill material to approved by CPS Engineer
label | Records - Lab test reports, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Grade 3/5 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | Conformance Criteria - Comply with NZTA M/6 specification
label | ○ Source property testing
label | ○ Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery Dockets
checkpoint | 1.9 - Cement Material cert
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Material certificate(s)
checkpoint | 1.10 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
checkpoint | 1.11 - Galvanised Traversable grate
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-Culvert ID 614
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Galvanised Traversable grate mounted on headwall
label | Records - Manufacturer cert, Delivery dockets
checkpoint | 1.12 - Precast Headwall
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-Culvert ID 614
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Delivery Dockets are collected and signed before precast headwall materials are removed from the truck.
label | Records - Manufacturer cert, Delivery dockets
checkpoint | 1.13 - Precast RCRRJ 1050 pipe
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614, AS/NZS 4058
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
label | ○ Class 4 RCRRJ 1050 pipe to comply with AS/NZS 4058
label | Records - Manufacturer cert, Delivery dockets
checkpoint | 1.14 - Precast materials
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.15 - Rock Rip-Rap
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - D50=150mm Rock
label | ○ Rock size to be confirmed by CPS Engineer
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.16 - Hydroseed
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | Frequency - Prior to hydroseeding commencing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Records - Delivery dockets
checkpoint | 1.17 - 35 Mpa Concrete
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Mix design 35 Mpa concrete @ 28 days for haunching
label | Records - Mix design cert, dockets
checkpoint | 1.18 - AP20 (Bedding material)
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.19 - D16 Rebar
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Comply with AS/NZS 4671 & NZS3109
label | ○ Shall be D16 rebar for concrete pipe haunching as per design
label | Records - Mill Cert, Delivery dockets
checkpoint | 1.20 -
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
label | Frequency - Prior to cutting or bending on site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
section | Section 3: CULVERT OUTLET EXTENSION
checkpoint | 3.1 - Foundation compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | Records - 1M Scala check sheet (CS-4000), Scala test results
checkpoint | 3.2 - Foundation compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - CPS to inspect and approve formation level at outlet
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Records - Photo's
checkpoint | 3.4 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | Records - Survey As-Builts
checkpoint | 3.5 - Pipe and headwall Bedding (AP20)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - AS/NZS 3725:2007
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Comply with AS/NZS 3725:2007
label | ○ Ensure correct thickness of bedding is placed and compacted.
label | ○ 100mm thick bedding for <1500mm dia pipe
label | Records - Photo's
checkpoint | 3.6 - Pipe and headwall Bedding
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - NZTA F3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
label | Records - Test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Pipe and headwall laying
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
label | Records - Survey As-Builts, Photo's
checkpoint | 3.8 - Pre-Backfill inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - NZTA F3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface. Check for gaps and/or defects and check pipe alignment for straightness
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Backfilling (Haunching AP65)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
label | ○ Remainder of backfill to be done with excavated material.
label | ○ 95% of MDD shall be achieved
label | Records - NDM test reports
checkpoint | 3.10 - Existing road side Swale
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Reshape and form both ends of road side swale to match the rock chute invert.
label | Records - Photo's
checkpoint | 3.11 - Swale geotextile installation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Class D geotextile to be placed in the swale prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 3.12 - Swale rock line
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - >1:50 slope rock line D50=150mm, 300mm minimum thickness over Class D geotextile to be placed
label | Records - Photo's
checkpoint | 3.13 - Swale rock line alignment
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - At completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Slope rock line should be >1:50 slope
label | Records - Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.14 - Outlet rock chute
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Rocks should be placed to a length of 1800mm in front of the headwall.
label | Records - Photo's
checkpoint | 3.15 - Geotextile installation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 3.16 - Rock Riffle
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - Largest rocks 900mm to be installed closely to form an arc shape facing upstream.
label | ○ Reduce grading of rocks towards the toe of the slope.
label | ○ Wash gravel/grit over to fill all voids.
label | ○ Rock riffle to be installed to approx. 1V:5H slope and tie into existing streambed minimum 200mm
label | Records - Photo's, Survey As-Builts
checkpoint | 3.17 - Slope above the rock chute
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - Daylight at maximum 1:2 existing ground and hydroseed / cover with pinned biodegradable erosion control mattting
label | Records - Photo's, Survey As-Builts
checkpoint | 3.18 - Galvanised Traversable grate installation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Grate mounted on headwall in accordance with manufacturer's recommendation
label | Records - Photo's
section | Section 4: BUTTRESS TYPE A
checkpoint | 4.1 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | Records - Photo's
checkpoint | 4.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess drainage location suitability.
label | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Bulk Fill placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | ○ Fill should be placed on dry subgrade.
label | Records - Photo's
checkpoint | 4.4 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - Compaction test reports
checkpoint | 4.5 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | ○ Slope angle of buttress is to not exceed 2H:1V
label | Records - Photo's, Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Rock Armour Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | Records - Photo's, Survey As-Builts
checkpoint | 4.7 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | Records - Photo's, Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
section | Section 5: CULVERT INLET EXTENSION
checkpoint | 5.1 - Foundation compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202A-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | Records - 1M Scala check sheet (CS-4000), Scala test results
checkpoint | 5.2 - Foundation compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - CPS to inspect formation level at outlet
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Records - Photo's
checkpoint | 5.4 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | Records - Survey As-Builts
checkpoint | 5.5 - Pipe and Bedding (AP20)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - AS/NZS 3725:2007
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Comply with AS/NZS 3725:2007
label | ○ Ensure correct thickness of bedding is placed and compacted.
label | ○ 100mm thick bedding for <1500mm dia pipe
label | Records - Photo's
checkpoint | 5.6 - Pipe and Bedding (AP20)
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - NZTA F3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
label | Records - Test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Pipe laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA F3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
label | Records - Photo's, Survey As-Builts
checkpoint | 5.8 - Pre-Backfill inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - NZTA F3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface.
label | ○ Check for gaps and/or defects and check pipe alignment for straightness
label | Records - CPS COR report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.9 - Backfilling (Haunching AP65)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
label | ○ Remainder of backfill to be done with excavated material.
label | ○ 95% of MDD shall be achieved
label | Records - NDM test reports
checkpoint | 5.10 - Concrete haunch around inlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing and visual inpsection
label | Conformance Criteria - 300mm concrete apron to be poured around the inlet. 35MPa concrete @ 28Days.
label | Records - Concrete compression test results and Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.11 - Concrete haunch around inlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 300mm concrete apron around the inlet with D16 reinforcing bar centrally, 50mm NOM. Cover.
label | Records - CPS COR report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.12 - Inlet pipe cut
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3202 Stormwater inlet details
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Mitre pipe at 1V:2H. Grind back exposed steel 20mm and place bead of epoxy mortar on cut surface
label | Records - CPS COR report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.13 - Rock chute and rocks around inlet
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202 Stormwater inlet details
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Extend rocks to top of the embankment.
label | Records - Photo's
checkpoint | 5.14 - Geotextile installation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3202 Stormwater inlet details
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
section | Section 6: BUTTRESS TYPE C
checkpoint | 6.1 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | Records - Photo's
checkpoint | 6.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess suitable drainage location suitability.
label | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Bulk Fill placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | ○ Fill should be placed on dry subgrade.
label | Records - Photo's
checkpoint | 6.4 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - Compaction test reports
checkpoint | 6.5 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | ○ Slope angle of buttress is to not exceed 2H:1V
label | Records - Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.6 - ClassE (A49) Geotextile placement along the face of fill batter
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 6.7 - Rock Armour placement along the face of fill embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
label | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | Records - Photo's, Survey As-Builts
checkpoint | 6.8 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | Records - CPS COR report, Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
section | Section 7: IN PROGRESS INSPECTIONS (Pavement)
checkpoint | 7.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
checkpoint | 7.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | Records - Test reports
checkpoint | 7.3 - Subgrade Cement Application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | Records - Bag test records
checkpoint | 7.4 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | ○ Average 95% of MDD with nothing less than 92%
label | Records - Test reports
checkpoint | 7.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports
checkpoint | 7.6 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey As-Builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.7 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ○ Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 7.8 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Bag test records
checkpoint | 7.9 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey As-Builts
checkpoint | 7.10 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Test reports, Photo's
checkpoint | 7.11 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.12 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Spray report, Pre-seal checksheet (CS-4060), Photo's
checkpoint | 7.13 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 7.14 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Grade 3 and 5 chip seal
label | Records - Material certificate(s), Photo's
section | Section 8: FINAL INSPECTION & HANDOVER
checkpoint | 8.1 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - CCTV inspections of culverts
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - CCTV inspection
label | Conformance Criteria - CCTV to inspect the alignment, no defects, joints are sealed properly
label | Records - CCTV footage
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 8.4 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - Turitaka Slip Repair - F2601A - Works | itp |  |  |  |  | ITP - Turitaka Slip Repair - F2601A - Works | 72a85c26-6540-489f-9a57-5060ee8ac317
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - 4t Ecogreen/Kyowa bags
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Purchased from Bluemont or similar approved
label | ○ Traceability of all materials delivered to site
label | Records - Material cert, delivery dockets
checkpoint | 1.2 - Screen river run
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11/SH12
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - River run to fill bags 50mm to 175mm screened rock < 2%fines
label | ○ Provide written evidence of supply source to CPS Engineer prior to delivery
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11 TNZ F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D Traceability of all materials delivered to site
label | Records -
checkpoint | 1.4 - Granular fill AP65
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Suppliers grading certificate
label | Conformance Criteria - Hard durable well graded free draining material 65mm not more than 5% passing 75 micron screen free from organic fines and vegetive matter.
label | ○ Traceability of all materials delivered to site
label | Records - Material cert, delivery dockets
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of works and check against design drawings. Check and agree on set-out and number of Ecogreen Rock bags required with CPS Engineer
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Remove and clear deleterious material when excavating to formation level. Excavated material to be disposed of off-site. CPS engineer to inspect and approve the foundation level material
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Granular Backfill AP65
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | Conformance Criteria - Comply with TNZ F/1.
label | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | Records - Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Rock Bag installation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | ○ The final layer will be determined by the CPS Engineer on site
label | Records - Photo's, CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Class D (A39) Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 2.6 - Bulk Fill Placement access roads
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3435.SM(6) SH13, NZS4431:2022, TNZ F/1
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | Records - Bulk Fill Earthworks checksheet (CS-4020), Photo's
checkpoint | 2.7 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Completion
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Upon completion of the works the CPS engineer will be given the opportunity to inspect the works having been done to the required standard and sign it off for completion
label | Records - CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.3 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | e960010f-82d1-4b8e-b659-ffb1fcc3dbc4
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Excavation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Photo's
checkpoint | 2 - Excavation (2)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Existing ground/bank & foundation for rock toe to be excavated/trimmed to remove any deleterious and loose material
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to inspect and approve trimmed surface & founding level material before proceeding further.
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Geotechnical Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any areas of concern with the face at any time, ensure the Geotechnical Engineer is involved and any changes that are required are documented
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - NTC/NFD
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Any changes to the design (soil nails, rock bolts, shotcrete etc.) are to documented individually
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - NTC/NFD
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Formation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Once cut is down to Formation level complete Scala check sheet
label | Frequency - At completion of section
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - As per design/drawings
label | Records - CS-4000 1M Scala check sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | 53a7e31a-58e7-41f4-be59-b3a5b3b43ae8
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ground Improvements / Dig Outs for soft areas
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Granular Fill (AP65)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Granular fill material to fill any voids in the batter slope shall be crushed AP65 material
label | Frequency - Prior to receiving rock rip rap
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - AP65 shall be a hard, durable, well graded, free draining material with a maximum particle size of 100mm and 65mm respectively and not more than 5% by mass passing a 75- micron sieve. The fill material shall be free of organic fines and vegetative matter.
label | Records - Delivery Dockets, Material certificate(s)
checkpoint | 4 - Subgrade Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Subgrade Cut and Fill Construction
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Ensure clearing and topsoil stripping does not extend past survey & clear the site with organic material / unsuitable soils
label | Records - CS-4100 Subgrade Approval Check Sheet
checkpoint | 5 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any voids larger than 300mm to be filled with 100 to 300mm diameter chinker rock
label | Records - Photo's
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Granular Fill (AP65) used in voids for batter slopes shall be placed in layers not exceeding 200mm loose thickness and be compacted
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - The material shall be compacted by using hand-held mechanical tampers achieving 95% of the maximum dry density as determined by NZS 4402 1986 Test 4.1.1.
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | c14bda9b-0f1c-4b37-b664-054c087e0a17
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Precast Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Delivery Dockets are collected and signed before precast materials are removed from the truck
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Delivery Dockets
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All Steel brackets, bolts/nuts & steel wire ropes must be inspected on delivery. Any damaged items shall be isolated, repaired or replaced
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Document review
label | Conformance Criteria - Comply with AS/NZS 5131. Brackets will be manufactured from 16mm thick 300 grade steel plate. Steel wire ropes shall be 20mm in diametre. Any welding required to be approved in writing by CPS Engineer
label | Records - Photo's, CPS COR Report, Manufacturer Test Certificates, Welding tickets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the pre-start/OFI
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual inspection
label | Records - OFI, Photo's
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Precast Components are to be installed in accordance with the design/drawing. Each unit is to be butted tightly against the adjacent unit to present a coherent mass
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - The position of the dolos groynes will be set out and agreed to with the CPS Engineer
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Dolosse’s will be secured in position using 20mm diameter steel wire ropes passed through the lifting eyes of the Dolosse’s and secured to brackets welded onto the existing sheet pile wall.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per design/drawings. Welding to be inspected and be approved in writing by CPS Engineer
label | Records - Photo's, CPS COR Report, Welding tickets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | itp |  |  |  |  | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | 8df91791-bce1-4754-87d3-02e9ead54bc7
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out extents and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Geotextile material
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile filter fabric to be compliant with Bidim A49 or similar approved
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - The material shall be non-woven geotextile and comply with TNZ F/7: 2003 meeting filtration class 1, strength class E requirements.
label | Records - Material certificate(s), Photo's
checkpoint | 3 - Rip Rap Grading
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Armouring Construction Material compliant with Rock Rip Rap Grading tableas per Typical Sections Views sheet S03 Rev 1
label | Frequency - 1 test per 75m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing, Visual inspection
label | Conformance Criteria - 100% smaller than 2400Kg, 20% greater than 1000Kgs,50% greater than 600kgs 80% greater than 175Kgs. Stone shape shall be as close as possible to cubical. Long, thin, slabby shapes are unacceptable.
label | Records - Lab Test Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Geotextile Filter fabric installation (1)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filter fabric shall be placed under rock and against the end faces of the excavation as per design/drawings
label | Frequency - Prior to placing rock fill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Placement of fabric shall be as per design shown on Typical Sections Views sheet S03 Rev 1 and be laid/overlapped as per manufacturers recommendations
label | Records - Photo's
checkpoint | 4 - Geotextile Filter fabric installation (2)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area
label | Frequency - Pre/ During install
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - tears shall be repaired by contractor
label | Records - Photos
checkpoint | 5 - Armour/Riprap Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that rock material is placed in such a manner to minimise segregation. Rock is not to be end dumped or allowed to fall from an appreciable height. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per design/drawings. Rock toe construction to be sighted and approved by CPS Engineer
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - Te Puia Subsidence Site - F3001B Fault ID609 - Concrete Barriers (Precast or Cast Insitu) | itp |  |  |  |  | ITP - Te Puia Subsidence Site - F3001B Fault ID609 - Concrete Barriers (Precast or Cast Insitu) | 20cd30fd-064c-4178-b260-ef0bfb10f11e
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour (D50=450)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results
checkpoint | 1.2 - BulkFill (GAP65/GAP100) or similar
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | ○ Material source testing
label | Records - Material source test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - TNZ F/2 drainage material
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material source test results
checkpoint | 1.4 - Class D A39 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - On dry bed below fill
label | Records - Material certificate(s)
checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | Records - Material certificate(s)
checkpoint | 1.6 - Biocore erosion control matting
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | Records - Material certificate(s)
checkpoint | 1.7 - Enkamat 7018
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | Records - Material certificate(s)
section | Section 2: IN PROGRESS INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | Records - Photo's, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation materail and engineered fill.
label | Records - Photo's
checkpoint | 2.6 - Sub soil drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent
label | Frequency - As works progress in agreement with the engineer
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
label | Records - Photo's, Drainage Line Record check sheet (CS-4025)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Installed in accordance with manufacturers recommendations
label | Records - Photo's
checkpoint | 2.8 - Bulk Fill Placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
label | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
checkpoint | 2.9 - Bulk Fill Compaction
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing (Clegg 100kpa)
label | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | Records - 1M Scala Check sheet (CS-4000), Lab test report
checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
label | Records - Site inspection on completion, Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the engineer. Rock armour to be added to the toe as required
label | Records - Photo's
checkpoint | 2.12 - Verge Reinstatement
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
label | Records - Photo's
checkpoint | 2.13 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: Final Inspection and Handover
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - Mangahauini Bridge Scour - F3002H ID501 | itp |  |  |  |  | ITP - Mangahauini Bridge Scour - F3002H ID501 | 11e4bafe-5e72-4b7c-b205-8f6b9e52ca4e
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Rock Armour
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall comply with Grading as per design (Rock Rip Rap Grading table) with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Class E A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | Records - Material certificate(s)
section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Remove and clear the vegetation
label | Records - Photo's
checkpoint | 2.3 - Subgrade Excavation
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer to assess foundation material suitability
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Inspect fill foundation.
label | ○ Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Form and cut fill batter as per design
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | Records - Survey as builts
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Class E (A49) Geotextile placement along the face of fill batter
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
label | Records - Photo's
checkpoint | 2.7 - Rock Armour placement along the face of fill embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Install Rock riprap as per design; material to comply with requirements set out in Rock Rip Rap Grading Table located in design documentation
label | Records - Photos, Survey as builts
checkpoint | 2.8 - Rock Armour key into ground
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer.
label | Records - CPS COR report and survey as built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 3: FINAL INSPECTION & HANDOVER
checkpoint | 3.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 3.2 - Completion Sign Off From Fields Below
label | Records - Signatures