## Amenity Bldg
Metlife Care, Clevedon
Amenity Building
Stage | Suite | Item #
1 | AS106 | D039.1
1 | AS106 | W039.1
1 | AS106 | W037.1
1 | AS106 | W036.1
1 | AS158 | W035.1
1 | AS158 | W035.2
1 | AS158 | W035.3
1 | AS158 | D035.1
1 | AS158 | W035.4
1 | AS158 | W035.5
1 | AS158 | D035.2
1 | AS158 | W034.1
1 | AS158 | D034.4
1 | AS158 | D034.3
1 | AS158 | D034.2
1 | AS158 | D034.1
2 | 125 FG | D001.1
2 | 125FG | ID001
2 | AS106 | W003.1
2 | AS106 | W004.1
2 | AS106 | W004.2
2 | AS106 | W038.1
2 | AS106 | W005.1
2 | AS106 | D005.1
2 | AS158 | D025.1
2 | AS158 | D025.2
2 | AS158 | D025.3
2 | AS158 | D025.4
2 | AS158 | D025.5
2 | AS158 | W025.1
2 | AS106 | D022.1
2 | AS106 | D020.1
2 | AS106 | D019.1
2 | AS158 | W009.4
2 | AS158 | W009.3
2 | AS158 | W009.2
2 | AS158 | W009.1
2 | AS106 | D006.1
2 | AS106 | W002.3
2 | AS106 | W002.2
2 | AS106 | W002.1

## Glazing Checklist
Glazing frame prepped and cleaned
Check for defects
Glass Installed to spec
Sufficient cover on glass perimetre
Glazing wedge installed to spec
Backing wedge to spec
Trade Cleaned
Final photo taken

## Install Checklist
Substrate prepared for Install (Waterproofing etc.)
Hole centres as specified, Countersunk (450 mm max, 150 mm from corners/Mullions)
WANZ bars fixed/Level (Maximum hole centres 300 mm)
Window Level, Plumb and fixed in the correct position on the horizontal plane
Window packed and fixed off
Window aligned Vertically (Where required)
PEF Rod fitted
internal air seal complete
Head Flashing Installed as specified (When Required)
All Frames Glazed, Sash Installed, Sliding Door fitted
Threshold Installed (Hinge doors)
Free from marks, dents, scratches,