## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Insulation Checklist | [5 empty] | Insulation Checklist (01. Zone A Roof - Gym)
section | Material Inspection
checkpoint | Insulation - Roof Sarking - Proctor Wrap HTR
checkpoint | Insulation - Roof - Glasswool on Perforated Sarking - 80mm
checkpoint | Thermal Spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation Checklist | [5 empty] | Roof Installation Checklist (01. Zone A Roof - Gym)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Roofing screws without Neoprene washer
checkpoint | Foam Infill Strips
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (01. Zone A Roof - Gym)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations Checklist | [5 empty] | Roof Penetrations Checklist (01. Zone A Roof - Gym)
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Penetration with backtray
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (01. Zone A Roof - Gym)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: 80mm Blanket
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Stainless Steel 0.55mm 304
checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint | Overflow Side Outlet 0.61mm Colorbond
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulated Panel Installation Checklist | [5 empty] | Insulated Panel Installation Checklist (02. Zone B Roof - Pool)
section | Material Inspection
checkpoint | Panel: 100mm Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | 14G TEK Screw with bonded washer to suit
checkpoint | Buildex 10 x 16mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Askin Performance Panel Spec (between 3 - 6 Degrees of Fall)
checkpoint | Panels located correctly
checkpoint | Fixings as per Askin Performance Panel Spec
checkpoint | Stitching screws 500mm centres
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (02. Zone B Roof - Pool)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations Checklist | [5 empty] | Roof Penetrations Checklist (02. Zone B Roof - Pool)
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Penetration & backtray
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (02. Zone B Roof - Pool)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: Insulated Panel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Sumps / Outlets: Siphonic inline sump (install only)
checkpoint | Overflows: Siphonic overflow (install only)
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (02. Zone B Roof Parapet - Pool)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Ledger Angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (02. Zone B Roof Parapet - Pool)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation Checklist - Lift over run | [5 empty] | Insulation Checklist - Lift over run (03. Zone C Lift Roof)
section | Material Inspection
checkpoint | Insulation - Roof Sarking - Proctor Wrap HTR
checkpoint | Insulation - Roof - Glasswool on Perforated Sarking - 80mm
checkpoint | Thermal Spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation Checklist | [5 empty] | Roof Installation Checklist (03. Zone C Lift Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Roofing screws without Neoprene washer
checkpoint | Foam Infill Strips
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (03. Zone C Lift Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulated Panel Installation Checklist | [5 empty] | Insulated Panel Installation Checklist (03. Zone C Roof Insulated Panel)
section | Material Inspection
checkpoint | Panel: 125mm Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | 14G TEK Screw with bonded washer to suit
checkpoint | Buildex 10 x 16mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Askin Performance Panel Spec (between 3 - 6 Degrees of Fall)
checkpoint | Panels located correctly
checkpoint | Fixings as per Askin Performance Panel Spec
checkpoint | Stitching screws 500mm centres
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (03. Zone C Roof Insulated Panel)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations Checklist | [5 empty] | Roof Penetrations Checklist (03. Zone C Roof Insulated Panel)
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Penetration & backtray
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (03. Zone C Roof Insulated Panel)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: Sisalation
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: Insulated Panel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Sumps / Outlets: Siphonic inline sump (install only)
checkpoint | Overflows: Siphonic overflow (install only)
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (03. Zone C Roof Parapet - Office)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Buildex 10 x 16mm stitching screws
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Ledger Angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (03. Zone C Roof Parapet - Office)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (04. Zone D Roof - ITF)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: 80mm Blanket
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: Stainless Steel 0.55mm 304
checkpoint | Sumps / Outlets: 0.61mm Colorbond
checkpoint | Overflow Side Outlet 0.61mm Colorbond
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation Checklist | [5 empty] | Insulation Checklist (04. Zone D Roof - ITF)
section | Material Inspection
checkpoint | Insulation - Roof Sarking - Proctor Wrap HTR
checkpoint | Insulation - Roof - Glasswool on Perforated Sarking - 80mm
checkpoint | Insulation - Thermoseal 993 Black Perforated
checkpoint | Thermal Spacer - Ashgrid 1200mm - 60mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Arcoplus Polycarbonate Installation Checklist | [5 empty] | Arcoplus Polycarbonate Installation Checklist (04. Zone D Roof - ITF)
section | Material Inspection
checkpoint | Material Item: Multicell Polycarbonate Sheet Acroplus polycarbonate skylight
checkpoint | Clips for Arcoplus
checkpoint | Wafer head screw
section | Installation
checkpoint | Under & Over Flashings between transition of roof material
checkpoint | Are the side lap perimeters sealed with thick sealing foam strips
checkpoint | 150mm Ashgrid Spacer to be installed Longitudinal so spacer does not interfere with view from underneath
checkpoint | Material installed as per manufacturer's recommendations.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation Checklist | [5 empty] | Roof Installation Checklist (04. Zone D Roof - ITF)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Roofing screws without Neoprene washer
checkpoint | Foam Infill Strips
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (04. Zone D Roof - ITF)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations Checklist | [5 empty] | Roof Penetrations Checklist (04. Zone D Roof - ITF)
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Penetration with backtray
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulated Panel Installation Checklist | [5 empty] | Insulated Panel Installation Checklist (05. Zone E Roof - Airlock 2 & Stairs)
section | Material Inspection
checkpoint | Panel: 125mm Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | 14G TEK Screw with bonded washer to suit
checkpoint | Buildex 10 x 16mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Askin Performance Panel Spec (between 3 - 6 Degrees of Fall)
checkpoint | Panels located correctly
checkpoint | Fixings as per Askin Performance Panel Spec
checkpoint | Stitching screws 500mm centres
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (05. Zone E Roof - Airlock 2 & Stairs)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (05. Zone E Roof - Airlock 2 & Stairs)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter: Insulated Panel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Sumps / Outlets: Siphonic inline sump (install only)
checkpoint | Overflows: Siphonic overflow (install only)
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulated Panel Installation Checklist | [5 empty] | Insulated Panel Installation Checklist (05. Zone E Roof - Main Switchboard Room)
section | Material Inspection
checkpoint | Panel: 125mm Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | 14G TEK Screw with bonded washer to suit
checkpoint | Buildex 10 x 16mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Askin Performance Panel Spec (between 3 - 6 Degrees of Fall)
checkpoint | Panels located correctly
checkpoint | Fixings as per Askin Performance Panel Spec
checkpoint | Stitching screws 500mm centres
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (05. Zone E Roof - Main Switchboard Room)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (05. Zone E Roof - Main Switchboard Room)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter: Insulated Panel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Sumps / Outlets: Siphonic inline sump (install only)
checkpoint | Overflows: Siphonic overflow (install only)
checkpoint | Rainhead
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulated Panel Installation Checklist | [5 empty] | Insulated Panel Installation Checklist (05. Zone E Roof - Theatre)
section | Material Inspection
checkpoint | Panel: 125mm Insulated Panel
checkpoint | Internal liner colour: TBC
checkpoint | External liner colour: TBC
checkpoint | 14G TEK Screw with bonded washer to suit
checkpoint | Buildex 10 x 16mm stitching screws
checkpoint | 6mm Kingspan Butyl tape
section | Installation
checkpoint | Internal flashings installed straight and close fitting - joins hidden
checkpoint | Joins and fixings hidden
checkpoint | Butyl sealing tape installed to Askin Performance Panel Spec (between 3 - 6 Degrees of Fall)
checkpoint | Panels located correctly
checkpoint | Fixings as per Askin Performance Panel Spec
checkpoint | Stitching screws 500mm centres
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (05. Zone E Roof - Theatre)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (05. Zone E Roof - Theatre)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter: Insulated Panel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Sumps / Outlets: Siphonic inline sump (install only)
checkpoint | Overflows: Siphonic overflow (install only)
checkpoint | Rainhead
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (05. Zone E Roof Parapet)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Ledger Angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (05. Zone E Roof Parapet)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation Checklist - Lift over run | [5 empty] | Insulation Checklist - Lift over run (07. Zone F Roof - Curved)
section | Material Inspection
checkpoint | Insulation - Roof Sarking - Proctor Wrap HTR
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation Checklist | [5 empty] | Roof Installation Checklist (07. Zone F Roof - Curved)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond - Custom Orb / Corrugated
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Roofing screws without Neoprene washer
checkpoint | Foam Infill Strips
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (07. Zone F Roof - Curved)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (07. Zone F Roof - Curved)
section | Material Inspection
checkpoint | Box Gutter Brackets: #3
checkpoint | Box Gutter: 1.2mm 316 Stainless Steel
checkpoint | Gutter Flashing: 0.55mm 304 Stainless Steel
checkpoint | Gutter Insulation: 80mm blanket
checkpoint | Sumps / Outlets: Colorbond inline sump
checkpoint | Overflows: Colorbond overflow
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Soffit Cladding Checklist | [5 empty] | Soffit Cladding Checklist (07. Zone F - Curved Soffit)
section | Material Inspection
checkpoint | Soffit Cladding type: 0.48mm Custom Orb/ 0.55mm Dominion Panel [TBC]
checkpoint | Top hat support: 0.75mm 15mm tophat
checkpoint | Flashing Material: 0.61mm Colorbond
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (08. HETAF East Elevation Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 75mm x 150mm x 1.6mm Galvanised
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (08. HETAF East Elevation Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (09. HETAF South Elevation Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 75mm x 150mm x 1.6mm Galvanised
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (09. HETAF South Elevation Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (10. HETAF West Elevation Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 75mm x 150mm x 1.6mm Galvanised
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (10. HETAF West Elevation Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (11. HETAF North Elevation Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Flashing Material: 0.61mm Colorbond to suit
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 75mm x 150mm x 1.6mm Galvanised
section | Installation
checkpoint | Butyl Tap to Panel Top & Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (11. HETAF North Elevation Cladding)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Box Gutter Installation Checklist | [5 empty] | Box Gutter Installation Checklist (12. Pavilion Roof)
section | Material Inspection
checkpoint | Box Gutter Brackets: #1
checkpoint | Box Gutter Brackets: #3
checkpoint | Insulation under gutter: 80mm Blanket
checkpoint | Gutter Board: Spandek Zincalume
checkpoint | Box Gutter: 0.55mm Stainless Steel 304
checkpoint | Gutter Flashing: Stainless Steel 0.55mm 304
checkpoint | Material Separation Barrier
checkpoint | Sumps / Outlets: Syphonic Inline Sump (Install only)
checkpoint | Overflow: High Capacity Overflow stainless steel 0.55mm 304
section | Installation
checkpoint | Gutter Brackets installed correctly
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Rivet spacing for sump / box gutter are adequate
checkpoint | Rivet spacing for pop / sumps are adequate
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Insulation Checklist | [5 empty] | Insulation Checklist (12. Pavilion Roof)
section | Material Inspection
checkpoint | Insulation - Roof Sarking - Proctor Wrap HTR
checkpoint | Insulation - Roof - 100mm Glasswool - 2nd layer
checkpoint | Insulation - Roof - 100mm Glasswool with Medium Sarking - 1st layer
checkpoint | Thermal Spacer - Ashgrid 1200mm - 150mm
section | Installation
checkpoint | Insulation to entire roof area
checkpoint | Correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | Insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation Checklist | [5 empty] | Roof Installation Checklist (12. Pavilion Roof)
section | Material Inspection
checkpoint | Roof Sheets: 0.48mm Colorbond - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roof Clip: Galavanised
checkpoint | Roof Screws: Roofing screws without Neoprene washer
checkpoint | Foam Infill Strips
section | Installation
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (12. Pavilion Roof)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations Checklist | [5 empty] | Roof Penetrations Checklist (12. Pavilion Roof)
checkpoint | Dektite #2
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | To fit the purpose
checkpoint | Adequate support around penetration to prevent roof
checkpoint | Sheet from buckling
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (13. Internal Cladding)
section | Material Inspection
checkpoint | Wall Cladding type: 0.48mm Kliplok Colorbond
checkpoint | Wall Sarking - Proctor Wrap HTR
checkpoint | Top hat support: 0.75mm x 25mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Matt
section | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Louvre Wall Penetration | [5 empty] | Louvre Wall Penetration (14. Louvre Grills)
section | Material Inspection
checkpoint | Louvre
section | Installation
checkpoint | Adequate Fixings according to Manufacturer's Specification
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (16. Pavilion Wall East)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 1.6mm Galvanised to base of panels
checkpoint | EBS1 - base support to bottom of panels
checkpoint | Screws - 150mm Stainless Steel
section | Installation
checkpoint | Butyl Tape to side laps
checkpoint | Butyl Tape to Panel Top & Bottom
checkpoint | Structural seal behind ledger angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (16. Pavilion Wall East)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Wall Flashing - Internal Wall Trim inc. Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (17. Pavilion Wall North)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 1.6mm Galvanised to base of panels
checkpoint | EBS1 - base support to bottom of panels
checkpoint | Screws - 150mm Stainless Steel
section | Installation
checkpoint | Butyl Tape to side laps
checkpoint | Butyl Tape to Panel Top & Bottom
checkpoint | Structural seal behind ledger angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (17. Pavilion Wall North)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Wall Flashing - Internal Wall Trim inc. Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (18. Pavilion Wall South)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 1.6mm Galvanised to base of panels
checkpoint | EBS1 - base support to bottom of panels
checkpoint | Screws - 150mm Stainless Steel
section | Installation
checkpoint | Butyl Tape to side laps
checkpoint | Butyl Tape to Panel Top & Bottom
checkpoint | Structural seal behind ledger angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (18. Pavilion Wall South)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material 0.61mm Colorbond to match
checkpoint | Wall Flashing - Internal Wall Trim inc. Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checklist | Wall Cladding Checklist | [5 empty] | Wall Cladding Checklist (19. Pavilion Wall West)
section | Material Inspection
checkpoint | Wall Cladding type: 150mm Mineral Wool Panel
checkpoint | Type of Fixings: to suit Askin Performance Panel
checkpoint | Ledger Angle - 1.6mm Galvanised to base of panels
checkpoint | EBS1 - base support to bottom of panels
checkpoint | Screws - 150mm Stainless Steel
section | Installation
checkpoint | Butyl Tape to side laps
checkpoint | Butyl Tape to Panel Top & Bottom
checkpoint | Structural seal behind ledger angle
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist | [5 empty] | Flashing/Capping Installation Checklist (19. Pavilion Wall West)
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Matt
checkpoint | Flashing Material: 0.61mm Colorbond
checkpoint | Capping Material top of the curved wall - 0.61mm Colorbond Cool max
checkpoint | Wall Flashing - Internal Wall Trim inc. Tape
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition