## ITP Cover Page
Retaining Wall 4 - Enabing works - sheet piling - Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2 - 010-001 - Rev 2
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | 010-001
Project Number: |  |  | DN1210 - SP2 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Retaining Wall 4 Enabling works - sheet piling |  |  |  |  | Revision: | 1000 |  | 2
Contract Number: |  |  | NZTA8287 |  |  |  |  | Drawing Sets: |  |  | Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1 RW4 Sheetpile Wall - Elevation - DN1210-05-DRW-001 IFC REV 0 Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1 RW4 Sheetpiles General Arrangement - DN1210-05-DRW-035 IFC REV 0 WSP Geotechnical Interpretive Report Document Reference: 2-32735-WSP-RP-GEO-0003
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specification
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-12 | [7 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved | 2025-02-13 | [7 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Nick Adams | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
ITP Item # | Inspection and test point | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  |  |  | Test Frequency |  | QA Record |  | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[11 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | IFC Drawings and Specification | Drawings to be issued by DNZ Temporary Works team - IFC stamped | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction |  |  |  | Once |  | N/A |  | H
3.2 | Method Statement & JSEA Development | The Downer Standards (TDS) | Prior to construction: document review. |  |  |  | Once |  | Method Statement & JSEA Completed & signed by site crew |  | H |  |  | Sign | Date
3.3 | Survey Model | N/A | Model Review. |  |  |  | Once |  | Visual Inspection & measurement Survey Check set out as per design |  | H |  |  | Sign | Date
3.4 | Lift Plan | DG-ZH-ST047 Cranes and Lifting Equipment Standard | Prior to construction. For lifting of sheet piles with Excavators. |  |  |  | Prior to Construction when required |  | Permit number …................ |  | H |  |  | Sign | Date
3.5 | Hot Works | DG-ZH-ST041 Hot Work Standard | Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction. Permit in the work package.. |  |  |  | Prior to Construction when required |  | Permit number …................ |  | H |  |  | Sign | Date
3.6 | Working at Heights | DG-ZH-ST042 Working at Heights Standard | Prior to construction, permit in work package. |  |  |  | Prior to Construction when required |  | Permit number …................ |  | H |  |  | Sign | Date
3.7 | Assess geotech reports and confirm driveability for sheet piling | WSP Geotech Report | Prior to construction: document review. |  |  |  | Prior to Construction when required |  | Visual Inspection & discussion with operator on ground resistance profile |  | H |  |  | Sign | Date
3.8 | GSI (Ground anchor installation) | BS 8081:2015 | Load test schedule, test locations and test sheets are reviewed and approved by GSI Engineer |  |  |  | Prior to Construction when required |  | Test sheet and job pack |  | H |  |  | Sign | Date
3.9 | GSI (Ground anchor installation) | n/a | Slope assessment completed and reviewed by GSI Project Manager. |  |  |  | Prior to Construction when required |  | Slope assessment checksheet |  | H |  |  | Sign | Date
3.1 | GSI (Ground anchor installation) | n/a | Confirm site extents agreed with Engineer and aligns with general intent of the design |  |  |  | Prior to Construction when required |  | Written confirmation to design team |  | H |  |  | Sign | Date
3.11 | GSI (Ground anchor installation) | n/a | Sacrificial test nail number and locations agreed and approved by GSI PDE / PM |  |  |  | Prior to Construction when required |  | Job pack signed |  | H |  |  | Sign | Date
3.12 | GSI (Ground anchor installation) | n/a | Pre-construction sign off - Subcontract agreement signed, TMP approved, all staff and subcontractors inducted , CMP reveiwed and in place . |  |  |  | Prior to Construction when required |  | Job pack signed |  | H |  |  | Sign | Date
3.13 | GSI (Ground anchor installation) | n/a | Plant - Ensure plant suitable for use on site and calibration up to date. Rig capable of reaching all anchor locations. |  |  |  | Prior to Construction when required |  | Job pack signed |  | H |  |  | Sign | Date
3.14 | Sheet Piles | NZGS Spec SPERW | Sheet Piles are in good condition, free from rust and debris. Leading edges cut to assist driving 40mm lifting eyes cut in side wall of sheets, lengths as per IFC drawings |  |  |  | Once |  | Visual Inspection |  | R |  |  | Sign | Date
3.15 | Driving Gates | n/a | Check suitability amd alignment |  |  |  | Once |  | Visual Inspection |  | R |  |  | Sign | Date
SECTION 4 - CONSTRUCTION ACTIVITIES
4.1 | PILING
4.1.1 | Piling - Pile Set-Out | DWG details to be provided | Before commencing sheet piling operations, survey set out wall alignment based on model. Set out to include offset. |  |  |  | 10m chainage |  | As-Built |  | W |  |  | Sign | Date
4.1.2 | Piling - Driving Gates | n/a | Position gates to wall alignment |  |  |  | 10m chainage |  | As-Built |  | R |  |  | Sign | Date
4.1.3 | Piling - Install sheet piles | Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-001 REV A.4 Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1RW4 Sheetpile Geometry - Elevation - DN1210-05-DRW-035 REV A.4 | Sheet piles driven to the required depths / embedment |  |  |  | As required |  | Written record, sheet length and embedment depth |  | R |  |  | Sign | Date
4.2 | GROUND ANCHOR INSTALLATION
4.2.1 | Install Tie Back Anchor | Drawings | Confirm drill depth, angle and orientation of tie back anchors - per IFC drawings |  |  |  | Each nail |  | Drill log | Drill log | R |  |  | Sign | Date
4.2.2 | Install Tie Back Anchor | Drawings | Ensure grout sample cubes or cylinders are available and ready for use (1 set of 3 samples per day) |  |  |  | Prior to drilling | Prior to drilling | Grout log | Grout log | R |  |  | Sign | Date
4.2.3 | Install Tie Back Anchor | FHWA-NHI-14-007-Soil Nail Wall | Drill logs (fully) complete, including hole ID, diameter and length of hole drilled - as well as geology i.e. colour, type (rock/soil), moisture (i.e. dry, slightly moist, wet). Ensure to stipulate which holes are to be used for test anchors - based on D7. |  |  |  | During drilling | During drilling | Photo Test result sheet | Photo Test result sheet | W |  |  | Sign | Date
4.2.4 | Install Tie Back Anchor | Drawings | Grout to have reached at least 7 days prior to testing. |  |  |  | During drilling | During drilling | Photo Test result sheet | Photo Test result sheet | H |  |  | Sign | Date
4.2.5 | Install Tie Back Anchor | Drawings | Ensure tie back anchors have the correct debonded length for the sections they are installed in. Refer to IFC pages 1 and 2 for respective debonded lengths. |  |  |  | During drilling | During drilling | Photos | Photos | W |  |  | Sign | Date
4.2.6 | Install Tie Back Anchor | TBC | Install 2No. 150mmØ open hole sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 150mmØ open hole sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 150mmØ open hole sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 150mmØ open hole sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | During drilling | During drilling | Photos Drilling logs | Photos Drilling logs | W |  |  | Sign | Date
4.2.7 | Install Tie Back Anchor | TBC | Install 2No. 130mmØ grout flushed self drilling sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 130mmØ grout flushed self drilling sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 130mmØ grout flushed self drilling sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | Install 2No. 130mmØ grout flushed self drilling sacrificial test anchors in locations indicated in (drawing sheet number, length and debond specs TBC) | During drilling | During drilling | Photos Drilling logs | Photos Drilling logs | W |  |  | Sign | Date
4.2.8 | Install Tie Back Anchor | TBC | Sacrificial anchors installed with Rockbond A301 Accelerant Additive as per manufacturers instructions. Crush test at 3 and 5 days (TBC) | Sacrificial anchors installed with Rockbond A301 Accelerant Additive as per manufacturers instructions. Crush test at 3 and 5 days (TBC) | Sacrificial anchors installed with Rockbond A301 Accelerant Additive as per manufacturers instructions. Crush test at 3 and 5 days (TBC) | Sacrificial anchors installed with Rockbond A301 Accelerant Additive as per manufacturers instructions. Crush test at 3 and 5 days (TBC) | During drilling | During drilling | Grout log | Grout log | W |  |  | Sign | Date
4.2.9 | Install Tie Back Anchor | IFC Drawings | Install up to 108 no. of 14.4m long, Galvanised T40 anchors across 2 rows in 150mmØ HOLES. Check drawings for varying drill angles. Anchor centers and cutting out sheetpiles are completed by others | Install up to 108 no. of 14.4m long, Galvanised T40 anchors across 2 rows in 150mmØ HOLES. Check drawings for varying drill angles. Anchor centers and cutting out sheetpiles are completed by others | Install up to 108 no. of 14.4m long, Galvanised T40 anchors across 2 rows in 150mmØ HOLES. Check drawings for varying drill angles. Anchor centers and cutting out sheetpiles are completed by others | Install up to 108 no. of 14.4m long, Galvanised T40 anchors across 2 rows in 150mmØ HOLES. Check drawings for varying drill angles. Anchor centers and cutting out sheetpiles are completed by others | During drilling | During drilling | Photos Drilling logs | Photos Drilling logs | H |  |  | Sign | Date
4.2.10 | Install Tie Back Anchor | GSI grout sampling procedures | Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing. Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid). | Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing. Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid). | Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing. Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid). | Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing. Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid). | During drilling | During drilling | Grout log | Grout log | W |  |  | Sign | Date
4.2.11 | Install Tie Back Anchor | GSI grout sampling procedures | Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter. | Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter. | Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter. | Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter. | During drilling | During drilling | Grout log | Grout log | W |  |  | Sign | Date
4.2.12 | Install Tie Back Anchor | GSI grout sampling procedures | Grout mud balance testing - per relevant SOP | Grout mud balance testing - per relevant SOP | Grout mud balance testing - per relevant SOP | Grout mud balance testing - per relevant SOP | Per hour during grouting session | Per hour during grouting session | Grout log | Grout log | R |  |  | Sign | Date
4.2.13 | Install Tie Back Anchor | N/A | Grout logs i.e. number of grout bags per hole and total. Volumes to be recorded for each sol nail anchor. Ensure nails are appropriately numbered with relevant ID. | Grout logs i.e. number of grout bags per hole and total. Volumes to be recorded for each sol nail anchor. Ensure nails are appropriately numbered with relevant ID. | Grout logs i.e. number of grout bags per hole and total. Volumes to be recorded for each sol nail anchor. Ensure nails are appropriately numbered with relevant ID. | Grout logs i.e. number of grout bags per hole and total. Volumes to be recorded for each sol nail anchor. Ensure nails are appropriately numbered with relevant ID. | Each grout session | Each grout session | Grout log | Grout log | W |  |  | Sign | Date
4.2.14 | Install Tie Back Anchor | N/A | Grout top-up complete. Update grout logs with those test nails that have been topped up. | Grout top-up complete. Update grout logs with those test nails that have been topped up. | Grout top-up complete. Update grout logs with those test nails that have been topped up. | Grout top-up complete. Update grout logs with those test nails that have been topped up. | Each grout session | Each grout session | Photo | Photo | W |  |  | Sign | Date
4.2.15 | Test Results | IFC Dwg | Verification Testing for minimum 4 tests, 2No. 150mm open hole anchors and 2No. 130mm grout flush anchors. Pullout failure is defined as the inability to further increase the test load while there is continued pullout movement of the test anchor . Record the pullout failure load as part of the test data. |  |  |  | After Drilling |  | PhotoTest (result sheet) | Photo | H |  |  | Sign | Date
4.2.16 | Test Results | IFC Dwg | Production testing on 25% of tie back anchors. Duiring the creep test i.e.1.0 Design Working Load, the difference between the reading taken at 5 mins and 10 mins should be less than 1mm. If it exceeds 1mm in this period, the test shall be held at 100% DWL for a further 60 minutes. |  |  |  | After Drilling |  | PhotoTest (result sheet) | Photo | H |  |  | Sign | Date
4.2.17 | Cut Anchors to Length | IFC Dwg | Confirm length of bar to be left extending from portal of each hole. |  |  |  | After Drilling |  | Email confirmation |  | W |  |  | Sign | Date
4.2.18 | Cut Anchors to Length | IFC Dwg | Cut bars to length and leave plate and nut attached |  |  |  | After Drilling |  | Photos Note on day report |  | W |  |  | Sign | Date
4.2.19 | Cut Anchors to Length | IFC Dwg | Confirm with client lengths are correct and hand over for waler install |  |  |  | After Drilling |  | Photos Email confirmation |  | H |  |  | Sign | Date
4.3 | Ground Anchor Installation
4.3.1 | Ground Anchor Installation | N/A | Drill and Grout logs |  | Drill and Grout logs |  | Daily |  | Drill and grout logs |  | W |  |  | Sign | Date
4.3.2 | Ground Anchor Installation | IFC Dwg | Sacrificial and Production test nails |  | Sacrificial and Production test nails |  | Per IFC Drawings |  | Test logs |  | H |  |  | Sign | Date
4.3.3 | Ground Anchor Installation | 30MPa at 28 days | Grout crushing test |  | Grout crushing test |  | 7, 14 and 28 days result |  | Test Results |  | H |  |  | Sign | Date
4.3.4 | Ground Anchor Installation | N/A | Photo records |  | Photo records |  | Daily |  | Photos |  | W |  |  | Sign | Date
5 | FINAL RECORDS
5.1 | Pinling - Survey Records | N/A | Installed sheet pile wall surveyed and records are assembled for asbuilting |  |  |  | Once |  | As-Built |  | H |  |  | Sign | Date
5.2 | Ground Anchor Installation | N/A | As-Built |  | As-Built |  | Once |  | Updated Drawings |  | H |  |  | Sign | Date
ITP APPROVAL PROCESS
Prepared By: Quality Engineer |  |  |  |  | Signed: |  |  | Date:
Reviewed By: Project Manager |  |  |  |  | Signed: |  |  | Date:
Reviewed By: QA Manager |  |  |  |  | Signed: |  |  | Date:
Reviewed By: TW Design Engineer |  |  |  |  | Signed: |  |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  |  | Date: