## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
ffa49522-242d-4b38-932b-f19241019e91 | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
99a7b3b5-e2d6-47e6-9bcc-1711bbb2092e | section | Details
049c6544-bfe3-4cff-a5c4-a45c66b58c1c | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
47fb1123-1688-5977-8e87-6e2889df1827 | note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
34c1b68f-9458-597c-9895-47e2af2306d6 | note | Check Item - Check Item
330b9e0e-d7f0-59d7-8429-1c4cde2056ac | note | Reference - MRTS02 Cl. 5.2
a6a02aa6-c563-4f8d-9595-feb72a659575 | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
a277f572-6a62-588b-b75e-2d69ad076bbe | note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
c2f9c715-9b51-58b7-a20e-aee54135d76e | note | Check Item - Hold Point 1
250f7251-62c6-51da-809d-11b65b49a894 | note | Reference - MRTS02 Cl. 5.3
c6b13fbf-6263-4ec6-aaf5-06e83cd73257 | signoff | HOLD POINT
39ffa090-b672-48c8-bc32-9053c3a18518 | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
95aa3bca-7948-515b-b8af-5d4ebefc9ee0 | note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
8549ce65-1cda-5f0a-abaa-63a542976045 | note | Check Item - Check Item
678b3ba5-8964-54fc-bcdf-55bd0c3c3346 | note | Reference - MRTS02 Cl. 5.6.4
d8f11b66-538d-4534-a404-564eae5fa970 | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
08278d4c-5e5d-56e3-bde5-ee76d4e854d0 | note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
cf6be4cc-792b-5d37-8c8e-d1c5c430dab2 | note | Check Item - Check Item
b2bda304-bc5a-5bdb-a480-d6f662a30827 | note | Reference - MRTS02Cl. 5.6.5
a7720a1f-9fbc-4843-96f1-8ad0c092de4b | checkpoint | The minimum number of lanes to be maintained on midblock sections of road will be determined as per the method (a), (b) or (c): As Mentioned MRTS02.1 Cl .3.2, 3.3, 3.4, 3.5
4defac0f-92ed-597f-ac7b-8e905e453289 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
8b491b3d-3f7f-5497-a419-780ef8d276e8 | note | Check Item - Check Item
0cf5686e-c2c8-5ed5-820f-8b22b9dc5db6 | note | Reference - MRTS02.1 Cl. 5.7.3
29f62de0-f9b2-4c35-8d83-0cf300bcfd16 | checkpoint | Traffic may be altered from its existing route via the following Cl 3.8 MRTS02.1
61e5013f-a9ce-5a7b-ad77-ab5380f45f42 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
92f9c5c4-0389-5c62-a766-7fa614e692a3 | note | Check Item - Check Item
153d6fa9-2fd4-5f47-8cf7-6e30891f8b0e | note | Reference - MRTS02.1 Cl. 5.7.4
53e43ad0-919e-4f7c-a80d-d7432ba59539 | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
7f6cdcfd-df80-5ef2-a221-1331d6f7a18f | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
4931c554-970a-56bd-84f1-27d9b5b1f794 | note | Check Item - Hold Point 2
0bd37ae4-2589-5081-9656-3701a3425601 | note | Reference - MRTS02 Cl. 6.2
798c9b30-a93d-4d51-aac9-7067f04490c1 | signoff | HOLD POINT
c56abdf7-5b94-4a03-a82e-e87854038543 | checkpoint | The Contractor shall provide a minimum of two VMS (one in each direction) for the works under construction on Steve Irwin Way. VMSs shall be in place a minimum of 2 weeks prior to the commencement of the works on site to provide advance warning to the road users of the impending works. The requirements of Clause 6.5.2.1 of MRTS02 shall apply with regards to their use
0705a5d8-6260-574e-8211-8d3e51e7e815 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
12c677ea-2b40-51f6-a40a-17092231d5b9 | note | Check Item - Check Item
f81a0d10-62fc-58aa-8704-58e5abf750bb | note | Reference - MRTS02.1 Cl. 6.5.2.1
20d6f41a-4fa9-4e67-b243-5df2cb9c4928 | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
a52a361c-1100-5650-8b9b-dc4c8236c23e | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
c9d5c55f-4bf4-5346-bb5a-44455438e50f | note | Check Item - Milestone
563212af-822d-563d-b732-eb42c4a4971c | note | Reference - MRTS02 Cl. 7.5
8c338c06-c7b3-4b4d-9290-63cdb42bd000 | checkpoint | The following requirements for side tracks shall apply as Stated in MRTS02.1 Cl 5.7
398e7e53-8ae2-508a-ba96-01fcbe9cce8a | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
57d67034-550b-5bb1-9081-f4e9b3243808 | note | Check Item - Check Item
43aacd82-c8d7-5059-8dcd-df2ea424b357 | note | Reference - MRTS02 Cl. 6.5.3.3
1b6d9d4a-a611-43b9-8800-8fa80a3a93b2 | checkpoint | The following additional control measures are required to mitigate end of queue crashes as stated in MRTS02.1 Cl 5.8
a9634df2-1dbc-5cc6-8643-0196d0692516 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
dee8b662-9646-5500-814b-0984970e6375 | note | Check Item - Check Item
016440ec-2710-5b45-91b2-ecc88dfbaa7d | note | Reference - MRTS02 Cl. 6.5.7
94c72e36-38b6-4238-9abc-70e69f036b4d | checkpoint | On asphalt and bituminous surfaced pavements, when permanent linemarking will not be in place outside working hours, temporary raised pavements markers (Stick and Stomps) are to be installed and maintained on centre lines, lane lines and edge lines at spacing of not greater than 25 m (except for side-track tie-ins where spacing shall not exceed 5 m). Temporary pavement markers shall only be in use for a maximum of 48 hrs and shall be replaced by linemarking after such time. If the Contractor is unable to complete line spotting by the end of each day’s work and the road is to be trafficked, the Contractor shall delineate all separation and lane lines as above. Existing longitudinal lines are to be removed by abrasive blasting or approved other method approved in writing by the Administrator when temporary lanes are in place
a6e079e2-4404-52ac-b63c-3246fa5f523b | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
8495afc3-ef92-5363-b57f-a0da4d89049c | note | Check Item - Check Item
98a8823f-1c41-5d4d-bb28-c994a6d19037 | note | Reference - MRTS02 Cl. 6.5.8
6e3ec475-9baa-4878-bb5c-b1b6361b6726 | checkpoint | Temporary road lighting shall be installed in accordinance with MRTS02.1 Cl 5.12
213a8517-84bd-5107-8ee3-6bbacecc8b5c | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
ba873dd6-42e4-5bea-8d16-d2aa0f6d99d1 | note | Check Item - Check Item
b760fe56-7a54-5267-92c7-3a7590b9d358 | note | Reference - MRTS02 Cl. 6.5.13
09b3934c-4e3d-4530-8074-7e83b4032a3c | checkpoint | In addition to the requirements of Clause 7.1, there is a need for an independent review to establish conformance with the approved TMP and TGS and with the performance requirements of MRTS02 – Provision for traffic
24b576f9-afa5-5cde-985e-bea88cc995f8 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
6fc91213-b217-5760-8cd3-b3d5485a48cf | note | Check Item - Check Item
9446c8a4-c5cc-5f09-8826-f1db96300bcd | note | Reference - MRTS02 Cl. 7.1
dbeb1337-913e-4559-8d53-133a00393feb | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 8
1afcd634-e7be-51be-b647-690d43afb264 | note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
70f73fff-1d30-518e-ace7-a1d79556f4f0 | note | Check Item - Check Item
46096d3f-b700-50b3-8380-32a7c998406c | note | Reference - MRTS02 Cl. 9
323ea9e3-1a9d-4706-88d3-4d1cf3ac7760 | checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 9
13064714-406e-5dad-848e-b8575470d9c8 | note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
f1d5e2d9-6fad-5e2c-9187-9a59de72bb0d | note | Check Item - Check Item
1a17ad4f-73cd-53be-a56d-568b07b98ec0 | note | Reference - MRTS02.1 Cl. 9
ceae5293-0111-48db-be30-18222ba4d00f | checkpoint | Final Verification
3d7f5e5a-e9ed-578d-b674-e7e10e1a10fb | note | Project Manager Verify that the Above has been Constructed according to Specification
0db17b06-a817-51da-ba40-f3792f23a633 | textbox | Print Name:
875f52bd-a446-5cbf-83fe-d91348eb6400 | date | Date:
32128058-cf4f-5f2c-8821-041dbf0c2f06 | note | Client Verify that the Above has been Constructed according to Specification
0a03d32c-9063-5b41-ac54-eb1d9c97d11e | textbox | Print Name:
471bd482-376f-50fc-91a3-c9d9f3b2656d | date | Date:
1689bf5b-e9ef-4a68-b967-fffa2bc4123b | signoff | Signature
1b0971aa-52d7-453b-b288-e2888f055878 | checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs
38cc4255-823e-4da2-a84c-f6f46deffcae | section | Details
e09938fa-cf31-4449-8c7f-efda4be225c0 | checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
78b8427d-d576-58fb-9905-0061a3c72129 | note | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
6a8fe765-f349-5d5b-85ba-c1359ef08785 | note | Check Item - Check Item
7f702d55-b25b-571c-af1e-b2097b5c72b0 | note | Reference - MRTS03 Cl 9.2
72e2f534-779c-400c-9245-385ab3447c45 | checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
10ec2cc8-bef1-518e-a6ec-0f3eb93725f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
4f6fed3d-2fd6-5a09-828c-6f9ae20ebf73 | note | Check Item - Check Item
3ebb67dc-a857-54c4-ab78-63e80b8302c0 | note | Reference - MRTS03 Cl 9.2
53bbc197-ae3d-4cd7-b11f-9436a64408b6 | checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
a830f049-345a-57e0-921c-a83c241474ee | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
2dee6cf2-6523-58e1-b52c-6c2ec49eb038 | note | Check Item - Check Item
708291f3-88ac-5fb7-9c3d-f115dd08e5c1 | note | Reference - MRTS03 Cl 9.2
883fc953-e2fa-41c8-a23f-f4c443dd0264 | checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
43e334dd-092b-5c38-ac2e-63d403c541e9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
e338d339-3116-5d58-9670-d425f70c38ff | note | Check Item - Check Item
0cb25827-186b-5df7-84a1-3bab367cbd8c | note | Reference - MRTS03 Cl 9.2
b5bdc5da-a85d-4b64-9a52-57317ab70087 | checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
92adedfe-d527-5de7-a5af-e50040b56a81 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
52b370fd-930f-5891-9816-cbad399e5b1e | note | Check Item - Check Item
5dc67e4b-fd68-5aed-8930-ef5d2646e308 | note | Reference - MRTS03 Cl 9.4
ed1f1c9a-6d29-4e2e-8642-dfc8f30238d3 | checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
d46e5836-3210-5c93-92aa-0a5a58a8aad3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
99cbab33-e27f-5820-9090-250fd8dc0bc7 | note | Check Item - Check Item
2cab07c8-dad2-5ad1-8869-9457d5553bc5 | note | Reference - MRTS03 Cl. 9.4
9718f7bc-cdfc-4da3-8bb5-bcfe935a7338 | checkpoint | Kerb excavations backfilled to flush with the surrounding area.
18f4ceeb-f3ae-50f6-9df1-60bd2bfd4f7f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9b929561-54a2-5271-a4f6-c88e0f8380d1 | note | Check Item - Check Item
59d73ee2-9a66-5d7b-b973-744cb5055749 | note | Reference - MRTS03 Cl. 9.4
7243eea4-c701-4dc4-8849-c87e11475b7b | checkpoint | Final Verification
1b07f099-ae41-5047-a3d4-4f181f621762 | note | Project Manager Verify that the Above has been Constructed according to Specification
b24eb458-ba7b-5a9c-a9f2-b59da67745ef | textbox | Print Name:
cecbe3cc-ed18-5fa9-afe5-a0e65cf8ade3 | date | Date:
27e1f1a3-c3c7-58a4-96dd-f3c44d861196 | note | Client Verify that the Above has been Constructed according to Specification
877e4893-9e7a-58b9-a2f3-917179039661 | textbox | Print Name:
71c0d24b-0bc7-5c52-8d6a-fc0891c81736 | date | Date:
10ef73c1-9465-42c6-8639-9a0a9600b9bb | signoff | Signature
3bb63a59-5710-4cb5-82b8-dca5053dff91 | checklist | 03.02 - Supply and Installation of Precast Concrete Pipe | itp | 03.02 - Supply and Installation of Precast Concrete Pipe
0fd3652b-52e3-402e-be0f-3d5f44bbfe88 | section | Details
06bce0b3-3f18-47c9-bba3-b6a17a87afc9 | checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
cf19f29b-83a5-53af-ba68-5aeeef1d3f02 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ad20a30f-68d6-5fef-b7b1-34414fe6b6b1 | note | Check Item - Hold Point 1
c3154863-b96e-5394-9ff6-97e4ef484548 | note | Reference - MRTS01 Cl. 8
bae54f34-f129-4758-8d04-4100a6e9b8a1 | signoff | HOLD POINT
1f5481cf-1501-47e7-9321-0f9cd846bc95 | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
4a688f1d-2a65-5441-b962-7328f2b475cf | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
7a806595-700f-5984-b973-205b54d89d0d | note | Check Item - Check Item
f9f79b19-c723-52d4-af87-0cab9eb6524e | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
e1956f3c-ebd1-42f2-9774-475c08d0aa5c | checkpoint | Component size, wall thickness and class is as specified in the drawings
15075398-207d-551d-9400-651dc4388b3d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a6a922a8-370f-50db-8659-e514c89da8b7 | note | Check Item - Check Item
f7dcb5c7-c3f2-5986-8132-f782e1c0cfef | note | Reference - MRTS03 Cl11.2
0fdf074d-832f-45cf-8839-3a674dabcc76 | checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
8f2b49e5-032f-508e-b784-7b7db27081e5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a6023260-76b8-569d-a2dc-c2f812f180ff | note | Check Item - Hold Point 1
7de49b76-62ca-5620-837a-8ef2e68c7ec0 | note | Reference - MRTS03 Cl11.2
157d50b1-6abd-4c42-9de5-03da6ca10903 | signoff | HOLD POINT
697271c0-ece6-473c-be42-a8a17141bfce | checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
593e920c-ef29-5ece-a00c-0465c4004622 | note | Acceptance Criteria and Frequency (Project Specific) - Written
3f264056-4d5b-5881-bda1-4cbbc86a29ab | note | Check Item - Milestone
76e59b8e-3315-5c42-a003-4c999f8d9185 | note | Reference - MRTS03 Cl11.3.1
5561b8db-eb4a-4b9b-8d3b-fdc90e5f568a | checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
9f34ec4a-9692-593e-a921-ac828d3e838b | note | Acceptance Criteria and Frequency (Project Specific) - Written
23953feb-dd5f-5da5-a3af-c06606f07c27 | note | Check Item - Hold Point 2
a903d64a-f7da-5969-afbb-5247b57dd837 | note | Reference - MRTS03 Cl11.3.1
654614fb-9c20-4a7a-b5d3-95a8e0a3e138 | signoff | HOLD POINT
9ba2a480-7c6a-4a5f-846f-5ebb72ff99cc | checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
6318c06b-f2cb-59e7-abb3-dc22d3449dc2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
83dc603e-235d-50b1-b612-8dab6db29b48 | note | Check Item - Check Item
395bb955-b29c-5390-9fec-3389d62dd335 | note | Reference - MRTS03 Cl11.3.1
ba13c4f7-6b09-41a2-b982-a5a6773b03e2 | checkpoint | Excavations completed as per MRTS04
d1a8268e-9d8e-5981-b2f4-f5de57df60f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
546f2ba5-c697-5dab-b2a7-0d4a8e5cc2a6 | note | Check Item - Check Item
50ece440-a69d-5062-9700-931774547fbb | note | Reference - MRTS03 Cl12.3.1, MRTS04
83663f41-e683-42ee-9b59-da4b0e37a62a | checkpoint | Foundation bedding and Haunch zone material placed in Accordance with MRTS04
fd98cc2f-ea36-550f-8fd5-aa87c7324b66 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dd7570be-57b9-5360-902d-b21002c56a0d | note | Check Item - Check Item
ca0f6609-5fac-56ef-83bc-5d1bf798b6f5 | note | Reference - MRTS03 Cl11.3.2
e3b58908-2168-46ff-a352-47fc062459bd | checkpoint | Components are assembled as per manufaturers specifications
04fffc7d-c5dd-539e-9eaf-68e408f9a484 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
459449b1-7cdb-592a-9d1e-71530847110e | note | Check Item - Check Item
08761e79-1f31-5920-aced-71ea53c0fa74 | note | Reference - MRTS03 Cl11.3.3
fdf10636-0336-4068-b3e8-b5155eec097f | checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
99881a61-ae46-595a-9d6f-08caa15ffb16 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3d8f33a7-08cc-5c51-b054-2db0b3b39b48 | note | Check Item - Check Item
ec3353ed-6879-5a22-87e8-7922b40a8290 | note | Reference - MRTS03 Cl11.3.4
938db42a-5a1d-4676-b1a8-69839aaa7c9c | checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
6daf7f87-ce95-55c7-b9b1-3e4359eb2fae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d258a417-1ade-5bd6-b236-292d363f9f0f | note | Check Item - Check Item
a6fcf990-de8b-52b8-a834-e003ef087bd5 | note | Reference - MRTS03 Cl11.3.5
fc904df1-fa6e-4378-b864-feb3fa2f1eee | checkpoint | Pipes laid with the word 'TOP', where marked, or lifting hole facing the top. Lifting holes plugged after the pipe is installed.
ad029b1e-767a-5f24-9939-f90cbd0506a4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
97dcd0c6-ef88-5653-b59d-0717a5593c17 | note | Check Item - Check Item
d4dae214-425a-5d7d-9bbe-ce1222654665 | note | Reference - MRTS03 Cl11.3.5
de0e6709-aeae-4aba-953e-857188e8939c | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
608a4b6f-b028-542b-a7f2-a37b7afdc847 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e001dc54-dc4b-5999-96c4-e5218c38dbbe | note | Check Item - Hold Point 3
0cc32fab-ff2b-5352-b54b-25e33e9df7d3 | note | Reference - MRTS03 Cl11.3.5
3a5a0174-92e3-4f87-a00d-8de6eea4bb9d | signoff | HOLD POINT
6179f88c-a7d3-4c1c-98a4-eba992b831c6 | checkpoint | Where RCP's are required to be cut, the cut surface shall be given two coats of a surface tolerant epoxy.
ce0c8e35-0b5d-5aea-9d92-09a6035a8838 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e0e9cd28-5281-5d2c-8d62-452fc03a236e | note | Check Item - Check Item
5ea024b0-e9f0-5ddd-a58a-664c9c3ba1ca | note | Reference - MRTS03 Cl. 11.3.9
251ddb1f-0753-448e-8c1a-1ba7bcf3ec03 | checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
d3dfef9c-0732-52ae-b19b-dae7811cca6a | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
7add0278-28d6-5084-9456-e45f85cd6e38 | note | Check Item - Check Item
81dfaf90-314f-5b85-ad8f-9ad4dbba670e | note | Reference - MRTS03 Cl. 11.3.10
8c824cac-6c12-4002-9b3e-66f06f2a5c2e | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
50e6380a-4b28-55c3-9ff3-ec8913765d43 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
71c66363-4c4a-5e43-98a6-2a50fabad255 | note | Check Item - Hold Point 4
7939675a-14dd-564e-a908-905b3c29958d | note | Reference - MRTS03 Cl. 11.3.10
fbb14d6c-cadc-440d-bbb6-4c646a019ce3 | signoff | HOLD POINT
6e5f5b2e-d568-4f9c-98f5-204b2d2f762e | checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
94baca06-4cf9-50ba-8297-adca93899a32 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a98cf83a-1159-50f0-a182-22e9b19224e6 | note | Check Item - Check Item
4ef8b08e-4d00-5077-8e17-bcd8e22a8871 | note | Reference - MRTS03.1 Cl. 1
a23f0154-db8c-446d-bd4d-75ef0bb5a49e | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
5c335b0d-00ff-55e8-8c33-95831da4a575 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2010c089-8aba-5b54-a7ed-88ef791ec118 | note | Check Item - Check Item
03ec58cd-9bd2-5f07-878e-4c360a12c31a | note | Reference - MRTS03.1 Cl. 6
278c61ed-a444-459f-96ac-9d1d4d9562ff | checkpoint | Final Verification
e2afd941-5ce5-5d30-b318-3ed1648e961d | note | Project Manager Verify that the Above has been Constructed according to Specification
f8e9158f-f262-52fe-a6e4-503be28f7ee0 | textbox | Print Name:
e55a81e5-2a35-5f4f-beef-4dbe613773b7 | date | Date:
1191e013-69e5-52a8-aa88-22a44b945957 | note | Client Verify that the Above has been Constructed according to Specification
d40495e0-c31d-5aef-867b-0818a7629f0c | textbox | Print Name:
5d888fb6-4d19-54f6-942f-aa0d1619c09f | date | Date:
78a3b2dd-ddce-4f02-bea5-c8e87b39b0c6 | signoff | Signature
6bea74b5-a151-425e-a074-0c668525f702 | checklist | 03.03 - Culvert Component/End Structure Insitu Cast | itp | 03.03 - Culvert Component/End Structure Insitu Cast
518dc7eb-88b1-4502-bf81-36d9218e3aee | section | Details
e4b0279b-6fd5-4fa2-a9f9-c47ecb90c7d3 | checkpoint | Concrete Conforms with Cl 6.1 (MRTS 70), Concrete Mortar conforms to Cl6.2, Steel Reinforcing conforms to MRTS71, Rock Masonry conforms to Cl33, Grouted Rock Pitching complies with Cl 34, Steel Wire Matresses comply with Cl 37
a77ad683-de11-52d4-b494-1c1ccf138d7d | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS70 ITP
6b4c1247-d262-50fb-862b-6bf640698dd8 | note | Check Item - Check Item
7c15074a-f688-5e2e-972f-219f1ede06b7 | note | Reference - MRTS03 Cl 14.2, Cl 15.2, Cl16.2
1e2a3e84-13d7-4826-98b5-97a3f8ed86ca | checkpoint | Cast-in-situ end structures such as headwalls, wingwalls, aprons and kerbs to culverts constructed in the locations specified on the project drawings and comply with standard drawings 1304, 1305 for pipe culverts and 1240, 1250 & 1260 for box culverts as applicable
3d5993ad-063e-5dee-b4c6-14643c03965b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
48cd561f-f04f-5187-9dd2-677a7c4c6d3c | note | Check Item - Check Item
a4202485-2419-5c64-991d-04f40a91076f | note | Reference - MRTS03 Cl 15.3
9e39244e-27c3-4b83-bd31-144c5dad124a | checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
3b37c670-3934-555a-9b77-125af37b8edb | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
8b5a554c-5782-5d9d-92cb-49f9b2cdcd2a | note | Check Item - Check Item
1848905c-6a47-52be-a740-5830979cb824 | note | Reference - MRTS03 Cl 15.3
aeff75d2-8277-444c-8dd7-da553cf07c4c | checkpoint | Endwalls, wingwalls and concrete aprons constructed without a foundation bedding unless specified otherwise in the drawings.
b6694cef-a8c5-59ca-b85c-a37c1f3940bb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
427dd9c7-91a8-5330-8a84-063ff8dd6829 | note | Check Item - Check Item
243475d7-6c10-5f21-b5ae-e03cd8a28295 | note | Reference - MRTS03 Cl 15.3
ebc54b54-9359-4927-a108-d4ceb55f8960 | checkpoint | Endwalls and wingwalls seperated with an expansion gap unless otherwise specified on the drawings.
487cb628-f045-5a71-945a-d2ed7c5fc41a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3cc8ebe4-f7a7-5f6a-9d2d-ca815aa8a4ac | note | Check Item - Check Item
478ea0b4-c098-58e0-96a1-7052620fbc6e | note | Reference - MRTS03 Cl 15.3
16d2b5c8-b784-40f4-98a4-1fff061960b7 | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
1fe737e4-618b-5097-b4f2-fbe144fcb4c3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
26136557-e45c-5dec-9708-0e6e127100ac | note | Check Item - Check Item
7b889912-ee0d-5ead-a683-a90395c5fd3e | note | Reference - MRTS03.1 Cl. 6
02d47a13-c5d5-42a9-9d33-e0d1b6a3ef6e | checkpoint | Construction of culvert base, walls or endwalls shall include the construction of integral nib or cutoff walls where relevant
055780f8-eb2c-5d4c-966d-b791a6441b2c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0d74dccd-f16b-500c-b664-714762b5546b | note | Check Item - Check Item
ee3e0ed3-8015-5a7b-9e52-fd15c8a058d3 | note | Reference - MRTS03 Cl 17.3, Cl 18.3
55d31920-6f8d-473f-9023-5dcba37276e7 | checkpoint | Construction of culvert base, walls or endwalls shall comply with the Geometrics Section stated in Clause 1.5. MRTS03.1. For Each Structural Element, testing requirements must contain: Dimensional, Positional, and Relative Position
2677f25e-c9df-5a76-a3ac-1f5111bab1c3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
398d5b5c-a9d0-5877-8c7a-9f557f146b7d | note | Check Item - Check Item
94b603b5-cf6c-5acf-a9cc-9bfe3c101699 | note | Reference - MRTS03.1 Cl 1.5
a6d81021-ca3e-44f4-8508-15e38f7af67c | checkpoint | Final Verification
6c49a883-0c07-53de-bf13-d126f22a0c03 | note | Project Manager Verify that the Above has been Constructed according to Specification
02b29993-de26-5f33-b7bb-33795deebede | textbox | Print Name:
33d74825-8aa6-56a2-bb57-08d4bb5a7804 | date | Date:
0f8ee9da-b686-5f75-a76d-b18d624c4756 | note | Client Verify that the Above has been Constructed according to Specification
4c40aaa3-115b-54a0-9dd9-f71ed27e70dc | textbox | Print Name:
e6ea9c2f-3670-59ed-b7f9-4ebf113a8fff | date | Date:
34254d8d-3d38-4429-abae-2f1b1372d0de | signoff | Signature
f6073377-d828-43ff-8f25-3ae5d64c6351 | checklist | 03.04 - Pre Cast End Structure | itp | 03.04 - Pre Cast End Structure
866605a2-5bd9-4bc1-a42e-1125fd552319 | section | Details
de0469b9-4c65-471d-96d7-2064b4d61c23 | checkpoint | Precast end structure conforms to Cl6.6, Concrete Mortar conforms to Cl6.2
6a1cf060-03b0-5612-86c2-f3483563a12d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a78de990-10ad-5125-af04-a0c3c788c858 | note | Check Item - Check Item
210d5a25-9387-5f3b-87cb-ed21920d31a5 | note | Reference - MRTS03 Cl 16.2
eeaad388-2a49-4d09-915d-6a271c582c2b | checkpoint | Constructed in the locations specified on the project drawings
1ddb222a-6f74-5c54-8540-079b883abaa5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
954052f5-9583-59c4-af38-6d3a85223721 | note | Check Item - Check Item
9418dc1e-00cc-5406-b103-8daee5458a48 | note | Reference - MRTS03 Cl 16.3
f2dac38f-cad6-41b4-a6cf-eecaa7b1b566 | checkpoint | Where material on or against which end structures are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
508319bd-44a4-5847-9e55-ad3a9c114310 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
4f137dc6-ce0d-5272-8b05-eb954f800880 | note | Check Item - Check Item
d069d604-ec70-58ab-a7c6-d94dba04fe49 | note | Reference - MRTS03 Cl 16.3
a75f7fea-1a45-4ab0-afc1-976b1128f514 | checkpoint | End Structures laid on foundation bedding which provides continuous even support
fa0b891a-2931-5789-89cd-94c517b43911 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
64236e82-0f89-5ac3-8e5f-f16652a4241c | note | Check Item - Check Item
f4276634-204e-5fd7-a889-68a7357e8864 | note | Reference - MRTS03 Cl 16.3
8284f4a2-7e80-41ba-8bfb-8346a5c40066 | checkpoint | Joints between end structure and culvert in addition to any holes and recesses are filled with cement mortar and finished smooth and uniform and cured for 48hrs
d2f2d8c1-cf4d-593e-9887-7d5f4040d248 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0766442b-ee39-50e5-b07c-581e938dd598 | note | Check Item - Check Item
40305d02-ae55-52b4-bb07-480856827efd | note | Reference - MRTS03 Cl 16.3
fc9c7a3e-6efc-4555-af57-3d496c315204 | checkpoint | Backfilling operations not undertaken during curing period and complies with MRTS04
4260e2dc-f45c-57fb-84aa-78545ffad8f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
6ee9325f-7970-5eee-8c40-15c00a81c20d | note | Check Item - Check Item
cc983c69-4695-5fc2-b646-9990fc0d3617 | note | Reference - MRTS03 Cl 16.3
d3feb147-d7aa-4a96-8e2a-5b0dc0d75903 | checkpoint | Geometrics: All points for which levels are shown on the drawings
773f82eb-4cc2-5ee0-9fe8-2b16f52affa6 | note | Acceptance Criteria and Frequency (Project Specific) - Horizontal: ±100mm, Vertical Invert: ±10mm
25140010-705c-5a31-ac33-d40426d08837 | note | Check Item - Check Item
004b337a-995c-5bd7-a95b-589e22ef74cd | note | Reference - MRTS03.1 Cl. 1
9419a146-618e-4128-b3ed-a466109770a9 | checkpoint | Final Verification
7c7429a4-b30f-5525-b4f9-ec659319786e | note | Project Manager Verify that the Above has been Constructed according to Specification
1cdddf0a-0ea6-5d8b-bab6-20807a2e67f2 | textbox | Print Name:
4ea440b1-b969-5758-b446-8d1f39387b27 | date | Date:
239cebfb-ffa7-5f91-bd77-087855a28921 | note | Client Verify that the Above has been Constructed according to Specification
da0d3660-e3e0-53e0-9e15-faabb3202489 | textbox | Print Name:
2260aa8d-6389-5e40-8cba-cb440ec02cfa | date | Date:
741d21a2-dead-4c05-957e-4b33a9c6b5c5 | signoff | Signature
556cc9b2-87ec-49b8-a9dc-14433181f94f | checklist | 03.05 - Supply and Installation of Precast Box Culverts | itp | 03.05 - Supply and Installation of Precast Box Culverts
92ab1b86-54ed-4973-8d8e-1876c7bcaf6d | section | Details
bd760bc5-6ad6-49a5-9719-e645879f5f3f | checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
d7a1ce8c-2ccd-5b08-8480-476442069b62 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6e7f5a39-211e-5850-83aa-0a14554a3f16 | note | Check Item - Hold Point 1
0ab4f6c1-fe4b-59a5-98f9-6f4f3fb16fda | note | Reference - MRTS01 Cl. 8
946f3d10-6365-47bc-8019-5d7a2bf10285 | signoff | HOLD POINT
fae92e64-2430-49fc-ae3d-565dff3bc85f | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
5afb98e6-d857-594d-8428-ce97df95a37c | note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
199f974b-ba48-5fad-a41e-9047313900a9 | note | Check Item - Check Item
4f632822-b677-5d27-8b8f-bcf7b3f5804e | note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
56a3b7d5-d6ce-49e5-8211-c794b9c747f0 | checkpoint | Component size, wall thickness and class is as specified in the drawings
a4029812-f115-5840-a78a-d73b45ac6571 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0ceb9ba1-b6b4-5fb5-8f22-f9cc6c771d1b | note | Check Item - Check Item
d1d514ac-4f9e-5f96-9032-ab863d007fb6 | note | Reference - MRTS03 Cl11.2
02dfabe4-e647-4bb5-8233-ea3b2d638af1 | checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
b378ad06-b1b0-52e5-932b-5ae2ea61aea3 | note | Acceptance Criteria and Frequency (Project Specific) - Written
f3e3c34c-0407-5607-a040-e2515a592b43 | note | Check Item - Milestone
09c20a5a-7a9f-5c2d-9842-cf2cf58e8d2b | note | Reference - MRTS03 Cl11.3.1
ff81df74-2b8c-487e-aa1d-b57694f7e3f4 | checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
6250f992-2354-5ff5-abbe-00befa9e8e4c | note | Acceptance Criteria and Frequency (Project Specific) - Written
7e10e210-2254-5be6-a00d-bf1034aff43a | note | Check Item - Hold Point 2
352fde66-6a75-57c9-ad16-cc1301f6ce58 | note | Reference - MRTS03 Cl11.3.1
b2846a56-24b2-437d-ac22-17d9156235b0 | signoff | HOLD POINT
91342381-2c01-4b3a-91c3-566cc0f890f4 | checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
3c6186df-5ae8-54d3-8753-eee38d7afaa3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a687a5f8-d036-5883-a02f-e7ac9850d824 | note | Check Item - Check Item
3780afe3-e555-5370-bdf1-b70e212c5dfc | note | Reference - MRTS03 Cl11.3.1
94d0d8ff-498e-422a-9681-a94800b5b074 | checkpoint | Excavations completed as per MRTS04
060b7b34-7e82-570c-a8ab-c9503342115b | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
e56863bf-1b8c-55a7-869b-3ebcac8e2d11 | note | Check Item - Check Item
61ce36b1-9a06-54fb-aedd-a923430736f6 | note | Reference - MRTS03 Cl12.3.1
dc0fea98-cdd2-402d-81a9-05eeb5e0d257 | checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
9ea2ff5e-1175-5037-a1c5-e94c99a1b2d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
75bb5899-f14b-5372-a7e8-376ba34f4b4d | note | Check Item - Check Item
1fb53c23-cfee-5c57-9ccc-d4d3f9c7d5e7 | note | Reference - MRTS03 Cl14.3.1
04b9431b-4d94-46ec-b599-6d26263da979 | checkpoint | Cast in-situ concrete bases, footings, infill floors and box culverts constructed without a foundation bedding unless specified otherwise in the drawings
8ece70a0-065a-5dd7-a080-05988cd85c1c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
aa66907a-6d4b-56e7-97db-ec23645dddd2 | note | Check Item - Check Item
8f5acd06-7a74-5222-8a88-2307230c3348 | note | Reference - MRTS03 Cl14.3.1
7a38e45f-cfeb-448c-96ea-6a671cbc4f71 | checkpoint | Construction of bases, footings, infill floors and box culverts include the construction of nibs and integral cut-off walls
3b6d02af-4d73-5ce0-89ee-0ec19b11b45d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
46c9eb6f-58e0-58fb-b5b7-cdb04fc8e26d | note | Check Item - Check Item
2fdff958-01af-5e25-9cc2-261dce7d9320 | note | Reference - MRTS03 Cl14.3.1
14d74316-a9f1-49fa-9eb2-c809510adff8 | checkpoint | Components are assembled as per manufaturers specifications
3b36c0ac-5920-525f-8b90-7ce4b1357bef | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b988d0e3-2c0b-5ba3-9913-0f83bdbe813a | note | Check Item - Check Item
5de4053c-2b85-575c-a1e6-f19132d3f7f9 | note | Reference - MRTS03 Cl11.3.3
6dfcec39-c1fd-41c3-98c2-ab7ffc5e1988 | checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
eae54cdb-f679-5ff6-97b8-4298708d440c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2f09fe11-ed91-5f99-a603-2d144a5a22c1 | note | Check Item - Check Item
02d3ef20-83ef-5fa7-aed4-e29756bbb030 | note | Reference - MRTS03 Cl11.3.4
b776904c-1faf-4e3a-bd1c-fcb87cd66fbc | checkpoint | Box culverts installed in accordance with Standard Drawings 1250 and 1260 or project drawings.
9cc2c426-22ca-5894-aeff-0589c1532650 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
93f63460-c361-50c6-826d-9ce89ec3de33 | note | Check Item - Check Item
3d6a4aca-43c9-568b-9aef-9ad7fc27ac92 | note | Reference - MRTS03 Cl11.3.6
f5d24cb9-eca0-4ba1-8886-71616996fb7c | checkpoint | Holding down anchors installed to retain the units, where specified, as per the details on STD DWG 1250 and 1260.
c703da6d-46c9-5170-91c3-92560d4a77ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5e563bb4-a06b-53fd-b17e-33e7be12dac9 | note | Check Item - Check Item
5e349624-0872-5242-ba0a-8000b0c1962e | note | Reference - MRTS03 Cl11.3.6
aeb8e77e-a0b5-4fca-bf25-37978f5d4359 | checkpoint | Where spanning slabs are installed, locating dowels installed in the tops of the units and the spanning slabs seated on continuous cement mortar pads on the adjacent unit.
ce12e8d8-a5c1-59a2-8f07-a44d04ef4f3e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a917c341-a20b-524d-bfdf-5b4755b34075 | note | Check Item - Check Item
c7fe7267-a174-56f4-a632-584ff535b8fe | note | Reference - MRTS03 Cl11.3.6
4b0c46af-262f-4139-a119-ecc9b96981c4 | checkpoint | In multiple cell culverts, the gaps between the lines of installed cells shall be a minimum of 40mm wide and filled with 1:10 leanmix with max 10mm aggregate.
e7dd1c53-452c-5c6d-83f7-167763671eed | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32e3179f-90fe-591b-8cb6-a3f496087dc5 | note | Check Item - Check Item
6d749d67-2c10-5166-8ccf-a800f4cf5362 | note | Reference - MRTS03 Cl11.3.6
dd4c219e-a578-4606-857a-0991094c5cee | checkpoint | Where spanning slabs are installed, the space between the slabs is filled with lean mix concrete.
8025bcd1-5799-5adf-a46e-656941fd2653 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d9a079d4-433c-5ff0-b888-4bf0bdeec690 | note | Check Item - Check Item
a7601178-a845-5ee1-a299-0b1353f4d6fa | note | Reference - MRTS03 Cl11.3.6
e7c3089e-5945-4fdd-ac76-1c3f6a98d138 | checkpoint | Lean mix backfill cured for 24 hours before any other backfill material is placed over the culvert.
dabfd670-7a5c-5b38-b8e5-b6679ca9814b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
20bf10ae-521f-508d-a1f6-0e40e825072e | note | Check Item - Check Item
885394d6-ff1e-5294-8b05-2512c597a861 | note | Reference - MRTS03 Cl11.3.6
0240729d-ba4a-4617-aca8-88fa47de1f26 | checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
0bc886c4-1c30-5722-9118-6e3ab65dd736 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
e3135867-1d04-5430-9a03-a26d9d77195c | note | Check Item - Check Item
e46e525c-1ada-5dfa-80a0-2c7f2ef302c0 | note | Reference - MRTS03 Cl. 11.3.10
7af2204f-a300-4fd1-b982-c11a22921868 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
3ad3ae82-76ea-5e8c-bb9f-198957941a9c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3461f582-c6d5-514c-8921-58e8c2574449 | note | Check Item - Hold Point 4
aae43ed1-5f00-5d92-9187-9038a7faca73 | note | Reference - MRTS03 Cl. 11.3.10
d3305eda-caf4-47c6-9833-b88339dcd173 | signoff | HOLD POINT
b85bd6cc-caf8-4c2b-8cf5-7cdc295fafb0 | checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
270aa9af-ec63-5f70-9659-7c8223b44884 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b4cd3cb0-0435-537d-ad09-b1394ce3661d | note | Check Item - Check Item
8dab3655-0ce1-59e2-9acc-f37fc4a049f6 | note | Reference - MRTS03.1 Cl. 6
0c946a53-2883-4819-a214-54bfa7c369cb | checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
b1ab87f7-e0e9-5b28-97f6-391705f55680 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cc5eb9a8-59cd-5118-b41b-cb7f50928084 | note | Check Item - Check Item
05e7f73c-1ecb-58a3-b430-4b28204cd47a | note | Reference - MRTS03.1 Cl. 1
d9fe9e60-abe8-4516-953d-b1a6d174f1fc | checkpoint | Final Verification
b8e1e4dc-2c8d-50a5-8a06-f4b48e222aa5 | note | Project Manager Verify that the Above has been Constructed according to Specification
32cef9e4-a39d-53f7-9cd6-a561938eb006 | textbox | Print Name:
a3e42659-3f39-5cfd-b181-cd5af55ada62 | date | Date:
048af850-669d-5c38-92ea-fcebe5c6f8f0 | note | Client Verify that the Above has been Constructed according to Specification
1ed7dc31-d95a-537a-bea1-6384682b0c71 | textbox | Print Name:
f657bbc3-946e-5335-81a7-59028e53965a | date | Date:
11ad8ded-554e-444e-87f0-1874aa478784 | signoff | Signature
25e13070-b1d2-4b48-b007-9c6034ce41ee | checklist | 03.20 - Kerb - Cast Insitu/Extruded | itp | 03.20 - Kerb - Cast Insitu/Extruded
6b86b347-2d09-473e-89af-9dd4e4026a4c | section | Details
b218757d-4d73-44c2-853b-10c5d7ee47f3 | checkpoint | Supplied Concrete complies with MRTS70/71. MRTS70 and MRTS71 ITP completed.
0551947b-241d-5ffc-8b8c-ce3bdc7bf5fb | note | Acceptance Criteria and Frequency (Project Specific) - ITP 70.01
9aa21cf5-cb19-52ce-8fa8-76d3cbe4d40c | note | Check Item - Check Item
591ba3ba-1c39-5833-8109-01027a3065e2 | note | Reference - MRTS03 Cl 18.2
2b3bceba-549c-4fe8-895c-814c949c65d4 | checkpoint | Cast-in-place concrete kerb / channel constructed in the locations shown on the Drawings and in accordance with the details shown on Standard Drawings (1033)
ac49602c-d3c1-573e-bee0-d265ef0f4336 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f83ed48f-86d0-56ea-871a-9a5cf8f969c5 | note | Check Item - Check Item
ae122d02-08f3-500a-a9d1-91675f8535db | note | Reference - MRTS03 Cl18.3
f6a94fda-36c1-4c47-8607-d8e633db62ab | checkpoint | Excavations / foundation preparation in accordance with the requirements of MRTS04 General Earthworks. The ground surface moistened just prior to placing concrete.
11f8fbc2-6435-5878-92de-02a09d8748de | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2e81448a-72c2-5d0d-acb8-22864181f6b1 | note | Check Item - Check Item
bc2609f3-94d3-516a-a1d0-9c46b6924928 | note | Reference - MRTS03 Cl18.3
0d44556a-bb07-4f01-97a3-800a535817c7 | checkpoint | Exposed surfaces of manually placed concrete to be steel-trowel finished.
4d768e8e-377b-5d65-9730-140a0f938a0b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
11d17327-e72a-57e8-946a-1a5ce872d069 | note | Check Item - Check Item
cb5f5dda-82d2-598e-833d-1fc0781c996c | note | Reference - MRTS03 Cl18.3
c233ae88-5743-4898-ba28-00576ffa8dbf | checkpoint | Expansion Joints shall be installed at regular intervals not exceeding 20m. The joints shall have a compressible packing with maximum thickness of 6mm covering the full cross section.
48ddd554-b334-5c77-a59f-12280a6b1d00 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
46c82a79-beba-5df5-9ff7-2591312cfaf4 | note | Check Item - Check Item
373eab59-06a7-5748-8876-f00b3b6ff2e1 | note | Reference - MRTS03 Cl18.3
78db6ac6-1733-4503-8c42-c81230058551 | checkpoint | Contraction Joints shall be installed at regular intervals not exceeding 5m. They shall be constructed be forming grooves 40mm deep and not more that 6mm wide.
0121e2af-3da7-5113-8e9f-6e43bb86ecc3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
be277f5f-931d-594e-a043-f7b02c09c7a1 | note | Check Item - Check Item
5cd343c7-dfad-5254-95b4-11b5f080ef5e | note | Reference - MRTS03 Cl18.3
2618ad9d-6ae6-438e-a54a-94a48b56540a | checkpoint | Concrete shall be cured at least 7 days before any other roadworks operations are carried out adjacent to the kerb / channel.
599316e4-f26e-5bf6-8e0d-8ba1f820e10a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0a009ccf-f7da-5120-b614-44bac0faf0ca | note | Check Item - Check Item
4ef15adb-afe4-51db-9999-c706c2a39c72 | note | Reference - MRTS03 Cl18.3
f5a9a71c-94b7-4e8e-b6d4-5339f3ec3517 | checkpoint | The Horizontal and Vertical alignments shall vary by no more than ±10mm from those specified. Alignments exhibit smooth lines. Overall dimensions are at least equal to that shown on the Drawings.
2356c87a-daa1-504a-9502-7f056bc211bd | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm from Drawings, 1 test per 10m (invert levels)
9883a9f4-538d-5b05-a06c-8153e1317f87 | note | Check Item - Check Item
376928ea-cbe2-5a87-82d0-f0a3c662d2a1 | note | Reference - MRTS03 Cl18.4
688b02f4-12c8-4df3-8d57-9c15226352b3 | checkpoint | WATER TEST: (on channels where the longitudinal grade is less than 1%). The test carried out as soon as possible after the concrete in the channel has hardened and water shall not pond to a depth of more than 5mm
197e6cad-6b15-501b-8ec8-cad2e802a844 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f598c8c9-c4fd-5708-9828-d12e9d574fa9 | note | Check Item - Witness Point
18504043-8fda-5724-9e98-777165754a26 | note | Reference - MRTS03 Cl18.5
4c9a0a49-d33d-4353-b655-81200da19174 | checkpoint | Final Verification
c2515287-92d3-571e-ac68-079118843853 | note | Project Manager Verify that the Above has been Constructed according to Specification
bd968f89-27af-5974-bb47-dfc5cfd9e4dd | textbox | Print Name:
ed02cdd7-aa63-55bb-93df-54fde9335d33 | date | Date:
0d345e0d-2f6c-5b89-ab25-3a4175b4cadf | note | Client Verify that the Above has been Constructed according to Specification
e43f855f-b1d0-52b9-96f6-69846b7dd3b2 | textbox | Print Name:
221de21a-b906-5113-bc62-2fc7ed0f0dd6 | date | Date:
b209e2f0-21c7-414f-90ec-7991bc2d15a0 | signoff | Signature
637ce4b9-9ca3-4a8f-ad58-9f3f0fdba9a6 | checklist | 03.27 - Subsoil Drains | itp | 03.27 - Subsoil Drains
4f101bd6-6d5f-48b4-84bc-64f8f4d9f8c7 | section | Details
4325bda3-a013-4ae6-af78-db0591564fd5 | checkpoint | Subsoil Drains constructed to appropriate dimensions, Geotextile surround and Pipe perforated with textile suround (Inspect trench prior to backfill)
64df269c-cbf5-54e9-907a-5d2735df327a | note | Acceptance Criteria and Frequency (Project Specific) - Type B: 700x300mm Trench, 100mm Pipe - 50mm off base
4ccb88dd-a515-59dc-948a-4ba24be4bb8d | note | ○ Type D: 100mm Wide Trench, 40mm Strip Drain
be8cbed5-73be-54c2-9234-49a630cb7535 | note | Check Item - Check Item
5f2439ce-b46f-5b6b-9ab3-a1c0479a6923 | note | Reference - MRTS03 Fig 22.1
03952651-ddec-427d-96c8-8088b56b499e | checkpoint | Type B subsoil drains backfilled with either 10mm/20mm drainage agregate or 20mm no fines concrete. Type D subsoil drains backfilled with either course sand or 20mm no fines concrete.
00906670-ec2a-5b50-8ce6-60cc01217a32 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
47e99667-c890-57ee-b374-16dec8fa80a9 | note | Check Item - Check Item
f7a24279-7606-5ee3-900d-4e71d5c1fca8 | note | Reference - MRTS03 Cl22.2.5
b5f06234-8eef-4f56-87b2-0145c7e2fceb | checkpoint | Minimum cover over strip filter drains comply with Table 22.3.1 of MRTS03 for the relevant compactor size used for construction. Hand Held Unit - 100mm, < 15 tonnes - 200mm, > 15 tonnes - 300mm
fd7df560-3fdb-5045-b98a-2f03437f9e0d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d38dd9a9-0551-5b41-9849-7dd53849f0f0 | note | Check Item - Check Item
c4fce5aa-b349-5396-a27c-57e6a3a59690 | note | Reference - MRTS03 Cl22.3
88cd9781-fe3b-4dde-afda-800d33dcdfd3 | checkpoint | Minimum grades for subsoil drains comply with Table 22.3.2 of MRTS03. Type B - 0.5%, Type D - 1.0%
fa829173-988b-5aed-9ecb-62e92615fc4f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e1f4eca7-4c6f-5c87-9828-da6b446c86c7 | note | Check Item - Check Item
9bcae637-da07-57c1-a4d7-376fe6ce225a | note | Reference - MRTS03 Cl22.3
649961e8-0721-4f91-b5b1-93219ef00d43 | checkpoint | Clean outs installed at head of all subsoil drains and at 60m intervals (Type B - pipe drain) / 50m (Type D - strip drain). Clean outs in accordance with standard drawing 1116
644c5a32-4edd-5fea-8b93-41fe31ab2c98 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2d3f1d4c-534d-5288-9682-5430aaf2b937 | note | Check Item - Check Item
8d47654b-26fb-5249-9c51-1b35a1ee5f70 | note | Reference - MRTS03 Cl22.3, TMR SD 1116
000fb4c9-af15-40b7-9340-9a88078b0f4c | checkpoint | Backfill material dampened when placed in trench. Placed in 200mm layers and tamped.
c5bc70ca-4fbf-551e-b038-8345b2721cf5 | note | Acceptance Criteria and Frequency (Project Specific) -
b585e474-6d9a-5b4e-bf1e-c7cc9ce0f8fe | note | Check Item - Check Item
17fe9317-de82-5f0c-9000-f2fb8c2c4097 | note | Reference - MRTS03 Cl22.3
8f55f8ce-138f-4c58-b03b-26c7a449a7b0 | checkpoint | Concrete outlets, surrounds ,chicken wire cones, pest proof flaps, cast iron/PVC caps, rock pitching in accordance with standard drawings.
4c9d1b9f-be1b-5149-8b45-7c269f833676 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
be848a39-751d-58ee-8c3d-37e98e2c4a45 | note | Check Item - Check Item
a101e9ef-3191-54f5-b826-488c611ae304 | note | Reference - MRTS03 Cl22.3, TMR SD 1116
dbcfbb48-6c59-446b-ba61-93cde6a77693 | checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
545553fd-588f-54ca-91e3-eb2e2f51bab9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
78d3654b-0f18-5c0d-8fa5-28016b461a47 | note | Check Item - Check Item
d1f2c2e6-6ee0-5ec5-8259-c38d3982d42e | note | Reference - MRTS03 Cl22.3, TMR SD 1116
642ae65d-1a25-4c80-b2a2-397ec52afc14 | checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
17da945b-4eac-5796-93a3-201bc693f09b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
95836e66-cfd8-54d4-8fc2-99ef3cf6f2e2 | note | Check Item - Check Item
4415b3fc-d70e-59c0-893a-aef2ce650c5f | note | Reference - MRTS03 Cl27.4
0d7f9122-c1fe-4d43-a041-a32021816fdb | checkpoint | As Constructed drawings prepared / All geometric tolerance requirements met
4ffbbc8a-5754-5aa3-88ff-167349df113e | note | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
41e768a5-169f-568b-a156-51b992448aeb | note | Check Item - Witness Point
c73da1be-9139-46a9-b4a1-2af7c6332afe | checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
eb81e43a-822d-5ce0-8cd0-f617387d30ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6936b8a0-4e28-506c-a8c5-e02ca852f605 | note | Check Item - Witness Point 4
888ef12f-38c6-5766-a7b9-092aba23a107 | note | Reference - MRTS03 Cl22.3
fcf08dc2-9b37-404b-b8cf-976e578845e8 | checkpoint | Final Verification
064d55b4-d749-5a07-8990-938774577f63 | note | Project Manager Verify that the Above has been Constructed according to Specification
de303d2a-35bc-534f-a6c5-2b21d48e568f | textbox | Print Name:
9f202c18-4e1d-54c5-81bb-53a59f39a942 | date | Date:
0f85ed53-02ee-5c05-8aff-bdc1be18fcde | note | Client Verify that the Above has been Constructed according to Specification
707e191f-19ee-5b02-a646-b487740eebc0 | textbox | Print Name:
f847c820-7de0-5d30-9ff9-3fcffa85395a | date | Date:
42d8d2c3-c547-40d5-b79d-87e3ccefbc84 | signoff | Signature
a391ae17-3e08-493d-9dd7-964a67cc800a | checklist | 03.28 - Sheet or Strip Filter Drains | itp | 03.28 - Sheet or Strip Filter Drains
7efc890d-65d0-4cc0-8e5f-53404f309efd | section | Details
9ea7d18a-9068-475d-85c2-939b0a9b70c1 | checkpoint | Sheet filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 18mm, encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
a0ec60b4-6c3a-5e16-aeca-1af1a1ea194c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9070e1b2-40bf-5406-b785-8d813327e433 | note | Check Item - Check Item
936729c2-915c-566b-8f76-df7fbe211a92 | note | Reference - MRTS03 Cl 23.2
69632a1e-a88c-4718-a46a-447872c98438 | checkpoint | Strip filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 40mm, designed to allow the drainage of water along the drain and encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
ae6305cc-1933-5a96-a23f-3ab6fdb7302b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0ec799d8-f54c-5705-aa86-a092af4f4009 | note | Check Item - Check Item
ac71fa40-1da3-5822-8420-0b734beb1e7e | note | Reference - MRTS03 Cl 23.2
661c2338-b2c3-4f9b-ad27-8e1ae372d404 | checkpoint | The plastic core shall permit the passage of high water flows, and shall have a crush strength not less than 200kPa
32a37f5c-69c2-5b3b-bfe2-99131b7b71b2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a0655dd6-a8a8-5895-83ab-171f34ef1f89 | note | Check Item - Check Item
8f4248c5-0894-54eb-b08b-0d7b3c02ab03 | note | Reference - MRTS03 Cl 23.2
beddbdab-b529-47a9-a0df-9b60629bdc84 | checkpoint | Drainage pipes, fittings, and joining materials/procedures shall comply with the relevant requirements as specified.
4df294d8-35af-5a34-a81a-654e1852c853 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
56b2b28f-0bd4-51ef-b9df-7eab37af45b1 | note | Check Item - Check Item
b3782fdc-228e-57b4-a674-4a8b1802beb1 | note | Reference - MRTS03 Cl 23.2
f144c234-8b95-4a2e-9b58-33fc1029a74f | checkpoint | Concrete, where required, shall be grade N20/20 in accordance with clause 6.1
c11726d9-a21b-5835-979d-60ebcb8428bb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1cd541cd-c711-50ed-9201-443c9fa074cd | note | Check Item - Check Item
f2981159-1d16-53c5-a177-038db21028a9 | note | Reference - MRTS03 Cl 23.2
703256f7-3b83-4ed6-87f7-83c537ad908a | checkpoint | Materials shall not be exposed to heat or direct sunlight or stored directly on the ground.
90042f3e-f72f-51da-b542-bd3b557544fd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7ef2afa6-95fd-52af-9c0b-05ac1ca0b45a | note | Check Item - Check Item
f840c10f-f71a-5352-895b-1c758d9e60a0 | note | Reference - MRTS03 Cl 23.3
44b77fba-9287-4073-8453-ce5cbc37dcf4 | checkpoint | Sheet/Strip filter drains shall be constructed in the locations and in accordance with the drawings and manufacturer's recommendations.
50422fa0-af03-5b37-8d38-1cced911fdf1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
77cd31ec-3eaa-5685-9c23-933f0bf7e6bd | note | Check Item - Check Item
58d4611c-5e6e-5bb3-9267-56a216db4944 | note | Reference - MRTS03 Cl 23.4
94d8ed71-95b3-433b-a2e0-0fd4a8a6890a | checkpoint | Where sheet filter drains are used against structures employing weepholes, the core of the drain shall have cutouts of a size and spacing recommended by the manufacturer.
605114af-c12f-5c26-847f-57b560da50f7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
32ac310b-cf31-5154-b4ba-a22a57421e28 | note | Check Item - Check Item
0329189c-eff1-55b8-a686-3a2a5abd7563 | note | Reference - MRTS03 Cl 23.4
06a763b8-fb7e-4a25-bda8-b8975a9e0114 | checkpoint | Collector pipes shall be constructed to the shapes specified in the drawings and jointed in accordance with the manufacturer's recommendations.
badc8b4f-29dd-56f4-809e-c951e2bab489 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c039a251-9150-5eb6-8dd3-5fbaa55fbfef | note | Check Item - Check Item
f092b7e0-0fe2-570b-9dbe-1a3476f16c2a | note | Reference - MRTS03 Cl 23.4
65101bb9-8652-4cbe-8709-a7e56dd91fd6 | checkpoint | Filling around collection pipes shall be general backfill in accordance with Clause 20 of MRTS04. Fill material shall be compacted to a relative compaction not less than 97%.
f9013b1c-8835-5e9a-bd75-81d52dce40b1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
86bc0f7c-fb8b-5e2e-a9a7-0f3baed47f79 | note | Check Item - Check Item
e3f1865a-c670-531d-bae1-0be59ffec240 | note | Reference - MRTS03 Cl 23.4
4db3d97c-5691-4ba0-b6e0-ea7e7079b0c5 | checkpoint | Concrete outlets, concrete surrounds, galvanised chicken-wire cones and pest-proof flaps shall be provided in accordance with Standard Drawing 1116.
1036eafd-3566-5856-8e88-493ba786209a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8cccc599-e832-5f2b-9afe-2260c641d414 | note | Check Item - Check Item
62a6096b-67e4-5757-b3a2-e0fd97bbc54b | note | Reference - MRTS03 Cl 23.4
0a863406-7820-4204-ae92-bd508c72d786 | checkpoint | Final Verification
03bfad74-98a0-50e8-a708-1159415e363c | note | Project Manager Verify that the Above has been Constructed according to Specification
3329a5a5-dcb6-5b5e-a602-e58153bda6c2 | textbox | Print Name:
2966eb56-6f1e-5844-a9e9-50c6f737e047 | date | Date:
ebd16e1d-a55a-5d95-9266-85cb93017187 | note | Client Verify that the Above has been Constructed according to Specification
555d0c12-10eb-5b4e-8dab-5e939b532240 | textbox | Print Name:
0db14669-3886-5c06-8b9b-883b7bf84fb0 | date | Date:
9938ef8d-7794-48bb-9007-42c0c7762ab8 | signoff | Signature
97da462c-dfb6-497b-8be9-5a3897acad78 | checklist | 03.41 - Rock Protection | itp | 03.41 - Rock Protection
89f8362a-7da3-44af-95cd-1c3474587ad8 | section | Details
1f5ac942-967f-441a-a54f-345c1d98628f | checkpoint | Rock complies with size requirements specified on drawings, otherwise shall be not less than 150mm and not greater than 500mm. Rock shall be well graded with not less than 50% larger than a size twice the minimum specified
09267ba3-c96f-5df5-a324-8ae0c8be493d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
62351184-7e8d-5b08-a766-2d8007063e87 | note | Check Item - Check Item
4dcf9135-cd36-5d5c-baad-2fae2af0ea1f | note | Reference - MRTS03 Cl. 35.2
16cd4b39-ded4-4118-a316-7eeaa289c277 | checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
8a24479c-62fb-52ed-8648-e171739f708b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
314abfac-3d89-5d06-854a-725b4475599b | note | Check Item - Check Item
88d5e38a-93f0-5a95-bd2f-02e66fa471ae | note | Reference - MRTS03 Cl. 35.2
b2ee6975-78ca-46a5-a99e-9d7baddc0cec | checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
a129a747-3d8d-562d-bcba-af64e15e2bdf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bcb186d2-20b4-5ec6-be6d-cec7ef2a4f66 | note | Check Item - Check Item
1d46b346-0185-55d2-ba69-1afea576865f | note | Reference - MRTS03 Cl. 35.3
7e9fcc49-24d3-498e-ae8f-0c59b53a6d86 | checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
31508339-1d5c-5699-81d0-0e7a75be2cff | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0d09f560-f5ce-5430-aa3a-c956711e1c88 | note | Check Item - Check Item
2fa856af-c2d0-5396-8dd4-e4ba3283f5f3 | note | Reference - MRTS03 Cl. 35.3
54f428cf-f5c2-4489-89de-fb2f5485e421 | checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
f99b2b59-3664-546d-90fd-85616f41ee05 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c7b2b40a-16ec-5bb4-9181-af989f3d61e1 | note | Check Item - Check Item
96d90131-daf4-5cd3-8928-12fb535dc639 | note | Reference - MRTS03 Cl. 35.3
de3f5fc8-b0b8-450d-9f46-8f87401871dd | checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
835c6413-a039-5348-baaf-f35bf3883475 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
69fd8bee-d859-5c0f-adcb-933af606c811 | note | Check Item - Check Item
39f15ff2-e6aa-5a15-9e03-771323cfd6e8 | note | Reference - MRTS03 Cl. 35.3
a7ba451b-40c3-4f23-8d39-8418ef9eb35e | checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
86674177-bf2a-521e-bea0-889e16e9d9e4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7eef59a9-6d3e-5acb-9a52-2e5f0612929a | note | Check Item - Check Item
5d74bd83-7877-5817-baec-e4a037368ec0 | note | Reference - MRTS03 Cl. 35.3
9afd4431-610d-44c0-929d-474f134f028b | checkpoint | Final Verification
63b4f05c-e87c-514c-88ad-f4fd22846e3a | note | Project Manager Verify that the Above has been Constructed according to Specification
82c9d7e3-9c79-55e2-a3af-26da1de4a7ef | textbox | Print Name:
dfe3df8a-f3fb-5fb3-ab34-635eeec8bf9e | date | Date:
156d1968-745f-521a-af62-4086c41a083b | note | Client Verify that the Above has been Constructed according to Specification
b36ab261-1ce6-5af6-9e2b-7d8b9fa7dd21 | textbox | Print Name:
2715211d-3442-5968-975a-4174be6abd3d | date | Date:
13667e38-0f69-4c1b-bcae-b60384e9bb13 | signoff | Signature
bc53022c-cd17-43a8-ba75-610869cf2f69 | checklist | 04.01 - Clearing & Grubbing | itp | 04.01 - Clearing & Grubbing
ef5feec6-b282-4431-9465-a827fcf54a29 | section | Details
a38d0ee5-ac4e-4366-952d-2ac650d045bd | checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
80741a87-b389-5609-98a8-cccdd1b7b1c2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a5469692-042d-5f86-8d3b-1f1fb5dbcb1a | note | Check Item - Check Item
5336abc6-d62f-59a3-a41f-623587f5f5e0 | note | Reference - MRTS04 Cl 7.2.1
20da6a2c-5da7-42cc-87d5-f64024570768 | checkpoint | Tree Protection Zones installed as per Arborists recommendations
d1422a2d-5b50-53d1-ac2b-ce164916c17d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e60526c-20cf-541f-9da9-03d1226fee40 | note | Check Item - Check Item
6881cfcb-fb6a-5b6e-a7f5-31c95f34767d | note | Reference - MRTS51.1 Cl 9.1
3ffa0f73-b72f-49a7-abb4-39c4da2d51ba | checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
a1dbb0f6-df07-5559-9170-db9b88f44d11 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d16d22fb-9ce2-5050-9a5a-aa072d43b700 | note | Check Item - Check Item
ea15eb86-d1b4-57ae-96f6-0c9a0d616b24 | note | Reference - MRTS51.1 Cl 9.1
5e2de108-a1ea-4e24-819f-116c39210cbc | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
f62524dd-6dbc-5ca0-8c69-183a121a305a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a916f78a-9f32-5a76-aad6-8def8b2a192f | note | Check Item - Hold Point 2
7e973fea-8e3f-5bb9-90d2-c023dc44e047 | note | Reference - MRTS04 Cl. 7.2.2
e86e0a5a-1f76-4907-89eb-e6952b964313 | signoff | HOLD POINT
be6a6db6-3297-47c8-97ba-a092810c69b3 | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
2a1eb19f-72cf-535f-a3e2-01db50a60a50 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
bb9672d2-3a70-55fd-9c73-3d5ad0de2ec1 | note | Check Item - Hold Point 3
ab06720a-cfba-5be8-a984-07a3b3defbab | note | Reference - MRTS04 Cl. 7.2.3
11153f87-9b97-4bf1-8856-bfd8d6960180 | signoff | HOLD POINT
a5264fdc-b024-4b20-8646-06d6df0a9f9a | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
e27def40-0eab-5015-b955-08275d830bf5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3864e1cd-d003-563b-b2e3-24d9581565be | note | Check Item - Hold Point 2
135632e7-c11d-5b87-b3f8-7557f576aa94 | note | Reference - MRTS52 Cl. 7.1
45938c29-d399-4143-baa9-94338b888541 | signoff | HOLD POINT
b16d84a3-517d-4921-ae88-6cb38c1b81e2 | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
4c17de8a-0aa3-5ae1-af2b-2ef29f72fbc8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
da56b20b-0a06-5e04-ba9d-ebe7f73cb420 | note | Check Item - Check Item
8a4998e6-e30f-5781-9af7-568bc985cd9c | note | Reference - MRTS04 Cl. 7.2.5
6e1e5df0-9a8e-4d1f-8377-1e487710af4a | checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
7b6865df-51c1-51be-a102-d8af2ea9bfa8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
27e26f20-6a9a-5d84-8009-456d026699b2 | note | Check Item - Check Item
527d322c-01bc-5b08-9ece-38b58db82d49 | note | Reference - MRTS04 Cl. 7.2.7
36d757e3-0b32-46f9-85e1-58a45406d6ae | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
d85db905-264f-504d-a9b9-92d3193f30f4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7bd560cb-8493-56e5-b6d5-65b61a8bda88 | note | Check Item - Check Item
894c092a-314e-5de5-aa14-2454eba177f2 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
63cdc072-96a2-4670-95bb-31db71cb0ac1 | checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
721e5418-eac6-545f-ab47-26fab21a53ef | note | Acceptance Criteria and Frequency (Project Specific) - Visual
95a3b4cd-d466-576b-adf8-739f839cd12a | note | Check Item - Check Item
69333f9d-6418-582d-99d0-890dcd93a144 | note | Reference - MRTS04.1 Cl13.1
f19f1c69-fb90-4a22-b052-1f524193fabd | checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
b1bf51e6-a2a0-5ec5-97df-d5daee9f5689 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0cd939a8-31ba-524c-88c1-9ba35390c679 | note | Check Item - Check Item
97b727e9-2547-58c2-aa6b-8a9ac9d15f2d | note | Reference - MRTS04.1 Cl. 1.1
d88ea6c4-e9ba-41c6-8171-cb7ce097ba8a | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
f1e69bac-d1db-5ae5-868e-1a244421fb31 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0937d28d-53de-5f58-b954-52de807ed56f | note | Check Item - Check Item
7482b6b7-9162-5d1e-89a5-9e09081050a9 | note | Reference - MRTS04 Cl. 8.4.3
e780332b-e704-4008-979a-ff8e3c656e0f | checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
6dc54b44-68a4-5282-8973-3aba2decafcc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
48d4f1c3-bc0f-552e-9374-81184abced1f | note | Check Item - Check Item
955be074-df7d-55d5-9cdd-705df2907172 | note | Reference - MRTS04.1 Cl 1.4
596c9a29-7d8a-4c30-89a8-524cb4195508 | checkpoint | Final Verification
37b4a70e-84cb-5b4b-9f36-d1191246b72c | note | Project Manager Verify that the Above has been Constructed according to Specification
78137cfc-e985-500b-8f41-1fc2b7a71e29 | textbox | Print Name:
778a4648-ff7f-594e-a0b6-a41a35858146 | date | Date:
c707ae8b-4929-5442-83e0-94305cf59ed6 | note | Client Verify that the Above has been Constructed according to Specification
03fb37e9-cae6-52f5-8bf3-dcb87d695500 | textbox | Print Name:
db09a090-3da0-5f85-995d-939a2eb107eb | date | Date:
2a3656e0-1f26-40dd-b314-08cfe942e4f0 | signoff | Signature
11e024f6-cffb-4549-ba4c-bbd5dcd42bd3 | checklist | 04.04 - Ground Surface Treatment | itp | 04.04 - Ground Surface Treatment
b8137b45-c92b-48bc-9b70-385cbac57b79 | section | Details
934acc7a-9328-4c98-aad2-8ea08aad7c8c | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
242a0a65-22a5-5467-9fe7-930ec45cbcbc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ff2cec44-5a5b-5ee9-9083-20c6f56b2333 | note | Check Item - Check Item
e466d31d-b3e1-5c78-a926-4298af904452 | note | Reference - MRTS04 Cl12.2.1.1
16e57702-4436-4a9b-b460-db9ccf74362b | checkpoint | Holes and local depresions filled with similar material and compacted in accordance with Cl15
266c9d85-f340-5e4b-922f-2d657104b619 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
13be15f0-14e0-58b6-a82d-5adc58672435 | note | Check Item - Check Item
12555ef6-a18e-5b48-9a4a-4ae10eb31481 | note | Reference - MRTS04 Cl12.2.1.2
b6e46fbb-1d25-4078-90e7-e5f1054abf17 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a depth of 300mm using appropriate methods.
72386812-8c57-5f13-b440-63b48f511d3c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
07239a56-3de7-54da-a9b3-997f7a2677a8 | note | Check Item - Check Item
81d3fe2d-ff5c-5183-aba2-b744d2d1cf59 | note | Reference - MRTS04 Cl12.2.1.3
4bff9954-820a-4f10-a93f-04acf44cadb1 | checkpoint | Construction Testing Requirements: Test Method
e2abbf08-867a-5191-a6bc-91ec6e960850 | note | Acceptance Criteria and Frequency (Project Specific) -
f0a5b3ed-d30c-51ff-a767-7db6815be6ef | textbox | Max. Lot Size
466ac14f-9951-56e4-8b26-06803ab24fd7 | textbox | Min. Testing Frequency
f200793d-aec9-584d-b05b-ad01b4846a6e | textbox | Min. No. of Tests
f106bed4-cbc5-5969-859c-138a0aac9add | note | Check Item - MRTS04
6f21ef90-d058-5752-981a-c2fd213d735f | note | Reference - Table A1
d72d85c0-340d-4ba8-bb37-9cba4d8c2d81 | checkpoint | Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
1ae00050-9295-50dd-bb7c-441e0d7cec31 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: 5000m2
215f26db-6f69-588a-ad42-4c19eea467e3 | note | ○ 1 per 500m2
6c7866c9-0ddc-5612-935f-98533e8c05df | note | ○ 1 per lot
a1459c25-9db4-5b4d-855c-62a39229263b | note | Check Item - Check Item
bc8dc22c-6b65-530d-b4ab-058422409abd | note | Reference - Table 15.3b
d8c0fe55-7698-4573-bde0-f4270c5e716e | checkpoint | Final Verification
bcfcb95b-3d6c-52b7-b6e1-e679db9ed244 | note | Project Manager Verify that the Above has been Constructed according to Specification
19dad550-0d79-5c09-a35e-50dbb365eb9d | textbox | Print Name:
4eca7734-d98a-52c7-97a4-fe07867ff0f7 | date | Date:
f027279c-7b41-5379-9d37-0610ae95bc8e | note | Client Verify that the Above has been Constructed according to Specification
15dddb1b-14af-522e-99da-3527c04a6a54 | textbox | Print Name:
ee4c9eda-32a8-5197-bfc0-44324f6ba2bc | date | Date:
6eb677f3-4d35-4bf0-ab07-f466815f3bf3 | signoff | Signature
09320c7c-7f99-4ce1-9d33-d62fd3f77b4a | checklist | 04.05 - Embankment | itp | 04.05 - Embankment
861c4052-6583-4cba-b0ed-ccd0aab0f3e4 | section | Details
ad9f85f9-4f54-4668-9fb6-619f545dc562 | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
721b7000-ba54-5f54-a653-defb40b17957 | textbox | General Fill Class:
9bc14d4f-0214-5815-9f41-c63b37bb4d8a | note | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
9d28decd-9aa9-5139-8d79-c4486417398f | note | ○ WPI< 1200, PI>= 7,
ef922957-8084-5a9a-90b9-3aace184b3ea | note | ○ % passing .075mm 15 - 30
0499975b-a6e3-51f0-a296-b49d5502914d | note | General fill material Class B
08a3898d-5617-5ff8-ab01-430ac0b38340 | note | ○ 1200 < WP < 2200
51c5474a-063e-59a4-bbc1-b7cfd02caf29 | note | General fill material Class C
696cacae-b8c4-5167-8691-9ba7c2dbc653 | note | ○ 2200 < WP < 3200
46cafb56-da1a-57fc-9010-83f0588290f7 | note | General fill material Class D
be6c1352-8b5e-53d4-8d5f-19c27810fd9b | note | ○ 3200 < WP < 4000, PI <=50
be21b2b0-2f79-5f7b-a166-428aa615003d | note | – CBR as Specified
67095ff4-4659-592e-8904-cf8df9080676 | note | Check Item - Check Item
8022e200-4ab7-5da5-a46c-43ca0468bdb6 | note | Reference - MRTS04 Cl14.3.1 Table 14.3.1
6dd4c1df-1747-4da2-8280-4ed209e784da | checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
b38f419f-cf88-57b2-b3fa-7f713c4fb59a | note | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
0d5a5fcd-40d0-5540-989e-270d761b94f4 | note | Check Item - Check Item
32303f66-b7ff-50ee-b130-b005e56a3184 | note | Reference - MRTS04 Cl14.2.3
889853ec-b11a-41a7-98c7-b2af6c7a88fe | checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
5dbcb826-135f-5892-b121-5facb13dc420 | note | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
43d74922-f720-56ee-a832-211f4f8562d5 | note | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
ba4c43de-3ed9-5e76-8124-6887ef3fe500 | note | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
f9664fc6-9227-5f04-ab15-87990835e5df | note | Check Item - Check Item
98e36424-cb2d-4a53-8670-1b0a2910f431 | checkpoint | Compaction methods suitable for material type
bc437913-3ec3-5fee-b1c7-d8c095908931 | textbox | Compaction Method:
1476162a-9d61-59c0-8455-c169cd895f80 | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
4f96e20b-694c-56ba-a044-99f317e7873c | note | Check Item - Check Item
91c904e4-9bc4-5f27-a173-62f93fd5db9a | note | Reference - MRTS04 Cl15.2
32696f2e-8c7d-4f04-955c-7a970393d809 | checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
48152b64-2856-5595-88eb-ddfea44cbcb8 | note | – General Fill 150-300mm
11739d5a-4dc1-570a-bb9f-c8f73e30760d | note | – Fill in Water Retaining Fill 150-200mm
45dd2c3d-08f9-54e3-9d1b-f4e1beade177 | note | – Subgrade 100- 200mm
56ead049-031a-5de2-b588-772b7026732d | note | – Backfill except Sand 100mm-100mm
913782ef-77f8-5a3e-9145-40d6ce40c544 | note | – Sand 150-300mm
ade8c608-7714-5666-a721-e3bee6727251 | note | Acceptance Criteria and Frequency (Project Specific) - RDD%
cee509e4-2411-5ead-92f9-91fa8cdc9988 | note | ○ Insitu - >95%
e5c0ce56-dbf2-5afe-ba7a-78dae2a6a012 | note | ○ Bottom of Excavations - >95%
fa338d19-d561-5bd2-9b63-303a58381050 | note | ○ Subgrade (A/B) - >97%
e60feab1-624e-5e60-911c-e97e410d30da | note | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
f0ae5598-7514-59c0-8ded-1dd62e7dcd00 | note | ○ Road Embankment(A/B) ->95%
8b0e3839-01b0-531e-ba02-cd6ed42eeafb | note | ○ Road Embkmnt(C/D)' -90<96%
95f4e4da-92b1-52d7-bc39-9139033c3182 | note | ○ Road Embkmnt(C/D)* ->95%
2a646204-d086-5930-8178-e0f59e1fa75e | note | ○ Levee Embkmnt(A/B) - >97%
f6f49bcd-955c-5558-a20e-699527c6aa02 | note | ○ Backfill(Sand) - >70%
9b548e3e-fc10-5edc-abe4-f16e02dea188 | note | ○ Backfill(Not Sand) - >95%
6607c76f-be06-5811-b87a-abab6c3f1c52 | note | ' High Rainfall Zone
7b900395-cfad-5025-a194-872f31c58d6e | note | *Low Rainfall Zone
7b07b862-037f-5db8-8b49-216a8e6d48f9 | note | Check Item - Check Item
9a18d210-9686-5b2b-a47a-5c98e89ebeb8 | note | Reference - MRTS04 Cl15.3
701d3580-2fb3-4b43-ab0f-1e464922a16c | checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
1f66bf71-5cea-5174-aca4-cc475baea2ee | textbox | Rainfall Zone:
025530d0-92c2-5855-bca1-c1151e738a9f | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
1171abb8-368f-5e30-be2c-fb6dc6e5a8ea | note | Check Item - Check Item
018a5eff-d020-5f7f-9512-aba9f3fb9ce5 | note | Reference - MRTS04 Cl15.3
d2a02d47-85f7-48ef-83c2-a22712c6dc2f | checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
3babc697-38fd-5294-bad9-2009b6fad60a | note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
ab279e0b-8839-59a3-9ce1-0b604e576724 | note | Check Item - Witness Point 4
b7310807-c689-56d0-a3b5-0071e6d05377 | note | Reference - MRTS04 Cl15.4
5cef4bdf-a493-45a0-b445-3202e80371d5 | checkpoint | Geotextile placed at interchange between compaction methods
b5153794-b670-5117-98e3-e768d5639ff8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5e313c4-1ade-5f78-a6d7-f1eb13270af6 | note | Check Item - Check Item
41386088-d99b-501d-92b9-0afa8878e858 | note | Reference - MRTS04 14.3.2
7898f319-1ef8-439e-b025-51abcf75fe8f | checkpoint | Within Geometric Tolerance
e718f9d5-4d6e-57cc-8964-93d7a684fd15 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
8b145d67-2954-5211-982d-b9c601c03d0a | note | Check Item - Check Item
7f650f32-690c-584a-93d5-95a6c4f94e5e | note | Reference - MRTS04.1 Cl1.2
2fd01471-9fa5-4b58-ba20-c0b72d4a3d4c | checkpoint | Construction Testing Requirements: Test Method
faa87c47-857c-5f91-b1fe-62664da4a7da | note | Acceptance Criteria and Frequency (Project Specific) -
411171a8-6321-5983-9184-ca1f9879607a | textbox | Max. Lot Size
a380e2e4-9fc9-5d7a-92cc-fc5bca9eac93 | textbox | Min. Testing Frequency
4ab595a9-0224-5ee5-a10b-d00937b42622 | textbox | Min. No. of Tests
1c003d20-9f17-525c-89dc-01516f4e8ba2 | note | Check Item - MRTS04
d7ce95ea-5d9f-55c0-b99a-3020f70a68fc | note | Reference - Table A3
2110bb74-320d-5b58-8c33-70eb254a7bcd | note | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
79ab12ab-7027-4bb2-b451-e8848b541ee7 | checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
03b563be-2f02-51ff-9eb8-a7dbcccf5459 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
1cd5c724-c54e-5bcc-a757-d03fbe67b341 | note | ○ 1 per 500m2/per layer
4a4136e4-4c1f-51df-8b1a-c4d765f7e742 | note | ○ 4 per lot
aa1f9466-1197-5492-ae44-14b7eb8bdc0c | note | Check Item - Check Item
c1674a21-dbe5-5826-8a49-288134dea399 | note | Reference - Table A1
685bba5c-0066-43bc-8147-b6186305fd3a | checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
8f858c0f-d243-5062-bffd-235475a24d42 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
87fa83e6-1290-57c2-a386-254390cf103e | note | ○ 1 per 500m2/per layer
d85e50b5-27d8-5530-98b4-257c70ad4600 | note | ○ 4 per lot
12fe49e5-9ab9-521a-bbf6-fd4dd7eebfda | note | Check Item - Check Item
f0005f85-b534-58e4-b018-f591a449582c | note | Reference - Table A1
0aec33fb-57cf-4a63-a334-79a8540648a3 | checkpoint | Grading: Q103A
d6fe38fe-6c5e-55a0-b9aa-c7cee20dff34 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
c12aea30-724c-50a0-bdb9-6feaadebba1b | note | ○ 1 per 1000m2/per layer
c4d849f9-ac1d-58ea-a3b5-7824562bad71 | note | ○ 2 per lot
cc57a882-ecfb-5dbe-bee2-1c1ba4515216 | note | Check Item - Check Item
10b22c8f-826e-5b8c-a136-be1ff73a48d6 | note | Reference - Table A1
5fb8d2a8-394f-412b-969e-75422b23bb00 | checkpoint | Plasticity Index: Q105
f7a16551-7f5b-5da1-9afc-57e7dd494b36 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
bdbfc5bd-f1df-52db-b69c-df0e662fd77f | note | ○ 1 per 1000m2/per layer
a8785bc2-a57f-5677-b9b7-6775f65b3087 | note | ○ 2 per lot
fc8893b9-b33b-5f78-a913-3f9cdbe1e677 | note | Check Item - Check Item
2f051c94-07b3-5905-bfef-5025fa220db8 | note | Reference - Table A1
004b9b4a-a570-4704-98ce-40be627199e5 | checkpoint | Stockpile Testing Requirements: Test Method
3d48beaa-84d8-5b61-b169-90f5f124f899 | note | Acceptance Criteria and Frequency (Project Specific) -
50bedf0a-783c-5d31-8a9b-14354632cfe3 | textbox | Max. Lot Size
d32ee850-2e80-5c9e-9596-62adb8034d3e | textbox | Min. Testing Frequency
fe3e73b5-61e7-5514-90aa-7de98819ef73 | textbox | Min. No. of Tests
bab3796d-d469-5bf8-87c6-21cfb0fc1026 | note | Check Item - MRTS04
dfe64310-9f39-578a-a6c6-44dc10a1b096 | note | Reference - Table A3
1be705ad-f7cb-4c27-b1a0-cc01a2adae84 | checkpoint | Grading: Q103A
5bddeaab-4f46-5034-bade-c4c6a162e26b | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
e0ffed64-09f2-5fd7-8b26-536d9dacd697 | note | ○ 1 per 1000m3
7290abb3-ab92-53b0-91fd-ee0417ff8d7b | note | ○ 2 per lot
2e34fa3a-c819-543d-8301-efaf29e3208a | note | Check Item - Check Item
0e180307-54ca-5daa-87a7-8a97cf2c5406 | note | Reference - Table A1
adb9710e-4c5a-481a-80a3-00d56e1cc8c0 | checkpoint | Plasticity Index: Q105
f8983f86-380f-5b7b-adb2-616087139608 | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
60a6ca65-986e-5a27-bae1-8a9d9a7f6ae2 | note | ○ 1 per 1000m3
87a4cf66-703c-5214-a980-c1b6b54b64c7 | note | ○ 2 per lot
106f4386-94c2-520d-be94-3ce7cc31ae97 | note | Check Item - Check Item
73eebb09-242d-51e4-91b5-775e5453d93d | note | Reference - Table A1
0a538d9e-4ba5-49bf-88c6-ea6588b0e6f9 | checkpoint | Emerson Class Number: As 1289.3.8.1
6b17cd1e-e639-50b7-bfc3-0a77b14d442f | note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
c1ecb7e1-b4fa-5ce4-aeb0-b9a3da5dd80f | note | ○ 1 per 1000m3
0580f8dd-c9f6-5a12-aba5-901e5d31334e | note | ○ 2 per lot
3efe68c2-1c90-5dff-b10f-ab5ac3259c3e | note | Check Item - Check Item
c1a07ae3-6a17-5fd9-aae4-d6e203d65379 | note | Reference - Table A1
346fe327-f22b-457c-a182-3e9ea8f8e532 | checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
58df424b-2258-5a04-8a49-ff715b9caa89 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2df6c395-6856-5bae-9baa-3494bd8460eb | note | Check Item - Hold Point 8
348aa483-9f22-5447-9e83-60851e934117 | note | Reference - MRTS04 Cl. 14.2.1
ceb4bb47-2abf-411c-99f2-4a2ba906b5c2 | signoff | HOLD POINT
54a18e6f-c884-4102-8d9b-42770018f3f5 | checkpoint | Final Verification
307ca5ca-9686-53aa-9bbb-cde50f49c615 | note | Project Manager Verify that the Above has been Constructed according to Specification
276dea44-c924-562a-a258-1c319c5f2208 | textbox | Print Name:
feb883f5-a1ad-5ac7-8dee-8f2e39de11c5 | date | Date:
52b142c7-b6c8-55e1-b8fe-692e6dc7c610 | note | Client Verify that the Above has been Constructed according to Specification
25d05909-d4a6-5f03-ae71-bfa55904add3 | textbox | Print Name:
481177de-858b-514b-a3ee-55409f3a0186 | date | Date:
a7321798-5528-4d0b-bbf1-cb29966778df | signoff | Signature
04c7e10c-c8d7-419f-9260-eeb9cf21e8fb | checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation
5b6517dd-500b-4cff-b4b9-3c9dc4fb147d | section | Details
c5c433e7-c1a0-4078-8a3d-95fe4414986d | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
52f4c389-68d5-52b2-a86e-4a6b0d1e7110 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
885fa1a4-a90a-5773-8b69-6c659c050fd5 | note | Check Item - Hold Point 4
a87adb61-7a5f-5b97-8a50-2d12fd51077a | note | Reference - MRTS04 Cl. 9.4
04d1f0fe-0b09-444d-8c38-7c43abf63766 | signoff | HOLD POINT
adc1423e-d536-4d5d-8315-a331e1e04d8f | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
0f8605bb-cafd-5bff-b450-34f9288dd459 | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
721e6713-a6c0-53ea-90b3-f5180603d5b3 | note | Check Item - Hold Point 6
6a763540-cf83-5aeb-99b7-15820555e1da | note | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
1963507a-1aad-4610-a732-e33d8f792607 | signoff | HOLD POINT
c9e6b8ae-6d06-4d16-9cf9-3c196acd97d5 | checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
b7afa293-509c-5067-a929-724fccfe073b | note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
51ca0fd0-3269-5e9f-9c19-e98bf7bbf51a | note | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
898d8763-bcb4-5bdc-ab5f-aa0bd6bea67f | note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
6719c260-a26d-50b1-8d93-5fd89b60c70d | note | Check Item - Hold Point 6
cc873acc-17c0-5ce9-b037-579f0152f9e9 | note | Reference - MRTS04 Cl.13.3.2.2
6a5e5538-4711-448b-8947-16cd9fda165c | signoff | HOLD POINT
25ebd33a-44f5-42bc-bcf5-a8ca8f8ee926 | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
2994c2ce-3e6b-544f-9558-36fddbc9fe0d | note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
20127657-77a7-5c38-b123-c9d206eb7677 | note | Check Item - Check Item
6a251a06-a958-538a-8b94-771d047164f6 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
4772e43f-8f9d-452e-bff7-3b1f24b3cf4c | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
4e7f6aee-2722-55ed-bfc3-1d9ac6e9f208 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
79abb2e6-5f55-5d46-94d8-12dcdd925b8a | note | Check Item - Check Item
3fe2012c-02c7-5e4f-bdfb-2ef3d97cd9eb | note | Reference - MRTS04 Cl. 13.3.3.3
a06fe0c4-4805-41f9-816e-f2571f531736 | checkpoint | Dewatering of excavations shall comply with requirements of EMP
4091e60c-6265-58bb-8673-a05f9def68ff | note | Acceptance Criteria and Frequency (Project Specific) - Visual
90d74c15-386d-52c9-be8f-86235744adef | note | Check Item - Check Item
b8807c29-2e99-58c6-88ba-ac32f844d722 | note | Reference - MRTS04 Cl. 13.3.8
8949f8e2-6f9e-46b2-928b-8bf5a2abb185 | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
f27ca1c8-2ed1-5c8c-aa63-af540f66e637 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c4712d3b-1083-5ec2-b9ec-2c413aa279f1 | note | Check Item - Check Item
ccb06d4d-0545-57c9-9af1-6f50b6e92bc0 | note | Reference - MRTS04 Cl. 16.1
efee6388-1dbf-4443-8053-a76a8a04863a | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
67f385a9-56e7-53ca-9319-af4dd4455259 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f9763a2b-59a7-55ad-85cd-87971292a833 | note | Check Item - Check Item
c1ad6a29-445c-5b5d-9af1-8f8f7d83ba2f | note | Reference - MRTS04 Cl. 13.3.2.4
69122e42-7033-4517-ae6f-c02bf13229eb | checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
60d7f80b-4f29-5568-a006-f7e3cd5a819a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
89416e19-0eed-53de-a3aa-98122c02475d | note | Check Item - Check Item
64fdbbc0-fc57-5aeb-b4b4-b424eb569af4 | note | Reference - MRTS04 Cl. 13.3.3.1
d85bf46e-89cf-4e36-80b8-b292cd80e163 | checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
ecc863cd-2f98-5c80-b442-42bdd4c29012 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8d367b4b-66de-5683-b4b7-518f7c5b256c | note | Check Item - Check Item
6fe64d0c-0b42-5d2e-9db5-31ccd20e2c57 | note | Reference - MRTS04 Cl. 13.3.3.2
c338e27b-3f18-41f4-b89d-b0f384881aa0 | checkpoint | Final Verification
45a87a1c-4fcc-59ac-9a2f-da7d552593df | note | Project Manager Verify that the Above has been Constructed according to Specification
a01f0eef-faa9-5f2b-8b52-5b431cf99445 | textbox | Print Name:
e6768741-1e7e-5d48-9752-b8e82082bbf3 | date | Date:
fa2f9caf-2efa-5713-a76e-526aaa9e580f | note | Client Verify that the Above has been Constructed according to Specification
66ce72d2-8961-567f-b539-fb8cc037329e | textbox | Print Name:
b9f46097-dfea-57d5-9616-4aa3582b935b | date | Date:
c988dc00-4093-4616-b372-1cbb2406799b | signoff | Signature
ce16ea3e-aee5-4a9b-87b1-6e7df1f4bc4a | checklist | 04.07 - Structure Excavation (Unsuitable) | itp | 04.07 - Structure Excavation (Unsuitable)
34076b13-ebbc-4aab-b276-9b3fcd5b8dbd | section | Details
1f7125cc-c906-45b4-8de9-2fedf27490d7 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or pottentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
29355cdc-6725-594c-960e-28f5384da8f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
eb5ba414-2e97-58ea-ad27-9fd30814e9b6 | note | Check Item - Hold Point 4
e8a00d09-c0bc-5957-9a4d-d9bcc0cb0034 | note | Reference - MRTS04 Cl9.4
cd603482-771b-41f0-aaa1-5e87aa24a90d | signoff | HOLD POINT
d94e7251-ac05-4980-a841-c766d6bf12e1 | checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
ca6ed149-1ef1-5d42-b4b9-2da0a07b17cc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c20d931b-9457-5983-8fed-c904c593ca51 | note | Check Item - Hold Point 5
9b9e0d7d-7e1a-52bb-9d76-effdb5d31779 | note | Reference - MRTS04 Cl10.
785e7566-5cd3-4cce-8906-f55dcaedf12e | signoff | HOLD POINT
f30286ef-eccc-47f4-b3d4-2de27cd7db27 | checkpoint | Where shown on the drawings or specified elsewhere, a layer of blinding concrete shall be placed over the foundation material as soon as practical. The top surface of the blinding concrete shall be screeded neatly to the shape and levels shown on the drawings
250d2016-99fa-5464-b0f7-678b7700abf9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0a4c007a-56a6-52c3-a7c8-3e4113dc78a9 | note | Check Item - Check Item
9c28c4bb-de60-5b81-9958-2d6c9ae2e438 | note | Reference - MRTS04 Cl13.3.4.1
8877189d-6a41-4fa3-8e9e-28c2aab08d0b | checkpoint | The widths of excavations for culverts shall be the minimum necessary for their construction and placement of backfill against them, provided that nowhere shall such widths be more than those shown on standard drawings 1359.
c613fd92-786a-501f-a1b6-10f8bb800287 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6de08678-dd7a-547a-8727-4661fabf6337 | note | Check Item - Check Item
7d500f27-885c-5429-ace1-7ff025345aa6 | note | Reference - MRTS04 Cl13.3.6
113d2780-de53-443d-9472-963e7b12f2f5 | checkpoint | The material in the bottom of excavations shall comply with the density requirements of Clause 15 and compacted to a depth of at least 150mm.
92d5e7a2-b7a6-5d9b-854e-bccd710f0e7e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
12625dd1-46cb-56ee-b40f-056944933994 | note | Check Item - Check Item
67365e1b-eaa0-5d78-9b23-e84444618876 | note | Reference - MRTS04 Cl13.3.6
6ebf3af5-e520-4b6e-9d0f-556272f24872 | checkpoint | Compaction: Q140A, Bottom of excavations = 95%
1ff8e869-fc7d-57fb-9d0c-80485315dd53 | note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: each culvert or end structure
ffbab4c4-a699-5b6e-81f8-0f793b8cd7c0 | note | ○ Min. Test Frequency: 1 per 50m2
0c86ba10-2a2d-518e-89d1-ce0362de258d | note | ○ Min. no of Tests: 2 per lot
50ae2886-765d-5f15-b6f2-9e8b446b4fac | note | Check Item - Check Item
4c50eb10-a9a1-5f18-bbb6-4c4ca0ab9ce4 | note | Reference - Table A2 No. 2.6
d55fe106-9a0a-4480-b1e1-9c2c7392e663 | checkpoint | Supplementary Requirements as per Clause 22 MRTS04. The material used in backfilling unsuitable material excavations, in addition to the requirements specified in Clause 18.3.4.2 of MRTS04, shall satisfy the minimum CBR requirements of Clause 3 of this annexure.
c4c141b8-73e7-5984-ae87-06575727315d | note | Acceptance Criteria and Frequency (Project Specific) - Testing requirements
63a49ee7-b46b-577e-9041-b051752047fd | note | Check Item - Check Item
076ce852-52e5-54d3-970b-73d265c591c5 | note | Reference - MRTS04.1 Cl. 13
43db904a-f6d9-4454-b46f-20f639c1cb6d | checkpoint | No areas on Site are available for the disposal of excess and Unsuitable Material. If no areas are indicated, all such material shall be removed from the Site
e0e06a39-1ef0-50d5-b80d-f6d24d355055 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
af1a7ff9-78d2-51d5-979a-998fb7e838eb | note | Check Item - Check Item
701c051e-bd12-5105-977a-a12de0515bd8 | note | Reference - MRTS04.1 Cl. 5
707c6091-acc6-4047-9480-cd810409f8ee | checkpoint | Final Verification
c6c31c33-94d4-5476-bb69-28cb01021b05 | note | Project Manager Verify that the Above has been Constructed according to Specification
f7daa40b-cfe7-5b25-99a6-baec325e6223 | textbox | Print Name:
c0cf6823-9a5b-5570-8b0c-a61ee0813359 | date | Date:
cc040076-9958-5949-8cad-0c6dd141e69c | note | Client Verify that the Above has been Constructed according to Specification
5383089c-8234-5c8e-a0f2-ea8b7ddda0ed | textbox | Print Name:
1a0d9aff-c8ce-5026-9578-325cb1793ba7 | date | Date:
33dcb7c4-44fb-45d0-93be-75e50e064632 | signoff | Signature
0712b0e1-6353-4871-8adb-fe9800611e1b | checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil
229a722b-8fdb-4355-998e-5282906eed02 | section | Details
f1509e99-5211-493b-b110-ceafb3389462 | checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
983ba1ba-2c90-5e3b-9730-b8e0f8cec1df | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e8449945-3cd3-5ceb-b2f7-b863639c6427 | note | Check Item - Check Item
08203cb6-0664-54ba-a244-9902eb947326 | note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
87456ede-264a-4d7a-a12f-a0e283796a20 | checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
18e8087f-0abf-54e1-83d8-e81a246fe9a9 | note | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
8e5ff08e-892a-508f-b8bc-cdb62080a593 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
b569f06c-cd7b-566b-9120-a3b462772839 | note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
338b59e8-1cc8-55dd-a817-fa8150d8cb3a | note | Check Item - Check Item
4adc3eb5-16e2-5aff-acc5-e8c335a920ae | note | Reference - MRTS04 Cl. 8.3
bdfd1002-409b-4fa2-ae25-eab35a662894 | checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
84bed0c7-ca17-5db0-b1eb-839e903c147a | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
8e8acea4-6ff4-504e-8db9-c37fd73997fb | note | Check Item - Check Item
95b9d6f6-9b06-5a20-af3b-98f4af2cfcac | note | Reference - MRTS04.1 Cl. Cl. 5
d3d533ab-8806-4d7c-8e0e-d9009b9139a0 | checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
74b99a5a-284f-5067-a060-cefe69ddb9a9 | note | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
673755f4-6cd6-5259-932b-7a62335ebf4b | note | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
87fbcf12-f598-5be0-aab8-7f70aaea293a | note | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
00d4ea5a-5af8-5e71-beb4-8ef07f40633c | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
91c97582-4c56-5cfb-bd67-e78912ddd367 | note | Check Item - Hold Point
aaeebede-9fda-594e-ad75-f5ec760ae67b | note | Reference - MRTS04.1 Cl. 2.2
e640fd9e-1e34-4ee8-a490-9e48a8f3b808 | signoff | HOLD POINT
33bc783e-4762-487d-b343-d8a40103ffbf | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
18cad80c-89a8-59f1-8937-d36eb730650b | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
95620579-f329-5981-998e-25b7506cf486 | note | Check Item - Hold Point
db9f8775-b25c-5048-bef0-f56623eb156a | note | Reference - MRTS04 Cl. 8.4.3
b17086fe-90fc-4b14-9531-761de56676fe | signoff | HOLD POINT
deb998f6-2992-40b1-a2b7-08245a1e5436 | checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
997d07f9-7300-5f1d-8367-4bd9397ebd67 | note | Topsoil Stockpiles are;
8db08bdd-d6a1-514e-b9b0-d89290a38469 | note | ○ Less than 3m High
d0970840-7f7b-5b6f-83bb-bac8474bc19c | note | ○ Less than 10m wide
341539a6-740b-583a-9b49-45e8033901c2 | note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
28856029-74e4-5869-aae1-5060784f27b6 | note | ○ Stockpiled for the minimum duration
2cf744bd-c281-54ca-bac6-1013efe59be3 | note | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
c1fd7a99-d860-5225-9ae9-8f700ab8737c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
21104ef8-f37b-532a-aeec-94d0594b350e | note | Check Item - Check Item
a4eb517c-96bf-5603-b5ac-36fb816f8090 | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
6256dbee-3354-4872-8ea7-ea6418c46c43 | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
a71b43f8-1807-5b2e-bd3f-fd672e506ecd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3e12f3c7-138f-599a-8d39-66a402232828 | note | Check Item - Hold Point 2
b7097265-d08f-54e8-95e5-79adb66e463c | note | Reference - MRTS52 Cl. 7.1
95aa400b-6078-4c70-9e9d-edd710e0f454 | signoff | HOLD POINT
75ee8cb2-443c-4b09-b5a4-bd7193f25ec0 | checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
c1db97ab-3d2c-591f-8dfc-9e5d7d7675cf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5680ccd-7697-5887-b87b-93550567f721 | note | Check Item - Check Item
2a2e7551-4575-59d3-bebb-867f547ec91c | note | Reference - MRTS04 Cl 8.4.5
64361277-a5cd-4d0b-9aef-2b6066f8e45b | checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
e4ba6c86-fcef-52de-8395-e62ef466c826 | note | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
cb3ba2df-1a4b-5d93-9ab3-def2791748aa | note | Check Item - Survey Report
5f48e5df-56d4-5e72-9443-3916b0a92065 | note | Reference - MRTS04 Cl 8.4.5
97d2a7aa-9b31-4316-a4cc-ffcf879d35e3 | checkpoint | Final Verification
3188cb3f-d4ae-5587-b86b-60aaf788ea69 | note | Project Manager Verify that the Above has been Constructed according to Specification
38f9e5af-5b90-5cb8-90f6-cf19cb6fd058 | textbox | Print Name:
88d7136c-bd1b-5e58-9672-8731caec9fc9 | date | Date:
ebc96473-d6a8-5f1d-b26d-d5e3bd434ef2 | note | Client Verify that the Above has been Constructed according to Specification
ab766fa8-c3df-580b-8896-d8415cfb4f6e | textbox | Print Name:
968f26f7-67e1-5326-bc6a-70cbe44e713a | date | Date:
c8060176-9074-4af3-a809-8faa41a44829 | signoff | Signature
445081bf-016d-4343-8f94-31c8e5f98a6d | checklist | 04.10 - Backfill | itp | 04.10 - Backfill
feb55145-2196-44ee-9454-45db7a50a93c | section | Details
f04f4fca-4b64-4ff5-9046-58d9f9a55748 | checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
2ee6b860-b228-5a18-985b-28d62d4db816 | note | Acceptance Criteria and Frequency (Project Specific) - Written
6f9b108a-97a1-5308-85a9-b93f0dbe8889 | note | Check Item - Hold Point 11
928eb49a-4122-5ee5-9550-ab9470341abf | note | Reference - MRTS04 Cl19.1
2681fdd1-1b38-44dd-a6c4-3e50031a98fe | signoff | HOLD POINT
1cc9097f-7f0d-4b90-b13c-fdc189e88acb | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
bd98cc36-d8a8-5e2f-bc7e-4dd9125cd601 | note | Acceptance Criteria and Frequency (Project Specific) - Grading
88676622-119d-5743-b9bc-b982912729af | note | Check Item - Witness Point 6
7f091b31-0798-5da4-9ee9-79a7513f05e2 | note | Reference - MRTS04 Cl19.2.2, Cl19.3.1
88037842-06e4-49aa-895e-4fea38f62553 | checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
df3b78ce-87cf-5cf5-ae2d-b2512fc2fb2f | note | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
efb94057-2067-53c2-819d-af1d29576ea4 | note | Check Item - Check Item
122b255b-ab2d-530b-b77d-0dc42880c0d7 | note | Reference - MRTS04 Cl19.3.1
4d6e3551-e11f-4b4f-aefa-b6ad7db23337 | checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
d2e483bb-3d02-51f1-b33b-61f1491eea94 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec444dfc-1ea0-50b7-b728-bca760ba353b | note | Check Item - Hold Point 12
e27651ac-19cb-5db3-a1c7-581641e252ee | note | Reference - MRTS04 Cl19.3.3
95c5856d-9de5-49ae-8ef8-969c4f8bbb12 | signoff | HOLD POINT
bd16153c-8664-41cb-b88e-00a8151178ca | checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
437dbac9-af34-5bf4-89cd-93d0fbaaf2e8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
78331fa0-64f0-567b-911b-30a1c89ceb86 | note | Check Item - Check Item
364cdcf8-5058-5826-9688-8e2423f941bb | note | Reference - MRTS04 Cl19.3.3
3ec58ec7-02d4-45ff-9a85-fa22b296ed23 | checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
2bdce6e4-4dba-5eee-8429-bcca9c98f5bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
032b975b-eb76-5bd5-9b8b-8de302c5a165 | note | Check Item - Check Item
65127a7c-5e5a-55cd-ab02-864db9d787df | note | Reference - MRTS04 Cl19.3.4
c31ba28a-16a8-41e0-b7b6-9022d3551ce3 | checkpoint | Construction Testing Requirements: Test Method
994568ed-f64d-5225-98ee-c1c82c90718c | note | Acceptance Criteria and Frequency (Project Specific) -
2a99b1dd-787f-504b-bfdf-ad6fae32683f | textbox | Max. Lot Size
410c40d0-cb23-5c17-9b77-a200542b803e | textbox | Min. Testing Frequency
32d26164-5aa7-593b-9bfb-a9046d3cd85e | textbox | Min. No. of Tests
b4f2f349-d32f-581f-be8f-765c66ee456d | note | Check Item - MRTS04
f9a3c45a-c8da-5e1f-ab95-2a9542baf1a5 | note | Reference - Table A3
d53b5094-0e44-4e65-a0ff-28f9d32aabb8 | checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
1ab92680-d332-5ee3-a0cd-1fda8027fbcf | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
cc7171da-332e-5103-bca1-405b2534d7f0 | note | ○ 1 per 100m3
2042c734-1913-5d1b-bb51-878f7ecac9c6 | note | ○ 2 per lot
6ada4c11-c97f-5868-b002-13862704db2f | note | Check Item - Check Item
ca56f5ac-4fb6-5869-8e7d-328a938a05d9 | note | Reference - Table A1
d8ddfcf1-e50f-430b-986e-48f29fa5261f | checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
35893465-64c3-5d76-b2eb-83a8b160aa43 | note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
e17b919c-f9c3-5e54-b72f-c602c5e1fb8f | note | ○ 1 per 100m3
8bbebc83-1129-5658-96a7-5ae574de0251 | note | ○ 2 per lot
59895bc2-a11f-543c-886f-4bb0d90f2313 | note | Check Item - Check Item
2542eb93-378f-5922-9aab-5698f44b7f47 | note | Reference - Table A1
4af4fd07-7f43-45d4-b436-820e265b5675 | checkpoint | Stockpile Testing Requirements: Test Method
c1e5aaf5-7743-59c2-9c16-9c67cc4c847b | note | Acceptance Criteria and Frequency (Project Specific) -
b99fa55b-45e3-5c03-8b02-120d13d968fc | textbox | Min. Testing Frequency:
f189b1f3-1b76-56ef-8900-dfe16eb548d5 | textbox | Quarry Source
6c8462c7-9e86-5a7a-aaa1-2e66b7218c2b | textbox | Other Source
2c04df19-f811-5bb1-9403-33869792d498 | note | Check Item - MRTS04
409c4cd4-4849-586c-a524-e1e423c4f488 | note | Reference - Table A3
ff602c3e-bdfe-45a1-b9c9-e1220da1aaa7 | checkpoint | Grading
d50cb8e6-72ca-53ba-b60b-1a5840120f87 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
635ee411-ef66-5c68-9ab8-9e9a3f0d4e37 | note | Check Item - Check Item
1b69ffbe-bab4-553f-8b15-229105d00438 | note | Reference - Table A1
30066735-d62d-42d9-9291-dff1425aa152 | checkpoint | Plasticity Index
960fafa0-989d-5d1e-99dc-901355852ae5 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
5727b54c-6102-520a-bcbb-308d5c982684 | note | Check Item - Check Item
05f2022d-dc17-5813-b108-47120b7aef1c | note | Reference - Table A1
f564d3fc-1392-4762-8c01-50de380c0b19 | checkpoint | Linear Shrinkage
5b33c2b5-2f63-593a-aaf4-feb2a037c28e | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
1ab9e871-0002-52d8-a80d-0c92ce4a7b02 | note | Check Item - Check Item
ccbaa4ab-bbab-5bf8-bf14-b78a07b356a0 | note | Reference - Table A1
cdc11683-b813-4409-baa6-59d4a88bd754 | checkpoint | Emerson Class Number: AS 1289.3.8.1
6ee5421d-dec6-56f7-b040-4d0533cc3bc2 | note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
55233159-f8d6-5862-ad10-290814bf6a09 | note | Check Item - Check Item
af64374d-c6ba-5c3d-8b6b-79044e5ad4d0 | note | Reference - Table A1
25a2df38-db2a-4b31-a43f-ffc7bf2b6521 | checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
952d11e0-8c85-5bcf-af7a-b7ae2a37a5c9 | note | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
18668d0b-9e15-5780-898f-32f837c5c922 | note | Check Item - Check Item
443607c8-43db-5f4d-be5b-71632af11466 | note | Reference - Table A1
7af59a03-5835-4d8a-8f04-c23f01b6c95d | checkpoint | Final Verification
5628236c-e95a-58ec-a73a-e266dd26db52 | note | Project Manager Verify that the Above has been Constructed according to Specification
90285c50-2c5b-50c0-952a-fa542687c9ee | textbox | Print Name:
3bfb0955-e4e4-57c7-ae33-94c4c2aacda4 | date | Date:
f39ba63d-8227-5fb1-a4c1-361390f7cf4f | note | Client Verify that the Above has been Constructed according to Specification
937f2cc3-099c-5fda-80cf-273f883c614e | textbox | Print Name:
8abaf67b-4c03-556e-a36a-2f06f68bcf45 | date | Date:
e60ceaf4-32be-4ac3-9b35-71cd9e77648f | signoff | Signature
224dc503-6f35-4b24-8380-e4979f159c7e | checklist | 04.11 - Demolition of Road Furniture | itp | 04.11 - Demolition of Road Furniture
4c78fe31-ddf5-4ebc-afd7-1f890d89a5c2 | section | Details
6e2b4232-e9db-476b-b649-f0131b6649f1 | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
4761c97d-1c97-506d-8b8f-7f9dc0befa05 | note | Check Item - Check Item
be669a6f-6ca3-5ea1-a949-84bf9cefd2de | note | Reference - MRTS14.1
d89a134d-fe58-45dd-b0b5-4db78e3bae0f | checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
cb3c5cb1-f34b-5dbf-a552-8f02cd4c37fa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6f5ba8f2-932d-59bc-b650-af760e1384e8 | note | Check Item - Check Item
40c0a31e-ed34-56b7-a8b6-5eb105d1be81 | note | Reference - MRTS14 Cl.7.3
b117034f-656b-4cbe-bab1-043db8f07ac3 | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
924c967e-59dd-59d2-9973-25edc87135da | note | Acceptance Criteria and Frequency (Project Specific) - Visual
86c95370-09c6-511f-a091-bd84abe1ef10 | note | Check Item - Check Item
950ac250-39ca-52c0-8fe6-004285b00dcf | note | Reference - MRTS14 Cl.7.3
afec2033-d428-4b3d-8c46-19afca2bcc1d | checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
99e9c402-54a0-58be-879a-8a760f1a0e7e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
570b477d-3def-56fb-ba0b-7d4dc549048f | note | Check Item - Milestone
ca34f4f6-41f4-5beb-87ed-b83dee9ca4ef | note | Reference - MRTS14 Cl.7.3
116f6cd6-a412-4bd4-8bcc-98965b2e6a7f | checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
92a0ae24-9fd1-5520-8137-cdce44f9891c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9b1f9e48-bdce-5297-938c-f4c945767f9e | note | Check Item - Hold Point 2
f0b1f07f-257a-52fb-ba17-0669a6afd13c | note | Reference - MRTS14 Cl.9
dbf0a989-aa4c-48d5-b289-7f7eb7af8d6c | signoff | HOLD POINT
e21c3a52-8a95-4f3a-80f5-34975437fe81 | checkpoint | Final Verification
44854862-a8f0-5abb-9fa3-891dd1823e47 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
5c46cc2d-3f00-51d1-bb2a-0a6522268c64 | textbox | Print Name:
9354b220-8180-5b7b-974e-d21b877c2d29 | date | Date:
baf0afe1-59e7-56f8-9742-642c02d36715 | note | Project Manager Verify that the Above has been Constructed according to Specification
0fa232da-3428-5cc1-877c-2f4f63769af4 | textbox | Print Name:
cd53fe0e-d8fd-5741-8579-32963b4f1417 | date | Date:
83f3604b-741c-4e82-a464-93574965a49d | signoff | Signature
7f7fdf57-1e69-4872-92c3-894c1170e6d4 | checklist | 04.18 - Subgrade Testing | itp | 04.18 - Subgrade Testing
5fea2480-35e6-42b5-96d5-56832cc46eaa | section | Details
ca7b41e2-bdc5-43c2-b0dc-271074fe6e2c | checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
203d6762-28a9-58ec-9eef-7bb387222b3b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ea831302-7bae-5416-a969-5eef30a2ffa3 | note | Check Item - Witness Point 5
652879b0-4ca2-56a0-bdab-f2e963f35db2 | note | Reference - MRTS04 Appendix B.3
76112c33-bdd7-4a4e-adbb-1d8fa6dec107 | checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
0e156546-2c5b-5c8a-a5d7-1c539e0a0a94 | note | Acceptance Criteria and Frequency (Project Specific) - Testing
25affc2c-85b8-5a55-82f2-afc414a25efb | note | ○ 1.5m below subgrade in CUT
27317f9e-bd06-5824-9d4e-6f7f3f5aacd3 | note | ○ 2.0m below subgrade in EMBANKMENT
683b1c09-19a9-5453-8bdf-141a94e50780 | note | Check Item - Check Item
9ad4c2f2-31ae-516d-97a8-47f6c63824ad | note | Reference - MRTS04 Appendix B.3
d1d5aec8-2ce9-4e8f-871a-18ca1138d9ae | checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with RMS Test Method T103
27045efb-324d-57ff-a5e6-d6b9f1c89081 | note | Acceptance Criteria and Frequency (Project Specific) - Testing
3b2f126d-6132-5856-bbd2-b7ac0e792a19 | note | Check Item - Check Item
fb8859b6-97b7-5158-bbfd-2e8337270aa5 | note | Reference - MRTS04 Appendix B.3.1
8617305a-c305-4de2-9215-2da0708364f8 | checkpoint | Fill Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include: – Lab preconditioning, – Field compaction using construction methods propsed for the works. The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5.
274b4537-edb2-53a8-ba7a-e186100bf5c2 | note | Acceptance Criteria and Frequency (Project Specific) - Pre-Conditioning
9a379411-3d71-5438-aeaf-84bf2e7d545f | note | Check Item - Check Item
231f1506-ba26-57ba-acb4-788eed8fba84 | note | Reference - MRTS04 Appendix B.4
af3492c8-9eeb-496e-8d31-049aa5240520 | checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
1c44af4e-82ab-5418-8c95-c39fca48b284 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports
f8d76e0a-177f-5ff4-83d8-3240aaa7810f | note | Check Item - Check Item
fc12919e-9cbe-5d8b-a01a-fdf1982d491e | note | Reference - MRTS04 Cl. B3.2.2
31c52d71-0322-4f0a-be48-9add3405c4e4 | checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
4429c24d-ac44-5a22-9b69-eb27796a168b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2d31c143-ecb4-578e-a5bd-caa7223b3b58 | note | Check Item - Witness Point 6
258dba69-e3c3-5a1d-afe4-51413d695897 | note | Reference - MRTS04 Appendix B.4
efe9b689-1b11-4cb9-91a4-b08baa95abb1 | checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
9232fc7e-be71-5e2b-8ff2-9f75efdaa1d6 | note | Acceptance Criteria and Frequency (Project Specific) - Testing per material type
f56a2309-a292-57d5-8b36-2af818e03bad | note | Check Item - Check Item
b5082942-afd4-546e-9e0a-632781758e27 | note | Reference - MRTS04 Cl. B.4 & MRTS04.1 Cl 3
3a9ff274-313d-46c8-bc1b-7af59b5044af | checkpoint | Final Verification
f7bb8231-e22c-5057-be8c-93d518d1ff1c | note | Project Manager Verify that the Above has been Constructed according to Specification
d59899ab-83bd-530e-9071-8c7135cc3d3c | textbox | Print Name:
196d3f1a-89f4-58c2-85ab-b61be827a796 | date | Date:
d72f4a38-5d99-5629-859f-eb34a0f8320c | note | Client Verify that the Above has been Constructed according to Specification
0fde5148-3913-5b88-9814-703f5c60e983 | textbox | Print Name:
0ab71559-14cc-537e-a3f9-4a1cbdca06f4 | date | Date:
fe4f7e1e-3ec3-40ee-9aa0-cd5f7126c104 | signoff | Signature
5d3129d4-31f3-43aa-adcd-04444938daa3 | checklist | 05.01 - Placement of Unbound Pavement | itp | 05.01 - Placement of Unbound Pavement
8ad1e37a-2533-4222-a70c-27f555b24c52 | section | Details
4fc8dfd6-899f-4aa0-ba55-df6ad159e2a1 | checkpoint | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
1104eab2-9d84-5857-87e2-dc330a5b9445 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5c12760-f884-536c-a0fc-aedf484d8704 | note | ○ Layer Thickness: 75mm - 250mm
799021c4-9042-5783-a1a7-2996a0597fb8 | note | Check Item - Check Item
056f0ee1-4e23-599c-8dea-167558c97b02 | note | Reference - MRTS05 Table 8.3.3
456bcbf9-de7c-4033-ac4d-2561bbf72333 | checkpoint | Relative Dry Density Requirements: C.V of RDD >= 100% MDD for Type 1 Materials, = 100% SDD for type 2.3, 2.4 and 2.5
c1205a4f-3b72-54a5-ba64-6c8b2bb837cf | note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD (1 test / 500m2, min 1 / production day, min 4 per lot)
0ccca87a-3c5f-502f-b448-958c365ddc1d | note | Check Item - Check Item
ed2cef93-6c5f-5f0d-987b-854430b6ec38 | note | Reference - MRTS05 Table 8.4.3
5462132a-a59b-4095-8f29-32718b009b40 | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
41bc32d8-84b0-57e2-b394-ed3d179d5c29 | note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
c28afa4f-5244-524d-80e5-a3786cfac1e5 | note | Check Item - HOLD POINT 3
6ae93189-0630-55af-ba49-e1e7ec121220 | note | Reference - MRTS05 Cl. 8.2
9daada6a-9526-4fcf-ad3a-1302a19cc942 | signoff | HOLD POINT
ed8d2ba6-30fe-4ddd-a89f-74f8e0faa2ad | checkpoint | Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
b96ba49d-e67a-5c34-bf8f-7ac39e20e60f | note | Acceptance Criteria and Frequency (Project Specific) - S < 60% (1 test / 500m2, min 4 / lot)
80b3f548-eb09-55e5-aa8f-5473519bcc92 | note | Check Item - HOLD POINT 4
554ce9d3-7bdf-530f-8fa2-afdc1c98abc4 | note | Reference - MRTS05 Table 8.3.4.1
6057c80c-4b82-4ac3-9e39-18845a88122e | signoff | HOLD POINT
74496b9f-2840-4c3f-b33e-3f5f67c71b68 | checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
8e6b6f81-980a-504f-ab7a-ab6bbcca5317 | note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
af145a03-b819-57ff-94cd-ac9d09324bd6 | note | ○ Additional tests as directed by the Administrator
73187555-6060-5798-8cee-f8cf99cb231b | note | Check Item - Check Item
0b870fe4-c3f8-5105-b280-18a5cc9357c6 | note | Reference - MRTS05 Table A3
69ff1e5d-5c15-48a1-9165-c8b917458a5f | checkpoint | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
684251cc-452b-55b9-87b6-7a12cf9b9dbc | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
1cc6a863-8d35-5673-aec4-9e236acac61a | note | ○ ±15 mm in all other cases (1 test / 20m)
d8a6ad18-a1f9-5311-9e7c-73214dbf7971 | note | Check Item - Check Item
4e20ad36-ea58-5409-8222-5abb79946ce1 | note | Reference - MRTS05.1 Cl.8.4.4.3
157e5492-4208-4d9f-a873-a078341a2a4d | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
0bba8066-010d-5a50-a377-5e14e7a680ff | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
c6cf12a2-1dbb-52cc-b4f3-6292b16fabf0 | note | Check Item - Check Item
d65d0c83-e7cd-5463-9377-2f8ba37e600f | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
b4e17ab5-0e29-4e71-815a-8b4a05abd24f | checkpoint | Deviation from a 3m straight edge shall be less than 5mm.
2f4d4a9d-400d-5885-8440-04ed52d5c6f3 | note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
e92d91ef-69f8-5dbb-a346-54d35a8e313a | note | ○ Less than 5mm
c4549d57-cce7-559f-88ec-b92f93f93e8d | note | ○ 1 test per 20m
4299b1bd-78f6-5a39-bd8f-c51bfc7ed465 | note | Check Item - Check Item
3fdfffea-c85c-59bd-9eb8-a97e4780ce0c | note | Reference - MRTS05 Cl. 8.4.5
96d56521-c8cd-47c4-83f2-1c3babeb6678 | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
42d1169c-22f1-5c00-8439-845e1b028c50 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
19a43088-5fc3-569f-b602-5ef82e4ba035 | note | Check Item - Witness Point
5d9a139b-1981-561b-b43a-c10c6b985a6b | note | Reference - MRTS05 Cl.9.4.7
940f3109-e3ac-4f20-95bb-3119ca1fef93 | checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
2f8b5cdf-39fb-5eb0-9b1f-b64b8c29c1a8 | note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
8975bb0e-b9ed-5ec0-8fc9-8e71cc1fc1f3 | note | Check Item - Check Item
a3b1aa9e-f754-5d6b-ae10-0cffb3923bdd | note | Reference - MRTS05 Cl.8.4.4.4
4bd5c507-31b1-4000-a6be-088097fe432d | checkpoint | The finished surface of any unbound pavement layer shall: – be hard and homogenous in apperance, – not have any loose, segregated or contaminated areas, – have the coarse particles slightly exposed, – not be affected by delamination, and, – not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
21431be5-cff9-5c38-b18b-e8e57b7203f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
007db574-aa7e-5626-b6bd-8e772b22dd30 | note | Check Item - Check Item
1c7a32cc-392e-5cba-89fb-f6ab4e6befe8 | note | Reference - MRTS05 Cl.8.3.5.1
5863ceff-df0c-4715-a9c9-06b147e36b17 | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
9b057d5d-b306-5b99-9ceb-785693b6ea59 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
bf41b9c3-0537-5b2e-abcc-5e8f0a43b02e | note | Check Item - Hold Point 5
fb81c2e6-f999-52ac-b598-d8f55b18b41a | note | Reference - MRTS05 Cl.9.1
baf12acb-e6ef-4e37-8a77-8c66e1c7cacb | signoff | HOLD POINT
d4db2477-6a7d-4317-9bc2-83fc538b0b4b | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed, b) the surface finish of the layer complies with the requirements of Clause 8.3.5, c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator, d) the layer has been presented to the Administrator for inspection, and, e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
3188f803-c959-53aa-93f4-6017c83b0fb7 | note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
46b62e8c-5aa8-5ecb-a0d3-405115bb9990 | note | Check Item - Hold Point 6
36b198db-c148-575e-9cb4-220af52fc032 | note | Reference - MRTS05 Cl.9.5.1
1b04adc3-0492-4e49-8a10-eba0784a71b9 | signoff | HOLD POINT
c4c401e5-93f9-4213-8c99-b83e127b9553 | checkpoint | Final Verification
2d26e7b7-369b-5307-9ee9-bb32c2ee227c | note | Project Manager Verify that the Above has been Constructed according to Specification
59a5474e-a4f5-5f05-ac4b-de7f3296c545 | textbox | Print Name:
03b782b3-a693-5e86-a2a9-cd07ad3adc78 | date | Date:
279c5c18-bbcf-5d31-9534-0b218b69e870 | note | Client Verify that the Above has been Constructed according to Specification
cc0a6a08-bbcd-5460-b0bd-d4906a118cad | textbox | Print Name:
ef75e904-740c-515d-9473-ddffc08a3a6c | date | Date:
6297eb77-34de-4574-b789-c281bbae610f | signoff | Signature
218f3cb8-e185-42a9-aa20-b1d2ae55f865 | checklist | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | itp | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements
295dc15d-4ad8-47ae-97b5-c47c9e802ec8 | section | Details
a2d087b0-f371-48a2-88a8-3b27ed241396 | checkpoint | No lightly bound pavement works commenced until all relevant construction procedures have been accepted by the Administrator.
3fac37f8-dca4-5330-b826-da35dcd94302 | note | Acceptance Criteria and Frequency (Project Specific) - Written
ae64d00a-4157-57bc-ad10-302f21b0ecb4 | note | Check Item - HOLD POINT 1, Milestone
fa97d802-a8dd-5b83-8e87-45c5d6142306 | note | Reference - Clause 5.2 MRTS10
0d871517-2e1b-4e21-bed5-c38e395d9ca1 | signoff | HOLD POINT
318e6f54-cf59-4e44-bab5-1662db1094c0 | checkpoint | Lightly Bound Pavement Constution Procedure submitted to Administrator at least 14 days prior to commencement of pavement works.
bb3dfd02-ef88-503c-97eb-03d4b935bcd3 | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
416781d1-2dfb-524e-abe0-9022d19788ca | note | Check Item - Milestone
1ccc025c-df31-5731-a3fb-38f04c2fc3db | note | Reference - MRTS10 Clause 5.2.1
5d483f55-5607-4d0f-b918-b61d94616bf9 | checkpoint | The unbound pavement material to be used as part of the plant-mixed lightly bound pavement conforms to the requirements of MRTS05.
38e8af11-2979-53c7-a2c1-613ad1c9366e | note | Acceptance Criteria and Frequency (Project Specific) - Written
1296525b-2c48-555b-88be-81e574e28034 | note | Check Item - Hold Point 2
ce179a5a-2862-5fed-95cf-ab5926fe5605 | note | Reference - MRTS10 Clause 6.1
c3c4a8d7-0782-447e-ae29-28d431cf4e87 | signoff | HOLD POINT
4df76c70-a0fb-45a7-927d-2af57cd7d624 | checkpoint | Regsitered mix design and terget content of stabilisation agent nominated and submitted to Administrator along with: 1. Stabilised Mix Design Certificate, 2. Quarry Registration Certificate
843efec0-528c-551e-9f9e-d52d05810a6b | note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
c87f0039-4fa0-5f75-9a2e-c364ddbe8556 | note | Check Item - HOLD POINT 3
8e2a9335-ee0b-5429-ba6d-c74d0ce1b083 | note | Reference - MRTS10 Clause 7.1
b8e8b914-531e-4f1c-90ed-4172020b844b | signoff | HOLD POINT
a157ee74-65b9-4af8-b0a8-065e2d0fdc6f | checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
3cd4ba06-babd-5a8f-bcf6-665bfdaba10c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
38838959-8ad8-5a6b-b9d5-071971184fda | note | Check Item - WITNESS POINT 1
952e7822-3e80-5128-ab87-756396706afd | note | Reference - MRTS10 Clause 8.1
65929615-5eb9-46b1-855b-b8c99c1f3d27 | checkpoint | Prior to continuing works after completion of the trial, records which demonstrate compliance submitted to the Adminstrator for acceptance.
071dea10-e2ba-5f4e-aa2e-e7683de2e39f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a0253a39-924c-559d-8ee3-34ebb9f37b25 | note | Check Item - Hold Point 4
b0c0250d-4b25-5bc8-a3fb-af23f94cd838 | note | Reference - MRTS10 Clause 8.1
9477162f-7376-4206-9ca7-32cc779f36ec | signoff | HOLD POINT
ba6395ee-dd36-4918-9324-ecb2fc9c6f45 | checkpoint | Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
6f300fd7-f864-55ad-915d-6b1438090df1 | note | Acceptance Criteria and Frequency (Project Specific) - Written
27bc7761-de55-5e60-b785-b4fc7c215ba7 | note | Check Item - Check Item
2fe90ccf-68d0-5d06-bcdb-e0c3a743eaf7 | note | Reference - MRTS05 Clause 7
e2e27adf-2898-403d-b28e-86faf90b5099 | checkpoint | Equipment as specified in approved construction procedure.
fdf6f08c-4341-5293-b0d7-b09a93ede507 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
05546616-2070-510d-b71d-4fb1fe3850d4 | note | Check Item - Check Item
5fadd777-10d2-5886-9ef9-ab55cadb92dd | note | Reference - MRTS10 Cl.8.2.1
c0d5e5d0-ea9b-4ee6-8a0e-8a3caf31aaaf | checkpoint | The time between the commencement of mixing the stabilisation agent into the unbound material and the completion of compaction of a single layer is less than the allowable working time. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Tested working time shown on the mix desing certificate, b) Four hours
e58581b9-c011-5e13-aba3-ac3de11c6564 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0d4fd6a5-9346-577b-ba57-c415705a606f | note | Check Item - Check Item
f2a6aa01-eeda-53a4-85f3-6123eb8c44ef | note | Reference - MRTS10 Clause 8.2.3
dc981e80-4db3-4799-93b3-d7714bc89374 | checkpoint | Lightly bound pavements not constructed when: a) air temperature is less than 10°C or greater than 40°C, b) during rain or when rain is likely to fall during placement, c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the pavement layers
9d0ca19f-fd7d-5eda-befc-6048537712c8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b739f9b4-705b-5eb1-945b-56b9586dc63e | note | Check Item - Check Item
90caa82e-9ced-522f-ad13-04c007a8e645 | note | Reference - MRTS10 Clause 8.2.4
32b9c70d-db22-47ca-a118-d6c3cac10ca7 | checkpoint | Individual compacted layer thicknesses in accordance with Table 8.2.7.1. Minimum - 125mm, Maximum - 250mm
b14bda63-042c-54db-a787-c276a308cfcb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
442de5c5-261f-5f7d-b984-bf56c9df0896 | note | Check Item - Check Item
0cb875df-8f06-5b0b-b452-b550427716f6 | note | Reference - MRTS10 Clause 8.2.7.1
5a9a2a0c-a8f9-4a9f-8ccd-f329ccad31ea | checkpoint | Where a lightly bound pavement layer is to be overlaid directly with another lightly bound pavement layer, the finished surface is hardcut to uniformly roughen the surface across the full width of the layer.
1fa5a34b-2108-505c-8321-062edc073cc6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
86368dbd-681e-5277-ae1c-e679b9b245ff | note | Check Item - Check Item
218a0764-13bf-5df3-9a5e-eb6394e48be2 | note | Reference - MRTS10 Clause 8.2.7.2
c1acf89e-46f7-4889-b359-adb69acd76b2 | checkpoint | Unless constructed in the same shift, a cement slurry is applied to the hard-cut surface prior to placing the next lightly bound pavement layer.
56a61f47-3089-5c4b-be06-87f7a7cbac08 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9cac05b9-8a44-5c80-aaa8-36f78980963f | note | Check Item - Check Item
8eaffae3-260b-50ef-95bf-6f1b25bfdd2d | note | Reference - MRTS10 Clause 8.2.7.2
4465ccce-959f-476e-b7e7-05ddd0d67953 | checkpoint | Each layer of lightly bound pavement cover with the next layer or bituminous surfacing within seven days of placement. Lightly bound layers not covered with a sprayed seal or prime within 48 hours of placement.
b5db5c2d-ce6f-5bb0-bc30-b984fa778306 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
25737713-fc3d-572f-b4d6-6b8e80f89c5b | note | Check Item - Check Item
fb6c5d50-fdf5-5161-bb48-0c549b70551a | note | Reference - MRTS10 Clause 8.2.9
59cbdb2a-105b-4585-95c6-d92bc9e4237e | checkpoint | Longitudinal joints offset by a min. 150mm from joints in underlying layers, located away from wheel paths and in the final layer coincide with the lane-marking or change in crossfall. Transverse joints offset by a min. 2.0m from joints in underlying layers.
4b1cf618-18b3-52c7-ac50-bb6088980cc2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e25e3e30-6254-5c48-a7b4-4a9f67e7cdb5 | note | Check Item - Check Item
62bd335b-ec91-5368-bfba-6b03244b6c26 | note | Reference - MRTS10 Clause 8.2.10
adbbb70e-f86d-49d5-bece-1264a9baed74 | checkpoint | For fresh joints between adjoining or adjacent run, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
07c6b0cb-da06-5025-a354-93b8f1712698 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fa9536f0-07d9-5f51-8f10-c9eb2e983ab5 | note | Check Item - Check Item
4c3f9fa0-c932-5be3-a148-74d518eab548 | note | Reference - MRTS10 Cl. 8.2.10.1
f7a590e4-4f5c-436a-823d-36ebe42a8092 | checkpoint | Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
096751e8-184e-54ac-830b-9cadd0e61130 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
719d8312-2241-520f-b41a-fdaa3aafd1c1 | note | Check Item - Check Item
d1a17ed2-e2cb-5cb9-9a01-df611cfa1577 | note | Reference - MRTS10 Cl. 8.2.10.2, Cl.6.4
5deaceb8-6544-4852-bdba-e4ec79ea42ef | checkpoint | With the exception of vehicles directly involved with curing, compliance testing, sealing operations and construction of overlaying pavements and subsoil/pavement drains, lightly bound layers not opened to traffic until the lost has been tested and passes proff rolling.
e3a54a88-09f3-5093-a68e-1309591efd33 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
20d79377-8052-5968-8f5a-d54020005f94 | note | Check Item - Check Item
7c2c3390-d0b7-5832-9260-fe4a5939df54 | note | Reference - MRTS10 Clause 8.2.11
bfa2889b-cc79-4133-b29b-bc363bd4a8a0 | checkpoint | Intelligent Construction (IC) rollers shall be used to compact lightly bound pavement material
68db17f4-7f56-5bfa-ba4a-87eec2ac2c3a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
12ae05ec-d58f-5ffe-8176-0cdfd6a88fa6 | note | Check Item - Check Item
b4a09dec-bbd6-593e-9a0d-d079a11fab78 | note | Reference - MRTS10.1 Clause 8.2.1.7
1e8f0a1d-e6f8-49a9-a9d2-4756fd256485 | checkpoint | The actual content of stabilising agent for each lot complies with the requirements in Table 8.3.2. Min/Max Value = Target Content +/- MPV (Mixing-Plant-Variability)
457b0b53-dcd4-585f-b90e-146f87e2a3cd | note | Acceptance Criteria and Frequency (Project Specific) - Written
6ee0fc80-7d21-5495-8120-8b17f22688b6 | note | Check Item - Check Item
2971011a-341d-539b-bdce-9eaf87c58c29 | note | Reference - MRTS10 Clause 8.3.2
e27d7f66-9e2f-4e59-afe2-4fb5536dbc00 | checkpoint | Unconfined compressive strength between 1 - 2MPa
d1423eb0-ecc2-5973-bd8a-4f86077c6542 | note | Acceptance Criteria and Frequency (Project Specific) - Written
02bd0a15-35ce-5427-a76a-83c99487804e | note | Check Item - Check Item
6dcd55f6-38c8-55a2-971f-fe65848d9ea0 | note | Reference - MRTS10 Clause 8.3.3
17252c97-974e-47f4-a105-6a81af2b3526 | checkpoint | The characteristic value of relative compaction shall not be less than 100%, except for the upper most layer of lightly bound base which shall not be less than 102% Compaction testing will be conducted at the 4hrs working time after batching.
1f134561-d954-554e-bf64-da17467bf911 | note | Acceptance Criteria and Frequency (Project Specific) - Written
bad38184-5013-5250-b5ad-b64c41f27e16 | note | Check Item - Check Item
8076649c-69e8-549f-8692-9d3017f6f2bd | note | Reference - MRTS10 Clause 8.3.4
aa3577ab-4e1f-4d21-8d3b-79e071d57197 | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
0f7f42bb-e720-5808-bfea-dbb826315df0 | note | Acceptance Criteria and Frequency (Project Specific) - Written
43d11230-f4ac-5e50-b57b-84e32cf65bbd | note | Check Item - Check Item
637e4c5b-172c-5d01-801f-712803997ae0 | note | Reference - MRTS10 Clause 8.3.5.2
eadce4fa-1a3f-4157-9268-0d2c1f06dde8 | checkpoint | The primary tolerance for the Lightly Bound Layer shall be ± 10mm. Further, the total thickness of the constructed Lightly Bound Layer shall be within -20mm, +unspecified of the specified thickness.
63c38388-d104-5507-b12b-9ce2b0545135 | note | Acceptance Criteria and Frequency (Project Specific) - Written
c27aba56-bda6-50b2-9cf3-53cdf9298d21 | note | Check Item - Check Item
4588aad5-e953-5aa5-97d1-3c1c3a3b8e94 | note | Reference - MRTS10 Clause 8.3.5.3
f1c0e9ee-2298-4b8c-ba96-222e7715649b | checkpoint | Deviation of a straight edge placed anywhere on the surface shall not exceed 5mm over 3m
47a2f503-6d13-54a4-9a89-68ab1c9c2a35 | note | Acceptance Criteria and Frequency (Project Specific) - Written
67fdd4f0-1333-53c5-aba4-7fbc68f59089 | note | Check Item - Check Item
0b0db81b-992b-54ec-b815-dcddd65f975f | note | Reference - MRTS10 Clause 8.3.6
dd5a9700-4422-418a-8e39-704741f521cf | checkpoint | Crossfall shall not differ from the designed crossfall by more than 0.5% absolute.
b82dec9f-eb74-562e-8a7c-a3cd3cd7730d | note | Acceptance Criteria and Frequency (Project Specific) - Written
bf66d068-869c-50ed-8a9a-6b14bdb3a376 | note | Check Item - Check Item
fb5a85b8-3573-5d90-8197-2b5fd89d7854 | note | Reference - MRTS10 Clause 8.3.5.4
06fbcd1d-7049-417e-84a8-baba09d3705a | checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
b377bbe0-e0fd-5b0e-82a6-c8a61ae848f5 | note | Acceptance Criteria and Frequency (Project Specific) - Written
23b545c9-9fa3-5cfb-9bfe-e310e5d03296 | note | Check Item - Check Item
0b73d18c-6123-5393-9bb2-b8caefe78b6a | note | Reference - MRTS10 Clause 8.3.5.2
2b6fe658-9816-4ef6-9deb-701a424e4184 | checkpoint | The Maximum Road Roughness shall not be greater than (Rs) "2.31m/km"
121cf090-6086-589a-bf45-e1e5b1d432af | note | Acceptance Criteria and Frequency (Project Specific) - Visual
041cf712-3b96-53de-a8d7-bc224755a241 | note | Check Item - Check Item
f7aa2dd7-f02c-5a1d-9b24-d269a28ccbc8 | note | Reference - MRTS10.1 Clause 8.3.7
90138525-204a-48fe-a374-4274df078e68 | checkpoint | For lightly bound layers that are to be covered by a sprayed bituminous surfacing, the maximum ball penetration is less than 3mm
c5bef26c-8901-5387-9a6a-b9534d0e871b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8c5cb0cf-c232-539d-87ad-a426a85f6d75 | note | Check Item - Check Item
3d4eda04-1298-562e-8960-617cefbb9387 | note | Reference - MRTS10 Clause 8.3.8
6cf569fc-5a83-435f-bb96-72d410659bb5 | checkpoint | The perceptible surface deformation test shall be undertaken in the presence of the Administrator
b46ec4ca-c52e-5b4f-baa2-046646c0f7bc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b1a9fdc3-583a-5913-9cf9-5f18db42057a | note | Check Item - WITNESS POINT
cc069a40-c566-57fa-910c-272a3f31e9af | note | Reference - MRTS10 Clause 9.4.10
fd428e6d-712f-44c5-9f3e-1b1500ba12fe | checkpoint | No lightly bound layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed, the surface finish comlies with Clause 8.2.7 and the layer presented to the Administrator.
af6eff58-0052-5895-864a-1b29023cd588 | note | Acceptance Criteria and Frequency (Project Specific) - Written
c204fe40-53f2-5f46-a85e-25846d9ce37b | note | Check Item - HOLD POINT
805236e1-293c-58eb-a41c-1a9c39c56a4c | note | Reference - MRTS10 Clause 9.5.1
1d9351d3-2a91-4d78-9b3d-2b5ecb20c7cd | signoff | HOLD POINT
b3a38277-b2ad-447e-b880-503e45bf2c9b | checkpoint | Final Verification
77935261-52a5-5b13-a4ac-6151d6d61f28 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
fc2a1421-dc72-5869-acf6-e449126bd78a | textbox | Print Name:
9fd99c50-8972-537e-bd05-2a0881dafbd5 | date | Date:
11382ee7-2d49-5a1c-8963-2192d63fc7f7 | note | Project Manager Verify that the Above has been Constructed according to Specification
811e5933-3ff3-5d21-aff4-d03283c2c64a | textbox | Print Name:
604e76b2-481a-5e03-ab20-a6cfa929144e | date | Date:
34cabb87-58a3-4b24-be95-02cc0bdf6fde | signoff | Signature
c1c79b0e-3c33-4e59-91b9-93c2dabde7e7 | checklist | 14.01 - Supply and Installation of Road Signs | itp | 14.01 - Supply and Installation of Road Signs
0edc2530-b85f-4869-8dc8-b818e83539b8 | section | Details
79cff15b-524b-4d69-afa7-e77f40d4e5d2 | checkpoint | Dismantling of items to be salvaged
7b733d80-0633-56a9-b951-0a7b6549fb51 | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
38c3b8dd-23e2-5dac-a7ff-2edca1abdc45 | note | Check Item - Hold Point 1
f4337d97-ee53-59ca-9308-a1e5dfa0ef6c | note | Reference - Cl8.2
833cb40f-0134-4bbd-9865-2ae03704cf99 | signoff | HOLD POINT
364eda0e-142f-4ad9-b32b-95cbe0d96269 | checkpoint | Dismantling of items to be re-erected
84de6e32-5c71-538e-86e3-9ba1426084ef | note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
1584d949-c0d4-58c7-be49-f91e0dab910a | note | Check Item - Hold Point 2
abd4d64e-c122-5605-8038-bdef73721822 | note | Reference - Cl9.2
354eb31b-342b-4e13-8db4-403ad967cce2 | signoff | HOLD POINT
4e7aecc2-a27d-447e-8f0d-3919e01a84b9 | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings
4f929543-078e-5ca7-a197-d146d79459bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdf6dc85-8f6c-54c4-beac-034b83cc64e8 | note | Check Item - Check Item
08c43b71-85e5-50bc-a006-91bb53eb2fbe | note | Reference - MRTS14 CL 13.2
65883c9b-fab8-42a7-96f2-f395927761ed | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744
a4980c87-081f-5b64-ad6b-ad40637bba25 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
39292a81-d228-5cc4-b1df-5da756de56da | note | Check Item - Check Item
3b1f2f24-7dcd-59b8-befc-43f024c522e2 | note | Reference - MRTS14 CL 13.2
f288e623-3b24-467c-b381-265e7bd09ea2 | checkpoint | Other materials may be considered but evidence of the full approvalof the department will be provided to the administrator prior to their use.
f14ad94b-891f-52d3-8ad0-98f720f90e28 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
774b17a0-3c8b-51be-9c09-2c5c8aa3d48d | note | Check Item - Hold Point
9962fce9-4e2f-520b-9a12-76a7aaff89a6 | note | Reference - MRTS14 CL 13.3.1.1
2a27ef8c-732f-4c85-b8a1-5f8b88300f53 | signoff | HOLD POINT
e76fb91a-1ed7-4176-ba19-d8498df4164d | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3
0bbf7616-d0f9-5493-b194-1739926ab08d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2efa68ec-9beb-5ad5-ac3e-991672df3e82 | note | Check Item - Check Item
5ad43bc0-906f-561b-a5b9-2b61789eac5d | note | Reference - MRTS14 Cl 13.3
6ee7bf11-fbf4-4ad9-966c-cf93ed0cdfae | checkpoint | Sign faces are fabricated in accordance with the requirements of the Design Guide for Road signs to the size specified in the contract
9aabc27a-8b3e-542e-9a8f-4d2f027ed36d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
196031ca-2c2a-5c46-b65c-df5e7977ba4f | note | Check Item - Check Item
05309656-07f7-5aa6-abf4-7e48cabd2944 | note | Reference - MRTS14 Cl 13.4
bd60c00b-385d-4783-82ae-d2641dc86f7f | checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
02793c22-8f27-579d-9966-300cf307e0b5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d6951fd2-a216-59cf-99bc-be3555ca3520 | note | Check Item - Check Item
4c460e50-0ce3-5f4e-b5ed-4f68b9616a12 | note | Reference - MRTS14 Cl 14.2.3
158c9128-e300-4f96-abce-24762b01f24e | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required
711c6600-6b33-5d83-a46a-af7018854a03 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
80d2c92c-9268-57df-b301-9e3128c14210 | note | Check Item - Check Item
a6da2342-ed3b-5cfb-a19e-7f098cd93cc1 | note | Reference - MRTS14 Cl 14.2.3
228996fe-e6b3-4a4d-888e-d3e4026e46a8 | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
03a39757-31c5-59bc-8c89-d5c72e6414c9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
09d1dc7a-aa0d-50b2-8695-0bfbdcad7188 | note | Check Item - Check Item
cb99f20f-8005-5d2a-866e-8d40805974d7 | note | Reference - MRTS14 Cl 14.3
e531a614-45f7-4513-8583-f32710dbb2e5 | checkpoint | Erection of Road Signs
0c2efd9d-b352-5ddf-bd2c-b9f4899395f0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1dcebf57-9855-5f57-8907-7650f66d614c | note | Check Item - Witness Point
706b2143-98c7-5f61-a32b-46b3f460c9a3 | note | Reference - MRTS14 Cl 14.4
77d214ee-00a1-4c7c-a625-f7bbc8c91c4e | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD
922d1a18-e78c-5a26-ac87-49305059acb8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ff6eef4e-5f81-5504-bed6-823e4b79fb5b | note | Check Item - Check Item
3ca31879-6eec-5cee-8a77-9b03cc28132c | note | Reference - MRTS14 Cl 14.4.2
ebeef656-6baa-40e3-a66f-ffe76ade1bd2 | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete
8231ef8f-4d67-50c0-b093-212d9807ce5f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
25c0e858-185d-5af9-bcb3-40944044cd04 | note | Check Item - Check Item
816d4b7f-6352-5ad1-9e05-3ef93474afc7 | note | Reference - MRTS14 Cl14.4.5
06fe25a0-b65e-4220-90e8-8ec0a6b21211 | checkpoint | Final Verification
476e2199-f732-5d8c-acb0-9beb9cb93988 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
7af15af2-11ca-5294-9e10-2b43d78ad232 | textbox | Print Name:
43a2cb91-c5bc-5cc2-bc0d-26b43215f0b2 | date | Date:
e64936d6-1ced-56cb-9240-0e58a353bba4 | note | Project Manager Verify that the Above has been Constructed according to Specification
e2eab12e-a69f-524e-989b-08f1597d927e | textbox | Print Name:
c32dbc49-e800-5d94-8bec-5932266737f2 | date | Date:
e7c9ec97-fc65-4995-bdf6-03d5b59aa889 | signoff | Signature
6df2416d-ec24-4e4b-95b6-93b1e7a67504 | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
ee754299-b6b0-49d1-81a0-f2af95daba19 | section | Details
e402a246-3aa9-4aa6-9803-84ee931ec265 | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
241eff59-5a0f-5530-8c56-2a350a2ac426 | note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
4d1502fe-f61d-538a-8120-a1cf6451430f | note | Check Item - Hold Point 1
7cc9c404-4f7e-56a8-bf36-06e7702bf4ca | note | Reference - MRTS16 Cl 5.2.1
f3e2b87c-4020-4a98-a548-8bc4dcc4993d | signoff | HOLD POINT
7ac2f799-177a-40f7-95fb-0fb6a78ff77a | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
de3d3ab6-d83c-5600-bcdf-d59c9992240f | note | Acceptance Criteria and Frequency (Project Specific) - Plan
d9047038-3d66-5309-9616-8a0ac4935a62 | note | Check Item - Hold Point 2
ddfdc40d-87d4-59ab-a795-735292b6013a | note | Reference - MRTS16 Cl 5.2.2
546e4fe0-49d6-4b35-bc17-c425e60dd4c4 | signoff | HOLD POINT
8b4e6e63-b3d3-476f-8a30-57d31151cb11 | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
47b05514-6051-536c-97f8-5e2ddc3b3e48 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
65c953d5-81cc-51f4-9511-371737d0072e | note | Check Item - Hold Point 3
3c9a316f-d147-5172-bedf-dbf6ec3917c0 | note | Reference - MRTS16 Cl 5.3.1
f5ddd684-bc55-40f4-a2f8-56278382739b | signoff | HOLD POINT
bb33f4b5-0669-486c-b2db-5f98c95b99dc | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
9f1dd9e5-ad26-5963-9f34-b34c7c87b8b1 | note | Acceptance Criteria and Frequency (Project Specific) - Plan
d1bee38a-8ad7-5ce2-977f-d8a7bd27eeba | note | Check Item - Hold Point 5
e94b1efe-b818-5a00-a3a8-bcb75485aa44 | note | Reference - MRTS16 Cl 5.3.3
8d1131f3-12dc-4a13-b2bb-1d0cc1a57406 | signoff | HOLD POINT
21558d8a-b791-4b7e-9fe8-358d795f8517 | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
addc1625-d211-579c-a838-595254c22b6d | note | Acceptance Criteria and Frequency (Project Specific) - Plan
05dd3e9f-8c40-5cb3-8d6b-df899f6e01b5 | note | Check Item - Hold Point 6
b7294022-b00c-575c-a97b-fd4a81090029 | note | Reference - MRTS16 Cl 5.3.4
b20aaee9-f7b1-4bbf-a42a-996c25b4b202 | signoff | HOLD POINT
cdbdea4f-8cce-402b-a0d1-c3abd023b896 | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
3c9937a6-6b4c-52af-b9ff-674916606c36 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1e1ae428-5d9a-5a15-8cba-9fbb91ac644c | note | Check Item - Check Item
d4ca9d33-b5e2-5d60-afc1-c6e0c38fa3d1 | note | Reference - MRTS16 Cl 7
d033e1e7-b82f-4bfc-853d-7c6c0915fbc9 | checkpoint | Materials are stored to ensure no deterioration or contamination occurs
811e4196-3170-5263-8dfd-5d5084e86b01 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6bb21b24-e41f-5a99-9e77-e63cbd42553d | note | Check Item - Check Item
c8c77d4d-ae9d-5fa5-be3c-f1e2dca9c09d | note | Reference - MRTS16 Cl 7
e6d59bbf-db2b-4175-ba7a-8721e06a6906 | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
ade3de81-9cd5-56d7-99ff-675bd1e175b0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5966e850-4e40-5a3d-a7a5-0922cc140dc0 | note | Check Item - Check Item
4628ff63-039a-50c2-a09e-0061af36d985 | note | Reference - MRTS16 Cl 7
ce21e459-b7c9-4082-a709-e90c02dc0644 | checkpoint | containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
abe54546-faa7-54b0-ba2d-198ca84203c6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
caff5bc9-bde1-59e2-8baa-b947beb373e7 | note | Check Item - Check Item
ed82b2cd-1ff4-54d1-aa52-46d078398179 | note | Reference - MRTS16 Cl 7.6.2
0b2c0cb3-8cd8-49d1-88b1-d83c91bfac41 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
28969472-fba0-5acf-8671-6f5bc77f888f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0787c0af-9ae8-5b99-a8a8-97f06bd50c87 | note | Check Item - Check Item
96ad4e16-5d05-5a11-8ffc-5aa7e8b822bf | note | Reference - MRTS16 Cl 8
101f24af-5684-44be-936b-fca39d5b16bb | checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
2365981b-740b-513f-96d0-be7373059529 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6999179c-d925-5f6c-89a8-158672662979 | note | Check Item - Check Item
40090480-57ce-5dc2-b144-ebc7e965113e | note | Reference - MRTS16 Cl 8.4 TMR SD 1644
7d4ce39d-66a7-46df-a619-473dff94bb75 | checkpoint | Site is weed free prior to ground preparation operations
a2a7a258-88c6-5629-8b75-d837cfe86669 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
34b96d46-3d43-5617-b6ec-d9c501121308 | note | Check Item - Witness Point
5acaa8c6-1ad0-5c36-b4f5-86d2b6341dee | note | Reference - MRTS16 Cl 8.3
25be023c-622b-4bae-8c1b-2d1ec89e07a0 | checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
2a6db389-6653-5981-9f5f-da806b094ea1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
920a73d5-0168-50bb-9166-434d5a5e9337 | note | Check Item - Witness Point
52c22825-a3c7-5a03-9ee9-c48d64e03e23 | note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
d0eb0899-93c0-438c-9483-29e02cb7876c | checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
779e8f96-8040-5dd3-8f14-d473607d52eb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fafb6a8c-bd2b-572d-97f8-2b8ce3d6acdd | note | Check Item - Hold Point 7
b4eee6ed-7a84-5ad2-946e-8b7cb5d46383 | note | Reference - MRTS16 Cl 8.2.1
e289fddb-cc01-4fb1-8e4f-2758d6927316 | signoff | HOLD POINT
bb358b67-22d9-4a27-9fbd-8cc98bca1fe0 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
31b79a46-3f76-5c57-8a0b-a682679cdea7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ea445365-8af1-5c6f-83c1-4c787a079bf2 | note | Check Item - Hold Point 8
e28e28ac-3e30-5ca0-8ae5-c7d5eac5a59e | note | Reference - Cl 8.4.1.1
5e05a44c-c66f-41d0-bee0-71759c047d6c | signoff | HOLD POINT
a9e85d08-bd22-49d2-840c-12a9c87c6097 | checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
271a50a8-89df-5c1e-b809-9ae35c33d947 | note | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
b74a2078-c328-51b2-9642-7da717c31a73 | note | Check Item - HOLD POINT
395fe7b7-f328-51aa-a014-cdc423f2df04 | note | Reference - CTS16 Cl. 3.1.6
dba958c2-1739-482e-bb3a-a3d181dd5ac9 | signoff | HOLD POINT
0dd9b5d2-4f83-4944-b8ee-430a31c23022 | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
1b46a65e-e5ab-5179-b931-af48321a05d2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
30cb5de9-9a54-514c-928f-9c9ffb4ec401 | note | Check Item - Witness Point
c8e5b133-ac5a-51e0-ae65-daccf20cd15d | note | Reference - MRTS16 Cl 8.4.2.1
06258adf-7993-4666-a9b7-ab052cb941ba | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
9d79d29a-8352-551d-9204-3a7faa82062e | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
6aeb80cc-cf6b-5b54-86ba-07b63e2f7b09 | note | c) on the day turf is delivered to site
011fd950-b5ee-5052-9abd-6b444eecc5ef | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
50c3d089-7823-5aff-a5d4-06d1d8fd33c7 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
58fd286b-e265-5857-8f42-c8991fed1125 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
909e92c7-7e61-5da5-a90e-d953ee2139aa | note | Check Item - Check Item
688e088b-19e0-50b6-8def-d156a9e3788d | note | Reference - MRTS16 Cl 8.5.2.
8aa35d47-4f49-435e-b2b3-855eab8c51b2 | checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
08a4754f-f30a-5250-9e24-71b8f77bf3c1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ccefdbd1-b0f1-508c-9738-209e2aa05737 | note | Check Item - Check Item
74d4406c-1678-561a-910d-90c4c7ee8908 | note | Reference - MRTS16 Cl 8.5.1.3
e5470a54-2179-489a-b23f-637e5a4d6ad1 | checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
2e5e31c5-8db5-545b-b262-0f2596a5ae5f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a8d0409d-6bfd-51a7-b1bc-2d1525840dab | note | Check Item - Check Item
7fe642b9-8622-5650-95a3-a948e8ff1a31 | note | Reference - MRTS16 Cl 8.2.1.4
11bf2f6f-ce0c-4117-8c4b-fa101f2d07e3 | checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
064830b9-36ac-5b81-85a3-e0d2887998fc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
962de919-691e-5478-bad2-15ea6dcaffa5 | note | Check Item - Check Item
4379d714-bd03-5596-9694-5f9be972a2a9 | note | Reference - MRTS16 Cl 8.5.1.3
ab3d2efa-431c-424b-8f7a-f99c6e74018d | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
538e2b40-fa25-5446-bfcd-4b2e4026bfc7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9db3f8e1-9a74-5e5b-907c-0edd53b0e101 | note | Check Item - Check Item
9c965f5e-aea2-5836-a596-7926b506152e | note | Reference - MRTS16 Cl 8.5.2
a3f421e8-f325-4edf-b9ea-6627ee696006 | checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
33ec899f-1c12-5c51-9a19-4e297fa3bf99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5e17c5af-34c6-589a-a7a5-ef0434fc549f | note | Check Item - Check Item
68eac35c-df9b-50b5-b16b-d7293f6b61c4 | note | Reference - MRTS16 Cl 7.6.3.1
fb49caff-fff6-4e71-b43e-982c2c229aaa | checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
c491a6e9-14bf-5352-bab0-9dac6d2b5e4e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
229478c7-e81f-5208-850a-48459e088616 | note | Check Item - Check Item
b7fd4b87-9227-568e-81bd-4a88332e8722 | note | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
9d359c36-638a-4934-acfc-9a59657c04ed | checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
7a61b7e3-12b0-5100-a33e-d5cbc9d20748 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
41ad72af-5784-55c4-abf1-a55aa7312dbd | note | Check Item - Check Item
82b388d2-3228-5b46-aa47-1d8cd9c01794 | note | Reference - MRTS16 Cl 8.5.3.2
1eef640b-8be1-4f9d-8020-28c5f12c4999 | checkpoint | Administrator notified of plant delivery to allow for inspections
e6f18727-6cda-5a2b-b383-2e8b97b908f6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b46c490f-1e5e-5f48-b4c2-7881b93bfbbb | note | Check Item - Witness Point
b712e48d-19cb-561b-bff7-937ef0d8f629 | note | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
449c7e39-6904-4233-9edb-dcd6c2546171 | checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
f4b847ca-dd4f-5c68-970f-1315403fc273 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b56ce27-0ce3-56e7-82b5-9aff22c1b8d9 | note | Check Item - Hold Point 11
d2a5fb7d-45cd-5ce0-b8fc-277d85f75ec9 | note | Reference - MRTS16 Cl 8.5.3.3
2c65f71f-a22b-4f0f-9f1c-c4f93f9ab149 | signoff | HOLD POINT
f1ee9af5-7247-4373-8ecc-05e8dcbf8635 | checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
ea72d950-5bae-57a5-81a8-0f84309ef0f9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c1d28fac-c5ff-5e6b-9230-c5f083bc829a | note | Check Item - Check Item
49228d44-c655-503e-9b4d-67f675b057d5 | note | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
75ffe0e9-030b-4424-93b1-3569e14de23b | checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
5b1b440e-d8e2-54c0-b358-47df06b5b8bf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ed4abca3-d766-512d-98e2-7a302341ef02 | note | Check Item - Check Item
c4fdaf4b-ed54-58d3-8840-a48a2a5803c1 | note | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
4c224fb8-3574-498e-82f1-f3f57c93cbd7 | checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
6a0878ef-7c8a-52ac-8c2a-3fe17a4f776f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1af8f003-2e2c-52a4-9662-11918a8e5587 | note | Check Item - Check Item
cdf16be0-0bd0-5a95-b750-c45f6ef8e9c9 | note | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
48b82376-d514-4f62-82b7-f4503ec963eb | checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
a498061c-853b-51cf-ad7d-e4cbeeba941f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0a307350-b3d3-5ad7-a706-9120a3bf8a04 | note | Check Item - Milestone
e59e538c-9882-5f25-967c-7e893ef0b871 | note | Reference - MRTS16 Cl 9.1
f0c57f56-48a8-4e9a-8cb6-0399ef8cb620 | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
f9bda4a9-78cf-5a36-9596-aaa82dd5cad1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3db7ba5c-69c9-52f5-a401-d576da160a3c | note | Check Item - Check Item
1af6196f-f04e-5691-a040-635ac223bcf5 | note | Reference - MRTS16 Cl 9.1.1
ffb52583-4000-40b4-bfe7-112cb26aec90 | checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
be235f74-6f36-5878-b092-c9b080b698f3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
739974c9-4dbd-5c15-b772-582248901f3e | note | Check Item - Hold Point 10
d9cf4576-ab1b-562e-bf8f-4cf99640279b | note | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
61d9f4d4-d125-4c58-8768-73dd7c93d282 | signoff | HOLD POINT
5a994460-c085-4631-8604-5e330c7b37d2 | checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
ba7bde0b-480b-51aa-a531-afc06c89ecfb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fc458ab0-1be4-5e95-ae8e-0c218ef351ef | note | Check Item - Milestone
564084af-2c55-5a73-9086-b23accf79209 | note | Reference - MRTS16 Cl 9.2
c5cd9a24-5472-4c9a-810b-868f9c317cec | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
01fe484e-665f-54d2-94b1-a432e6945484 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8f060bb8-0bba-5f1f-b0b1-9af6f3aa7384 | note | Check Item - Check Item
59ded11a-df1f-509b-865f-a871434ed4de | note | Reference - MRTS16 Cl 9.2.1
13675ca7-a4b9-4a2d-93f6-d082d0451b5a | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
bd3665c8-6486-559f-b294-d93cbe91925a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
16670177-4057-52ed-97bf-8e823ef9a61e | note | Check Item - Milestone
50f7c79d-4596-5b56-83c8-f66949e83988 | note | Reference - MRTS16 Cl 9.2
9ccb5ec8-1785-4805-b59b-c7d93596d6c0 | checkpoint | Final Verification
1d04b934-9ef8-53ad-a112-9a9c1b7232e8 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
745342e4-b4ca-5d22-8ba2-4a096ba1ef4c | textbox | Print Name:
fe6b80db-c39d-580a-8183-85962c791b3e | date | Date:
617b8515-364d-58c5-9da5-57df776dd0f5 | note | Project Manager Verify that the Above has been Constructed according to Specification
a08f020b-ca45-581f-85b3-ef9ec3e5d2a1 | textbox | Print Name:
dbec6cbf-445b-5eb7-908e-24e84276c6b9 | date | Date:
3ea03ffd-0aaa-4713-aa31-84ebabeeeb24 | signoff | Signature
43ccc3d5-2fd9-426e-a2cc-911c62f5e5e4 | checklist | 28.01 - Contractor's Camp and Site Facilities | itp | 28.01 - Contractor's Camp and Site Facilities
9876f7db-f505-4099-982f-d1b8c168221b | section | Details
7560b6e1-80df-4725-8159-2fb0ba99b87d | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
f76a96a1-e4fe-5839-93c1-e8c4134b3fd0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2e018929-50b4-5afe-b27c-c806b3ee7348 | note | Check Item - Check Item
fd54dd74-ca52-5a7a-9bcf-fd9908c08f95 | note | Reference - MRTS28 Cl. 4.2
db742b81-8206-47ec-b8b9-41e6ab17028e | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
05e23c62-4dfa-5861-b519-c31f39046864 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
2d1f50e2-44c9-5dd2-9a82-0c0e3a7d140f | note | Check Item - Check Item
2d6f7513-24c4-5613-a584-b64328642c39 | note | Reference - MRTS28 Cl. 4.3
693655b9-6e03-4223-95c1-5a5bca15befe | checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
ea54fb4e-6192-5fa8-905b-fd74dd1f5186 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
cdea91c2-bc32-562d-a06e-b862309a7152 | note | Check Item - Check Item
f5a70c88-25e0-5f83-b0fd-8a50cba86641 | note | Reference - MRTS28 Cl. 4.4.2
58594c6c-dbf0-41d1-8561-1059de0a7980 | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
93e1effe-e4ff-55e1-a9b7-a7536b20b110 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
71100931-595a-5c3d-9d24-841e531122bd | note | Check Item - Check Item
c9f011cb-b929-5ca3-a7bc-79605741c87a | note | Reference - MRTS28 Cl. 4.5.7
975d61e0-f197-4cce-aa48-16811a96db76 | checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
be10267a-13cd-5236-9962-4d954d98e60b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8731bbf0-bd78-5658-8190-5b5ddba743c4 | note | Check Item - Check Item
967e26b8-08ef-5e29-a524-71d4ae139d91 | note | Reference - MRTS28 Cl.4.5.1
bd5ecfc1-9e8a-4e2d-9a15-423ddf8cdd40 | checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
779873c4-9b20-51bc-88fe-10816ab43c19 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1aeef7b0-8ab1-5eb6-b556-e844fb32641c | note | Check Item - Check Item
bc603445-5756-56c2-b429-1008677889b4 | note | Reference - MRTS28.1, C.l 3
885d6772-3677-4eca-a7f2-4390de4bab01 | checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
dd49690e-41e3-5368-bbaa-520aa6d13506 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b7c824fc-4844-5354-9118-ec36cf701a3b | note | Check Item - Check Item
9dd14055-820a-5964-ab77-8268111a4773 | note | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
a2183060-1f51-4c81-9640-fbb3c9b85182 | checkpoint | Final Verification
bf3a6cff-bd34-5f68-83a5-57e34b51b168 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
36d1bf4b-4e09-52dc-8b49-64b42b019102 | textbox | Print Name:
96a7cbe5-a1d3-58d5-80c1-1837646d21ba | date | Date:
91439e3f-c3b7-5b1c-9668-ebfe0aed955a | note | Project Manager Verify that the Above has been Constructed according to Specification
7016e40f-1893-55a5-a826-4fbe6f490ac5 | textbox | Print Name:
c9c6e222-fe6a-541b-8728-321d5ae4d012 | date | Date:
108b3352-ddf1-4254-9492-6e39494a7f33 | signoff | Signature
828c85b8-14bc-4e88-8429-fc1a01fcba79 | checklist | 30.01 - Dense Graded Asphalt | itp | 30.01 - Dense Graded Asphalt
b902a92c-9bdc-42e1-9c76-7aadf0450eaa | section | Details
3c17789f-b1d7-4287-aa41-92186f950c5f | checkpoint | Submission of Asphalt Quality Plan (7 days)
f7ce7005-512b-5bc8-a332-f8fd2ea1650a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dbf7614f-236a-5d23-84fb-f3e69fc36dfe | note | Check Item - Milestone
c54c073f-7d17-5aaa-90bd-006ca96673ba | note | Reference - MRTS30 Cl 5.2
416b30dd-b935-429a-91a2-7a11c8960cc3 | signoff | HOLD POINT
3876ed2c-7ad7-4761-844e-3c74b80439be | checkpoint | Recommencement of production after non conforming Tensile Strength Ratio
4933eb68-f6dd-56a3-8fb5-ac5e60372007 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3ab59510-15d2-5e65-aeed-42416fd93fcf | note | Check Item - HOLD POINT
309fa98e-28bf-5379-94ca-7343c0fe7f1a | note | Reference - MRTS30 Cl 7.2.5
5ecd3585-2b10-4635-9dd1-84613ad73010 | checkpoint | Submission of Asphalt Mix Design Certificate (7 days)
8a94d10b-4e08-526a-b6df-02c337b47d07 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3f1cda0e-3cf9-5889-9c15-11b291769722 | note | Check Item - Milestone
326cf307-fc9b-5d66-a1d6-cb167e42086b | note | Reference - MRTS30 Cl 7.3.3
be59db9e-5172-45da-8034-ad727d1c18db | checkpoint | Incorporation of asphalt into the Works
e387265c-d468-5947-b512-cfb637a40798 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
54b1914c-fcd8-5518-9eca-7a3dcbdbc5fc | note | Check Item - HOLD POINT
0d462a28-8430-5ece-9e45-d72d8ea84edc | note | Reference - MRTS30 Cl 7.4.1
f8ce8ea9-c505-47da-9b8b-cb300d347300 | signoff | HOLD POINT
3f340096-42bd-4c9a-aa5c-df049e86d98b | checkpoint | Acceptance of a non conforming or nonstandard mix design for incorporation into the Works
ffac606d-8281-5cf4-8aea-36af9b8912fd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
066b9633-560c-5ca4-abfc-d70bc2e09e65 | note | Check Item - HOLD POINT
9c4264c0-507e-5ecb-8373-f9748062551e | note | Reference - MRTS30 Cl 7.4.1
f45e1359-4e06-4372-9019-4bc037e4bb09 | signoff | HOLD POINT
ab67883a-651f-4589-889b-89be64b253d8 | checkpoint | Approval to place asphalt over weak substrate substrate
010b7b78-ea54-5bab-9c4a-d46177097dec | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4ad9a62c-4ffa-5c85-8f6b-849fcff6bda2 | note | Check Item - Witness Point
eba055f4-b534-5052-92d1-b3b272de917e | note | Reference - MRTS30 Cl 8.2.2
1148fb89-43e0-4083-9604-7cc3757533fd | signoff | HOLD POINT
eb54e009-cd4e-4cfe-8f41-c29b5c3c4fd9 | checkpoint | Proof rolling of substrate
62e59cba-4176-5e89-acc9-9b4717a48d01 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a01506dd-d90e-50ad-bf87-d575ee10a468 | note | Check Item - Witness Point
21a68949-d30e-50ba-91dc-db6ed3bd5430 | note | Reference - MRTS30 Cl 8.2.2
e7d17ad3-89bc-4836-97cf-ecab5de569bc | checkpoint | Mark out of cracks to be filled substrate
1a0eaecb-40fa-5389-b73a-cf275abac1eb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d23f7526-1c27-5fe7-849d-528592a674c8 | note | Check Item - Witness Point
9cdefd59-426f-5c8e-a37f-9be066433805 | note | Reference - MRTS30 Cl 8.2.3
95af8b01-6fdc-4404-b541-a3dadb50a2ba | checkpoint | Marking out the areas on which strain alleviating fabric strips are to be applied
b3dfa47c-801b-597f-bbc9-f7b388eebde5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fbce355b-2461-5979-a202-756d951629d3 | note | Check Item - Witness Point
00dd47f2-64ec-5b54-a157-e58bae338ba5 | note | Reference - MRTS30 Cl 8.2.4
0bffde62-7223-4da6-bad7-9854f5c1404a | checkpoint | Approval to place asphalt at a nonconforming layer thickness
2e67e7cc-afe5-5ac6-b463-b04e4185717e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
356890e8-9600-50f4-a443-16fc0c1d6e14 | note | Check Item - Witness Point
a33fd589-2cd7-5043-a1ff-2651e5464040 | note | Reference - MRTS30 Cl 8.6.2
e9da2fc5-bdfa-4e4e-9c8b-2143cc1bd46d | signoff | HOLD POINT
86f32a40-84b9-417b-be68-68478e9c7d5c | checkpoint | Approval to place asphalt at a nonconforming pavement temperature
2c8e1bf3-7a01-597f-8050-f16f0c4c4996 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c3b411b0-8279-5cac-8746-22d272377611 | note | Check Item - Witness Point
22490bd0-59f1-582f-a624-e187662f2775 | note | Reference - MRTS30 Cl 8.7
bea927e4-613b-5cb2-b5f3-79673b722067 | note | HOLD POINT
edabe9bd-e51a-40b0-a732-9b5e95de87e6 | checkpoint | Placing of the nominated mix (after placement trial)
d3768b04-3a56-5a21-a530-728db881422a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3693a315-db0b-59a4-979f-2f4aad8974da | note | Check Item - Witness Point
77377749-7877-5b15-915a-b1b0dbf296fa | note | Reference - MRTS30 Cl 8.11
45332880-3b24-5923-b3f5-eda338a35088 | note | HOLD POINT
33892db6-03ae-448b-9808-9de9471e6a24 | checkpoint | Final Verification
33cbd047-71a0-517b-bc0a-ca1e8346ff55 | note | Project Manager Verify that the Above has been Constructed according to Specification
37b02aa4-cd35-5387-bd20-d5e6c5725893 | textbox | Print Name:
e6e8a1fe-04f4-5945-9371-1a482f899bc0 | date | Date:
00d3a006-cf44-54a1-911f-9eb4e9dd9516 | note | Client Verify that the Above has been Constructed according to Specification
a66bcffd-7d72-52f4-8cf6-604020a0e7e4 | textbox | Print Name:
500f1728-53db-58a9-8058-7231f6432408 | date | Date:
8203c64d-e98b-4094-8d1a-9885ac6f3764 | signoff | Signature
6ac0e7de-4baf-4269-8b2f-c9046832f2c4 | checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation
64d3f214-72d0-4bf0-9c29-b0120407b074 | section | Details
e2e298f9-a603-458f-8c64-a43f32607dbe | checkpoint | All material conforms to requirements set out in Clause 6 of MRTS45.
b5b93d40-b2de-5783-80ba-e9882a7708b1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3394776a-2863-5a80-b717-13b81a6f0c03 | note | Check Item - Check Item
5abe70d6-3142-5071-9f76-88ae7eebe57c | note | Reference - MRTS45 Cl 6
14be24ac-80fa-4174-98fc-511551474e4c | checkpoint | Installtion of Pavement Markings conforms to requirements set out in Clause 7.
c006a5ab-b89d-5750-a223-039d2d867d8b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1bb40681-8aaa-5d37-868c-244907185633 | note | Check Item - Check Item
9619017c-e9ff-5217-b308-783dfb3016fc | note | Reference - MRTS45 Cl 7
1f3bcfb6-202f-476a-9c1e-9c766e20fd78 | checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
bac51e33-d22a-5f37-bec8-b4ee2436f9ae | note | Acceptance Criteria and Frequency (Project Specific) - Visual
55a4a51a-175e-5dc6-aa1d-35f577b739d2 | note | Check Item - Check Item
489db692-a941-5c22-a9f5-c810138ff32f | note | Reference - MRTS45 Cl 7.2
be475857-a2e7-4140-addc-d527d1bffd72 | checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
53165f7e-1669-59e6-acbb-cad418eb34d4 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
77497482-828d-549b-a1ae-68b1b142d4d6 | note | Check Item - Check Item
c0f9e8a9-b3a8-5b2a-b672-f96c8abd4f7c | note | Reference - MRTS45 Cl 7.3
38569837-5fa7-446e-bed7-bbd921b42fa1 | checkpoint | In addition to Cl. 7.3, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
e10c922a-0774-53df-b78d-061b8929fdf7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ec237d19-41de-525f-af86-a1bfdb6985cb | note | Check Item - Hold Point 1
db7badd5-0e8f-53d4-a0af-cab3cf49e107 | note | Reference - MRTS45 Cl 7.3
004c5f34-90b9-4708-a134-2ebfc95ba63c | signoff | HOLD POINT
f57701be-d93a-4e92-826f-84a77b0f28ba | checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
041386b8-93fb-5480-95c1-a948132a7db7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
59a19b21-b04b-5034-a1fa-8bb314a93cf7 | note | Check Item - Hold Point 2
ddf85576-3f7c-57c3-9f4f-0b1d676b2e9e | note | Reference - MRTS45 Cl 7.4
76a646e9-61fa-4f4c-9e79-d1cb28001830 | signoff | HOLD POINT
fee2b286-b1cd-47e7-9ebe-6c36e6be0c30 | checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
19e934d9-2752-5dae-8172-07100e95f991 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0f20c1a5-d056-5e53-9e10-6a4ee3d7a48e | note | Check Item - Check Item
11970be3-e0ab-56b9-8a47-85f381b9e2ea | note | Reference - MRTS45 Cl 7.5
c00f209b-cb31-4bff-8370-60d6199e21ff | checkpoint | All Markings are of uniform thickness and intensity
02404ea8-df45-5c42-9c39-5c89a63f3153 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a0986302-b911-5189-b361-0a62b4718f01 | note | Check Item - Check Item
60fd74be-de49-5ba1-92b6-486595eea41c | note | Reference - MRTS45 Cl 7.5.2.3
a24cdcc2-4526-4e01-9aa7-5687f95b3d7e | checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
abc2b2aa-2a60-537f-9a24-c2f937315612 | note | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
bf9f16b2-f29a-5c93-a430-4b23ad0ecca8 | note | Check Item - Check Item
0e26633d-c9d6-53cf-b878-1008291e61cd | note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
412b6e4b-e78b-4643-9937-1bce36400cc0 | checkpoint | A primer was placed just prior to thermoplastic materials as per manufacturers specifications
20e959b4-cd2e-5a43-b941-30a06471e5ab | note | Acceptance Criteria and Frequency (Project Specific) - Visual
31ae8046-242d-5e6d-a219-93b5f7a5b670 | note | Check Item - Check Item
81f1773d-5843-57e0-83e1-8bbf95174d5d | note | Reference - MRTS45 Cl 7.5.3.1
0f227d17-c6c8-4156-bdc2-ee3270285d08 | checkpoint | Thermoplastic shall be applied at a temperature as per the manufacturers specifications
0820116e-214c-5ce6-a407-622c29df9e57 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e8bccb82-77b9-5562-99d2-a5b506330c6e | note | Check Item - Check Item
ae4d87a2-fcaf-5e55-a94a-945628bb286a | note | Reference - MRTS45 Cl 7.2, Cl 7.5.3.2
04eadb13-0896-4b13-8198-c63a548c9e19 | checkpoint | Thermoplastic applied at a minimum of 2mm thickness
49ac1078-01f5-506d-941d-3e7311a89c0a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
455b7c45-37b6-55f6-83c7-601ca711baff | note | Check Item - Check Item
fb0fbf8f-5e20-5814-b5dd-2b45256698fd | note | Reference - MRTS45 Cl 7.5.3.3
a6154111-6d52-4c1e-b1e6-b4c2c3ae4817 | checkpoint | Raised Pavement Markers installed in accordance with Cl 4.6.3 of the MUTCD
ad85848a-29cd-51fc-9288-2b3b07f4ebf6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
d4714742-2360-5218-b551-ca54b5dcc441 | note | Check Item - Check Item
bd5a0a62-4701-523d-878a-9ba258741803 | note | Reference - MRTS45 Cl 7.6
eeb96d35-37d8-4b69-bc08-17774645dfdb | checkpoint | Material complies with luminance and retro-reflectivity requirements
993e1e57-8815-59c3-b3e5-d998d5439e5d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5730f1d-6052-5013-be74-9c7fb46938ee | note | Check Item - Check Item
5034f731-1097-57e9-a05a-98622d1b9748 | note | Reference - MRTS45 Cl 7.7.6
14f16e1b-f93d-411f-a5c2-4e5dbae7b120 | checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
009bc7da-344a-55d5-837b-c2451520a113 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
42b14a8e-8a42-5811-b8a6-3d0a4bc091e5 | note | Check Item - Check Item
e18d7c7a-c2e7-56e4-94a1-81d4a57323fa | note | Reference - MRTS45 Cl 7.8
8f991e01-fd1e-4439-9e2a-cc2b6a98889a | checkpoint | Completed Pavement Markings are uniform, clean and well-defined edges with deformation and conforms to dimensions as set out in the MUTCD
b542ff1a-6100-5470-9965-a2089971a92c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ccaaab98-7519-590f-a2a7-cf3b7e588962 | note | Check Item - Check Item
3ab03ba2-1b79-51a2-a940-226ad549cd40 | note | Reference - MRTS45 Cl 7.9
f552c11c-1bf2-481e-bab1-6b364e5b6ee4 | checkpoint | Pavement Markings conform to all tolerances
9d7590ad-ba70-5429-af15-298ca24721eb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c5317b8-2883-59b4-8e9f-34d01d3651be | note | Check Item - Check Item
0c8e7dba-20ea-5bd8-8651-98ed1a934935 | note | Reference - MRTS45 Cl 7.9
d89bc270-36de-4b48-8007-016c7545717c | checkpoint | Quality Verification Requirements, Test Method
be119f10-2740-5f6f-8dae-8cfa5d493f0c | note | Acceptance Criteria and Frequency (Project Specific) -
834e8795-211c-5023-9003-a47804a39273 | textbox | Min. Testing Frequency
a5c5ad82-c16e-553d-93c0-f897c4ead6c2 | textbox | Min. No. of Tests
3198c8f0-1e7b-52e7-bc33-79782a4e127b | note | Check Item - MRTS45
28325dcd-50f7-5620-9de4-1de70bf86864 | note | Reference - Annexure
84e6a064-2ac1-4ef4-992b-3ee74ef922dd | checkpoint | Materials
938d27c4-2542-5c55-b5f0-914461dc1b43 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch, 1 test
0788d93c-73f0-5ee6-8f4a-36d8baeff48a | note | Check Item - Check Item
03e9fc18-8e59-5d14-a100-b90d7400485a | note | Reference - MRTS45.1
df105eb9-f1b3-450a-94b0-f204d9a36740 | checkpoint | Thickness of Pavement markings: Longtitudinal lines, Transverse markings
c3f4b551-3fe8-5afc-ac6f-5c71bdd397a3 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot/ 1 test
cf5f445a-cb54-5ec7-a574-0a0354970e4c | note | ○ 1 per lot/ 1 test
1404ef7c-0863-52bb-bc7f-910f65b7cece | note | Check Item - Check Item
50b21159-0b87-5869-9b9b-698c9d43730d | note | Reference - MRTS45.1
78a2834f-6acb-436d-89f8-9f9d67c6ecd2 | checkpoint | Dimensions of Pavement markings: Longtitudinal lines, Transverse markings
536a8345-9668-548c-ad6a-7c46c5e6b3d2 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 200m/ 1 test
58fb4aa6-be2c-5eb7-aea0-5f9f58e38816 | note | ○ 1 per type/ 1 test
30a19397-0e4f-51f5-8977-cfef4c0e0e32 | note | Check Item - Check Item
aa7a335b-55de-5066-b768-b5446e512fb2 | note | Reference - MRTS45.1
49e551f8-93da-4704-b716-bef461d7c87e | checkpoint | Dimensions of raised pavement marker placement
94afc59d-dd82-51ea-af9f-9ac8807469f8 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per 50 / 1 test
97e76f74-318d-5797-9a6e-298161e4595f | note | Check Item - Check Item
e69ed4c6-3d9c-59ee-abbd-42abf134e03f | note | Reference - MRTS45.1
d259b792-cc6c-43ed-b5e4-4d9c7d3fe126 | checkpoint | Retroreflectivity
bd52df72-2f0b-5772-8c50-035c0c7545f1 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot / 1 test
79b75a52-b0e4-528c-ad86-6f9cd60f4bfb | note | Check Item - Check Item
a3baa8ce-a7e3-5d93-8fbb-350eef71974e | note | Reference - MRTS45.1
e868c7d2-6c18-4bef-b00f-4adca2f5077f | checkpoint | Skid Resistance
8aa2a53a-bf2d-507a-8487-769810634c15 | note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch / 1 test
624b88ab-f611-5ca1-a470-f2057629e9e2 | note | Check Item - Check Item
761cf99e-5a84-500d-9513-06bfb1f11cfa | note | Reference - MRTS45.1
ab0c5d95-709b-434d-a732-a7634a282d44 | checkpoint | Final Verification
ba00794a-b4f1-5c0a-bf13-12eacabf3ebc | note | Project Manager Verify that the Above has been Constructed according to Specification
ff6535a5-4f1d-513f-8ab3-a78158b038c6 | textbox | Print Name:
3fd4d067-9cd9-562a-b0cb-588e52342065 | date | Date:
005df81c-4439-5278-88fe-7bb19b4f4658 | note | Client Verify that the Above has been Constructed according to Specification
ad80d0d4-1e8c-5bff-93e2-d3821a080bc1 | textbox | Print Name:
91c46643-861b-56c1-bcdf-2c6abcfa80c7 | date | Date:
4c7279f9-ebe2-46c0-a3b8-4695f5f7c323 | signoff | Signature
d2f86c20-40e7-4cca-b94c-c4204cbec887 | checklist | 51.00 - Environmental Management Systems | itp | 51.00 - Environmental Management Systems
e712e5dd-0ab7-4f01-808c-29ce6391cff7 | section | Details
5447fcb9-eda0-4d71-a740-9a4bc9bfd844 | checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
13960cee-20ce-5d8a-a281-926fe5900527 | note | Check Item - Milestone
65fc305a-f71b-5c64-97a2-0e037960633b | note | Reference - MRTS51 Cl. 6.3
b9f2151a-69b0-4337-b709-370a06dea28e | checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
09f1ae43-26ad-5709-9ea2-e343134a774b | note | Check Item - Hold Point 1
469bee5c-05bb-5f3b-85da-9c57d797d076 | note | Reference - MRTS51 Cl. 6.3
b89bed73-19b7-4a8d-8ea7-58449f0cc105 | signoff | HOLD POINT
11f95e1c-b7bc-452e-82b0-fc17e434e3de | checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
0cf223b0-f8e9-5992-b82e-5092f93361b4 | note | Check Item - Hold Point 2
f3497457-9be3-57f8-8c81-60ae4464f5a8 | note | Reference - MRTS51 Cl. 6.4
7a57f29c-4290-4d97-b11b-31fdec6cb3f4 | signoff | HOLD POINT
c73f55d1-d4ad-4861-a40d-442b06e5f707 | checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
6d7637f2-b307-5838-8db6-1d3b4fa8bbe1 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9943a71c-8fe6-5f90-a6e8-4894b81aac68 | note | Check Item - Check Item
ca22e60f-a541-544e-b684-e2c3ccdeef0b | note | Reference - MRTS51 Cl. 7.1
862dbed3-b0bd-4d18-82b2-affe719ef00e | checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
eb33f65c-902f-586a-afe4-b86622847bcd | note | ○ Landfill Gas Requirements
ff3445cf-ca49-5106-97ba-c04194cd81d3 | note | ○ Contaminated Land Requirements
ff402438-d3ef-5579-b3f8-9a7c5e2b008d | note | ○ Water Quality Requirements
c52ae4e4-63ed-59ca-89f3-cea8460925e5 | note | ○ Bio Security Requirements
11aead9c-4443-5003-b0ee-b53956665197 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8c3def78-40df-55b0-95b5-5579d7b7e1f8 | note | Check Item - Check Item
0c854cfd-a596-58cc-9971-b230d772ff29 | note | Reference - Contract Documents
8199a689-3dd9-4246-8f63-ce0f5c1dbb78 | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
1614adfe-6b23-579d-831e-14b386b80379 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4b92bdb6-e36b-5194-9328-82532c9d85c5 | note | Check Item - Check Item
62c109fb-9eed-58a1-8782-e6a9619202fb | note | Reference - MRTS51 Cl. 8.4.1
73bb2a1e-25af-4017-97e0-3fea62469676 | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
5027211d-04d1-5cbc-abe1-dba4f87ff5f5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
841e3ce5-f3b5-5b02-802f-a762d5e4ed3c | note | Check Item - Check Item
01b24022-314b-57c1-9260-d78e684c8844 | note | Reference - MRTS51 Cl. 8.5.2
1996fc54-9563-42cb-991a-e7638138ece4 | checkpoint | Project records shall include all noise monitoring results if required
a6009f88-a0c6-5f18-ba06-21bec40feb1b | note | Check Item - Check Item
563f4536-f6ba-59e5-b80c-0e0c1b0b3409 | note | Reference - MRTS51 Cl. 8.6.3
01a9344e-e191-4638-9f7e-84b14209c06a | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
f3e25909-7cf1-50ba-8faf-36b7f92f1dd5 | note | Check Item - Check Item
cf33e10d-f3bd-5189-8aec-aa59202ef395 | note | Reference - MRTS51 Cl. 8.6.2.3
b6e93900-872f-4f3b-b14c-7459f501ac91 | checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
3aca3251-935c-5570-8c50-60085c293a8d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
514a8788-3f11-5815-b5f8-12d40b969048 | note | Check Item - Check Item
ad1e89e1-59e1-5e0a-afd9-28fa96444817 | note | Reference - MRTS51.1 Cl. 8.6.1
6558baf3-6c93-4509-9d0a-39b44a49e35e | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
60d7aa93-b479-5043-aa7b-498114b83da7 | note | Check Item - Check Item
a64c360d-2a9a-5693-a5ef-d22d7200786a | note | Reference - MRTS51.1 Cl. 8.6.2
5d5ce3d9-6d51-4911-a304-21418c822068 | checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
5f0b7a1c-4cf4-5248-ae2f-b5da7911f058 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6c7472c7-89ec-5a4d-9ed1-4e6fbdc4a23c | note | Check Item - Check Item
d3cd795b-f1d1-59ec-95a9-480fa9ef4892 | note | Reference - MRTS51 Cl. 8.7.3
03e37f63-bf48-4814-9201-a883740bbcba | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
aad631f9-fc1e-57f2-a52c-013427b47d38 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fdc7ef84-0970-528a-960e-37239ae90644 | note | Check Item - Check Item
2fe1d2a5-6424-58f4-86f6-b9d02999a6ae | note | Reference - MRTS51 Cl. 8.8
6f3cd8bd-9e07-4514-8272-518aa76e1890 | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
a72cda7b-3c7b-50d1-bdb7-fea4ec7dfb2e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
abf7e775-b943-53a6-8a5b-de67ecdc1f05 | note | Check Item - Check Item
2217bfbd-abd0-50d8-b074-e9c501e153f2 | note | Reference - MRTS51 Cl. 8.9.1
9091fe20-f30c-42a3-8119-5c463b983e45 | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
b81dd9dc-88be-5b19-81f0-f21981beda35 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f1e2960b-6c22-5c8c-b436-4383a6f6f562 | note | Check Item - Check Item
860ed1b3-984e-5625-bfa8-04628cfab8d8 | note | Reference - MRTS51 Cl. 8.10.1
a397631c-1334-4241-84a7-2c68467d639e | checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
5bd95afe-f5b0-5e1f-9f96-658739d12d3a | note | Check Item - Check Item
2513a631-55a7-59fb-ab8c-bf3a69ded2fb | note | Reference - MRTS51.1 Cl. 8.10.3
ffea7250-b838-43a2-be3e-49a006691392 | checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
4a72f6b1-51ed-54bc-bd87-e3510dc06f78 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
877c96a1-4b29-556d-8aca-62727f992fe9 | note | Check Item - Check Item
fb4bc414-9239-5e32-8908-902a7f654863 | note | Reference - MRTS51 Cl. 8.11.1
08fa7380-8f31-4db2-a953-c0363749e4d8 | checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
08fe556b-c34f-5af0-97a7-40b4e81062a6 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
376c4c88-822c-5312-b651-f5d53bf6d9ac | note | Check Item - Check Item
a69fa958-af5d-5587-856a-a25ac77d9964 | note | Reference - MRTS51 Cl. 8.12.2
9cf32b55-2810-4c1e-84e9-5ee0d4b0b3e3 | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
39d904b4-aa9a-5e90-9212-31bf0fc57068 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4833d727-a8a1-5869-9fee-24c7db8d63f6 | note | Check Item - Check Item
e5a8f725-3f01-5911-9fd8-e9bfd18f402c | note | Reference - MRTS51 Cl. 8.13.2
3bbe55a3-49a8-4385-88da-d03ead0771d0 | checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
8f55bc1b-ac6f-5eeb-bbfe-0dc3e1a380b0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a85384df-3136-5798-a0bc-a9d725a2e075 | note | Check Item - Check Item
a8efcce5-81e6-505a-8ad6-8d1088bb966f | note | Reference - BCC Supplied Certificate
d6d24a15-ba4c-4b88-b9d4-2e37e4ce9733 | checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
fb7900b2-a2ee-544a-aff3-8f410df1eba8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b6fae3fd-3198-5e23-9251-90ac1ca270c9 | note | Check Item - Check Item
e620138b-bf12-5e67-9217-5b594e448c15 | note | Reference - MRTS51.1 Cl4.2
a732f2d2-4ae5-47f5-b2de-628c5bb8a083 | checkpoint | Maintan a animal tamping register inline with the SMP
eb4ef10e-0c2f-58c9-b5c7-264261f5e301 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
e97ba801-b9f0-5619-a638-629abeede2bf | note | Check Item - Check Item
50ac981a-cd08-516a-b41c-ab54a07478d7 | note | Reference - SMP requirement
0320be79-b5bd-496f-b21a-a08cca953da4 | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
af7ede6b-77e4-5793-ad3f-3f82f26f81bd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
119cde85-6047-57ad-8ad2-b59fcd206fff | note | Check Item - Check Item
92b4e78f-3729-5717-8e75-2a45416bbde5 | note | Reference - MRTS51 Cl. 8.14.1
746504b6-9865-4192-9b27-47dcb5c843fb | checkpoint | Final Verification
525a524a-4a59-547d-be27-5d04e09a9933 | note | Project Manager Verify that the Above has been Constructed according to Specification
8bb69c9b-88ee-5319-908f-0d88ff9214b2 | textbox | Print Name:
b13bfb06-7b05-5cce-a8e7-d5440a784da9 | date | Date:
cb33b584-6966-586f-8e9c-1981b793b2f8 | note | Client Verify that the Above has been Constructed according to Specification
c857b817-2232-5684-a3b9-a8ca510c615e | textbox | Print Name:
429a6db0-67f9-5ed8-9a24-a4ef1f54d7f8 | date | Date:
3dfa1c5a-482f-4024-8a93-048d9c4f7b2a | signoff | Signature
1274d293-8ef8-4a99-88d3-761181556015 | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
23015338-dec1-4008-a522-d7bff92d5601 | section | Details
aad98518-567a-4e10-b156-e21c9dc430e9 | checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
591ef78d-ae36-503b-8c24-6ab81f6173d7 | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
97c607d7-4d3f-5720-b771-598adfe2d27a | note | Check Item - Hold Point 1
059fed0c-5e8b-5225-b3d8-e3cf90dd00f6 | note | Reference - MRTS52 Cl. 6.1
fb4bdd24-d153-48ba-a680-65bf17e64e84 | signoff | HOLD POINT
37313a8a-e96d-42dc-bf48-bb08902be692 | checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
f73208ad-ff6d-5674-8c82-3a3c98f9bd1a | note | Acceptance Criteria and Frequency (Project Specific) - Check Item
6b24db0b-d982-5442-8ad7-747cbd27b8dd | note | Check Item - Hold Point 2
d471af13-31f6-5f45-99a7-27fe1faa225d | note | Reference - MRTS52 Cl. 7.1
fe190e7b-4446-4fb4-bcb2-5344a8879967 | signoff | HOLD POINT
ec8cb1f9-b4f2-47df-b17e-d3bc1947ecf8 | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
f2e1bf4c-cfd5-583e-864d-0a3eba4bd1e0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7a99bcd0-175c-5990-9ff2-06b9d90e2645 | note | Check Item - Records
de9d692e-189c-5792-bf31-08c36f6db332 | note | Reference - MRTS52 Cl. 8.1
9f1d6902-d13c-44d0-a029-8bcf7d1034b6 | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
c6387bf3-eee7-53d4-b864-207143ce14df | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3957c70b-448e-5937-8f08-ab62c3e01c7d | note | Check Item - Records
c0b8cb1e-dc2e-52b5-b358-bc52b8df5501 | note | Reference - MRTS51 Cl. 8.2.3.2.1
91eaeeaa-fb54-47d4-a5f5-926fcd4a501e | checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
f6324593-c8f8-5591-89b5-38f4059cf431 | note | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
29297c61-a7e8-5a09-bc9c-11b216daf194 | note | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
ea0a51d1-b2cd-5d03-b63f-57984140994d | note | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
c02eba01-e2e6-5271-8c30-c2f8fea9135d | note | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
d09d39d8-b420-5f5d-bf85-0f2b67874884 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
85b31bc7-e56f-5a09-b2b4-f333c3f2dce7 | note | Check Item - Check Item
53ba21f2-ee69-5d7b-b6bd-9e79261f02bc | note | Reference - MRTS51 Cl. 7.2
e1e1a213-47c2-44ce-a825-d968b3ee4f6a | checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
61b38c0c-f0e0-57f9-b2c5-600dfa2bf224 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ff293daf-76d8-554a-b574-86fbed5646c8 | note | Check Item - Check Item
24d41178-a02b-566e-be21-c8ffc7d33ff4 | note | Reference - MRTS51 Cl. 7.3
4a09ce1f-a3b3-4774-a5e0-53ba1a8dfc6a | checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
577e527e-75ac-5b22-84ad-f9552f962b28 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
9f9790e7-42bf-5a7e-9680-a03a4472c069 | note | Check Item - Records
5e5ed88b-bea4-51b1-840b-30e62d6045ef | note | Reference - MRTS51 .1 Cl. 4.1.1
2d165901-92be-49b5-b0f3-3f9a3318ec1d | checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
c1babc32-ea08-5f67-9c7b-b16426e4526d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
435661b7-6a65-58a8-8105-237ddbfb78bb | note | Check Item - Records
baeea84d-7fb3-5c94-9eab-95bf60f9d3cd | note | Reference - MRTS51.1 Cl. 4.1.3
5ffc4f7a-6d7f-4549-a4d3-252b83632a21 | checkpoint | Final Verification
9180e29c-2496-529d-91c6-d88687665d0f | note | Project Manager Verify that the Above has been Constructed according to Specification
03ce5d16-9dbc-5234-868b-1cceeed62003 | textbox | Print Name:
18be9f7d-bc21-5ece-b44a-4f0ed72973ae | date | Date:
8eb1e0fd-4eef-5e5f-a79f-8c515201a05e | note | Client Verify that the Above has been Constructed according to Specification
b80509f2-9f87-510b-887b-81111b86116f | textbox | Print Name:
bfbf18b5-b638-5950-b0fa-956773a5115f | date | Date:
31ccaa47-4682-4359-90fe-4c59d5457d32 | signoff | Signature
0300a05b-813d-41b5-a7e2-8407c703caa4 | checklist | 70.01 - Placement of Concrete | itp | 70.01 - Placement of Concrete
bbfd5aee-d3c2-40dc-b830-74a31415a2ac | section | Details
afeea851-ee7d-4bb5-8b0f-80c885546591 | checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
3df3aa6a-0e7a-5991-b8be-f15f9d1aeb7f | note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
0db6b309-bb27-56e5-b740-243c9d2ce585 | note | Check Item - Check Item
7b981837-bf83-5e92-96fd-04e97e17a6e6 | note | Reference - MRTS70 Cl 13.1
b647f718-74ce-469e-8fc5-ce057d729322 | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
ff4efecd-f758-5de1-a709-4607b98736ca | note | Acceptance Criteria and Frequency (Project Specific) - Visual
38bb7c84-7dc7-51fa-96a3-4588caa9abd8 | note | Check Item - Milestone
66e102ca-e285-5ece-8c6b-555e1d0e37c6 | note | Reference - MRTS70 Cl 15.3
90a55c64-4f0b-4372-98da-d0d2637a1d68 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
0d69a026-f251-5502-ba29-f475c7aca663 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3854f92f-2bf5-56e7-8028-73c438089bac | note | Check Item - Hold Point 2
824717ee-3197-5b48-9b48-10864f8ad133 | note | Reference - MRTS70 Cl 15.3
0211c252-d3f2-4cd9-a0b0-d14cfe2ab28d | signoff | HOLD POINT
bf109cac-2c7e-4533-b761-a86f6734e25d | checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
3783467a-9bbf-5fee-926f-450bde2dbd53 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
952a1680-d833-59f2-ad25-13edd8c5448f | note | Check Item - Hold Point 3
785a97ac-0007-5c7e-b18f-95df8825c257 | note | Reference - MRTS70 Cl 15.4.1
cd9a11cd-88b7-4ec2-82fd-513a5dc44509 | signoff | HOLD POINT
0f66cca9-9cca-407f-b029-8c45797ba015 | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
f3b56d81-75df-5675-a2a5-d359898d9e49 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fa659928-30f8-5281-940e-ad7ace58a858 | note | Check Item - Hold Point 4
6bc780df-5995-5ae0-8ca6-ed215c78b0f4 | note | Reference - MRTS70 Cl 15.6
5499869d-e940-4765-b760-3f8d97e64156 | signoff | HOLD POINT
ec8753c3-876f-4b58-b209-172c583f9e19 | checkpoint | No concrete shall be placed in the Works until:
23d3627d-0139-5d6d-ab61-6434775541a6 | note | a) the formwork and reinforcement have been inspected
2b2c778d-6a09-5585-a583-71885abe86b7 | note | b) all foreign material has been completely removed from the forms
da9bec6b-37aa-5818-9f13-ddc76b71af3f | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
0c216631-f085-5418-9ca7-7f701b1c2c9e | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0c320bc5-a35c-5b01-a897-7f057ba822cd | note | Check Item - Hold Point 5
8f481263-7058-5ecf-a53e-bbf4aa50bd02 | note | Reference - MRTS70 Cl 15.6.1
d7c760eb-ec8e-46bf-8350-27b01f716b29 | signoff | HOLD POINT
c77de891-f1e4-4b0e-99f9-5fe03bb2606b | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
316388f0-35ab-5bb8-89a0-a1a01a735610 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dc8af876-139f-5b6a-9492-a02cc4f43898 | note | Check Item - Witness Point
f88b874c-b8ac-5071-9ba3-3f8c3adec086 | note | Reference - MRTS70 Cl 15.6.1
078f3504-2602-44e1-8e09-e86eabb51f55 | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
f8c4d2bf-c125-5034-9172-1dc0a7dcb430 | note | Acceptance Criteria and Frequency (Project Specific) -
99537dd1-cb68-5978-b9dc-67f2fa0a5c1a | note | Slump Test: ¦¦ Spread Test:
2b66441b-146a-5671-8c50-b61699cc579c | note | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
3737c17a-2fdb-51c8-b204-fab994243dcc | note | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
152d658f-a1a8-5345-80ba-23177b8cb76b | note | 80<110 - ±20
75467924-014c-5a52-b260-caa6be46eafc | note | 110<150 - ±30
456ca454-f5c4-51c2-8d2d-4c08b8fac524 | note | 150< 200 - ±40
c12a7e1d-f217-5bb8-8385-0769d84f66e7 | note | Every Load
3869a03d-ecb1-5295-ac2b-637bb080e4ea | note | Check Item - Check Item
a6066e07-297d-5a7c-bb5a-d06e2198c5aa | note | Reference - MRTS70 AS 1379 Table 6
be8b8901-9316-4d6c-b964-754ede1f0d19 | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
02b62a4e-28d5-5622-95ed-a8b6aaef37ba | note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
807b0ec3-1d2e-5291-b0b3-008ac42cb14b | note | ○ 4-10 Loads - 4 Samples
e23d4dc1-8bed-53a7-bcda-8308df8461bf | note | ○ 11-23 Loads - 5 Samples
5771ec82-0eb7-590c-acea-00279323de82 | note | ○ >24 Loads - n/4
d5880fb1-6816-5b19-bf1f-f2eca33a6e8c | note | Check Item - Test Results
3792c436-91a8-5394-89d1-fe22a31b1bf9 | note | Reference - MRTS70 Cl 15.2
a1c8ce7c-469a-4033-b1fe-50f7b0dbf4ee | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
34104743-1c42-54b7-8865-638d346732eb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3890ab68-ba70-5f61-a98a-b2a8d6f97b39 | note | Check Item - Check Item
75347f3e-de03-56c7-a0c8-cbd2e07462f5 | note | Reference - MRTS70 Cl 16.5.2
7dc96c1e-c5dd-49c9-9385-2a529cf6f836 | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
ae6e4121-0654-5a0c-a884-f0eafa02c7c8 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fc54da76-653c-5192-90c5-9be73de51849 | note | Check Item - Check Item
61cdb60c-17db-5384-9585-91487308cf9a | note | Reference - MRTS70 Cl.16.5.1
4de6fb0a-ecf9-4ae0-bfd6-845fe93f4d97 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
810875c6-3b1d-521d-8742-69df994665bb | note | Acceptance Criteria and Frequency (Project Specific) - Visual
1c04b3b9-407b-59c3-85a3-25299aac6a38 | note | Check Item - Hold Point 7
f91bbec9-8f55-550d-b4ae-cad8babf1e25 | note | Reference - MRTS70 Cl 15.13
9c122476-32a8-4be7-8e4e-1aeb6c92aa34 | signoff | HOLD POINT
ad30d1bb-c055-4ab4-b988-40d03a815721 | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
25a2f75e-9308-56fc-bac8-5bb35f4fe508 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
441ecb8b-f582-51c6-929c-3c96d4bda361 | note | Check Item - Hold Point 6
850381d3-15d1-5028-9114-adb4153f9dd7 | note | Reference - MRTS70 Cl 15.8
a78da231-f57e-448c-9ef8-ef26456a8845 | signoff | HOLD POINT
2ce9d115-6816-4f68-91f6-1cee11afbfb8 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
446a4d0f-928b-5e0f-8f0d-19cd6c6a5e1c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
81ea1d47-b288-503e-8a65-119085b6f62e | note | Check Item - Witness Point
80e73de4-711f-5858-990f-15a40bb210d4 | note | Reference - MRTS70 Cl 15.8
66eb24d9-1e2b-4d2c-855d-7bf33bc426f1 | checkpoint | Following removal of forms
8486f5fe-7c0b-52bd-b52d-ace5ecb2fcee | note | ○ Fins and unwanted projections are ground off
5f4ee171-7040-5405-9b5d-2ce7c60ca547 | note | ○ Pockets and honeycombed areas repaired using approved methods
ca7f0d33-630b-584b-be5d-924fd7276ecf | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
f7202b34-8281-5af3-a07e-68ef937c9cf3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
524b5e4f-b7e1-521a-9278-f5db85fe2915 | note | Check Item - Check Item
cfad38fd-993c-5c63-9d98-ea8c9c6607cb | note | Reference - MRTS70 Cl 16.8.1
b75d731f-e71d-4d15-8e65-456c746d736f | checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
c16137a4-1541-5e37-bd20-8b71c828ed3b | note | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
479700ff-7c61-5867-92d9-dcd9d4a3700f | note | Check Item - Check Item
eff23531-d0f8-55c9-9905-d07f008a2816 | note | Reference - MRTS70 Cl 15.7.3
4fdac618-c8ff-459c-8b03-e5c5f36bf83e | checkpoint | Acceptance or Rejection of Hardened Concrete
439debb0-2a6c-5348-8fd5-92115e1d9b8e | note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
b721bcff-d075-5785-b667-ab904299652c | note | b) < Fc (Ave 3 consective samples from Lot)
b7b9bebd-9de3-57d9-9b4e-eab04ca12763 | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
5814683e-3dce-534c-9457-42c5be4307db | note | In addition
a28efccd-5fa3-5294-beee-3dbe6af2b6f4 | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
6f9b1e3b-5c17-528c-a481-3c7829d4218d | note | Check Item - Test Results
49f0f3c0-cb79-5081-ad4c-5a9d5c9cbec9 | note | Reference - MRTS70 Cl 12.5
7bb3675c-0027-4f8d-9e50-8b4d24820c1e | checkpoint | Final Verification
17a56d0c-96f4-5d13-a659-642b1ff9341b | note | Project Manager Verify that the Above has been Constructed according to Specification
4e1d1fa3-fd4d-50b7-a746-f2c78326e61d | textbox | Print Name:
a25f80b2-548b-5dc8-a750-6dc3b5d76f8d | date | Date:
4d42ece4-547d-5c70-abfc-cef0de711090 | note | Client Verify that the Above has been Constructed according to Specification
d106e5f5-d7b7-526d-a858-ed246fb7446d | textbox | Print Name:
61f3a327-7893-5d14-875e-c172ea50cfbc | date | Date:
da0b7b75-c5c6-4a38-99a4-7e63f6d4be8b | signoff | Signature
b3da7fad-8e85-4a2f-9e12-1bf4b0b24eab | section | Details: Concrete Record
7304ebf3-b10e-4197-af0a-a2a9e306a406 | checkpoint | 1 - Date
d41f8d81-4068-5391-9d7f-3b4f9d866f3f | date | Truck 1:
1f071dc0-7597-586a-a030-e3dbf607253d | date | Truck 2:
f99667b6-fa89-51cd-a456-4160abdf9e87 | date | Truck 3:
448dd8bb-8abd-533f-82ae-086be2281c88 | date | Truck 4:
3e3f161b-6538-4d2b-ad39-f40fc9f203dd | checkpoint | 2 - Docket
bf6c7ccd-3b4d-5c42-9640-358e457f026e | textbox | Truck 1:
b037278e-5ee8-5dd5-a0d4-44a4b599a14f | textbox | Truck 2:
7158c28a-4e85-5a82-aa30-e5c9238b84a3 | textbox | Truck 3:
b41a11ac-b9d6-5f61-9924-9c8f3e311950 | textbox | Truck 4:
5e5f60b6-569b-4e49-99e4-9e2e656bdeea | checkpoint | 3 - Time Batched
1d5dc7b3-5c72-5888-b4d9-448fc694e8e6 | textbox | Truck 1:
16772c4f-85e0-5b90-90ab-f8130a21fa59 | textbox | Truck 2:
1a5b0d3e-7d34-581f-b1f0-2a145d6fb078 | textbox | Truck 3:
948c0db4-1edd-5a12-9005-e1fc3d3e02af | textbox | Truck 4:
4f154790-8c5d-48d5-9af3-0a3c082e5c97 | checkpoint | 4 - Truck Arrival Time
bdc094ac-581d-514a-9821-c404a274aec4 | textbox | Truck 1:
28f423c9-e006-5caf-8fb7-3c1f01a19edb | textbox | Truck 2:
c4fe526d-ff76-5aa0-b42e-c5b4c740c6e5 | textbox | Truck 3:
c372b1f1-603f-5f1f-85f2-182e54c53c04 | textbox | Truck 4:
2213063c-4ec1-49fa-af1e-7ddd65c4bac2 | checkpoint | 5 - Load Size (m3)
b45e9b22-f9d6-5486-af9c-413ba1acb79b | textbox | Truck 1:
59a76fcd-619f-59dd-b7b5-5c432f58ea3f | textbox | Truck 2:
3fe2b93a-0bee-55a8-9224-8de59dfaa480 | textbox | Truck 3:
d8dc68db-b01e-5e5f-9efb-7e57590f77fd | textbox | Truck 4:
d9cdf456-f002-46b0-b68b-023622587f1d | checkpoint | 6 - Mix
6e57712e-0fe3-4b11-a967-edbb0869c2a5 | checkpoint | 7 - Slump (mm)
32b93708-d537-5daa-9047-fa45d3c841dc | textbox | Truck 1:
eadf64ab-7971-5669-b41a-1799ccd3f2ca | textbox | Truck 2:
afcb475c-000f-565a-802d-561604d61305 | textbox | Truck 3:
1f1b6d21-749c-5f07-81af-82a216242f2d | textbox | Truck 4:
3b9e62b0-cb4d-4d7d-a78b-795949088958 | checkpoint | 8 - Slump Time
cb626276-e17a-51a4-81a0-78937e60cd1e | textbox | Truck 1:
f2d42926-a0a6-5fe9-8418-7dc2423048ea | textbox | Truck 2:
18b133ce-3b14-58bf-9a81-8b72d00e3983 | textbox | Truck 3:
c806ae28-4d04-52b4-84b1-b1c8c6489038 | textbox | Truck 4:
4c7bcb00-1d20-4103-9038-73c8a0948a70 | checkpoint | 9 - Concrete Arrival Temperature (˚C)
ddb80e21-c4dc-5794-bed1-03227d17f8c9 | textbox | Truck 1:
6e61eaea-1899-5491-bb8b-a3e1f8699bec | textbox | Truck 2:
295f5031-ebdf-537f-8d00-ccd2750807f5 | textbox | Truck 3:
7c4f5f5b-6923-5684-9671-11ab65102a2c | textbox | Truck 4:
f4efe583-5427-4617-a93a-1b489eefa25c | checkpoint | 10 - Ambient Temperature at time of slump (˚C)
cf59ecf8-5397-5bf9-ac49-60b4d535fccd | textbox | Truck 1:
53bfe900-4b58-5dd1-b471-3d89dc0958f9 | textbox | Truck 2:
f772b772-efdd-5015-9cb5-b36514ce858f | textbox | Truck 3:
92a8d623-b1ea-5059-b7a4-ecf5b8cbba92 | textbox | Truck 4:
d37a2df3-c504-4e38-b6d4-ada1e13f061c | checkpoint | 11 - Time Start delivery
97cfbd03-b6d6-5b03-b3f3-d932b78892d6 | textbox | Truck 1:
ba4cead7-ca97-5fad-8ddd-1aadbb0295f4 | textbox | Truck 2:
0cf0879e-7abb-53eb-8794-c54b615598bb | textbox | Truck 3:
69b1bb08-2275-5067-b97c-58bfe304ac4e | textbox | Truck 4:
76ac243a-749b-4649-ad88-46ff9130ffa5 | checkpoint | 12 - Time Finish Delivery
20ba59b6-3078-5cd0-ad3a-e4bc1fe9f15c | textbox | Truck 1:
76ae1fe0-b9b2-5458-9256-98eb7793c904 | textbox | Truck 2:
089d6fac-40e8-57d9-b3b7-521049a788d4 | textbox | Truck 3:
7e2f9b25-d157-5bcc-8d4f-08b3693636e8 | textbox | Truck 4:
74448808-aa77-48a9-a7b2-676ac46cf970 | checklist | 70.02 - MRTS70 Normal Class Concrete | itp | 70.02 - MRTS70 Normal Class Concrete
80d27383-1d1f-4bd2-b0a3-2b694bd5614b | section | Details
775e35c7-e39a-4c68-9c98-2035130dffd2 | checkpoint | Concrete class - The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
61ac9813-c48e-52eb-9bb0-62754c8b39d7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
dcb96866-3a26-5fc5-a4ca-ccd9a8b1eda6 | note | Check Item - Check Item
ba3d2fb3-5e30-56ab-9567-21486aa56be9 | note | Reference - MRTS70 Cl 17.1
40a8731f-f524-4786-9fb9-ae2f221b97d2 | checkpoint | Acceptance and rejection of hardened concrete - Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall betested on a project assessment basis, where more than 25 m³ of concrete is used:
ca477802-f607-5c95-b4eb-7e66e3bbcacf | note | a) signpost footings and plinths with dimension greater than 150 mm
c5feeb00-6a3e-52cf-b356-ff8d1cdeb3d7 | note | b) spill through or rock grouting, and
00d1f68c-d41d-5f0c-8a7c-38cb8d12c4c8 | note | c) manually placed kerb and channel on or alongside concrete base.
76b78463-2f7b-579f-b4ba-3a14ef45bbb5 | note | ○ Production assessment reports in accordance with AS 1379 shall be submitted to the Administrator
932d61a0-b162-5200-8cfd-61975b2bcd9a | note | Acceptance Criteria and Frequency (Project Specific) - Visual
55e883c0-4ccd-5876-8eba-72e0e251bf4e | note | Check Item - Test Results
b0fa16dc-e47c-5b16-bf96-8eadae98964d | note | Reference - MRTS70 Cl 17.8
cb253795-aec2-48fb-a58f-0e1aa71262a2 | checkpoint | Approval of falsework - All formwork shall be subject to inspection and approval by the Administrator
311212dd-eb76-5f15-aeed-7878c9a24210 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c6e880f5-dfa1-5138-9f45-4cc4130ef4e8 | note | Check Item - HOLD POINT
c65a9f8c-dc57-5a4f-82e6-b621d955911f | note | Reference - MRTS70 Cl 17.10
5dd8e76f-d27e-43c4-b563-667e23429279 | signoff | HOLD POINT
694b62aa-7b14-41d5-9553-7855012a6010 | checkpoint | Approval of formwork - All formwork shall be subject to inspection and approval by the Administrator
f54bf845-a1f4-51e7-8a68-60f243226cf7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
92120d35-94f0-5ec9-a38a-44dbab090dc3 | note | Check Item - HOLD POINT
eda4e15a-fd62-50de-8663-4ceaae8a59ed | note | Reference - MRTS70 Cl 17.11
9154f67c-e0ef-4f01-9dbf-34b79a5b9449 | signoff | HOLD POINT
853d2b6a-32e6-4c63-b82a-f05ff4381473 | checkpoint | Supports (bar chairs and spacers) - All bar chairs and spacers shall comply with AS/NZS 2425
14e174ec-8603-5dd0-b82f-f3776dd5a8d7 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
51877d2d-48d7-57fc-84b9-a764098621c7 | note | Check Item - Check Item
5851ce75-d963-51a1-aa92-f55f55e5e824 | note | Reference - MRTS70 Cl 17.11.1
0bc689e5-04d7-4678-bfe0-8324993beb5b | checkpoint | Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground / bedding and the concrete
1cb163c6-e1a6-5751-847f-af020109eada | note | Acceptance Criteria and Frequency (Project Specific) - Visual
ed76ee70-b5e2-5322-b6f1-b9833170702c | note | Check Item - Check Item
36872d7d-7ed6-51c1-8e4e-c951778fd0bf | note | Reference - MRTS70 Cl 17.12.1
2a20b321-f6a7-48d2-8e90-4aff87331d5a | checkpoint | Approval to place concrete - No concrete shall be placed in the Works until the formwork and reinforcement have been inspected, and all foreign material has been completely removed from the forms.
e06e9b56-56ac-523a-a297-ca216ad7ca71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
424d9302-8faf-5df0-9efd-2148b2d6af02 | note | Check Item - HOLD POINT
5a738e33-bc01-5e97-8ec0-33c5112a2546 | note | Reference - MRTS70 Cl 17.12.1
c3bf1ff7-743f-4e5a-bc7e-e7c8cec4a74a | signoff | HOLD POINT
8cd72731-167b-40ee-9428-c6c5867d1a1d | checkpoint | Placing of concrete - The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
f210606c-21c6-557e-a406-82c75beded92 | note | Check Item - Witness Point
53083a17-8d35-5f37-8a8c-00898237de36 | note | Reference - MRTS70 Cl 17.12.1
d3df15a1-ada4-4716-a469-395293764432 | checkpoint | Removal of formwork - For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed.
7516fe76-d0f2-5a6c-9594-899be5e07c70 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
887cc3ef-199f-5f39-8c6c-092a9842f0df | note | Check Item - HOLD POINT
7bb6a73b-eee8-5999-8691-54d65e601c86 | note | Reference - MRTS70 Cl 17.16
c923b59b-6421-45a5-b22c-4f6614b7fdc8 | signoff | HOLD POINT
618034a3-c9f2-45a3-a91c-99b0ff7fdc28 | checkpoint | Final Verification
8af83f4e-18ea-5fb2-843f-5259f8d8f705 | note | Project Manager Verify that the Above has been Constructed according to Specification
330294b8-7b9b-58ca-bb73-8cd6c049522b | textbox | Print Name:
9c51917c-f3b3-5da5-96bc-f0e4a556ee07 | date | Date:
baffe8d1-8d32-5a29-a4be-54a7850b3561 | note | Client Verify that the Above has been Constructed according to Specification
7eebf2c3-1bbc-5ff8-a446-6e3ea5fcb510 | textbox | Print Name:
de4e39dd-8b24-5d9a-a03d-7114861b5c5a | date | Date:
22ee93ce-b630-429b-9597-e4c8e4ff7857 | signoff | Signature
8bebcbec-b8d0-4093-a031-e8bebce705bf | section | Details: Concrete Record
d0de3ff0-dda5-4fbe-9fe1-1dc536325ae8 | checkpoint | 1 - Date
4f9a42a0-24b7-558a-879f-1719816d990f | date | Truck 1:
e4ec1697-a585-542a-bd29-38582bcdd69a | date | Truck 2:
e0f24fd0-e62a-5173-953a-2cc14e85b9c7 | date | Truck 3:
2c66d202-d246-5dd6-be23-375202b890f2 | date | Truck 4:
139923a4-a70f-4691-8452-dab61b0cd52f | checkpoint | 2 - Docket
8e7b16de-d1a2-511e-9969-5e66b547cc15 | textbox | Truck 1:
3c0ebfeb-5522-5138-8e16-24d9d1215fec | textbox | Truck 2:
c1366a6c-4fba-5aca-9674-db8b84babf19 | textbox | Truck 3:
39a051ec-59b3-5174-a365-26564714547b | textbox | Truck 4:
f8ac5d3b-22a3-476f-bd55-b0b00cc89e03 | checkpoint | 3 - Time Batched
24edf93b-07e8-5c12-9e87-b2142a40da0d | textbox | Truck 1:
fb233f25-70b6-5f42-8f63-597a8af77661 | textbox | Truck 2:
7e68acf3-44ea-59eb-bd16-a2cdefa89049 | textbox | Truck 3:
75ec0204-bc9d-528b-92db-0c8587a8342e | textbox | Truck 4:
a7c004e5-1cff-4ad1-8e52-17c46fdb6018 | checkpoint | 4 - Truck Arrival Time
01b2c47c-efe5-57a4-b8de-8e457ec61da0 | textbox | Truck 1:
81c510f7-f3a3-5cf8-abfc-567ad03a1d80 | textbox | Truck 2:
2b3872d4-fb65-53a0-a258-1c1831d03954 | textbox | Truck 3:
ac672d39-81f0-5630-aa04-ec06a8550f7a | textbox | Truck 4:
4fec4153-18b0-4883-bc76-d97c34f792ee | checkpoint | 5 - Load Size (m3)
d2801f90-4e68-5c3b-9fb3-66bbb2027626 | textbox | Truck 1: | m3
ca5b784b-f754-5e76-8812-eefec5f1f7a2 | textbox | Truck 2: | m3
72cb8918-c2a2-5a0e-99aa-9049bdc3a3e4 | textbox | Truck 3: | m3
d78bb698-a624-58a5-8a82-e1582eacb1dc | textbox | Truck 4: | m3
5069ea03-56d6-421e-ba63-1603d677fc65 | checkpoint | 6 - Mix
75d8e774-f048-423a-8ee3-ccf8e2598762 | checkpoint | 7 - Slump (mm)
cfb9898a-3c60-52d0-9e05-51e37728dd5b | textbox | Truck 1: | mm
ac5dda45-8e3f-57a2-8420-0eb73eb46ccd | textbox | Truck 2: | mm
c5097294-6a1e-5812-b6eb-50ed096fc449 | textbox | Truck 3: | mm
2e19e053-8504-5f7f-9f78-5518659e188d | textbox | Truck 4: | mm
b28f2f4f-1dce-40d1-8648-ee9dc2a1905e | checkpoint | 8 - Slump Time
0db0c806-4848-57d0-8951-7ac73eed3510 | textbox | Truck 1:
defe5cb0-9f06-54ae-9b6d-3b97e16b8f5b | textbox | Truck 2:
ae48284e-fc08-5513-b8f3-15a15316e5ae | textbox | Truck 3:
89bfe907-40ad-5acb-8f3e-88594ce78b5d | textbox | Truck 4:
613ebef9-8456-44ca-9c68-9767347acde6 | checkpoint | 9 - Concrete Arrival Temperature (˚C)
b07e09ee-7956-5e50-a97a-c2ffb55dae48 | textbox | Truck 1: | ˚C
2d5184ed-8f0a-5631-bba5-f742d00d1f11 | textbox | Truck 2: | ˚C
635ecf2b-b5cd-560b-9d56-608d35f05f48 | textbox | Truck 3: | ˚C
40be0e45-cc1d-5aff-9a9a-e6488f29f6fe | textbox | Truck 4: | ˚C
f6ff6cd2-98d9-40db-8fb4-09d8f4cb1fb8 | checkpoint | 10 - Ambient Temperature at time of slump (˚C)
fdbe0e1e-2d38-5ce9-8f61-0effe4d00c66 | textbox | Truck 1: | ˚C
2fcfd49f-32dd-5701-99f0-6276f6ad6db9 | textbox | Truck 2: | ˚C
9a1a6c9d-4827-5921-9fff-1c1720033e8f | textbox | Truck 3: | ˚C
4e1b312c-96af-5120-af5b-92cecd8fe5e3 | textbox | Truck 4: | ˚C
8406177c-b7c7-4ebd-a516-b4b57ae60122 | checkpoint | 11 - Time Start delivery
0b886a63-041b-5377-b56c-ab48a9348a3f | textbox | Truck 1:
36a06fa9-b970-56c8-96aa-ce4ea28318fb | textbox | Truck 2:
ed6a45a6-fa1b-5e7e-8826-ab2066c61910 | textbox | Truck 3:
45374461-b709-57df-b035-6799068a1c18 | textbox | Truck 4:
9876cc44-fb09-425c-ae66-36f22de01fe7 | checkpoint | 12 - Time Finish Delivery
05b27d38-a520-5f2e-86ca-c4a4bec4d1c3 | textbox | Truck 1:
83d04fe6-1d70-557c-afab-32864c27340f | textbox | Truck 2:
b242d9e5-c0b9-55a4-80c2-011495f7e3ab | textbox | Truck 3:
7577ad95-e722-5533-8ac1-c4adcce08ddb | textbox | Truck 4:
f0662679-4900-43e1-83a2-155fe2279204 | checklist | 70.03 - Supply of Concrete | itp | 70.03 - Supply of Concrete
70675de8-818a-4083-92fa-172967611001 | section | Details
48e659ac-1b3d-4491-a939-1a5e792d7d56 | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
ed705f2f-4f73-5a77-804e-40123f94551d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
031236f5-866e-5a42-896d-e0ccbaaabcc4 | note | Check Item - Milestone
75690ab0-1040-5b14-aa44-574e44b62417 | note | Reference - MRTS70 Cl 9.2
a5f7aa6c-34d1-449c-a5ed-8979bdf6cb53 | checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
f2c0fc23-3b1a-544d-a0bf-8d04106cf35f | note | Check Item - Milestone
da2b26a2-4821-554f-85a8-db809fd1ad2a | note | Reference - MRTS70 Cl 17.6.1
3bcd4940-ef99-4356-a326-0d617015cda2 | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
90171238-8e49-5858-a038-75a24c838d36 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fb55fc0f-23cb-5a1f-990b-7debd883095f | note | Check Item - Milestone
45fc9ac1-9cb7-5af2-a951-c71b34dff958 | note | Reference - MRTS70 Cl 13.1
411d1f4f-f903-4309-9961-4c0cec58d071 | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
a31b7f46-3d86-58cc-8f11-b1a6131b9ec3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
99480a01-c7a7-53b9-b111-d8dbae3ece86 | note | Check Item - Milestone
dc27dd85-8e4e-5a65-9e19-d9120397cd45 | note | Reference - MRTS70 Cl 15.11.1
c66a1bd3-f425-484a-b05a-febef9624727 | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
7311b379-90e6-5b3b-bc77-530527c54e71 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
663bda85-a143-57b6-846f-724cc0fdf8b0 | note | Check Item - Milestone
8769df01-a5d3-5d04-ba22-065857d8b6f9 | note | Reference - MRTS70 Cl15.5
e92be31d-6163-4d6c-9298-60e2a93b4eda | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
69710532-36ec-542c-a34c-bbce772b0d13 | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
a4aca57b-3d5c-5cb1-9d14-6fc087a50759 | note | Check Item - Witness Point
9bb5284e-9a9b-52cf-8a8a-b1d924251180 | note | Reference - MRTS70 Cl 15.1.1
e86197c1-e77a-46f9-a35c-f245fd53564e | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
b21d3a33-dca0-550f-a626-b79e8bf846aa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4476bff5-b213-559b-b67f-64cc919ccc71 | note | Check Item - Hold Point 1
7bd7790f-90c9-513c-be15-e19afae308c9 | note | Reference - MRTS70 Cl 15.1
49f23c19-bfb8-477e-8a79-7245db70fb78 | signoff | HOLD POINT
406e4173-4c63-428b-96d7-8d599d81bd89 | checkpoint | Final Verification
c8b03f32-8954-59de-bf8b-8e787d301be5 | note | Project Manager Verify that the Above has been Constructed according to Specification
849db25d-b3dc-5617-8c40-7cdcfc47575e | textbox | Print Name:
d67804cb-697a-5a43-ac21-e23327908847 | date | Date:
8642c593-2a5e-5a3f-b3c0-cb6ef8e1138d | note | Client Verify that the Above has been Constructed according to Specification
ffdf10f7-1246-50c2-ae44-cf273f7ffbba | textbox | Print Name:
d86a1230-09b9-5093-bd1e-4fc09cc6e2ed | date | Date:
2b9efc01-8f78-4787-b19c-886be91f7e57 | signoff | Sign ITP
4acd32c0-1764-47f3-80cc-66ea39c84a2e | checklist | 71.01 - Reinforcing Steel | itp | 71.01 - Reinforcing Steel
dc6a933f-f51c-422d-bc35-fa7ac422d9e0 | section | Details
96c564e1-45f5-4d60-9c97-2dbd007510d0 | checkpoint | Submission of proposed supplier of reinforcement with three days notice prior to supply.
85708e8e-843f-5fee-8977-783a64bc99af | note | Acceptance Criteria and Frequency (Project Specific) - Visual
15d64664-db66-5ebf-87d1-ed0404237e22 | note | Check Item - Milestone
cd5ecd18-e812-52bb-9ce1-5583e3678169 | note | Reference - MRTS71 Cl 6.1
a9e9cee2-ddf2-4c8e-9a52-18181f9317c7 | checkpoint | Acceptance of supplier from Administrator
e0d93a77-b0f5-5586-aade-927a7b4e70af | note | Check Item - Hold Point 1
42b4d506-e609-5b2c-a404-3aeb46172235 | note | Reference - MRTS71 Cl 6.1
0134bbb9-aacf-4fd6-86cf-4bbd1637fe89 | signoff | HOLD POINT
6916725e-a1ce-400b-8333-2b9aa448b709 | checkpoint | Inspection of steel reinforcement before placement of concrete.
e88f7ff3-2aa1-5648-9771-d8739138ba02 | note | Check Item - Hold Point 3
99032442-404a-5576-8e49-a5e6b3e02274 | note | Reference - MRTS71 Cl 10
690ab2fc-3991-4a7f-bc3a-e0a5c2dbf88b | signoff | HOLD POINT
409d3b82-c3ae-45bd-b567-b7b1ee43d8bc | checkpoint | The min. clear distance between parallel bars other than lapped bars shall be the greater of:
ad11d3e4-d028-579b-b425-457c47e3cbf8 | note | ○ 1.5 x the diameter of the larger bar
e90b21ab-13e7-5ac1-9211-f8795a082abd | note | ○ 1.5 x max nominal size of aggregate
a402fd96-779e-51df-b150-a5d5fc59b700 | note | ○ or 40mm
2794fb5f-5366-522b-86ed-055b6841ba50 | note | Check Item - Witness Point
848290e1-a178-5663-9b0c-8349287e3c0d | note | Reference - MRTS71 Cl 10
d1947f72-89d4-4662-a7f3-68480f506070 | signoff | WITNESS POINT
5c1bbffa-c1fc-41c4-b644-a128de85c2a5 | checkpoint | Permitted mechanical reinforcing bar splices listed in Clause 1 of MRTS71.1.
574581f2-6585-5916-b0c9-836f9150ca42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
a5100bc9-7fae-5c13-a749-27cbe7312a21 | note | Check Item - Hold Point 4
bd9e3cd7-e49a-55c4-acb7-798be0be18b9 | note | Reference - MRTS71 Cl 11.3
73863450-cf4a-4f97-85ec-effde17c7434 | signoff | HOLD POINT
063ae2d8-1a72-4b04-8004-fd82ef82a3c8 | checkpoint | Installation of mechanical reinforcing bar splices as per provisions in Clause 11.3.2
8443dead-e56e-5dfe-ab66-8cb35a3d18bd | note | Acceptance Criteria and Frequency (Project Specific) - Visual
401ea4c6-898e-5b3e-b0fa-9a02b9beb56c | note | Check Item - Witness Point
dfddc24d-2557-5693-ab2b-9b0555af64d0 | note | Reference - MRTS71 Cl 11.3.2
65524138-b88e-4ef0-b71d-32dadc9c39fe | signoff | WITNESS POINT
66c02123-fdf0-47b6-97e1-8d41c73b1657 | checkpoint | No substitution of different size, grade or ductility class of steel reinforcement shall be placed unless approved by the Administrator.
2d229baa-81db-5ad9-9b35-5967fc556b6d | note | Acceptance Criteria and Frequency (Project Specific) - Visual
96ed9ff3-ae7a-5032-b574-030e6dd836ab | note | Check Item - Hold Point 5
576331ad-0adb-5f10-94be-919382fa3e9b | note | Reference - MRTS71 Cl 13
b053c483-dd0c-4fca-9554-7d040333e203 | signoff | HOLD POINT
5d56220b-ef5a-4323-9b48-830f4081be9d | checkpoint | Application for substitution of reinforcement forwarded to Administrator 3 weeks prior to supply
709d0d4f-1e15-5230-9301-318b4b59e5cb | note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
5a25bd5d-c22f-5488-bd36-04713c11beae | note | Check Item - Milestone
8838cc72-8fcf-5355-95ed-3bbd8c8ba7f6 | note | Reference - MRTS71 Cl 13
e9d0766b-5767-4fb6-a3d0-1592fbb05bd6 | checkpoint | Final Verification
78b088f7-f6a8-5f24-8430-ca77342e101e | note | Project Manager Verify that the Above has been Constructed according to Specification
a62e5288-2f7e-5903-b33d-ddcf64978e6a | textbox | Print Name:
40185eae-c969-5e91-ac81-09be33e1cfe9 | date | Date:
9ab6423b-05c8-5b0e-a063-2589910cd0e0 | note | Client Verify that the Above has been Constructed according to Specification
1b6a97e8-d2cb-571c-9500-b56d896b2144 | textbox | Print Name:
dc382203-6e96-5173-82a8-23cebdfb3ce1 | date | Date:
740dff7d-675d-4021-b60d-fc2d0fd78b56 | signoff | Sign ITP