## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 111 - Wastewater PE | itp |  |  |  |  | ITP - 111 - Wastewater PE Rev C
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.1 - Extent of Line Setout
label | Acceptance / Conformance Criteria - Ensure line and level of wastewater has been marked out and agreed with Engineer in accordance with the drawings.
label | ○ Identify any clashes before construction.
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 1.2 - Environmental Protection
label | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans
label | ○ Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | Standard / Specification - Project ESCP Plans
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction
label | ○ Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 1.3 - Stakeholder
label | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works
label | ○ Agree plans for maintaining access to properties during construction with landowners
label | Standard / Specification - Project Stakeholder Management Plan
label | Verifying Document - ITP Sign Off
label | Frequency - Prior to Construction with continue updates throughout the works
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 1.4 - Permits
label | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
label | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections.
label | ○ All known services must be clearly marked on site and briefed to the workforce.
label | Standard / Specification - Section 2.2.10 Project Specification
label | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | Frequency - Prior to Construction
label | ○ Reviewed and Reissued weekly or when site conditions change
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.1 - Pipes/Fittings/precast Units
label | Acceptance / Conformance Criteria - Confirm pipes diameter and class as shown on the drawings.
label | ○ Pipe dimensions given on the drawings are nominal outside diameters.
label | ○ Manufacturer verification/records of compliance of PE pipe (i.e. pipe resin data)
label | Standard / Specification - Project Specification
label | Verifying Document - Visual Check, Manufacturer's Verification
label | Frequency - Each Delivery to Site
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 2.2 - Undercut Backfill/Bedding/Side/Haunch/Overlay/Backfill Material Compliance
label | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand
label | Standard / Specification - AS/NZS2566 G1 (or otherwise)
label | Verifying Document - IANZ Lab Test Reports
label | Frequency - 1 Test per 1000m3
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.1.1 - Foundation Compliance
label | Acceptance / Conformance Criteria - Scala 3 blows/100mm
label | ○ Vane Shear Strength 70kPa
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Scala test result
label | Frequency - Every 20m along trench
label | ○ 1 test every 5m² at driveways and footpaths
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.1.2 - Undercut Backfill Compliance
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 95%(Average98%) of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD
label | ○ AS/NZs 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Based on Undercut Section
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.1.3 - Bedding Compaction Testing
label | Acceptance / Conformance Criteria - NDM Back Scatter
label | ○ Minimum Compaction 95%(Average98%) of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
label | ○ AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Every 20m along trench
label | ○ 1 test every 5m² at driveways and footpaths
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.1.5 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 92% of MDD
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD
label | ○ AS/NZS 3725:2007
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Every 20m along trench
label | ○ 1 test every 5m² at driveways and footpaths
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.1.6 - Collection of Waipa ITPs
label | Acceptance / Conformance Criteria - ITP 04 Butt Welding
label | Standard / Specification - PWRBSS Quality Management Plan
label | Verifying Document - Document Review
label | Frequency - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Backfill Inspection
label | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation. No damages caused to the pipeline.
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Photographs
label | Frequency - Continous
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 3.1.8 - Survey
label | Acceptance / Conformance Criteria - All wastewater lines shall be laid per design layout. The deviation from approved design alignment permitted either in plan or elevation shall be:
label | ○ Vertical tolerance ± 50mm on straight and 100mm in curves
label | Standard / Specification - Vertical tolerance +/- 50mm
label | ○ Horizontal +/- 100mm
label | Verifying Document - Survey Data
label | Frequency - Continous
label | Verification Activity: Activity - C
label | Verification Activity: By - SV
checkpoint | 3.1.9 - Backfill Compaction Testing
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC
label | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
label | ○ AS/NZS 2566.2/2002
label | Verifying Document - IANZ Lab Test Report
label | Frequency - Every 20m along trench
label | ○ 1 test every 5m² at driveways and footpaths
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.1.10 - End Caps
label | Acceptance / Conformance Criteria - Red-painted sealed end per RITS D5.4.
label | Standard / Specification - RITS D5.4
label | Verifying Document - Photographs
label | Frequency - Each End Cap
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 3.2.1 - Manhole Foundation Compliance
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - IANZ Scala test result
label | Frequency - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.2.2 - Undercut Backfill Compliance
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Minimum Compaction 95% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
label | ○ AS/NZS 3725:2012
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 1 Test/Manhole if Undercut required
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.2.3 - Bedding Compaction Testing
label | Acceptance / Conformance Criteria - NDM Back Scatter
label | ○ Minimum Compaction 95% of MDD
label | Standard / Specification - HS2 backfil Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD
label | ○ AS/NZS 3725:2012
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.2.4 - Backfill Inspection
label | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
label | Standard / Specification - Project Specification 4.3
label | Verifying Document - Photographs
label | Frequency - Continous
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 3.2.5 - Backfill Testing
label | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm
label | ○ Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
label | ○ Minimum Compaction 95% (Average 98%) of MDD
label | Standard / Specification - MDD Average of 98% with minimum of 95%, PS 4.5
label | Verifying Document - IANZ Lab Test Report
label | Frequency - 4 Density tests per layer at Quarter Points Around Structure
label | Verification Activity: Activity - H
label | Verification Activity: By - QE
checkpoint | 3.2.6 - Concrete Load Distribution Ring
label | Acceptance / Conformance Criteria - Installed per manufacturers requirements.
label | Standard / Specification - BBO Request
label | Verifying Document - Photographs
label | Frequency - Each romold manhole
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 3.3.1 - Pressure Testing Methodology
label | Acceptance / Conformance Criteria - Subcontractor to submit to method statement prior to testing.
label | Standard / Specification - PS Appendix L 3.10
label | Verifying Document - Engineer's confirmation of witness test
label | Frequency - Notification required 2 working days prior to testing
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
checkpoint | 3.3.2 - Pressure Testing Qualification
label | Acceptance / Conformance Criteria - Confirmation of qualification of personnel supervising the test.
label | Standard / Specification - PS Appendix L 3.10.3
label | Verifying Document - Qualification
label | Frequency - Once per supervisor
label | Verification Activity: Activity - S
label | Verification Activity: By - PE
checkpoint | 3.3.3 - PE Pipeline Pressure Test
label | Acceptance / Conformance Criteria - Unless otherwise specified and approved with line-specific methodolfy (i.e. Pressuremain 04 and 03).
label | ○ Testing to be undertaken on completion of invasive/major works.
label | ○ M5 per NZS 2566.2, test pressure 1.25x lowest rated component.
label | Standard / Specification - PS Appendix L 3.10.10 (RFI-0268)
label | Verifying Document - Pressure Test Report incl. data log in .csv or .xls format
label | Frequency - Per methodology
label | Verification Activity: Activity - H
label | Verification Activity: By - ENG
checkpoint | 3.3.4 - Romold Manhole
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.1 - Unforeseen Items
label | Acceptance / Conformance Criteria - Upload items which may not be captured appropriately above (i.e. EF Coupler Installation)
label | Standard / Specification - BBO Request
label | Verifying Document - Misc.
label | Frequency - Once per lot
label | Verification Activity: Activity - C
label | Verification Activity: By - PE
checkpoint | 4.2 - Survey As-Builts
label | Acceptance / Conformance Criteria - Quality Check on New Works
label | Standard / Specification - Project Specification
label | Verifying Document - Survey Data
label | ○ As Built Drawings
label | ○ Photographs
label | ○ Red Pen As-Builts including Undercuts
label | Frequency - Post Works Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SV