## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP2-006-004 ITP Northern Access Road & Car Park Footpath/Shared path | itp |  |  |  |  | DN1210-SP2-006-004 ITP Northern Access Road & Car Park Footpath/Shared path Rev 1
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 100kN
label | Standard / Specification - NZS4407:2015 Test 3.10 TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥60%
label | Standard / Specification - NZS4402 Test 6.1.1 TCC-IDC-IT-4.3.1-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Standard / Specification - NZS4407 Test 3.11 TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407 Test 3.8.1 TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407 Clause 4.3 TCC-IDC-IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.4 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - ≤ 8
label | Standard / Specification - NZS4407:2015 Test 3.4 TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.5 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent Washing method
label | Acceptance / Conformance Criteria - ≥25
label | Standard / Specification - NZS4407 Test 3.6 TCC-IDC-IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.6 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 80%
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.4 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% passing
label | 0.300mm ¦¦ 3-10% passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 28-48%
label | 19.0 – 4.75 ¦¦ 14-34%
label | 9.5 – 2.36 ¦¦ 7-27%
label | 4.75 – 1.18 ¦¦ 6-22%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 5-19%
label | 0.6 – 0.15 ¦¦ 2-14%
label | Standard / Specification - PS 20.9 TCC-IDC IT-4..8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 40
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 30
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4.6 - Clay Index NZS 4407 Test 3.5
label | Detail - Clay Index NZS 4407 Test 3.5
label | Acceptance / Conformance Criteria - ≤ 5
label | Standard / Specification - PS 20.9 TCC-IDC IT-4.8 table 4.7
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 - CONSTRUCTION - PREP FOOTPATH
checkpoint | 4.1.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ CBR: <3
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405 PS:27.4.2
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100M2
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Cut Subgrade Testing - Granular Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 2 blows per 100mm penetration or <3 CBR
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405 PS:27.4.2
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Proof Roll Subgrade
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface 225mm Below From Finish Height
label | Acceptance / Conformance Criteria - +0mm/ -30mm
label | Standard / Specification - TNZ B/02: 2005 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.2.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.2.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.2.4 - Hold point
label | Detail - Subbase signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface 125mm Below From Finish Height
label | Acceptance / Conformance Criteria - +15mm/ -5
label | Standard / Specification - TNZ B/02: 2005 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.4 - Hold point
label | Detail - Basecourse signoff
label | Acceptance / Conformance Criteria - Conqa signoff
label | Verifying Document - Conqa signoff
label | Testing Quantity Required (based from schedule qtys) - Each area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.1 - Surveyor check
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +100mm/ -20mm of design
label | Standard / Specification - TNZ B/02: 2005 5.1 PS:27.4.5 viii
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.2 - Surveyor check
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - NZS 3109:1997 PS:27.4.5 viii
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.5.1 - Reinforcing Mesh Check
label | Detail - Ensure the right mesh
label | Acceptance / Conformance Criteria - 665 Reinforcing mesh
label | Standard / Specification - Project Specifications 27.4.2
label | Verifying Document - Dockets
label | Testing Quantity Required (based from schedule qtys) - Measurements
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 4.5.2 - Reinforcing Mesh Check
label | Detail - Ensure that overlap and clearince from edges
label | Acceptance / Conformance Criteria - 50mm top cover, 300mm overlap
label | Standard / Specification - NZS 3109:1997 5.3.2
label | Verifying Document - photos
label | Testing Quantity Required (based from schedule qtys) - Measurements
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.6.1 - Concrete
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405 PS:27.4.5
label | Verifying Document - Concrete Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.6.2 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.6.3 - Final Finish
label | Detail - Finish to be either:
label | – Brushed finish
label | Acceptance / Conformance Criteria - U5 Finish
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405 PS:27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As-Builts
label | Detail - Final inspection of all concrete work.
label | ○ Red Pen Mark up
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red Pen Markup
label | Testing Quantity Required (based from schedule qtys) - All completed works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP2-011-001 ITP Northern Access Road & Car Park SW | itp |  |  |  |  | DN1210-SP2-011-001 ITP Northern Access Road & Car Park SW Rev 1
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.1.1 - Extent of Line Setout
label | Detail - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings.
label | ○ Identify any clashes before construction.
label | ○ Lot - Markup
label | Acceptance / Conformance Criteria - As Per Drawings & Markup drawing
label | Standard / Specification - Design Drawings
label | Verifying Document - ITP Sign Off
label | Testing Quantity Required (based from schedule qtys) - Prior to Construction & Every Revision of IFC Drawings/Data.
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.1.1 - Material grading: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - No Particles >200mm
label | ○ Maximum fines 10% passing 75micron sieve
label | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2 - Weathering index: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - Appendix XVIII, PS 16.5.5 Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3 - Crushing Resistance: Materials (Gap65/AP65)
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.1 - Material grading: Materials (GAP20/AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 19.0mm ¦¦ 100% passing
label | 13.2mm ¦¦ 80-95% passing
label | 9.5mm ¦¦ 64-76% passing
label | 4.75mm ¦¦ 37-58% passing
label | 2.36mm ¦¦ 30-40% passing
label | 1.18mm ¦¦ 18-28% passing
label | 0.600mm ¦¦ 12-22% passing
label | 0.300mm ¦¦ 6-14% passing
label | 0.150mm ¦¦ 2-7% passing
label | 0.075mm ¦¦ 0-3% passing
label | Standard / Specification - PS-21.5.7 PS-21.7.2 Table 21.2
label | Verifying Document - Lab Test Report NZS 4407.2015 Test3.8.1
label | Testing Quantity Required (based from schedule qtys) - 0-400m3 ¦¦ 2 Test
label | 400-1500m3 ¦¦ 3 Test
label | 1500-4000m3 ¦¦ 4 Test
label | >4000 ¦¦ 1 Test Additional 1000m3
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.2 - Weathering index: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - AA to CA
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.3
label | Verifying Document - Lab Test Report NZS 4407.3.11
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.3 - Crushing Resistance: Materials (AP20)
label | Detail - Bedding/Side Zone/ Overlay Zone/Embedment Zone
label | Acceptance / Conformance Criteria - >100kN
label | Standard / Specification - PS-21.5.7, PS-21.7.2 Table 21.4
label | Verifying Document - Lab Test Report NZS 4407:1991 Test.3.10
label | Testing Quantity Required (based from schedule qtys) - Prior to construction - 2 test per source
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.1 - Pipe and fittings. (Concrete pipe).
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Standard / Specification - PS- 21.5.1, PS- 21.5.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.2 - Stormwater- Structure (SWMH, SDMH, GMH, CP, DCP, CPMH, MP, HW)
label | Detail - Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition.
label | Acceptance / Conformance Criteria - Confirm diameter and size as shown on the drawings, and that the Structure are correct and in good condition.
label | Standard / Specification - PS- 21.5.4 NZS 3109:1997
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.3 - Granular Material (GAP20/AP20, GAP65/AP65)
label | Detail - Confirm Specification and material in good condition.
label | Acceptance / Conformance Criteria - Confirm Specification and material in good condition.
label | Standard / Specification - PS-21.7.2
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 2.3.4 - Geotextile/Geogrid
label | Detail - TNZ F/7geotextile is to be used in Trench Backfill of Drainage pipe in Wet conditions.
label | Acceptance / Conformance Criteria - Minimum Strength Class C & Filter Class 1
label | Standard / Specification - PS-21.5.9
label | Verifying Document - Delivery Dockets
label | Testing Quantity Required (based from schedule qtys) - Each Delivery to site
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.1.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Appendix V Table 21:11
label | Verifying Document - Shear vane or Scala test result
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - W
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 21.5
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Undercut Backfill Compliance AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per Undercut
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.4 - Bedding Compaction Testing AP65
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12, PS- 21.6.11
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.5 - Survey
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm.
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - 1 Test/Manhole
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.1.6 - Sidefill Compaction Testing
label | Detail - From the bedding layer to the overlay layer of pipe.
label | Acceptance / Conformance Criteria - AP20/GAP20
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | OR
label | ○ GAP20-Clegg12% CIV
label | Standard / Specification - PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.7 - Backfill Compaction Testing
label | Detail - From Overlay layer to the subgrade layer
label | Acceptance / Conformance Criteria - AP65
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | ○ AP65-Clegg28%CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - 4 Density test per layer at Quarter Points around the Structure.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.1.8 - Inspection
label | Detail - Inspection of Structure
label | Acceptance / Conformance Criteria - Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure.
label | Standard / Specification - PS- 21.6.11
label | Verifying Document - Manhole/Catchpit Record
label | Testing Quantity Required (based from schedule qtys) - 1 Checksheet per manhole/catchpit
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Foundation Compliance
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm
label | ○ Cohesive Material: Vane Shear Strength 70kPa
label | Standard / Specification - Appendix V Table 21:11
label | Verifying Document - Shear vane or Scala test result
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - W
label | Verification Activity: By - ENG
checkpoint | 3.3.2 - Undercut approval
label | Detail - On Subgrade
label | Acceptance / Conformance Criteria - Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material.
label | ○ Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material.
label | Standard / Specification - Table 21.5
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - If Undercut required
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3.3 - Undercut Backfill Compliance (GAP65/AP65/LRAP65)
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Average 95% MDD, min >92%
label | OR
label | ○ Clegg 25% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.4 - Bedding Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 100mm if D<1500 or 150mm if D>1500
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.5 - Haunch Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 0.3xD (outer dia of the pipe)
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.6 - Side Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - HS2- 0.3xD (outer dia of the pipe)
label | ○ Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.6, PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.7 - Survey
label | Detail - Surveyor to Setout
label | Acceptance / Conformance Criteria - Vertical design Setout:
label | ○ Pipes ≤ 1% grade: +/- 10mm variance
label | ○ Pipes > 1% grade: +/- 20mm variance
label | Horizontal design Setout:
label | ○ +/-30mm variance
label | Standard / Specification - PS- 21.7.6 Table 21.15
label | Verifying Document - Survey Data
label | Testing Quantity Required (based from schedule qtys) - Every 100m or at Chambers (whichever distance is the lesser)
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.3.8 - Overlay Zone Compaction Testing
label | Detail - On Granular Material
label | Acceptance / Conformance Criteria - Minimum Compaction- Trafficable & Non-Trafficable 95% MDD on metal.
label | OR
label | ○ Clegg 12% CIV
label | Standard / Specification - PS- Table 21.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.9 - Backfill Compaction Testing
label | Detail - On Granular or Cohesive Material
label | Acceptance / Conformance Criteria - AP65
label | ○ Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal.
label | OR
label | ○ Clegg 28% CIV
label | Standard / Specification - PS- 16.5.12
label | Verifying Document - Lab Test Report
label | Testing Quantity Required (based from schedule qtys) - One test per 10m evenly spaced intervals along pipelines with a minimum of 1 test between each pit/manhole.
label | ○ 0-5m: 1 Tests
label | ○ 0m-10m: 2 Tests
label | ○ 0m-20m: 3 Tests
label | ○ 0m-50m: 4 Test
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.3.10 - Inspection
label | Detail - Inspection of Drainage line
label | Acceptance / Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Standard / Specification - PS- 21.7.6
label | Verifying Document - Drainage line record
label | Testing Quantity Required (based from schedule qtys) - Continious 1 per Line
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.5.1 - CCTV Inspection
label | Detail - CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.)
label | Acceptance / Conformance Criteria - Every stormwater pipeline 225mm diameter or greater.
label | Standard / Specification - PS- 21.7.6, PS- 21.7.8
label | Verifying Document - CCTV Report
label | Testing Quantity Required (based from schedule qtys) - 1 per line
label | Verification Activity: Activity - S
label | Verification Activity: By - SE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.1.1 - As-Builts / Redpen markups
label | Detail - Quality Check on New Works based on the tolerances in RITS
label | Acceptance / Conformance Criteria - Meets spec and thickness requirements as per drawings
label | Standard / Specification - Project Specifications
label | Verifying Document - Red pen markup only
label | Testing Quantity Required (based from schedule qtys) - Post works completion of a lot
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature