## Scour Protection
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: Scour Protection |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | QA / Site Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. Construction
1.01 | Mark out earthwork extents | Check the start and end location of the rock riprap lining and width will be as per the design drawing | M | Prior to earthworks | Visual | QA/Site Engineers Approval | Setout Data/Checksheet | Contractor |  | A | I | R | dd/mm/yy
1.02 | Earthworks | Excavate to a depth specified in the design drawing | M | As per design drawings | Visual / Photo | QA/Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.03 | Bedding | GAP40 bedding placed in 100mm layers where required due to exsisitng water table depth | M | For site where scour protection is required | Visual / Photo | QA/Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.04 | Geotextile | Place geotextile pinned with minimum of 280mm using weed mat pins at 3m spacing along both sides | M | For site where scour protection is required | Visual / Photo | QA/Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
1.05 | Place rocks | Place rocks 150mm to 300mm in diameter and slope will be as per the design drawing | H | For site where scour protection is required | Visual / Photo | QA/Site Engineers Approval | Delivery Docket/Photo | Contractor | Make sure the riprap is shaped to the specified slope of the channel so water flows freely | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.