## Shoulder Widening
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M03 |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | QA / Site Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. AGGREGATE ACCEPTANCE TESTING
1.01 | AP65 | Crushing Resistance | H | 1 Test per material per source | NZS4407:3.10 | > 100KN | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 | AP65 | Particle size distribution | H | 1 Test per material per source | NZS4407:3.8.1 | As per NZTA M03 Specfication | IANZ report | Contractor |  | A | I | R | dd/mm/yy
2.0. Construction
2.01 | Mark out earthwork extents | Set out and approve extent of earthworks | M | Prior to earthworks | Visual | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.02 | Earthworks/Removal of organic material | Excavate/Remove organic material on granular shoulders and topsoil in grassed verge area | M | As per design drawings | Visual / Photo | Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | Determine subbase depth | Scala penetrometer | H | Test Every 20m | Scala penetrometer | As per digout table "Table 1: Digout Instruction table" | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.04 | Placement of geogrid | Geogrid used a contractors discretion as per "Table 1: Digout Instruction table" | M | Once during construction | Visual | Site Engineers Approval | Photos | Contractor |  | A | I | R | dd/mm/yy
2.05 | AP65 Placement | Compacted layers of AP65 shall be placed in layers to underside of AP40 layer | H | Test Every 20m | Clegg test | Clegg Result >30 | Checksheet | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.