## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Scour Protection | itp |  |  |  |  | ITP - Scour Protection Rev 0
section | 1.0. Construction
checkpoint | 1.01 - Mark out earthwork extents
label | Detail of Activity / Test - Check the start and end location of the rock riprap lining and width will be as per the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
label | Inspection / Test method - Visual
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Setout Data/Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.02 - Earthworks
label | Detail of Activity / Test - Excavate to a depth specified in the design drawing
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.03 - Bedding
label | Detail of Activity / Test - GAP40 bedding placed in 100mm layers where required due to exsisitng water table depth
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.04 - Geotextile
label | Detail of Activity / Test - Place geotextile pinned with minimum of 280mm using weed mat pins at 3m spacing along both sides
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photo
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 1.05 - Place rocks
label | Detail of Activity / Test - Place rocks 150mm to 300mm in diameter and slope will be as per the design drawing
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For site where scour protection is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - QA/Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Delivery Docket/Photo
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Make sure the riprap is shaped to the specified slope of the channel so water flows freely
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Shoulder Widening | itp |  |  |  |  | ITP - Shoulder Widening Rev 1
section | 1.0. AGGREGATE ACCEPTANCE TESTING
checkpoint | 1.01 - AP65
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - > 100KN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - AP65
label | Detail of Activity / Test - Particle size distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - As per NZTA M03 Specfication
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. Construction
checkpoint | 2.01 - Mark out earthwork extents
label | Detail of Activity / Test - Set out and approve extent of earthworks
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Prior to earthworks
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Earthworks/Removal of organic material
label | Detail of Activity / Test - Excavate/Remove organic material on granular shoulders and topsoil in grassed verge area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - As per design drawings
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Determine subbase depth
label | Detail of Activity / Test - Scala penetrometer
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 20m
label | Inspection / Test method - Scala penetrometer
label | Acceptance Criteria - As per digout table "Table 1: Digout Instruction table"
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Placement of geogrid
label | Detail of Activity / Test - Geogrid used a contractors discretion as per "Table 1: Digout Instruction table"
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Once during construction
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Photos
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.05 - AP65 Placement
label | Detail of Activity / Test - Compacted layers of AP65 shall be placed in layers to underside of AP40 layer
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - Test Every 20m
label | Inspection / Test method - Clegg test
label | Acceptance Criteria - Clegg Result >30
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | QA / Site Engineer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature