## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement Renewal | itp |  |  |  |  | ITP - SH39 Cannon Rd - Pavement Renewal
section | Part 1 - Pre-commencement Activities (Construction Manager, who has the authority to stop the works at a Hold Point)
checkpoint | 1 - Design & Renewal Quality Plan Approval
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that the Design & Renewal Quality Plan, including the Method of Work Plan and this ITP, have been approved by NZTA
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Review and approve (NZTA Hold Point)
label | CONFORMANCE CRITERIA - MS 5.3.2. Pavement Rehabilitation Design & Appendices 6.1 Guide to Auditing Opavement and Surfacing Renewals
label | QUALITY EVIDENCE (signed, test results or records) - RQP approval by NZTA
holdpoint | HOLD POINT
checkpoint | 2 - Site walkover with Client
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Pre-commencement walkover with the Client, Pavement Design, Construction Manager, Asset Manager and Site Supervisor to ensure the design addresses all known issues, including the clearance envelopes for overhead structures, vegetation and safety system heights e.g. barriers; and confirmation of construction methodology and TTM
label | FREQUENCY - One month prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual inspection
label | CONFORMANCE CRITERIA - Confirmation of design and construction methodology
label | QUALITY EVIDENCE (signed, test results or records) - ITP Signed and Walkover Notes sighted
holdpoint | HOLD POINT
checkpoint | 3 - Survey & Set-out
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Set-out design centreline and check extents of formation (pegs to be installed every 20m)
label | ○ Confirm that the proposed area is within 5% of that agreed to with NZTA. If not, Asset Engineer to agree new area with NZTA, prior to proceeding.
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Design
label | CONFORMANCE CRITERIA - Tolerance for set-out to be sub-base -25mm/+5mm and basecourse -5mm/+15mm (TNZ B/2)
label | ○ Within ±5% of area previously agreed with NZTA
label | QUALITY EVIDENCE (signed, test results or records) - ITP signed & survey set-out records sighted
label | ○ Evidence of revised area agreed to by NZTA if >5% change
holdpoint | HOLD POINT
checkpoint | 4 - Confirm Design Details
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Surfacing removal: 60mm
label | ○ Overlay depth (basecourse): 175mm AP40
label | ○ Stabi depth (basecourse): 175mm @1.0% Cem + 1.5% Lime
label | ○ OWC (laboratory test results) 5.0 %
label | ○ MDD (laboratory test results) 2.38 t/m3
label | Both ends
label | ○ Tie-in details: Remove 355mm across length
label | ○ Overlay depth (Sub-base): 180mm GAP65
label | ○ Overlay depth (basecourse): 175mm AP40
label | ○ Stabi depth (basecourse): 175mm @1.0% Cem + 1.5% Lime
label | Poor performing area
label | ○ Undercut depth (Sub-base): 180mm GAP65
label | Widneings
label | ○ Excavate 355mm
label | ○ Proof roll + scalas @ every 20m (5 blows/100)
label | ○ Sub-base: 180mm GAP65
label | ○ Basecourse: 175mm AP40
label | ○ Undercut to 515mm if less than 5 blows per 100mm. 360mm GAP65 (180+180mm GAP65)
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Design (NZTA Hold Point)
label | CONFORMANCE CRITERIA - NZTA B/2, B/5, B/6 or B/7, whichever is applicable
label | QUALITY EVIDENCE (signed, test results or records) - Design info from approved Design Report entered into this sheet & ITP signed
holdpoint | HOLD POINT
checkpoint | 5 - Materials
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Materials & Stabilising Agents: Supply & Stockpiling
label | ○ Basecourse, subbase, modified materials & cement meets specification & stockpiled correctly
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Testing, review & submit to NZTA (NZTA Hold Point)
label | CONFORMANCE CRITERIA - NZTA M/3, M/4 & TNZ B/5 Modified Mix (ITS, TSR, OWC & MDD)
label | QUALITY EVIDENCE (signed, test results or records) - Laboratory Test results attached
label | ○ Delivery dockets
holdpoint | HOLD POINT
checkpoint | 6 - Pre-commencement Activities
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Written confirmation that all the activities listed in the Method of Work Plan - A. Pre-commencement Activities are completed
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Review
label | CONFORMANCE CRITERIA - Written evidence
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed
holdpoint | HOLD POINT
section | Part 2 - Pavement Construction (Pavement / Site Engineer, who has the authority to stop the works at a Hold Point)
checkpoint | 7 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Surface Preparation, including:
label | ○ ripping existing surfacing (Granular Overlay)
label | ○ pre-hoeing or pre-milling e.g. high spots or where depth of surfacing matrix is required to be reduced (Stabilisations)
label | FREQUENCY - Prior to commencement
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual
label | CONFORMANCE CRITERIA - Appendix F: RQP for Pavement Renewals - 4. Inspection and Test Plans C. Overlays
label | ○ TNZ B/5 7.2.1
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed
holdpoint | HOLD POINT
checkpoint | 7 - Granular Overlay
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Layer Thickness
label | ○ Ensure uncompacted thickness does not exceed the specified limits, including tapers
label | Evidence of Material Supply
label | Supply the following:
label | ○ DJR (daily), with delivery dockets
label | FREQUENCY - Ongoing
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual & measure
label | CONFORMANCE CRITERIA - TNZ B/2 7.3 Layer Thickness & 7.4 Tapers
label | Average uncompacted thickness of any layer
label | ○ ≥ 2.5 times the maximum particle size
label | ○ ≤ 200 mm
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed & Delivery Dockets supplied
checkpoint | 8 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Establish Rolling Pattern
label | ○ Plateau Density Testing (using heavy vibe roller with NDM using Direct Transmission with the material at OWC)
label | ○ Use the greater of Plateau Density or Laboratory MDD
label | ○ To be repeated if any changes occur to establish new target MDD
label | ○ No need to plateu for smaller areas i.e. < 500m2. Visual assessment of layer compaction and surfacing to be used.
label | Record plant for each Plateau Testing stage:
textbox | Pre-vib:
textbox | High Vib:
textbox | Low Vib:
textbox | Secondary Static:
label | FREQUENCY - Minimum 1/day or 1/1,000 m2 per treatment depth (whichever is the higher frequency), and per noticeable change in material or per shift, unless Principal agrees to a lower frequency, but ≥ 1/day or 1/2,000m2 per treatment depth (whichever is the higher frequency)
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Measure and record
label | CONFORMANCE CRITERIA - TNZ B/2 7.5 Testing for Layer Compaction (G)
label | ○ TNZ B/5 7.7
label | ○ Plateu Testing Sheet
label | ○ Laboratory Results for MDD & OWC (CS & FBS)
label | QUALITY EVIDENCE (signed, test results or records) - Record:
textbox | No. of high amplitude vibe primary passes
textbox | No. of low amplitude vibe primary passes
textbox | No. of secondary static passes
holdpoint | HOLD POINT
checkpoint | 9 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - MDD and Moisture Content Testing
label | ○ Bulk sample taken on site below NDM using Direct Transmission during plateau testing for measuing the MDD and the Moisture Content. MC to be corrected in NDM for testing on Day 2 or as soon as available.
label | FREQUENCY - Minimum 1 per 5,000m2 per treatment depth, and per noticeable change in material or per shift
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Testing (NZTA Hold Point)
label | CONFORMANCE CRITERIA - TNZ B/5 7.7 Bulk sample taken at NDM testing locations to measure MDD and OWC
label | QUALITY EVIDENCE (signed, test results or records) - Plateau Testing Sheet, Laboratory Test Results for MDD & OWC
checkpoint | 10 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - I
label | DETAIL - Compaction Checks
label | ○ Ensure compaction targets are being met if not, stop and review equipment, compaction methodology and water content. NDM Testing to be Back Scatter for <= 100mm & Direct Submission for > 100mm. In addition, the 'squeeze' test can be used to monitor water content.
label | FREQUENCY - 5 tests per 1,000m2 randomly to confirm compliance (final test at pre-seal stage by lab)
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual & Testing (NZTA Inspection Point)
label | CONFORMANCE CRITERIA - TNZ B/2 7.6 Acceptance criteria for stabilised layer compaction (CS & FBS)
label | ○ Avg. >= 98% MDD and Min. >= 95% MDD (based on plateau)
label | ○ Adjust if Subbase to align with TNZ B/6
label | QUALITY EVIDENCE (signed, test results or records) - NDM Record Sheet
checkpoint | 11 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Control of Levels and Evenness of Surface
label | ○ Check evenness: Measure with straight edge, Roadroid App (using mobile phone in vehicle), a roughometer (e.g. ARRB Roughometer from Fulton Hogan Canterbury Technical Services), Walking Profiler or a drive through to check smooth ride
label | ○ Check levels: Survey measure, including total station, or stringline checks to ensure compliance with design levels & shape, including the clearance to structures
label | FREQUENCY - Every 20m (Tolerance = -10mm / +10mm over 3m; Basecourse with asphalt -15mm +5mm; Basecourse with chipseal -5mm +15mm; Lip of concrete channel ±5mm)
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Measure
label | CONFORMANCE CRITERIA - TNZ B/2 5. Tolerances (G)
label | ○ TNZ B/5 7.8 Surface shape (CS & FBS)
label | ○ Specified roughness value 75 (NAASRA)
label | QUALITY EVIDENCE (signed, test results or records) - Stringline and Straight Edge Checksheet
label | ○ Total Station Grader Benching Sheet
checkpoint | 12 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Traffic Management
label | ○ Ensure full surface width is trafficked to aid compaction. Move cones every hour or as required. (G only)
label | ○ Ensure constant active Traffic Management to shift the vehicles from side to side until the surface has cured sufficient to sustain the traffic loading. This can vary from a few hours (when windy and sunny) to 24 hours if wet and calm. (CS & FBS only)
label | ○ Maintain OWC: Ensure surface is kept damp but not wet during trafficking.
label | ○ Apply running course and drag-brooming, as required to 'cut' out any fatty areas and to protect the surface
label | FREQUENCY - Immediately after initial stabilising (CS & FBS only) and primary compaction (CS, FBS & G)
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual inspection
label | CONFORMANCE CRITERIA - TNZ B/2 10. Running Course
label | ○ TNZ B/5 7.7 Compaction
label | ○ Pavement Construction blue book, section 6. Finishing the Basecourse
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed
checkpoint | 13 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Final Surface Shape, Levels and Roughness
label | ○ Check evenness: Measure with straight edge; check roughness (using, for example, Roadroid App, using mobile phone in vehicle), a roughometer (e.g. ARRB Roughometer from Fulton Hogan Cantebury Technical Services), Walking Profiler or a drive through to check smooth ride, remembering that compliance criteria is applied 12 months after construction
label | ○ Check levels: Survey measure, including total station, or stringline checks to ensure compliance with design levels & shape, including the clearance envelopes for overhead structures, vegetation and safety system heights e.g. barriers
label | FREQUENCY - Prior to sealing
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Measure
label | CONFORMANCE CRITERIA - TNZ B/2 7.7 Surface shape (G), shape (CS & FBS)
label | ○ Measure longitudinal and lateral profiles
label | ○ Roughness
label | ○ Levels
label | QUALITY EVIDENCE (signed, test results or records) - Stringline and Straight Edge Checksheet and / or Total Station Grader Benching Sheet
label | ○ Roughness measurements and / or drive through recorded
label | ○ Pre-seal Handover Sheet
holdpoint | HOLD POINT
checkpoint | 14 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Camber
label | ○ Crossfall to be checked transverse to the centreline. Crossfall taken > 2m apart to be within ±0.5% of design.
label | FREQUENCY - Prior to sealing
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Measure
label | CONFORMANCE CRITERIA - TNZ B/2 5. Tolerances (G)
label | ○ TNZ B/5 7.9 Camber (CS & FBS)
label | QUALITY EVIDENCE (signed, test results or records) - This ITP signed
holdpoint | HOLD POINT
checkpoint | 15 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Surface Finish
label | ○ Check that surface is form, well-compacted an dready for sealing i.e. a stony mosaic surface with stones and fines visible, after sweeping (possible use of Clegg Hammer to confirm surface tightness)
label | FREQUENCY - Prior to sealing
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual and measure
label | CONFORMANCE CRITERIA - TNZ B/2 7.8 Surface finish (G)
label | ○ TNZ B/5 7.10 Surface finish (CS & FBS)
label | ○ Visual inspection
label | QUALITY EVIDENCE (signed, test results or records) - Pre-seal Handover sheet + Photograph(s) of swept site
label | ○ This ITP signed
holdpoint | HOLD POINT
checkpoint | 16 - Pavement Construction
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Pre-sealing Requirements – Wet / dry density, water content (degree of saturation)
label | ○ Offset determined for specific stabilising agent content i.e. cement and / or lime
label | FREQUENCY - Prior to sealing 5 tests per 1,000m2
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Testing (NZTA Holding Point)
label | CONFORMANCE CRITERIA - TNZ B/2 7.6 Acceptance Criteria for Pavement Layer Compaction (G)
label | ○ TNZ B/2 12. Presealing Requirements (G)
label | ○ TNZ B/5 7.7.1 Acceptance criteria for stabilised layer compaction (CS & FBS)
label | ○ TNZ B/5 7.12 Presealing Requirements (CS & FBS)
label | ○ DOS to be less than 60%, if design traffic loading > 5x10^6 ESAs; otherwise 65%
label | QUALITY EVIDENCE (signed, test results or records) - Pre-seal Handover Sheet
label | ○ Laboratory Test Results
holdpoint | HOLD POINT
checkpoint | 17 - Service Covers
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Check service covers are at correct finished design level.
label | FREQUENCY - Prior to sealing
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Measure
label | CONFORMANCE CRITERIA - Survey
label | QUALITY EVIDENCE (signed, test results or records) - This ITP signed
holdpoint | HOLD POINT
checkpoint | 18 - Pre Seal Inspection
label | ACTION (Hold, Monitor, Witness) - I
label | DETAIL - Provide NZTA the opportunity to inspect
label | ○ No sealing if fog, rain, wet road or if ambient shaded air temperature is less than 10 degrees Celsius
label | ○ No sealing if rain is forecast within 12 hours
label | FREQUENCY - Minimum 24 hours prior to sealing
label | ○ Weather forecast and air temperature checked
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Review (NZTA Inspection Point)
label | CONFORMANCE CRITERIA - TNZ B/2 7.8 & B/5 7.10 Surface Finish
label | QUALITY EVIDENCE (signed, test results or records) - Pre-seal Handover Sheet
checkpoint | 19 - Seal Construction
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Monitor Sealing QA
label | ○ Sealing ITP aligns with agreed treatment selection & design
label | ○ Spray Sheets (daily)
label | ○ Chipsealing Site Report (daily)
label | FREQUENCY - Daily
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Monitor
label | CONFORMANCE CRITERIA - Sealing ITP completed & Chipseal Site Report (daily) submitted)
label | QUALITY EVIDENCE (signed, test results or records) - Sealing ITP and Daily Reports
checkpoint | 20 - Roadmarking
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirming roadmarking set out as per directions from Asset Management Team, and then mark it out
label | FREQUENCY - After sealing complete and site has been swept
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual Inspection
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed
holdpoint | HOLD POINT
checkpoint | 21 - Roadmarking
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirming roadmarking undertaken in accordance with the Pavement marking ITP
label | FREQUENCY - After roadmarking has been set out and marked up
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Check Pavement Marking ITP and associated QA complete
label | QUALITY EVIDENCE (signed, test results or records) - Pavement Marking ITP & associated QA completed
holdpoint | HOLD POINT
checkpoint | 22 - Site Tidy-up
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Tidy up site, remove all stockpiles and rubbish. Clean out grass verges, swales, kerb and channel, culverts and remove any environmental proteciton and survey pegs.
label | FREQUENCY - After sealing complete and site has been swept
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Visual inspection
label | QUALITY EVIDENCE (signed, test results or records) - This ITP signed
holdpoint | HOLD POINT
checkpoint | 23 - Quality Management Folder
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Test results, checklists, delivery dockets and other quality records to be included within Quality Management folder on contract workspace
label | FREQUENCY - At completion of surfacing and after all test results received
label | INSPECTION / TEST METHOD (submission, design, visual inspection, testing, measure, review) - Document Review
label | QUALITY EVIDENCE (signed, test results or records) - This ITP Signed
checkpoint | Approved as complete (Project / Site / Quality Engineer):
holdpoint | Add Signatures