## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Subsoil Drainage | itp |  |  |  |  | ITP - Subsoil Drainage Rev0
section | 1.0 - Preliminary
checkpoint | 1.1 - Ensure latest drawing revision is being used
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Drawing No:
checkpoint | 1.2 - Use face of kerb set out to set out subsoil drainage
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZS4202
label | ACCEPTANCE CRITERIA - WP
checkpoint | 1.3 - Excavation to be set out according to survey marks and appropriate benchmark RLs
label | ACCEPTANCE CRITERIA - CI
section | 2.0 - Excavation
checkpoint | 2.1 - Excavation to be carried out using correct offsets based on FSL
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Drawing No:
holdpoint | HOLD - Continue only if the above is signed off.
section | 3.0 - Subsoil Drainage installation
checkpoint | 3.1 - Install Bidim and Subsoil drain and associated connections to Manholes/pipes/CP
label | SPEC REFERENCE / SPECIAL CONDITIONS - TNZ F/2
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Drawing No:
checkpoint | 3.2 - Backfill with drainage metal
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Photos and mark-up drawings
section | 3.0 - Backfill
checkpoint | 3.1 - Backfill excavation using GAP65. Backfill to be placed and compacted in 150mm layers.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Civil Specifications
label | ACCEPTANCE CRITERIA - CI
section | 4.0 - Handover to client
checkpoint | 4.1 - Handover to client
label | ACCEPTANCE CRITERIA - HP
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint-no-status | Comments / Required Actions:
checkpoint | Signed by:
label | Contractors Representative
label | Clients Representative
signoff | Signatures:
checklist | ITP - Stormwater Drainage | itp |  |  |  |  | ITP - Stormwater Drainage Rev1
section | SW1.0 - Set Out
checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Drawing Register;
checkpoint | 1.2 - Confirm existing and proposed drainage locations
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Survey Layout: Drawing
holdpoint | HOLD - Continue only if the above is signed off.
section | SW2.0 - Stormwater Excavation
checkpoint | 2.1 - Complete council Kick-off meeting
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council inspection report
holdpoint | HOLD POINT
checkpoint | 2.2 - All stormwater pipes and manholes shall be placed in accordance with surveyor's layout and locations given in design drawings.
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZA/AS 1260
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
checkpoint | 2.3 - Stormwater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
holdpoint | HOLD POINT
checkpoint | 2.4 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Geotech signoff
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint | 2.5 - Breakout to commence once Client issue site instruction
label | ACCEPTANCE CRITERIA - WP
label | VERIFYING DOCUMENTS - Site Instruction
holdpoint | HOLD - Continue only if the above is signed off.
section | SW3.0 - Stormwater Installation
checkpoint | 3.1 - All manholes shall be installed with accordance to locations shown on civil drawings. Any variations to be approved by Client prior to installation.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Survey Layout
checkpoint | 3.2 - Stormwater mains and downpipes to be laid out in accordance with design drawings. Any Variations to be approved by Client before installation.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Survey Layout
holdpoint | HOLD POINT
checkpoint | 3.3 - Pipes shall be laid true to alignment and with inverts true to grade. All manhole connections shall be in accordance with civil engineering specifications and Auckland Council standard drawings.
label | SPEC REFERENCE / SPECIAL CONDITIONS - SWCoP DWG No. SW05
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P Long Section Sheet, M&P Manhole Check Sheets
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint | 3.5 - M&P Drainage long section and Manhole sheets to be completed.
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
checkpoint | 3.6 - Pipes shall be bedded on 100mm minimum depth of approved fine granular material.
label | SPEC REFERENCE / SPECIAL CONDITIONS - AS/NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P Long Section Sheet, M&P Manhole Check Sheets
checkpoint | 3.7 - Lower surface to 1/4 of the pipe diameter shall be on the compacted material. From this point up to 300mm above the crown of the pipe, selected filling material (with 20mm maximum partial size) shall be rammed & tamped in layers of no more than 150mm depth.
label | SPEC REFERENCE / SPECIAL CONDITIONS - AS/NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
checkpoint | 3.8 - All pipework to be inspected by clients engineer and Council inspector and signed off before trench can be backfilled
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council & Engineer Approval Report
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint | 3.9 - If instructed by Client - Any pipe with less than 600mm cover must be concrete capped
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Site instruction
checkpoint | 3.10 - Trench to be backfilled with approved granular material and compacted sufficiently
label | SPEC REFERENCE / SPECIAL CONDITIONS - AS/NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
section | WW4.0 - Handover to client with PS3
checkpoint | 4.1 - Complete Council final drainage inspection
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council inspection report
holdpoint | HOLD POINT
checkpoint | 4.2 - Completed pipe sections to be CCTV'd
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - CCTV Footage
checkpoint | 4.3 - As build all pipe invert levels in manholes and CP and lid levels
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - As build report
holdpoint | HOLD POINT
checkpoint | 4.4 - Handover to client with PS3
label | SPEC REFERENCE / SPECIAL CONDITIONS - PS3 Drainage
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Hander documents
holdpoint | HOLD POINT
checkpoint-no-status | Comments / Required Actions:
checkpoint | Signed by:
label | Contractors Representative
label | Clients Representative
signoff | Signatures:
checklist | ITP - Wastewater Drainage | itp |  |  |  |  | ITP - Wastewater Drainage Rev0
section | WW1.0 - Set Out
checkpoint | 1.1 - Ensure that the latest revision of the relevant drawing is being used.
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZS 3107
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Drawing Register
checkpoint | 1.2 - Confirm existing and proposed drainage locations
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - Survey Layout; Drawing:
section | WW2.0 - Wastewater
checkpoint | 2.1 - Complete council Kick-off meeting
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council inspection report
holdpoint | HOLD POINT
checkpoint | 2.2 - All wastewater pipes and manholes shall be placed in accordance with surveyor's layout and locations given in design drawings.
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZA/AS 1260
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
checkpoint | 2.3 - Wastewater trench should be excavated to design levels given in drawings. Tolerances given are -0mm, +50mm for line and -50mm, +0mm for level. Trench to be benched or battered when depth exceed 1.2m. Trench width to be dependant on pipe diameter and trench depth. Use trench shield if battered cannot be achieve.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
holdpoint | HOLD POINT
checkpoint | 2.4 - IF rock is encountered levels and photos are to be taken. Geotech must inspect rock prior to any break out. Levels and photos must be taken post-breakout.
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Geotech signoff
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint | 2.5 - Breakout to commence only once Client have issued a site instruction
label | ACCEPTANCE CRITERIA - WP
label | VERIFYING DOCUMENTS - H&R Site Instruction
holdpoint | HOLD - Continue only if the above is signed off.
section | WW3.0 - Wastewater Installation
checkpoint | 3.1 - All manholes shall be installed with accordance to locations shown on civil drawings. Any variations to be approved by Client prior to installation.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Survey Layout
checkpoint | 3.2 - Wastewater mains and downpipes to be laid out in accordance with design drawings. Any Variations to be approved by Client before installation.
label | SPEC REFERENCE / SPECIAL CONDITIONS - Drawing C-C401 and C-C402
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Survey Layout
holdpoint | HOLD POINT
checkpoint | 3.3 - Pipes shall be laid true to alignment and with inverts true to grade. All manhole connections shall be in accordance with civil engineering specifications and Auckland Council standard drawings.
label | SPEC REFERENCE / SPECIAL CONDITIONS - WWCoP DWG No.
label | ACCEPTANCE CRITERIA - CI
textbox | VERIFYING DOCUMENTS - M&P Long Section Sheet, M&P Manhole Check Sheets: Drawing: _______________
checkpoint | 3.4 - M&P Drainage long section and Manhole sheets to be completed.
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P drainage long section sheet, M&P manhole sheet
checkpoint | 3.5 - Pipes shall be bedded on 100mm minimum depth of approved fine granular material.
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - M&P Long Section Sheet, M&P Manhole Check Sheets
checkpoint | 3.6 - Lower surface to 1/4 of the pipe diameter shall be on the compacted material. From this point up to 300mm above the crown of the pipe, selected filling material (with 20mm maximum partial size) shall be rammed & tamped in layers of no more than 150mm depth.
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
checkpoint | 3.7 - All pipework to be inspected by clients engineer and Council inspector and signed off before trench can be backfilled
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council & Engineer inspection and/or Approval report
holdpoint | HOLD - Continue only if the above is signed off.
checkpoint | 3.8 - Any pipe with less than 600mm cover must be noted to the client and wait approval to proceed
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Site Instruction
checkpoint | 3.9 - Trench to be backfilled with approved granular material and compacted sufficiently
label | SPEC REFERENCE / SPECIAL CONDITIONS - NZS 2566 Part 2: 2002
label | ACCEPTANCE CRITERIA - CI
checkpoint | 3.10 - Backfill materials must be compacted correctly and tested in 150mm - 300mm lifts
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - Council & Engineer inspection and/or Approval report
section | WW4.0 - Handover to client with PS3
checkpoint | 4.1 - Complete Council final drainage inspection
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Council inspection report
holdpoint | HOLD POINT
checkpoint | 4.2 - Completed pipe sections to be CCTV'd
label | ACCEPTANCE CRITERIA - CI
label | VERIFYING DOCUMENTS - CCTV Footage
checkpoint | 4.3 - As build all pipe invert levels in manholes and CP and lid levels
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - As build report
holdpoint | HOLD POINT
checkpoint | 4.4 - Handover to client with CS3
label | SPEC REFERENCE / SPECIAL CONDITIONS - CS3 Drainage
label | ACCEPTANCE CRITERIA - HP
label | VERIFYING DOCUMENTS - Hander documents
holdpoint | HOLD POINT
checkpoint-no-status | Comments / Required Actions:
checkpoint | Signed by:
label | Contractors Representative
label | Clients Representative
signoff | Signatures: