## Culvert Construction
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Project Name |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA F3:2010 |  |  | Approved Quality Manager.: |  | Nominated by Group Quality Manager | dd/mm/yy
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Engineer: |  | PE name | dd/mm/yy
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) | Inspection / Test method |  |  |  |  | Designer / PTG | Eng. Rep / NZTA | Contractor | Date
1.0. AGGREGATE AND PIPE / ACCEPTANCE TESTING
1.01 | Bedding Material | Well graded GAP 7 will be used and tested for Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities | H | 1 Test per material per source | Test Report | Compliant With AS/NZS 3725:2007 | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 | BackFill Material | Material Type | H | 1 Test per material per source | Test Report | Compliant with TNZ F/1:1997 | IANZ report | Contractor |  | A | I | R
1.03 | Culvert Pipe | Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes | H | 1 Test per material per source | Data Sheets | Compliance with TNZ F3 | Supplier QA Report | Contractor |  | A | I | R | dd/mm/yy
2.0. CONSTRUCTION
2.01 | Setout | Culverts to be placed in line with existing culvert | M | Prior to Commencement | Survey | Engineers Approval | Checksheet | Engineers Representative |  | A | I | R | dd/mm/yy
2.02 | Excavation | Excavtion of Trench should be within tolerances. | M | For each site where Culvert is Required is required | Visual / Photo | Trench width should wide enough to allow for adequate compaction. Trench should be excavated to the depth of the bottom of the existing culvert. | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.03 | Pipe bedding and haunch zone inspection | Bedding Material | H | 1 per trench length | Visual / Photo | The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.04 | Pipe bedding and haunch zone Density Testing | Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. | I | 1 per 15m trench length Minimum of 2 tests between pits/manholes | NDM / Clegg Report | The pipe bedding and haunching zone shall be compacted to a MDD of 90% | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.05 | Pipe laying | Pipe To be placed to Line | M | Test Each Pipe as it placed | Pipe Laser and other approved equipment | Placed to correct line and level as per IFC Drawings | Surevy Records | Contractor |  | A | I | R | dd/mm/yy
|  | Pipe to be place to grade | [10 empty] | dd/mm/yy
2.06 | Side zones Density Testing | Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. | I | 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes | NDM / Clegg Report | The Side zones shall be compacted to a MDD of 90% | NDM/Clegg Report | Contractor |  | A | I | R | dd/mm/yy
2.07 | Compaction above Pipe | Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe. | I | During Works | Site Records | Visual/Measurement | Checksheet | Contractor |  |  |  |  | dd/mm/yy
2.08 | Pipe overlay zone inspection | The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone | H | 1 per trench length (Between Chambers) | Engineers Record | Visual Inspection | Engineers Record | Contractor |  | A | I | R | dd/mm/yy
2.09 | Pipe Overlay Zone Density Testing | Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90% | I | 1 per 15m trench length Minimum of 2 tests between pits/manholes | NDM / Clegg | NDM/Clegg | NDM/Clegg Report | Contractor |  |  |  |  | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.