## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Culvert Construction | itp |  |  |  |  | ITP - Culvert Construction Rev 0
section | 1.0. AGGREGATE AND PIPE / ACCEPTANCE TESTING
checkpoint | 1.01 - Bedding Material
label | Detail of Activity / Test - Well graded GAP 7 will be used and tested for Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Test Report
label | Acceptance Criteria - Compliant With AS/NZS 3725:2007
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - BackFill Material
label | Detail of Activity / Test - Material Type
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Test Report
label | Acceptance Criteria - Compliant with TNZ F/1:1997
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Culvert Pipe
label | Detail of Activity / Test - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 Test per material per source
label | Inspection / Test method - Data Sheets
label | Acceptance Criteria - Compliance with TNZ F3
label | Record documents (QCP - Quality Control Portal) - Supplier QA Report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. CONSTRUCTION
checkpoint | 2.01 - Setout
label | Detail of Activity / Test - Culverts to be placed in line with existing culvert
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Prior to Commencement
label | Inspection / Test method - Survey
label | Acceptance Criteria - Engineers Approval
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Engineers Representative
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.02 - Excavation
label | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site where Culvert is Required is required
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - Trench width should wide enough to allow for adequate compaction. Trench should be excavated to the depth of the bottom of the existing culvert.
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.03 - Pipe bedding and haunch zone inspection
label | Detail of Activity / Test - Bedding Material
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length
label | Inspection / Test method - Visual / Photo
label | Acceptance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Pipe bedding and haunch zone Density Testing
label | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
label | Action (Hold, Monitor, Witness) - I
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
label | Inspection / Test method - NDM / Clegg Report
label | Acceptance Criteria - The pipe bedding and haunching zone shall be compacted to a MDD of 90%
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.05 - Pipe laying
label | Detail of Activity / Test - Pipe To be placed to Line
label | ○ Pipe to be place to grade
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Test Each Pipe as it placed
label | Inspection / Test method - Pipe Laser and other approved equipment
label | Acceptance Criteria - Placed to correct line and level as per IFC Drawings
label | Record documents (QCP - Quality Control Portal) - Surevy Records
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.06 - Side zones Density Testing
label | Detail of Activity / Test - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes.
label | Action (Hold, Monitor, Witness) - I
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
label | Inspection / Test method - NDM / Clegg Report
label | Acceptance Criteria - The Side zones shall be compacted to a MDD of 90%
label | Record documents (QCP - Quality Control Portal) - NDM/Clegg Report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.07 - Compaction above Pipe
label | Detail of Activity / Test - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
label | Action (Hold, Monitor, Witness) - I
label | Minimum Test Frequency (Lot = 1 day’s production) - During Works
label | Inspection / Test method - Site Records
label | Acceptance Criteria - Visual/Measurement
label | Record documents (QCP - Quality Control Portal) - Checksheet
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.08 - Pipe overlay zone inspection
label | Detail of Activity / Test - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per trench length (Between Chambers)
label | Inspection / Test method - Engineers Record
label | Acceptance Criteria - Visual Inspection
label | Record documents (QCP - Quality Control Portal) - Engineers Record
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Pipe Overlay Zone Density Testing
label | Detail of Activity / Test - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90%
label | Action (Hold, Monitor, Witness) - I
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 15m trench length Minimum of 2 tests between pits/manholes
label | Inspection / Test method - NDM / Clegg
label | Acceptance Criteria - NDM/Clegg
label | Record documents (QCP - Quality Control Portal) - NDM/Clegg Report
label | Responsibility - Contractor
label | Designer / PTG - A
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature