## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Kitchen Tiling | [5 empty] | B04 - Kitchen Tiling Checklist
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Acoustic matting installed
checkpoint | Floor Tiling installed
checkpoint | Correct Grouting Installed as per specifications
checkpoint | Silicone
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tilling Sign Off
checklist | Balcony Tiling | [5 empty] | B04 - Balcony Tiling Checklist
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Paving and Pedestals installed as per specifications
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tiling Sign Off
checklist | Bathroom Tiling | [5 empty] | B04 - Bathroom Tiling Checklist
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Previous substrate acceptable - Wall
checkpoint | Under Tile Heating cables installed
checkpoint | Floor preparation
checkpoint | Waterproofing to floors & walls
checkpoint | Floor Tiling installed
checkpoint | Wall Tiling installed
checkpoint | Skirt Tiling installed
checkpoint | Correct Grouting Installed as per specifications
checkpoint | Silicone
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tilling Sign Off
checklist | Tiling Common Lobby Areas | [5 empty] | B04 - Tiling Common Lobby Areas
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Screeding completed
checkpoint | Floor Tiling completed
checkpoint | Tile skirting
checkpoint | Correct Grouting Installed as per specifications
checkpoint | Silicone
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tilling Sign Off
checklist | WC Tiling | [5 empty] | B04 - WC Tiling Checklist
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Previous substrate acceptable - Wall
checkpoint | Floor preparation
checkpoint | Waterproofing to floors & walls
checkpoint | Floor Tiling
checkpoint | Tile skirting
checkpoint | Splashback Tiling Installed
checkpoint | Correct Grouting Installed as per specifications
checkpoint | Silicone
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tilling Sign Off
checklist | Sep Laundry Tiling | [5 empty] | B04 - Sep Laundry Tiling Checklist
section | Details
checkpoint | Area clear, tidy and accessible
checkpoint | Previous substrate acceptable - Floor
checkpoint | Previous substrate acceptable - Wall
checkpoint | Floor preparation
checkpoint | Waterproofing to floors & walls
checkpoint | Floor Tiling
checkpoint | Tile skirting
checkpoint | Splashback Tiling Installed
checkpoint | Correct Grouting Installed as per specifications
checkpoint | Silicone
checkpoint | Works completed 100% & area left clean/tidy
holdpoint | Sharp tilling Sign Off