## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 010 (ITP010) - Concrete Structures | [5 empty] | A181 - West Dapto - ITC 010 (ITP010) - Concrete Structures
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
text | INSPECTION:
checkpoint | 3 - Ground Preparation
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of base/subgrade before covering 1 day before laying underlay or placing concrete
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 4 - Formwork Design Certification
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Formwork design certification 3 days before erecting formwork – for in situ box culverts and retaining walls only
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Completed Formwork Certification
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Completed formwork certification 1 day before placing concrete (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Inspection of Formwork
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of completed formwork
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 7 - Reinforcement
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of completed reinforcement
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 8 - Machine Mixing Proposal
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Machine mixing: Submit proposals for mixing, placing, finishing, and curing. Include the following where relevant
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - 95% Strength Before Loading
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit results to show that concrete has achieved 95% of its design strength 1 day before superimposed load
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Concrete
label | ACCEPTANCE CRITERIA:
label | • Provide concrete delivery dockets, as well as concrete test results, if required
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Concrete dockets and test results
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature