## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 011 (ITP011) - Signposting | [5 empty] | A181 - West Dapto - ITC 011 (ITP011) - Signposting
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
text | INSPECTION:
checkpoint | 3 - Details of Manufacturer and Materials
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit details of sign manufacturer, materials and attachment system 2 weeks before fabrication (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Material Conformance
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: One week before ordering, submit evidence that sign materials and parts conform to this worksection (HP)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Material Compatibility
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: One week before ordering, submit details of materials and evidence that materials for background and legend are compatible
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Sign Supports Conformance
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: One week before ordering, submit evidence that sign supports conform to this worksection
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Steel Reinforcement Conformance
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: One week before ordering, submit evidence that steel reinforcement conform to this worksection
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Pre-delivery inspection
label | REQUIREMENTS / REFERENCE: 1192 1.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Fabricated purpose-designed sign structures
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Protection of Services
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Locate and protect services from damage 1 week before placing footings and erecting signs
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Inspection of Clearing
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of clearing 1 day after clearing
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - Inspect Sign Support Set-out
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Notice of inspection of sign support structure set-out 1 week before sign erection
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 12 - Inspect Footing Excavation
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of completed excavation for footings 1 day before placing footings
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 13 - Inspect Footing Reinforcement
label | REQUIREMENTS / REFERENCE: 0310, 0319
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of footings for steel reinforcement
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 14 - Adjustment of Existing Signs
label | REQUIREMENTS / REFERENCE: 1192 3.5
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notice of inspection of adjusted, relocated or replaced signs
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature