## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 012 (ITP012) - Spray Seal | [5 empty] | A181 - West Dapto - ITC 012 (ITP012) - Spray Seal
checkpoint | 1 - Mix Design
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit to the Principal documentation on material type, source, proportions, grading, application rates, test certificates and trial mix results as evidence of conformance for each constituent before commencing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Execution Details
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit to the Principal sprayed seal design details 2 weeks prior to commencing, with evidence that the design conforms to Austroads AGPT04K Clause 4
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Plant & Execution
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit to the Principal evidence of plant and equipment registration and insurance 2 weeks prior to commencing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Surface Preparation
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.6 & Cl 4.2
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit to the principal drawings and documents to final completed works
label | • Contractor supplied test certificates for dried back moisture % prior to spraying of primer, primer-binder or binder
label | • Perform embedment tests to Austroads AG:PT/T251 within 48 hours before spray application
label | • Pavement to be swept with a rotary road or suction broom prior to priming and extend sweeping 30mm beyond edge of spray area. Remove any foreign or loose material
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Pavement Defects
label | REQUIREMENTS / REFERENCE: 1143 Cl 4.2
label | ACCEPTANCE CRITERIA:
label | • Do not commence spraying until any defects in the pavement surface are rectified
text | INSPECTION:
checkpoint | 6 - Trial Section
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.6
label | ACCEPTANCE CRITERIA:
label | • Notify the Principal of inspection of a completed surfacing trial section
text | INSPECTION:
checkpoint | 7 - Spraying
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • Submit record of temperature and weather conditions during the course of the work. Record during regular intervals with appropriate measuring procedures. Record for both sun and shaded areas
label | • Submit to the Principal, spraying certificate, binder spraying temperature and work record for each spray run
label | • Notify the principal of the inspection of the spraying rate
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Spray records
checkpoint | 8 - Test Results
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.5 & Cl 3.7
label | ACCEPTANCE CRITERIA:
label | • Test for all characteristics in conformance with maximum lot size and minimum frequencies
label | • Pavement surface prep is to be tested to the ball penetration Austroads test
label | • Submit test results within the maximum lot sizes and minimum test frequencies
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Test results
checkpoint | 9 - Primer / Binder Application
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Notify the Principal 2 days prior to spreading aggregate for inspection of the completed sprayed surface
label | • Application rate is to conform to Austroads AGPT04K
label | • Measure application rates and quantities applied to the mixture at 15°C
label | • Primer drying period is at least 72 hours after application
label | • Binder application to conform to Clause 4.5
label | • Forward speed of bitumen sprayer is to be based on items in Clause 4.5
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Post Application
label | REQUIREMENTS / REFERENCE: 1143 Cl 1.6 & Cl 4.10
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Notify the Principal of inspection for completed rolled surface with linemarking, services fixtures and warning signs cleaned and in place prior to opening for traffic (if applicable), otherwise complete inspection of the swept surface
label | • Surface is to conform to Austroads AGPT04K and is generally of good quality
label | • Appearance is to be uniform, clean and with straight edges
label | • Loose aggregate is to be removed after sweeping and conform to Clause 4.10
label | • Provide warning signs for newly completed surfacing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 11 - Non-Conformance
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Notify the Principal of inspection for completed remedial treatment of non-conforming sections
label | • Area not within 5% of the application rate are non-conforming
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Works As Executed (WAE)
label | ACCEPTANCE CRITERIA:
label | • Submit drawings and documents of final completed works. Contractor to provide Schedule 6.2 – Schedule of Job, Details of Works As Executed (WAE)
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • WAE Drawings
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature