## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 013 (ITP013) - Asphalt (Roadways) | [5 empty] | A181 - West Dapto - ITC 013 (ITP013) - Asphalt (Roadways)
checkpoint | 1 - Road Occupancy
label | REQUIREMENTS / REFERENCE: 1144 Cl 2.1
label | ACCEPTANCE CRITERIA:
label | • Obtain road occupancy license prior to commencing
text | INSPECTION:
checkpoint | 2 - Mix Design
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 10 days prior to mix production, submit the following:
label | • Documentation for material type, source, proportions, test certificates and evidence of conformance for each constituent (agg, filler, binders etc)
label | • Documentation and test certificates verifying the mix design meets the project requirements
label | • Particle size distribution as a single grading and nominal size
label | • Mix design to be selected from Clause 3.4 and contents to conform to Table 3.6
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Test Certificates
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit test certificates for mix production 7 days prior to ordering materials
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Trial Mix
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • Submit trial mix testing results for review and approval
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Trial mix testing results
checkpoint | 5 - Production Mix
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • Submit evidence of conformity to the approved mix design and mix properties for each production batch
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Certificates of Conformity
checkpoint | 6 - Low Temperatures
label | REQUIREMENTS / REFERENCE: 1144
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 1 day prior to spreading, submit proposed procedures for spreading at low temperatures, if required
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Joints
label | REQUIREMENTS / REFERENCE: 1144
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 7 days prior to placing, submit a plan of joint locations
label | • Provide longitudinal joints if the width requires more than one run
label | • Transverse joints only to be used when required
label | • Align joints with wearing course or traffic markings
label | • Conform to requirements for hot, warm and cold joints
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Surface Preparation
label | REQUIREMENTS / REFERENCE: 1144
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: 7 days prior to placing, notify the Principal for inspection of the following:
label | • Completed surface preparation including repair of defects
label | • Confirm base gravel is approved for surfacing to commence
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Equipment Inspection
label | REQUIREMENTS / REFERENCE: 1144 Cl 4.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: 1 day prior to equipment use, mix production or spraying, notify the Principal to inspect the following:
label | • Asphalt production and delivery equipment condition
label | • Spraying equipment condition and calibration
label | • Mobile equipment condition
label | • Do not use faulty plant or equipment
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 10 - Placement and Compaction
label | REQUIREMENTS / REFERENCE:
label | • 1144 Cl 4.4
label | • 1144 Cl 4.6
label | • 1144 Cl 3.8
label | ACCEPTANCE CRITERIA:
label | • Mixing temperatures to conform to Table in Clause 4.4
label | • Clear surface of deleterious materials before tacking and placing
label | • Protect services and fixtures adjacent to surfacing area
label | • Apply tack coat using bitumen emulsion to AS 1160, applied at the unform rate detailed in Clause 4.6
label | • Uniformly compact asphalt as soon as sufficiently cooled. Use vibrating or pneumatic tyred rollers for compaction
text | INSPECTION:
checkpoint | 11 - Testing
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • Provide test certificates verifying compliance with specified compaction requirements
label | • Frequency of testing to conform to maximum lot size and minimum number of tests
label | • Test for all characteristics
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Test Certificates and Records
checkpoint | 12 - Tolerances
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.6 & 4.7
label | ACCEPTANCE CRITERIA:
label | • Levels for each course of asphalt ±10mm
label | • Average total compacted thickness of the combined asphalt courses ≥ documented thickness
label | • Average thickness of any individual course ≥ documented thickness by more than 10%
label | • Surface shape tolerance conforms to Table 1.6
label | • Density assessment to conform to Clause 4.7
text | INSPECTION:
checkpoint | 13 - Daily Work Records
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Submit to the Principal on the day of delivery, the asphalt work record as per Annexure 5.1 of 1144, along with delivery dockets
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 14 - Spreading & Compaction
label | REQUIREMENTS / REFERENCE: 1144
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Prior to commencing the next pavement lot or linemarking, notify the Principal to inspect the completed surface 2 days after compaction
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 15 - Asphalt Works Records
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: 7 days prior to finishing processes such as linemarking and placement of RPMs, submit to the Principal for inspection the following:
label | • QA documentation of delivery, finishing and testing
label | • Survey certificate showing surface level and thickness tolerance
label | • Inspection record verifying finish, shape, alignment and width
label | • Lot diagram with bounds
label | • Updated lot register
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 16 - Lot Package Closure
label | REQUIREMENTS / REFERENCE: 1144 Cl 1.7
label | ACCEPTANCE CRITERIA:
label | • Provide lot package closure certificates confirming the following:
label | • All inspections completed
label | • All tests completed and recorded
label | • All non-conformances notified
label | • Open non-conformances recorded in defects register
label | • Changes to design details reviewed, approved and recorded
label | • Construction records and as-builts available online
label | • Lot package closed
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Lot package closure certificates
checkpoint | 17 - Non-Conforming Sections
label | REQUIREMENTS / REFERENCE: 1144
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide the Principal with 1 day’s notice to inspect completed replacement and rectification of non-conforming sections prior to linemarking or opening to traffic (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature