## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 014 (ITP014) - Utility Adjustments (Water) | [5 empty] | A181 - West Dapto - ITC 014 (ITP014) - Utility Adjustments (Water)
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
text | INSPECTION:
checkpoint | 3 - Preparations
label | REQUIREMENTS / REFERENCE: 0223, 1341, 1391 Cl 2
label | ACCEPTANCE CRITERIA:
label | • DBYD and service locating completed
label | • Water utility design approved and accepted for use
text | INSPECTION:
checkpoint | 4 - Change Approved Design
label | REQUIREMENTS / REFERENCE: 1341 Cl 1.6
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: If a change to the approved design alignment is required, submit proposal(s) to adjust alignment or position to the Client at least 3 days prior to excavating trenches
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Materials
label | REQUIREMENTS / REFERENCE: 1341 Cl 2
label | ACCEPTANCE CRITERIA:
label | • Materials comply to requirements of drawings and Project Specifications
text | INSPECTION:
checkpoint | 6 - Change Trench Excavation
label | REQUIREMENTS / REFERENCE: 1341 Cl 1.6
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: In the event of unexpected soil conditions, submit details to the Client at least 5 days prior to preparing the trench floor
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Excavation Support Details
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit details of excavation support to the Client, including permanent stability proposals, at least 5 days before installing these measures
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Inadequate Supporting Foundation
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: In the event of inadequate supporting foundation material in any area, notify the Client at least 5 days before preparing the trench floor (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 9 - Repair Inadequate Foundation
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: In the event of inadequate foundation material, submit proposed details for providing adequate foundation to the Client at least 3 days before preparing the trench floor (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Prepare Trench Floor
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice of the completed trench excavation at least 5 days before placement of bedding
text | INSPECTION:
text | WITNESS POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Compaction test results
holdpoint | WITNESS POINT
checkpoint | 11 - Install Pipe and Fittings
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit notice that the pipe laying, jointing and corrosion protection has been completed, at least 2 days prior to the backfilling of the trench
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 12 - Connect to Existing Main
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Provide notice of connecting to the existing main and charging new main at least 5 days prior to connecting to the existing main (if applicable)
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 13 - Damaged Existing Main(s)
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: In the event of corroded or badly damaged existing water mains, submit notice at least 3 days before connecting to the existing main (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 14 - Backfill Trenches
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.10
label | ACCEPTANCE CRITERIA:
label | • Do not backfill trench until approval is received for installed works
label | • Backfill in dry weather conditions. Re-use existing surface materials where possible to do so. If not feasible, restore the top surface with grass, concrete, asphalt or paving, as per the approved project drawings
label | • Complete compaction testing to Project Specs and drawings, as required
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Compaction test results
checkpoint | 15 - Acceptance Testing
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • Complete other testing as required, based on WCC 1341 and drawing requirements
label | • WITNESS POINT: Provide notice of the date for acceptance testing being carried out, at least 3 days before starting acceptance testing
text | INSPECTION:
text | WITNESS POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Test results and documentation
holdpoint | WITNESS POINT
checkpoint | 16 - WAE Drawings, Close Out
label | REQUIREMENTS / REFERENCE: 1341 Cl 3.11
label | ACCEPTANCE CRITERIA:
label | • Prepare work-as-executed details and operation and maintenance information
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature