## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | A181 - West Dapto - ITC 015 (ITP015) - Pavement: HBB, CRS, CRB | [5 empty] | A181 - West Dapto - ITC 015 (ITP015) - Pavement: HBB, CRS, CRB
section | Heavily Bound Base (HBB)
checkpoint | 1 - HBB – Nominated Mix
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit the following for the nominated mix and materials – Source of supply, and Certificate of Conformance to 1113
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - HBB – Material Conformance
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of evidence of material conformance
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - HBB – Delivery Dockets
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Delivered material loads covered to prevent moisture loss, supply delivery dockets for each truck load upon material arrival
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 4 - HBB – Material Inspection
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Inspection of material upon delivery to site
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 5 - HBB – Trial Section Notification
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit details of a Trial Section of HBB placement, two days prior to commencement
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - HBB – Trial Section Results
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Construct a 50m Trial Section to be incorporated into the finished works, submit trial results a minimum two days prior to commencing the remaining works
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - HBB – Compaction Results
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of HBB compaction results
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - HBB – Survey Reports
label | REQUIREMENTS / REFERENCE: 1141, 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of the following – Survey report of finished surface levels, Survey report of compacted thickness, Recorded data of straight edge test
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
section | Crushed Rock (CRS / CRB)
checkpoint | 9 - CR – Material Details
label | REQUIREMENTS / REFERENCE: 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submit the following for each proposed material ten days before delivery – Source of supply, Blend proportions for blended materials, Test results (NATA)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - CR – Material Inspection
label | REQUIREMENTS / REFERENCE: 1113
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Inspection of materials at delivery
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 11 - CR – Trial Section Results
label | REQUIREMENTS / REFERENCE: 1113
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Construct a 50m Trial Section to be incorporated into the finished works, submit trial results a minimum two days prior to commencing the remaining works
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature