## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 016 (ITP016) - Utility Adjustments (Streetlights) | [5 empty] | A181 - West Dapto - ITC 016 (ITP016) - Utility Adjustments (Streetlights)
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
text | INSPECTION:
checkpoint | 3 - Preparations
label | REQUIREMENTS / REFERENCE: 0223, 1341
label | ACCEPTANCE CRITERIA:
label | • DBYD and service locating completed
text | INSPECTION:
checkpoint | 4 - Design Docs (D&C Contracts)
label | REQUIREMENTS / REFERENCE: 1197 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: For Design and Construct contracts, submit design documentation to the Client for their acceptance at least 2 weeks before commencement of these works
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Approval of Design
label | REQUIREMENTS / REFERENCE: 1197 Cl 1.5
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Provide evidence of design approval from the electricity distributor to the Client at least 5 days before commencement of these works
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Products and Materials
label | REQUIREMENTS / REFERENCE: 1197 Cl 2
label | ACCEPTANCE CRITERIA:
label | • All materials must conform to the electricity distributor’s standards
label | • HOLD POINT: Provide manufacturer’s information for luminaires, fittings and accessories to the Client at least 5 days before ordering these materials
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Exc. and Compaction
label | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • For footings of base mounted columns, excavate footings neatly from solid material and compact to 90% maximum dry density
label | • For other columns, install as per relevant Australian Standards, the electricity distributor’s standards, the manufacturer’s recommendations, and the project drawings and specifications
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Compaction test results (if needed)
checkpoint | 8 - Base Mounted Column Footings
label | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Provide notice to the Client of the upcoming formwork installation and anchor bolt assembly location(s), at least 1 day before installation
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Columns Buried in Ground
label | REQUIREMENTS / REFERENCE: 1197 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: In the event a column buried directly into the ground is unfeasible due to unsuitable soil conditions, provide details of an alternative pole mounting method to the Client, at least 3 days prior to the column installation
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Installation of Assets
label | REQUIREMENTS / REFERENCE:
label | • 1197 Cl 3.3
label | • 1197 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • Stand streetlights as per manufacturer’s installation instructions and in accordance with crane / plant lift plan(s)
label | • Install cables and power supply as per local electricity distributor’s standards, AS / NZS 3013 and as per the project drawings and specifications
text | INSPECTION:
checkpoint | 11 - Inspect Power Cables
label | REQUIREMENTS / REFERENCE: 1197 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Invite the Client to witness and inspect the completed power cable installations, at least 1 day before the inspection is due to take place
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 12 - Testing
label | REQUIREMENTS / REFERENCE: 1197 Cl 3.5
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Invite the Client to witness and inspect the commissioning and verification testing of the completed streetlighting works, at least 1 day before the inspection is due to take place
text | INSPECTION:
text | WITNESS POINT NUMBER:
label | COMMENTS / ATTACHMENTS:
label | • Acceptance of works from utility asset owner
holdpoint | WITNESS POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature