## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A181 - West Dapto - ITC 017 (ITP017) - Utility Adjustments (Traffic Signals) | [5 empty] | A181 - West Dapto - ITC 017 (ITP017) - Utility Adjustments (Traffic Signals)
checkpoint | 1 - Preparation Works
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • All site personnel inducted (includes environment and cultural)
label | • Required Safe Work Method Statements completed and signed
label | • Subcontractor’s safety plan/procedure approved
text | INSPECTION:
checkpoint | 2 - Environment
label | REQUIREMENTS / REFERENCE: Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Installation of soil erosion and sedimentation controls completed in accordance with Soil and Water Specs.
label | • Air quality to be visually monitored for dust etc. as a direct result of construction activities.
text | INSPECTION:
checkpoint | 3 - Design Approval
label | REQUIREMENTS / REFERENCE: TS101 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of cable installation drawings and cable connection chart
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Preparations
label | REQUIREMENTS / REFERENCE: TS101 Cl 2.3.1
label | ACCEPTANCE CRITERIA:
label | • DBYD and service locating completed
text | INSPECTION:
checkpoint | 5 - Materials (TCS)
label | REQUIREMENTS / REFERENCE: WCC Traffic Signals TSI-SP Series
label | ACCEPTANCE CRITERIA:
label | • Nominated TCS materials comply to the relevant requirements of the WCC Traffic Signals TSI-SP Series
text | INSPECTION:
checkpoint | 6 - Materials (ITS Devices)
label | REQUIREMENTS / REFERENCE: TS201 Cl 4.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Prior to supply of ITS Equipment for maintenance or project works, submit confirmation that proposed ITS Devices have been approved as per devices previously accepted by TfNSW (TS200), or by project based approval (TS202) via the Director of Intelligent Transport Systems or their delegate)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Materials (ITS Solution/s)
label | REQUIREMENTS / REFERENCE: TS202 Cl 8.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Prior to supply of ITS Equipment for maintenance of project works, submit confirmation that the proposed ITS Solution has been approved by the Director of Intelligent Transport Systems or their delegate
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Excavation – Open Trenching Work
label | REQUIREMENTS / REFERENCE: TS101 Cl 5.1.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of details of open trenching work
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Excavation – Modified Footing Design
label | REQUIREMENTS / REFERENCE: TS101 Cl 5.9.4
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of details of modified footing design (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 10 - Conduits and Cabling
label | REQUIREMENTS / REFERENCE:
label | • TS101 Cl 5.3
label | • TS101 Cl 7
label | ACCEPTANCE CRITERIA:
label | • Install conduits and cabling as per TS101 Cl 5.3 and TS101 Cl 7, respectively
text | INSPECTION:
checkpoint | 11 - Approval to Stand
label | REQUIREMENTS / REFERENCE: TS101 Cl 6.1.1
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of evidence that all requirements have been satisfied prior to erection of signal post or mast arm
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 12 - Approval to Impact Awning
label | REQUIREMENTS / REFERENCE: TS101 Cl 6.1.4
label | ACCEPTANCE CRITERIA:
label | • WITNESS POINT: Submission of evidence that all necessary approvals have been obtained prior to making any opening or hole through an awning
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 13 - Proposal to Overcome Obstruction
label | REQUIREMENTS / REFERENCE: TS101 Cl 6.2.7
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of proposal to overcome local obstruction to mounting of lanterns or target boards
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 14 - Backfilling
label | REQUIREMENTS / REFERENCE: TS101 Cl 5.2
label | ACCEPTANCE CRITERIA:
label | • Backfilling works comply with the relevant specifications and/or, where applicable, the conditions of the Road Opening Permit
label | • Backfill the excavations as per Cl 5.3.6
label | • Minimise the time each excavation is left open, remove excess spoil before the end of each day’s work
text | INSPECTION:
checkpoint | 15 - Blackouts at Existing Sites
label | REQUIREMENTS / REFERENCE: TS101 Cl 8.3
label | ACCEPTANCE CRITERIA:
label | • HOLD POINT: Submission of required details prior to traffic signal blackout at TCS reconstruction site
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 16 - Testing
label | REQUIREMENTS / REFERENCE: TS101 Cl 8.2
label | ACCEPTANCE CRITERIA:
label | • Complete preliminary inspections and testing and rectify any defects prior to completing commissioning tests. Provide the ITP test results to the Principal before commencement of the commissioning tests
label | • Provide the Principal with at least 5 working days’ notice of the upcoming final inspection and commissioning tests of the TCS works
label | • Record and submit to the Principal, the results of the final inspection and commissioning tests
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • ITP Test Results
label | • Results of final inspection and commissioning tests
checkpoint | 17 - WAE and Final Completion
label | REQUIREMENTS / REFERENCE: TS101 Cl 10.3
label | ACCEPTANCE CRITERIA:
label | • Restore surface above trenches as per drawings and project specifications
label | • Where the final restoration is to be completed by others, inform the Principal and the responsible authority/agency who will undertake the final restoration, once the temporary restoration is complete. Maintain the restored areas until final restoration is carried out by the other party
label | • Provide Works As Executed (WAE) drawings for the completed utility works as per TS101 Cl 10.3
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • WAE Drawings
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature