## Breakdown
Aquacraft Plumbing Limited (Kevin Hickman - Riccarton Park)
Project Build QA
Stage 7 - THB14, THB15, THB16, THB17
Underslab
THB14 (40, 41, 42)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
THB15 (43, 44, 45)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
THB16 (46, 47, 48)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
THB17 (49, 50, 51)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
First Fix
THB14 (40, 41, 42)
[5 empty] | TH 40 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 41 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 42 | Pre-populate | PRE - S - First Fix - Plumbing
THB15 (43, 44, 45)
[5 empty] | TH 43 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 44 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 45 | Pre-populate | PRE - S - First Fix - Plumbing
THB16 (46, 47, 48)
[5 empty] | TH 46 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 47 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 48 | Pre-populate | PRE - S - First Fix - Plumbing
THB17 (49, 50, 51)
[5 empty] | TH 49 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 50 | Pre-populate | PRE - S - First Fix - Plumbing
[5 empty] | TH 51 | Pre-populate | PRE - S - First Fix - Plumbing
Second Fix
THB14 (40, 41, 42)
[5 empty] | TH 40 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 41 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 42 | Pre-populate | POST - S - Second Fix - Plumbing
THB15 (43, 44, 45)
[5 empty] | TH 43 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 44 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 45 | Pre-populate | POST - S - Second Fix - Plumbing
THB16 (46, 47, 48)
[5 empty] | TH 46 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 47 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 48 | Pre-populate | POST - S - Second Fix - Plumbing
|  |  |  | THB17 (49, 50, 51) | TH 49 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 50 | Pre-populate | POST - S - Second Fix - Plumbing
[5 empty] | TH 51 | Pre-populate | POST - S - Second Fix - Plumbing
Compliance Documentation
|  | Stage 7 - THB14, THB15, THB16, THB17 |  |  |  | Pre-populate | CST - S - Completion Documents

## Checklists
Type | Name | Value
checklist | F - S - Underslab plumbing
checkpoint | Correct gradient of the pipework achieved
checkpoint | Pipe wrapped/protected and acceptable
checkpoint | Flood test completed and acceptable
checkpoint | Pipe capped and acceptable
checkpoint | All underfloor plumbing works installed as per specifications
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name | Value
checklist | PRE - S - First Fix - Plumbing
checkpoint | Hot water supply lines run the shortest
checkpoint | Specified Waste pipework is Acoustic lagged and acceptable
checkpoint | Penetrations through fire cells are fire protected
checkpoint | All joist Brackets or Reinforcement installed, if required
checkpoint | Nog's and fixings are installed for water closet, shower, hot water cylinder and etc.
checkpoint | Penetrations through building paper are trade sealed
checkpoint | Hot Water Ring main is thermally lagged
checkpoint | All Pipework clipped neatly and tidy
checkpoint | All pipework secured/ siliconed
checkpoint | Floor Waste Gully Flange is recessed into flooring and installed
text | Enter water pressure value tested for. Confirm loop not effect lining
checkpoint | Checked for drips on water and waste piping
checkpoint | Soil and waste piping hydrostatic test ( Flood test )
checkpoint | Test plug & Gauge removed from pipe system
checkpoint | Fire penetration Schedule is completed
checkpoint | Flange and all through installed pipework flood tested
checkpoint | Plumbing First Fix complete and acceptable and area clean and tidy for next trade
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name | Value
checklist | POST - S - Second Fix - Plumbing
section | Preinstall QA
checkpoint | Permission to begin work obtained
checkpoint | Drawings correct issue and construction set
Checkpoint | Area is left clean and tidy and work can begin
Checkpoint | Fit-off materials match schedule or drawings
Checkpoint | Setouts/min clearances as per specification
Checkpoint | Water pipework maintained test throughout
Checkpoint | No debris in floor wastes or subs
Section | Water Supplies
Checkpoint | Toilet full flush and half flush working as required. Visual check for leaks on pan cone and close coupled connection
Checkpoint | Vanity basin mixer working to required flow rate and overflow able to keep up with flow rate from mixer
Checkpoint | Sink overflow able to keep up with flow rate from mixer
Checkpoint | Dishwasher commissioned
Checkpoint | Showers - Mixer working to required flow rate and shower hoses fitted with non-returns
Section | Hot water cylinder
Checkpoint | Trap installed on tray if required
Checkpoint | HWC relief lines have 25mm clearance
Checkpoint | Restraints installed
Checkpoint | Hot water set to Min 60°
Checkpoint | Tempering valve set to required temperature
Checkpoint | Timber blocks installed
Section | Finishing
Checkpoint | Flanges installed on all pipework penetrations
Checkpoint | All soil pipes are connected to sanitary sewer
Checkpoint | No crossovers, hot on left and cold on right on all mixers
Checkpoint | All fixtures are siliconed down and splash sealed
Checkpoint | Hose taps are complete with Vacuum Breakers
Checkpoint | Area is left clean and tidy
Checkpoint | Work is 100% competed to required specifications
holdpoint | Raise remedial/Request signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name | Value
checklist | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
bool | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS