## QA Folder Structure
QA
Halsey Building
Basement
Foundation
Slab
Vertical
L00
Slab
Vertical
L01
Slab
Vertical
L02
Slab
Vertical
L03
Slab
Vertical
L04
Slab
Vertical
L05
Slab
Vertical
L06
Slab
Vertical
L07
Slab
Vertical
L08
Slab
Vertical
L09
Slab
Vertical
Pakenham Building
Basement
Foundation
Slab
Vertical
L00
Slab
Vertical
L01
Slab
Vertical
L02
Slab
Vertical
L03
Slab
Vertical
L04
Slab
Vertical
L05
Slab
Vertical
L06
Slab
Vertical
L07
Slab
Vertical
L08
Slab
Vertical
Flowers Building
Basement
Foundation
Slab
Vertical
L00
Slab
Vertical
L01
Slab
Vertical
L02
Slab
Vertical
L03
Slab
Vertical

## Tools Inventory
Tools & Equipment
| Section | Stihl Cut-Off Petrol Saw
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Electric (7") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder
| Checkpoint |  | CR Number
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Electric (5") Angle Grinder Cordless
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Cordless Impact Driver
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Portable Stick Welder
| Checkpoint |  | CR Number
| Checkpoint |  | Welding Gloves
| Checkpoint |  | Welding Helmet
| Checkpoint |  | Photo
| Section | Electrical Leads
| Checkpoint |  | Tag Tested Date
| Checkpoint |  | Photo
| Section | Bolt Cutter
| Checkpoint |  | Photo
| Section | Dog Bars
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Cutter Bender
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Electric
| Checkpoint |  | CR Number
| Checkpoint |  | Photo
| Section | Ramset Epoxy Gun Manual
| Checkpoint |  | Photo
| Section | Pipe Wrench
| Checkpoint |  | Quantity
| Checkpoint |  | Photo
| Section | Sledge Hammer
| Checkpoint |  | Photo
| Section | Spirit Level
| Checkpoint |  | Photo
| Section | 25/30m Measure Tape
| Checkpoint |  | Photo
| Section | Face Shield
| Checkpoint |  | Photo
| Section | Fire Extinguisher 3kg
| Checkpoint |  | Photo
| Section | Bar Stands
| Checkpoint |  | Photo

## Foundations
Site 6
Reinforcing Installation
Foundations
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Waterproofing
| Section | Pile caps
| Checkpoint |  | PC types. E.g. PC1
| Checkpoint |  | Pile starter orientation is correct
| Checkpoint |  | Welded hoops
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Stirrups/links diameter/spacing
| Checkpoint |  | Footplates on pile starters
| Section | Capping & Concrete beams
| Checkpoint |  | CB types. E.g. CB1
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Stirrups/links diameter/spacing
| Checkpoint |  | Correct laps
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | IMBMS
| Checkpoint |  | Set out
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Cover NF/FF CRITICAL
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | Penetration detail
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Lift Pit
Site 6
Reinforcing Installation
Lift Pit
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Base slab top & bottom
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Section | Ground beams
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section |  | Stirrup diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Sump
| Checkpoint |  | Location
| Checkpoint |  | Trimmers
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | IMBMS
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Column Insitu
Site 6
Reinforcing Installation
Columns
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Set out
| Section | Column
| Checkpoint |  | Starters IMBMS
| Checkpoint |  | Starter height, bar diameter
| Checkpoint |  | Main bar diameter/grade, quantity, and lap
| Checkpoint |  | Stirrups diameter/grade/spacing
| Checkpoint |  | Stirrups to top of concrete
| Checkpoint |  | All bars and stirrups adequately tied
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | IMBMS
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Walls
Site 6
Reinforcing Installation
Walls
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Wall verticals
| Checkpoint |  | Starters IMBMS
| Checkpoint |  | Starter height, bar diameter
| Checkpoint |  | Main bar diameter/grade, quantity, and lap
| Checkpoint |  | Correct laps & staggered if required
| Checkpoint |  | Staggered laps
| Section | Wall horizontals
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Horizontals flush at ends
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/grade/spacing
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | 1st handover for cast-ins
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | IMBMS
| Section | Final review
| Checkpoint |  | All reinforcing tied back correctly
| Checkpoint |  | All starters postioned correctly
| Checkpoint |  | Cover blocks/chairs/spacers

## Stitches
Site 6
Reinforcing Installation
Stitches
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Detail sheet #
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Bar
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel/K-brace
| Checkpoint |  | Cast-ins
| Checkpoint |  | IMBMS
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Slab on Ground
Site 6
Reinforcing Installation
Slab Ground
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Slab grade RL checked
| Section | Slab reinforcing
| Checkpoint |  | Bb/Bt bar diameter/grade/spacing
| Checkpoint |  | Chairs with height check
| Checkpoint |  | Tb/Tt bar diameter/grade/spacing
| Checkpoint |  | Additional bars
| Checkpoint |  | Saddle bars
| Checkpoint |  | Correct laps
| Checkpoint |  | Chair height
| Checkpoint |  | Vertical starters diameter/grade/spacing & cover allowing for horizontals
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Checkpoint |  | IMBMS
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Suspended Slab
Site 6
Reinforcing Installation
Suspended Slab
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab Comflor
| Checkpoint | C80/250 | H16-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/180 | H12-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/200 | H16-200 CRS-EW
| Checkpoint |  | Trough bars 30mm bottom cover
| Checkpoint |  | Typical trimmers at slab edge and openings
| Checkpoint |  | Diaphragm/Drag bar reo
| Checkpoint |  | Saddle bars running E-W
| Checkpoint |  | Edge hairpins and nosing bar
| Checkpoint |  | T1 Connections
| Checkpoint |  | Bar laps
| Checkpoint |  | Mesh laps
| Checkpoint |  | Correct laps at step
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Crane Base Insitu
Job
Reinforcing Installation
Crane Base
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Piles - Cut off height & linished
| Checkpoint |  | Flange nuts fixed and epoxied
| Checkpoint |  | Hoops/spiral installed with correct diameter/grade/spacing
| Section | Bottom bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Section | Miscellaneous
| Checkpoint |  | Cast-ins/Crane legs
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## PC Beam Stitch
BTR
Reinforcing Installation
PC Beam Stitch
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Starters from protruding from PC Beams as per drawings/no re-bending
| Section | Longitudinal T/B & sides
| Checkpoint |  | Correct laps
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Reinforcing secure
| Checkpoint |  | All reinforcing steel adequately tied
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| checkpoint |  | Area left clean & tidy

## Slab Comflor
Totara Haumaru
Reinforcing Installation
Slab Comflor
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Section | Slab Comflor
| Checkpoint | C80/250 | H16-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/180 | H12-200 CRS-EW and SE62 Mesh
| Checkpoint | C80/200 | H16-200 CRS-EW
| Checkpoint |  | Trough bars 30mm bottom cover
| Checkpoint |  | Typical trimmers at slab edge and openings
| Checkpoint |  | Diaphragm/Drag bar reo
| Checkpoint |  | Saddle bars running E-W
| Checkpoint |  | Edge hairpins and nosing bar
| Checkpoint |  | T1 Connections
| Checkpoint |  | Bar laps
| Checkpoint |  | Mesh laps
| Checkpoint |  | Correct laps at step
| Checkpoint |  | Nibs - note location
| Section | Concrete cover
| Checkpoint |  | Cover blocks/chairs/spacers correct mm - CRITICAL
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Checkpoint |  | Area left clean & tidy

## Ground Beams
Job
Reinforcing Installation
Ground Beams
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Prestart/area acceptance
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Blinding level surveyed
| Checkpoint |  | Waterproofing
| Checkpoint |  | Setout
| Section | Cover spacer blocks
| Checkpoint |  | Correct type/size
| Checkpoint |  | Staggered
| Checkpoint |  | No punctures to waterproofing
| Checkpoint |  | Sufficient spacing to avoid sagging
| Section | Top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | Development length into pile cap
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Checkpoint |  | Cover top, bottom and sides
| Section | Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Trimmers to penetrations/openings & additional stirrups
| Checkpoint |  | All bars adequately tied
| Section | Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Returns 90 degrees
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Setout correct
| Checkpoint |  | Template if required
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Couplers flush at concrete face
| Checkpoint |  | Couplers capped or taped
| Checkpoint |  | Footplates fixed
| Checkpoint |  | Setout correct
| Section | Miscellaneous
| Checkpoint |  | Penetrations/trimmers
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Pile Caps
Job
Reinforcing Installation
Pile Caps
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Workface acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Pile cap
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Piles - Cut off height & linished
| Checkpoint |  | Flange nuts fixed and epoxied
| Checkpoint |  | Hoops/spiral installed with correct diameter/grade/spacing
| Checkpoint |  | Vertical/Horizontal Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | GB top bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | GB bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Checkpoint |  | Cover top, bottom and sides
| Section | GB Stirrups/links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Checkpoint |  | Trimmers to penetrations/openings & additional stirrups
| Checkpoint |  | All bars adequately tied
| Section | D-Wall Starters/Pile Starters
| Checkpoint |  | Correct height & alignment
| Checkpoint |  | IMBMS threads
| Checkpoint |  | IMBMS coupler/lock nut/terminators
| Section | GB Side bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Cover to perimeter
| Checkpoint |  | All bars adequately tied
| Section | Starter bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Sufficient protruding lap
| Checkpoint |  | Starters perpendicular
| Checkpoint |  | Template fixed for couplers
| Checkpoint |  | IMBMS coupler/lock nut/terminators
| Checkpoint |  | IMBMS couplers/threads protected
| Checkpoint |  | Couplers flush at concrete face
| Section | Cover spacer blocks
| Checkpoint |  | Correct type/size
| Checkpoint |  | No sagging
| Section | IMBMS
| Checkpoint |  | Min thread insertion 42mm-H40
| Checkpoint |  | Min thread insertion 35mm-H32
| Checkpoint |  | Min thread insertion 30mm-H25
| Checkpoint |  | Min thread insertion 20mm-H20
| Checkpoint |  | Type C coupler with locknut
| Section | Miscellaneous
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| Checkpoint |  | No punctures to waterproofing
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Capping Beam
Job
Reinforcing Installation
Capping Beam
| Section | Delivery/Material Check
| Checkpoint |  | Material delivered to site correct
| Section | Workface Acceptance
| Checkpoint |  | Safe
| Checkpoint |  | Blinding levels correct/waterproofing/setout
| Section | Piles
| Checkpoint |  | Orientation
| Checkpoint |  | Correct height
| Checkpoint |  | Hoops bar diameter/grade/spacing
| Checkpoint |  | Hoops welded laps
| Section | Top Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | All bars adequately tied
| Section | Bottom Bars
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | Staggered laps
| Checkpoint |  | All bars adequately tied
| Section | Side Bars
| Checkpoint |  | NF/FF Bar diameter/grade/spacing
| Checkpoint |  | Correct laps
| Checkpoint |  | 40mm IMBMS couplers fitted and aligned
| Section | Stirrups/Links
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Footpath Starters
| Checkpoint |  | Setout correct
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Correct dimensions
| Section | Miscellaneous
| Checkpoint |  | Penetrations/trimmers
| Checkpoint |  | Structural steel
| Checkpoint |  | Cast-ins
| Section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request Review
| Checkpoint |  | Area left clean & tidy

## Stair Landing
Job
Reinforcing Installation
Location
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Checkpoint |  | Material at a minimum 1 level above or below
| Section | Prestart/area acceptance
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Setout
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Checkpoint |  | Starters from panel/slab/wall pre-bent & straight
| Checkpoint |  | Panel/slab/wall coupler inserts have are clean and at correct levels
| Section | Cover blocks
| Checkpoint |  | Correct type/size
| Section | Stair landing reinforcing
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Starters screwed in & epoxied
| Checkpoint |  | Correct laps
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Cover top, bottom and sides
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| section | Review & Handover
| Checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| Holdpoint |  | Request review
| Checkpoint |  | Area left clean & tidy

## Slab Mesh
Job
Reinforcing Installation
Slab Level 1
| Section | Delivery/material check
| Checkpoint |  | Material delivered to site correct
| Section | Prestart/area acceptance
| Checkpoint |  | Workface ready and clear
| Checkpoint |  | Level correct
| Checkpoint |  | Setout
| Checkpoint |  | Safe access
| Checkpoint |  | Edge protection
| Section | Cover blocks
| Checkpoint |  | Correct type/size
| Checkpoint |  | Sufficient spacing to avoid sagging
| Section | Slab reinforcing
| Checkpoint |  | Bar diameter/grade/spacing
| Checkpoint |  | Perimeter slab starters
| Checkpoint |  | Perimeter longitudinal. Positioned correctly either side of studs
| Checkpoint |  | Saddle bars over beams and walls
| Checkpoint |  | Cantilever steel
| Checkpoint |  | Drag bars
| Checkpoint |  | Column additional steel
| Checkpoint |  | Insitu slabs HD12-125EW
| Checkpoint |  | Correct laps
| Checkpoint |  | Correct mesh type SE62
| Checkpoint |  | Correct laps SE62
| Checkpoint |  | Insitu around openings and stairs
| Checkpoint |  | Trimmers to penetrations/openings
| Checkpoint |  | Cover top, bottom and sides
| Section | Housekeeping
| Checkpoint |  | All loose items removed off workface
| section | Review & Handover
| checkpoint |  | All reinforcing installed correctly, checked & reviewed as per specification
| holdpoint |  | Request Review
| checkpoint |  | Area left clean & tidy