## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name
Milldale School
| ZONE D | Cable containment
Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | Staff lounge DG7-5 | First fix
Tier 5: Flush boxes | please add: | Flush box
Tier 5: Cabling; Tier 6: Power | please add: | Power circuits first fix
Tier 6: Lighting | please add: | Lighting circuits first fix
Tier 6: Heating | please add: | Heating circuts first fix
Second fix
Tier 5: Switchboard | please add: | Switchboard
Tier 5: Power | please add: | Power circuits second fix
Tier 5: Lighting | please add: | Lighting circuits second fix
Tier 5: Heating | please add: | Heating circuts second fix
|  | Flex learn DG&-6 | same as Staff lounge DG7-5
|  | Flex learn DG7-15 | same as Staff lounge DG7-5
|  | Toilets DG-7 | same as Staff lounge DG7-5
|  | Reprographic DG7-3 | same as Staff lounge DG7-5
|  | Office DG7-9 | same as Staff lounge DG7-5
|  | Office DG7-10 | same as Staff lounge DG7-5
|  | Breakout DG7-11 | same as Staff lounge DG7-5
|  | Food/wet DG7-12 | same as Staff lounge DG7-5
|  | Science DG7-13 | same as Staff lounge DG7-5
|  | Flex learn DG7-14 | same as Staff lounge DG7-5
|  | Reception DG7-1 | same as Staff lounge DG7-5
|  | Staff work room DG7-2 | same as Staff lounge DG7-5
ZONE A - admin
Tier 3: Cable containment; Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | Staff lounge AG2-2 | same as Staff lounge DG7-5
|  | Office works AG2-7 | same as Staff lounge DG7-5
|  | Meeting AG2-11 | same as Staff lounge DG7-5
|  | Meeting AG2-12 | same as Staff lounge DG7-5
|  | Meeting AG2-5 | same as Staff lounge DG7-5
|  | Board room AG2-13 | same as Staff lounge DG7-5
|  | Reception AG-1-2 | same as Staff lounge DG7-5
|  | Health AG2-10 | same as Staff lounge DG7-5
|  | ACC WC AG2-10a | same as Staff lounge DG7-5
|  | Office AG2-8 | same as Staff lounge DG7-5
|  | Server AG2-6 | same as Staff lounge DG7-5
|  | Lobby AG2-3 | same as Staff lounge DG7-5
|  | Toilets | same as Staff lounge DG7-5
|  | Primary circ AG2-1 | same as Staff lounge DG7-5
ZONE A - Gym
Tier 3: Cable containment; Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | WC AG3-4 | same as Staff lounge DG7-5
|  | Store AG3-5 | same as Staff lounge DG7-5
|  | FM Store AG3-5 | same as Staff lounge DG7-5
|  | Hall AG3-8 | same as Staff lounge DG7-5
|  | Stage AG3-1 | same as Staff lounge DG7-5
|  | Servery AG3-2 | same as Staff lounge DG7-5
ZONE B
Tier 3: Cable containment; Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | Outdoor LEarning BG6-4 | same as Staff lounge DG7-5
|  | bathroom BG6-11 | same as Staff lounge DG7-5
|  | WC Lobby BG6-10 | same as Staff lounge DG7-5
|  | Wet area BG6-5 | same as Staff lounge DG7-5
|  | Learningn BG6-4 | same as Staff lounge DG7-5
|  | Breakout BG6-6 | same as Staff lounge DG7-5
|  | Breakout BG6-9 | same as Staff lounge DG7-5
|  | Staff BG6-2 | same as Staff lounge DG7-5
|  | Communal BG6-1 | same as Staff lounge DG7-5
|  | Meeting rm BG6-3 | same as Staff lounge DG7-5
|  | Learning BG6-7 | same as Staff lounge DG7-5
|  | Wet area BG6-8 | same as Staff lounge DG7-5
Tier 2: ZONE C - Ground; Tier 3: Cable containment; Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | SM breakout CG4-1 | same as Staff lounge DG7-5
|  | Flex learn CG4-2 | same as Staff lounge DG7-5
|  | Lrg Breakout CG4-3 | same as Staff lounge DG7-5
|  | WC CG4-5 | same as Staff lounge DG7-5
|  | Creative CG4-6 | same as Staff lounge DG7-5
|  | Bathroom CG4-7 | same as Staff lounge DG7-5
|  | Flex learn CG4-8 | same as Staff lounge DG7-5
|  | Lrg Breakout CG4-9 | same as Staff lounge DG7-5
|  | Lrg Breakout CG4-12 | same as Staff lounge DG7-5
|  | Sm breakout CG4-10 | same as Staff lounge DG7-5
|  | Sm breakout CG4-11 | same as Staff lounge DG7-5
|  | Flex Learn CG4-13 | same as Staff lounge DG7-5
|  | WC CG4-14 | same as Staff lounge DG7-5
|  | Creative CG4-15 | same as Staff lounge DG7-5
Tier 2: ZONE C - First; Tier 3: Cable containment; Tier 5: Catenaries | please add: | Catenaries
Tier 5: Cable tray | please add: | Cable tray
Tier 5: Floor penetrations | please add: | Floor penetrations
Tier 3: Documentation | please add: | Documentation
|  | SM breakout CF5-1 | same as Staff lounge DG7-5
|  | Flex learn CF5-2 | same as Staff lounge DG7-5
|  | Lrg Breakout CF5-3 | same as Staff lounge DG7-5
|  | WC CF5-5 | same as Staff lounge DG7-5
|  | Creative CF5-6 | same as Staff lounge DG7-5
|  | Bathroom CF5-7 | same as Staff lounge DG7-5
|  | Flex learn CF5-8 | same as Staff lounge DG7-5
|  | Lrg Breakout CF5-9 | same as Staff lounge DG7-5
|  | Lrg Breakout CF5-12 | same as Staff lounge DG7-5
|  | Sm breakout CF5-10 | same as Staff lounge DG7-5
|  | Sm breakout CF5-11 | same as Staff lounge DG7-5
|  | Flex Learn CF5-13 | same as Staff lounge DG7-5
|  | WC CF5-14 | same as Staff lounge DG7-5
|  | Creative CF5-15 | same as Staff lounge DG7-5
Tier 2: ZONE 7 - External; Tier 3: Underground Services; Tier 5: poles |  | Underground Services (Poles)
Cabling pole
Cabling (Signage)
Fit Off (Poles)
Fit Off (Signage)
Tier 2: SUBMAINS |  | SUBMAINS
Tier 2: Main switchboard |  | Main Switchboard checklist

## Checklists
Type | Name | Values
checklist-flat | Catenaries
checkpoint | Supported correctly
checkpoint | Correct locations
checklist-flat | Cable tray
checkpoint | Installed correct location
checkpoint | Installed correct height
checkpoint | Installed correctly
checklist-flat | Floor penetrations
checkpoint | Penetration/chase marked as per plan
checkpoint | Depth/width correct for conduit/floor box
checklist-flat | Flush box
checkpoint | Correct location
checkpoint | Correct height
checklist-flat | Power circuits first fix
checkpoint | Cable schedule
checkpoint | Cable size correct
checkpoint | RCD downstream outlets wired correctly
checkpoint | Cabling to correct locations
checkpoint | Cables to isolators ie kitchen outlets
checkpoint | Position on elevations confirmed
checklist-flat | Lighting circuits first fix
checkpoint | Cabling to correct location as per plan
checkpoint | Emergency lighting cabelled
checkpoint | Number of fittings correct
checkpoint | Local switch wire installed
checkpoint | Sensor control wire installed
checkpoint | Cabinet lighting confirmed/cabled
checklist-flat | Heating circuits first fix
checkpoint | Cable sizes confirmed
checkpoint | cabling run to heater locations
checkpoint | cabling run to push button locations
checklist-flat | Power circuits second fix
checkpoint | Outlets installed, level and labelled
checkpoint | RCD outlets correct rating for space 10ma/30ma
checkpoint | Starters installed
checkpoint | Floor boxes fit off
checkpoint | Kitchen outlets/isolators/hw kits
checklist-flat | Lighting circuits second fix
checkpoint | Correct light type installed
checkpoint | Correct number installed
checkpoint | Correct location
checkpoint | Local switching installed
checkpoint | Sensor installed
checkpoint | Emergency lighting type installed
checklist-flat | Heating circuits second fix
checkpoint | heaters installed correct locations
checkpoint | terminated correctly
checkpoint | push buttons wired
checkpoint | buttons / contactors tested
checklist-flat | submain
checkpoint | correct size confirmed
checkpoint | length of tails
checkpoint | lugs correct size / hole size
checklist-flat | Switchboard
checkpoint | Cables dressed
checkpoint | All cables terminated
checkpoint | Circuits labelled
checkpoint | Circuits tested
value entry | IRT Mohm
value entry | Earth Loop
value entry | Rcd
value entry | Polarity
value entry | Visual
value entry | bonding
value entry | Earth cont.
checklist-flat | Documentation
checkpoint | C.O.C.
checkpoint | R.O.I.
checkpoint | Test sheets complete
checkpoint | As builts complete
checkpoint | PS3
checkpoint | Emergency lighting labelled
checkpoint | EM test sheets
checklist | Underground Services (Poles) Checklist
checkpoint | Location confirmed
checkpoint | Duct correct
checkpoint | Draw tape present
checkpoint | Cages set to height
checklist | Cabling (Poles) Checklist
checkpoint | Cable size
checkpoint | Cable type
checkpoint | Cable route
checkpoint | Draw tape
checklist | Cabling (Signage) Checklist
checkpoint | Cable size
checkpoint | Cable type
checkpoint | Cable route
checkpoint | Draw tape
checklist | Fit Off (Poles) Checklist
checkpoint | Insulation test cables
checkpoint | Correct fitting identified
checkpoint | Polarity correct
checkpoint | Terminations correct
checkpoint | Bonding
checklist | Fit Off (Signage) Checklist
checkpoint | Insulation test cables
checkpoint | Correct fitting identified
checkpoint | Polarity correct
checkpoint | Terminations correct
checkpoint | Bonding
checklist | Main Switchboard Checklist
checkpoint | switchboard securely fastened
checkpoint | switchboard bonded
checkpoint | terminals correctly crimped
checkpoint | lugs heat shrinked
checkpoint | lugs torqued
checkpoint | polarity correct
checkpoint | All cables tested
checkpoint | All labels installed
checkpoint | Test sheets complete
checkpoint | C.O.C complete
checkpoint | R.O.I required
checkpoint | live tests complete

## Blank - New Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Instruction to CONQA | Checklist Name